## Progress
DỰ ÁN:M304 | [34 empty] | Gá lắp |  |  | Hàn |  |  | Tổ hợp thử |  |  |  | Nghiệm thu |  |  | Bàn giao
Information ID | [9 empty] | Information Item | [7 empty] | 2026-10-06 | Information Item DE | [10 empty] | Information | [5 empty] | 431 | 357307.692 |  | 429 | 344192.728 |  | 0 | 0 | M304- |  | 353 | 319728.568 |  | 353 | 319728.568 |  | M304-
TT | Số Dự Án | Group ID | Group/Shipment | Hạng mục | MH | Ngày giao hàng(WO) | Dạng sản phẩm | Phân loại | Phân giao | Tên bản vẽ | Số chi tiết | Size | T'Qty | U.Weight | T.Weight | Profile | ID | Note | Lastest REV | Note1 | Control List | Rev Control List | Date Control List | APL | Rev APL | DATE APL | CPCL | Rev CPCL | DATE CPCL | Hoàn thiện | Còn lại | Kế hoạch Tháng | Nhận Phôi | Khối lượng | Ngày Gá | SL Gá | KL Gá | Ngày Hàn | SL Hàn | KL Hàn | Ngày TH | SL TH | KL TH | Số AFI | Ngày NT | SL NT | KL NT | Ngày BG | SL BG | KL BG | Đơn vị nhận | Số biên bản | Check 1 | Check 2 | Check 3 | Row Labels | Sum of T.Weight | Sum of KL Gá
0 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0065 | CS11R | (746 x 3612.5 x 15990) | 1 | 5884.573 | 5884.573 | [14 empty] | 5884.573 | 0 |  | 100% | 5884.573 | 2026-03-26 | 1 | 5884.573 | 2026-04-01 | 1 | 5884.573 |  |  | 0 | M304-CS-U1-029 | 2026-04-14 | 1 | 5884.573 | 2026-04-17 | 1 | 5884.573 | PAC | M304-029 |  |  |  | M304 | 1405885.29 | 957900.569
0 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0071 | CS12R | (746 x 3612.5 x 14032.5) | 1 | 5400.906 | 5400.906 | [14 empty] | 5400.906 | 0 |  | 100% | 5400.906 | 2026-03-30 | 1 | 5400.906 | 2026-04-02 | 1 | 5400.906 |  |  | 0 | M304-CS-U1-030 | 2026-04-16 | 1 | 5400.906 | 2026-04-17 | 1 | 5400.906 | PAC | M304-037 |  |  |  | Shipment 1 | 219096.528 | 218325.928
0 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0094 | CS15R | (657 x 3425 x 13847.5) | 1 | 4450.375 | 4450.375 | [14 empty] | 4450.375 | 0 |  | 100% | 4450.375 | 2026-03-30 | 1 | 4450.375 | 2026-04-10 | 1 | 4450.375 |  |  | 0 | M304-CS-U1-028 | 2026-04-13 | 1 | 4450.375 | 2026-04-15 | 1 | 4450.375 | PAC | M304-028 |  |  |  | Casing U1 | 139639.818 | 139639.818
1 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0251 | CS21T | (1620 x 583 x 10816) | 1 | 5103.32 | 5103.32 | [14 empty] | 5103.32 | 0 |  | 100% | 5103.32 | 2026-03-20 | 1 | 5103.32 | 2026-03-24 | 1 | 5103.32 |  |  | 0 | M304-CS-U1-013 | 2026-03-31 | 1 | 5103.32 | 2026-04-15 | 1 | 5103.32 | PAC | M304-010 |  |  |  | Main Stack U1 | 48216.41 | 48216.41
2 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0253 | CS22T | (1650 x 1018 x 10816) | 1 | 5577.73 | 5577.73 | [14 empty] | 5577.73 | 0 |  | 100% | 5577.73 | 2026-03-20 | 1 | 5577.73 | 2026-03-27 | 1 | 5577.73 |  |  | 0 | M304-CS-U1-022 | 2026-04-07 | 1 | 5577.73 | 2026-04-10 | 1 | 5577.73 | PAC | M304-016 |  |  |  | Steel Structure U1 | 31240.3 | 30469.7
3 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0257 | CS23T | (2086 x 585 x 10916) | 1 | 6924.928 | 6924.928 | [14 empty] | 6924.928 | 0 |  | 100% | 6924.928 | 2026-03-17 | 1 | 6924.928 | 2026-03-20 | 1 | 6924.928 |  |  | 0 | M304-CS-U1-013 | 2026-03-31 | 1 | 6924.928 | 2026-04-15 | 1 | 6924.928 | PAC | M304-010 |  |  |  | Shipment 2 | 98113.02 | 98113.02
4 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0259 | CS24T | (2020 x 996 x 10916) | 1 | 7299.26 | 7299.26 | [14 empty] | 7299.26 | 0 |  | 100% | 7299.26 | 2026-03-17 | 1 | 7299.26 | 2026-03-26 | 1 | 7299.26 |  |  | 0 | M304-CS-U1-023 | 2026-04-07 | 1 | 7299.26 | 2026-04-14 | 1 | 7299.26 | Truong An | M304-017 |  |  |  | Casing U2 | 98113.02 | 98113.02
4 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0262 | CS25T | (2020 x 820 x 10616) | 1 | 6835.794 | 6835.794 | [14 empty] | 6835.794 | 0 |  | 100% | 6835.794 | 2026-03-19 | 1 | 6835.794 | 2026-03-24 | 1 | 6835.794 |  |  | 0 | M304-CS-U1-007-1 | 2026-03-25 | 1 | 6835.794 | 2026-03-31 | 1 | 6835.794 | PAC | M304-005 |  |  |  | Shipment 3 | 103333.528 | 102562.928
4 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0264 | CS26T | (2040 x 820 x 10616) | 1 | 6906.524 | 6906.524 | [14 empty] | 6906.524 | 0 |  | 100% | 6906.524 | 2026-03-16 | 1 | 6906.524 | 2026-03-27 | 1 | 6906.524 |  |  | 0 | M304-CS-U1-020 | 2026-04-04 | 1 | 6906.524 | 2026-04-15 | 1 | 6906.524 | PAC | M304-014 |  |  |  | Steel Structure U2 | 31240.3 | 30469.7
4 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0267 | CS27T | (2020 x 585 x 10566) | 1 | 6758.544 | 6758.544 | [14 empty] | 6758.544 | 0 |  | 100% | 6758.544 | 2026-03-17 | 1 | 6758.544 | 2026-03-20 | 1 | 6758.544 |  |  | 0 | M304-CS-U1-025 | 2026-04-13 | 1 | 6758.544 | 2026-04-17 | 1 | 6758.544 | PAC | M304-024 |  |  |  | Main Stack U2 | 72093.228 | 72093.228
4 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0269 | CS28T | (1461 x 2509 x 8454) | 1 | 3010.008 | 3010.008 | [14 empty] | 3010.008 | 0 |  | 100% | 3010.008 | 2026-03-20 | 1 | 3010.008 | 2026-03-27 | 1 | 3010.008 |  |  | 0 | M304-CS-U1-016 | 2026-04-01 | 1 | 3010.008 | 2026-04-03 | 1 | 3010.008 | Truong An | M304-012 |  |  |  | Shipment 4 | 183466.698 | 183466.698
4 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0273 | CS29T | (915 x 3619 x 8454) | 1 | 3930.556 | 3930.556 | [14 empty] | 3930.556 | 0 |  | 100% | 3930.556 | 2026-03-22 | 1 | 3930.556 | 2026-03-31 | 1 | 3930.556 |  |  | 0 | M304-CS-U1-015 | 2026-03-31 | 1 | 3930.556 | 2026-04-03 | 1 | 3930.556 | Truong An | M304-013 |  |  |  | Casing U3 | 183466.698 | 183466.698
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0276 | CS30T | (846 x 4084 x 8154) | 1 | 4847.212 | 4847.212 | [14 empty] | 4847.212 | 0 |  | 100% | 4847.212 | 2026-03-28 | 1 | 4847.212 | 2026-04-01 | 1 | 4847.212 |  |  | 0 | M304-CS-U1-031 | 2026-04-16 | 1 | 4847.212 | 2026-04-18 | 1 | 4847.212 | Truong An | M304-039 |  |  |  | Shipment 5 | 182913.404 | 182142.804
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0281 | CS31B | (1098 x 475 x 8366) | 1 | 2498.5 | 2498.5 | [14 empty] | 2498.5 | 0 |  | 100% | 2498.5 | 2026-03-14 | 1 | 2498.5 | 2026-03-19 | 1 | 2498.5 |  |  | 0 | M304-CS-U1-024 | 2026-04-09 | 1 | 2498.5 | 2026-04-10 | 1 | 2498.5 | PAC | M304-022 |  |  |  | Casing U4 | 98113.02 | 98113.02
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0283 | CS32B | (636 x 2465 x 8354) | 1 | 2159.476 | 2159.476 | [14 empty] | 2159.476 | 0 |  | 100% | 2159.476 | 2026-03-09 | 1 | 2159.476 | 2026-03-16 | 1 | 2159.476 |  |  | 0 | M304-CS-U1-002 | 2026-03-24 | 1 | 2159.476 | 2026-03-28 | 1 | 2159.476 | Truong An | M304-002 |  |  |  | Steel Structure U3 | 31259.1 | 30488.5
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0290 | CS33B | (1266 x 1023 x 8366) | 1 | 3022.746 | 3022.746 | [14 empty] | 3022.746 | 0 |  | 100% | 3022.746 | 2026-03-14 | 1 | 3022.746 | 2026-03-18 | 1 | 3022.746 |  |  | 0 | M304-CS-U1-019 | 2026-04-08 | 1 | 3022.746 | 2026-04-10 | 1 | 3022.746 | PAC | M304-019 |  |  |  | Main Stack U3 | 53541.284 | 53541.284
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0293 | CS34B | (686 x 1603 x 8454) | 1 | 1416.26 | 1416.26 | [14 empty] | 1416.26 | 0 |  | 100% | 1416.26 | 2026-03-17 | 1 | 1416.26 | 2026-03-23 | 1 | 1416.26 |  |  | 0 | M304-CS-U1-012-1 | 2026-03-30 | 1 | 1416.26 | 2026-04-03 | 1 | 1416.26 | Truong An | M304-007 |  |  |  | Shipment 6 | 210564.636 | 115552.367
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0296 | CS35B | (686 x 3425 x 8454) | 1 | 2720.12 | 2720.12 | [14 empty] | 2720.12 | 0 |  | 100% | 2720.12 | 2026-03-10 | 1 | 2720.12 | 2026-03-17 | 1 | 2720.12 |  |  | 0 | M304-CS-U1-012 | 2026-03-30 | 1 | 2720.12 | 2026-04-03 | 1 | 2720.12 | Truong An | M304-009 |  |  |  | Casing U5 | 123903.964 | 28891.695
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0299 | CS36B | (1448 x 475 x 8466) | 1 | 2876 | 2876 | [14 empty] | 2876 | 0 |  | 100% | 2876 | 2026-03-14 | 1 | 2876 | 2026-03-21 | 1 | 2876 |  |  | 0 | M304-CS-U1-024 | 2026-04-09 | 1 | 2876 | 2026-04-10 | 1 | 2876 | PAC | M304-022 |  |  |  | Main Stack U4 | 86660.672 | 86660.672
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0301 | CS37B | (686 x 3245 x 8454) | 1 | 2357.264 | 2357.264 | [14 empty] | 2357.264 | 0 |  | 100% | 2357.264 | 2026-03-10 | 1 | 2357.264 | 2026-03-14 | 1 | 2357.264 |  |  | 0 | M304-CS-U1-017 | 2026-04-02 | 1 | 2357.264 | 2026-04-03 | 1 | 2357.264 | Truong An | M304-013 |  |  |  | Shipment 7 | 321736.804 | 53855.484
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0306 | CS38B | (1666 x 2254 x 8466) | 1 | 5971.224 | 5971.224 | [14 empty] | 5971.224 | 0 |  | 100% | 5971.224 | 2026-03-13 | 1 | 5971.224 | 2026-03-19 | 1 | 5971.224 |  |  | 0 | M304-CS-U1-032 | 2026-04-18 | 1 | 5971.224 | 2026-04-21 | 1 | 5971.224 | PAC | M304-040 |  |  |  | Casing U6 | 98113.02 | 0
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0310 | CS39B | (1491 x 617 x 8166) | 1 | 3030.756 | 3030.756 | [14 empty] | 3030.756 | 0 |  | 100% | 3030.756 | 2026-03-13 | 1 | 3030.756 | 2026-03-16 | 1 | 3030.756 |  |  | 0 | M304-CS-U1-018 | 2026-04-08 | 1 | 3030.756 | 2026-04-10 | 1 | 3030.756 | PAC | M304-019 |  |  |  | Main Stack U5 | 53541.284 | 53541.284
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0313 | CS40B | (511 x 3645 x 8154) | 1 | 2362.776 | 2362.776 | [14 empty] | 2362.776 | 0 |  | 100% | 2362.776 | 2026-03-11 | 1 | 2362.776 | 2026-03-19 | 1 | 2362.776 |  |  | 0 | M304-CS-U1-017 | 2026-04-02 | 1 | 2362.776 | 2026-04-03 | 1 | 2362.776 | Truong An | M304-013 |  |  |  | Steel Structure U5 | 170082.5 | 314.2
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0318 | CS41B | (1491 x 619 x 8166) | 1 | 2874.756 | 2874.756 | [14 empty] | 2874.756 | 0 |  | 100% | 2874.756 | 2026-03-14 | 1 | 2874.756 | 2026-03-20 | 1 | 2874.756 |  |  | 0 | M304-CS-U1-024 | 2026-04-09 | 1 | 2874.756 | 2026-04-10 | 1 | 2874.756 | PAC | M304-022 |  |  |  | Shipment 8 | 86660.672 | 3881.34
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0321 | CS42B | (500 x 3645 x 8166) | 1 | 2276.424 | 2276.424 | [14 empty] | 2276.424 | 0 |  | 100% | 2276.424 | 2026-03-11 | 1 | 2276.424 | 2026-03-13 | 1 | 2276.424 |  |  | 0 | M304-CS-U1-011 | 2026-03-27 | 1 | 2276.424 | 2026-04-03 | 1 | 2276.424 | Truong An | M304-009 |  |  |  | Main Stack U6 | 86660.672 | 3881.34
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0326 | CS43B | (1448 x 475 x 8116) | 1 | 2763.922 | 2763.922 | [14 empty] | 2763.922 | 0 |  | 100% | 2763.922 | 2026-03-16 | 1 | 2763.922 | 2026-03-22 | 1 | 2763.922 |  |  | 0 | M304-CS-U1-014 | 2026-03-31 | 1 | 2763.922 | 2026-04-10 | 1 | 2763.922 | PAC | M304-011 |  |  |  | Grand Total | 1405885.29 | 957900.569
5 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0328 | CS44B | (841 x 2910 x 8154) | 1 | 4588.92 | 4588.92 | [14 empty] | 4588.92 | 0 |  | 100% | 4588.92 | 2026-03-09 | 1 | 4588.92 | 2026-03-17 | 1 | 4588.92 |  |  | 0 | M304-CS-U1-004 | 2026-03-25 | 1 | 4588.92 | 2026-03-28 | 1 | 4588.92 | Truong An | M304-002
6 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0341 | CS51F | (939 x 1868 x 8354) | 1 | 2435.221 | 2435.221 | [14 empty] | 2435.221 | 0 |  | 100% | 2435.221 | 2026-03-17 | 1 | 2435.221 | 2026-03-20 | 1 | 2435.221 |  |  | 0 | M304-CS-U1-009 | 2026-03-28 | 1 | 2435.221 | 2026-04-03 | 1 | 2435.221 | Truong An | M304-008
7 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0348 | CS52F | (939 x 2422 x 8354) | 1 | 2649.092 | 2649.092 | [14 empty] | 2649.092 | 0 |  | 100% | 2649.092 | 2026-03-15 | 1 | 2649.092 | 2026-03-20 | 1 | 2649.092 |  |  | 0 | M304-CS-U1-009 | 2026-03-28 | 1 | 2649.092 | 2026-04-03 | 1 | 2649.092 | Truong An | M304-008
8 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0357 | CS53F | (640 x 1868 x 8454) | 1 | 2248.038 | 2248.038 | [14 empty] | 2248.038 | 0 |  | 100% | 2248.038 | 2026-03-17 | 1 | 2248.038 | 2026-03-28 | 1 | 2248.038 |  |  | 0 | M304-CS-U1-009 | 2026-03-28 | 1 | 2248.038 | 2026-04-03 | 1 | 2248.038 | Truong An | M304-008
9 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0363 | CS54F | (640 x 2288 x 8454) | 1 | 2557.24 | 2557.24 | [14 empty] | 2557.24 | 0 |  | 100% | 2557.24 | 2026-03-16 | 1 | 2557.24 | 2026-03-23 | 1 | 2557.24 |  |  | 0 | M304-CS-U1-006 | 2026-03-26 | 1 | 2557.24 | 2026-04-03 | 1 | 2557.24 | Truong An | M304-006
10 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0369 | CS55F | (929 x 2088 x 8454) | 1 | 2495.414 | 2495.414 | [14 empty] | 2495.414 | 0 |  | 100% | 2495.414 | 2026-03-17 | 1 | 2495.414 | 2026-03-24 | 1 | 2495.414 |  |  | 0 | M304-CS-U1-003 | 2026-03-25 | 1 | 2495.414 | 2026-03-28 | 1 | 2495.414 | Truong An | M304-003
10 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0375 | CS56F | (859 x 2422 x 8454) | 1 | 2535.307 | 2535.307 | [14 empty] | 2535.307 | 0 |  | 100% | 2535.307 | 2026-03-14 | 1 | 2535.307 | 2026-03-20 | 1 | 2535.307 |  |  | 0 | M304-CS-U1-001 | 2026-03-23 | 1 | 2535.307 | 2026-03-25 | 1 | 2535.307 | Truong An | M304-001
10 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0382 | CS57F | (642 x 2088 x 8394) | 1 | 2835.166 | 2835.166 | [14 empty] | 2835.166 | 0 |  | 100% | 2835.166 | 2026-03-18 | 1 | 2835.166 | 2026-03-26 | 1 | 2835.166 |  |  | 0 | M304-CS-U1-027 | 2026-04-11 | 1 | 2835.166 | 2026-04-14 | 1 | 2835.166 | Truong An | M304-026
10 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0387 | CS58F | (773 x 2088 x 8154) | 1 | 2332.36 | 2332.36 | [14 empty] | 2332.36 | 0 |  | 100% | 2332.36 | 2026-03-14 | 1 | 2332.36 | 2026-03-22 | 1 | 2332.36 |  |  | 0 | M304-CS-U1-001 | 2026-03-23 | 1 | 2332.36 | 2026-03-25 | 1 | 2332.36 | Truong An | M304-001
10 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0391 | CS59F | (970 x 2088 x 8104) | 1 | 2778.406 | 2778.406 | [14 empty] | 2778.406 | 0 |  | 100% | 2778.406 | 2026-03-17 | 1 | 2778.406 | 2026-03-25 | 1 | 2778.406 |  |  | 0 | M304-CS-U1-007 | 2026-03-25 | 1 | 2778.406 | 2026-03-28 | 1 | 2778.406 | Truong An | M304-004
10 | M304 | Shipment 1 Casing U1 | Shipment 1 | Casing U1 |  | 2026-03-17 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0396 | CS60F | (970 x 2422 x 8104) | 1 | 2924.7 | 2924.7 | [14 empty] | 2924.7 | 0 |  | 100% | 2924.7 | 2026-03-17 | 1 | 2924.7 | 2026-03-22 | 1 | 2924.7 |  |  | 0 | M304-CS-U1-005 | 2026-03-25 | 1 | 2924.7 | 2026-03-28 | 1 | 2924.7 | Truong An | M304-002
11 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0251 | CS21T | (1620 x 583 x 10816) | 1 | 5103.32 | 5103.32 | [14 empty] | 5103.32 | 0 |  | 100% | 5103.32 | 2026-03-20 | 1 | 5103.32 | 2026-03-30 | 1 | 5103.32 |  |  | 0 | M304-CS-U2-009-1 | 2026-04-14 | 1 | 5103.32 | 2026-04-17 | 1 | 5103.32 | Truong An | M304-048
12 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0253 | CS22T | (1650 x 1018 x 10816) | 1 | 5577.73 | 5577.73 | [14 empty] | 5577.73 | 0 |  | 100% | 5577.73 | 2026-03-26 | 1 | 5577.73 | 2026-04-01 | 1 | 5577.73 |  |  | 0 | M304-CS-U2-009 | 2026-04-14 | 1 | 5577.73 | 2026-04-17 | 1 | 5577.73 | PAC | M304-030
13 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0257 | CS23T | (2086 x 585 x 10916) | 1 | 6924.928 | 6924.928 | [14 empty] | 6924.928 | 0 |  | 100% | 6924.928 | 2026-03-28 | 1 | 6924.928 | 2026-04-02 | 1 | 6924.928 |  |  | 0 | M304-CS-U2-003 | 2026-04-08 | 1 | 6924.928 | 2026-04-15 | 1 | 6924.928 | PAC | M304-020
14 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0259 | CS24T | (2020 x 996 x 10916) | 1 | 7299.26 | 7299.26 | [14 empty] | 7299.26 | 0 |  | 100% | 7299.26 | 2026-03-31 | 1 | 7299.26 | 2026-04-03 | 1 | 7299.26 |  |  | 0 | M304-CS-U2-016 | 2026-04-18 | 1 | 7299.26 | 2026-04-22 | 1 | 7299.26 | Truong An | M304-041
14 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0262 | CS25T | (2020 x 820 x 10616) | 1 | 6835.794 | 6835.794 | [14 empty] | 6835.794 | 0 |  | 100% | 6835.794 | 2026-03-28 | 1 | 6835.794 | 2026-04-02 | 1 | 6835.794 |  |  | 0 | M304-CS-U2-006 | 2026-04-11 | 1 | 6835.794 | 2026-04-17 | 1 | 6835.794 | PAC | M304-023
14 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0264 | CS26T | (2040 x 820 x 10616) | 1 | 6906.524 | 6906.524 | [14 empty] | 6906.524 | 0 |  | 100% | 6906.524 | 2026-04-01 | 1 | 6906.524 | 2026-04-04 | 1 | 6906.524 |  |  | 0 | M304-CS-U2-010 | 2026-04-14 | 1 | 6906.524 | 2026-04-21 | 1 | 6906.524 | PAC | M304-031
14 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0267 | CS27T | (2020 x 585 x 10566) | 1 | 6758.544 | 6758.544 | [14 empty] | 6758.544 | 0 |  | 100% | 6758.544 | 2026-04-03 | 1 | 6758.544 | 2026-04-06 | 1 | 6758.544 |  |  | 0 | M304-CS-U2-006-1 | 2026-04-11 | 1 | 6758.544 | 2026-04-14 | 1 | 6758.544 | Truong An | M304-017
14 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0269 | CS28T | (1461 x 2509 x 8454) | 1 | 3010.008 | 3010.008 | [14 empty] | 3010.008 | 0 |  | 100% | 3010.008 | 2026-04-02 | 1 | 3010.008 | 2026-04-07 | 1 | 3010.008 |  |  | 0 | M304-CS-U2-014 | 2026-04-17 | 1 | 3010.008 | 2026-04-22 | 1 | 3010.008 | Truong An | M304-042
14 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0273 | CS29T | (915 x 3619 x 8454) | 1 | 3930.556 | 3930.556 | [14 empty] | 3930.556 | 0 |  | 100% | 3930.556 | 2026-04-04 | 1 | 3930.556 | 2026-04-10 | 1 | 3930.556 |  |  | 0 | M304-CS-U2-010-1 | 2026-04-14 | 1 | 3930.556 | 2026-04-17 | 1 | 3930.556 | Truong An | M304-035
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0276 | CS30T | (846 x 4084 x 8154) | 1 | 4847.212 | 4847.212 | [14 empty] | 4847.212 | 0 |  | 100% | 4847.212 | 2026-04-08 | 1 | 4847.212 | 2026-04-13 | 1 | 4847.212 |  |  | 0 | M304-CS-U2-017 | 2026-04-27 | 1 | 4847.212 | 2026-05-03 | 1 | 4847.212 | Truong An | M304-049
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0281 | CS31B | (1098 x 475 x 8366) | 1 | 2498.5 | 2498.5 | [14 empty] | 2498.5 | 0 |  | 100% | 2498.5 | 2026-03-24 | 1 | 2498.5 | 2026-03-27 | 1 | 2498.5 |  |  | 0 | M304-CS-U2-008 | 2026-04-14 | 1 | 2498.5 | 2026-04-15 | 1 | 2498.5 | PAC | M304-027
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0283 | CS32B | (636 x 2465 x 8354) | 1 | 2159.476 | 2159.476 | [14 empty] | 2159.476 | 0 |  | 100% | 2159.476 | 2026-03-25 | 1 | 2159.476 | 2026-03-29 | 1 | 2159.476 |  |  | 0 | M304-CS-U2-001 | 2026-04-06 | 1 | 2159.476 | 2026-04-09 | 1 | 2159.476 | Truong An | M304-015
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0290 | CS33B | (1266 x 1023 x 8366) | 1 | 3022.746 | 3022.746 | [14 empty] | 3022.746 | 0 |  | 100% | 3022.746 | 2026-03-25 | 1 | 3022.746 | 2026-03-30 | 1 | 3022.746 |  |  | 0 | M304-CS-U2-011 | 2026-04-16 | 1 | 3022.746 | 2026-04-17 | 1 | 3022.746 | PAC | M304-038
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0293 | CS34B | (686 x 1603 x 8454) | 1 | 1416.26 | 1416.26 | [14 empty] | 1416.26 | 0 |  | 100% | 1416.26 | 2026-03-27 | 1 | 1416.26 | 2026-03-31 | 1 | 1416.26 |  |  | 0 | M304-CS-U2-002 | 2026-04-08 | 1 | 1416.26 | 2026-04-09 | 1 | 1416.26 | Truong An | M304-018
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0296 | CS35B | (686 x 3425 x 8454) | 1 | 2720.12 | 2720.12 | [14 empty] | 2720.12 | 0 |  | 100% | 2720.12 | 2026-03-26 | 1 | 2720.12 | 2026-04-03 | 1 | 2720.12 |  |  | 0 | M304-CS-U2-004 | 2026-04-08 | 1 | 2720.12 | 2026-04-14 | 1 | 2720.12 | Truong An | M304-021
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0299 | CS36B | (1448 x 475 x 8466) | 1 | 2876 | 2876 | [14 empty] | 2876 | 0 |  | 100% | 2876 | 2026-03-24 | 1 | 2876 | 2026-03-27 | 1 | 2876 |  |  | 0 | M304-CS-U2-008 | 2026-04-14 | 1 | 2876 | 2026-04-15 | 1 | 2876 | PAC | M304-027
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0301 | CS37B | (686 x 3245 x 8454) | 1 | 2357.264 | 2357.264 | [14 empty] | 2357.264 | 0 |  | 100% | 2357.264 | 2026-03-26 | 1 | 2357.264 | 2026-04-01 | 1 | 2357.264 |  |  | 0 | M304-CS-U2-007 | 2026-04-13 | 1 | 2357.264 | 2026-04-14 | 1 | 2357.264 | Truong An | M304-025
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0306 | CS38B | (1666 x 2254 x 8466) | 1 | 5971.224 | 5971.224 | [14 empty] | 5971.224 | 0 |  | 100% | 5971.224 | 2026-03-30 | 1 | 5971.224 | 2026-04-07 | 1 | 5971.224 |  |  | 0 | M304-CS-U2-015 | 2026-04-17 | 1 | 5971.224 | 2026-04-21 | 1 | 5971.224 | PAC | M304-043
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0310 | CS39B | (1491 x 617 x 8166) | 1 | 3030.756 | 3030.756 | [14 empty] | 3030.756 | 0 |  | 100% | 3030.756 | 2026-03-29 | 1 | 3030.756 | 2026-04-09 | 1 | 3030.756 |  |  | 0 | M304-CS-U2-008 | 2026-04-14 | 1 | 3030.756 | 2026-04-15 | 1 | 3030.756 | PAC | M304-027
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0313 | CS40B | (511 x 3645 x 8154) | 1 | 2362.776 | 2362.776 | [14 empty] | 2362.776 | 0 |  | 100% | 2362.776 | 2026-03-29 | 1 | 2362.776 | 2026-04-10 | 1 | 2362.776 |  |  | 0 | M304-CS-U2-005 | 2026-04-10 | 1 | 2362.776 | 2026-04-14 | 1 | 2362.776 | Truong An | M304-021
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0318 | CS41B | (1491 x 619 x 8166) | 1 | 2874.756 | 2874.756 | [14 empty] | 2874.756 | 0 |  | 100% | 2874.756 | 2026-04-01 | 1 | 2874.756 | 2026-04-11 | 1 | 2874.756 |  |  | 0 | M304-CS-U2-008 | 2026-04-14 | 1 | 2874.756 | 2026-04-15 | 1 | 2874.756 | PAC | M304-027
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0321 | CS42B | (500 x 3645 x 8166) | 1 | 2276.424 | 2276.424 | [14 empty] | 2276.424 | 0 |  | 100% | 2276.424 | 2026-03-25 | 1 | 2276.424 | 2026-04-03 | 1 | 2276.424 |  |  | 0 | M304-CS-U2-007 | 2026-04-13 | 1 | 2276.424 | 2026-04-14 | 1 | 2276.424 | Truong An | M304-025
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0326 | CS43B | (1448 x 475 x 8116) | 1 | 2763.922 | 2763.922 | [14 empty] | 2763.922 | 0 |  | 100% | 2763.922 | 2026-04-02 | 1 | 2763.922 | 2026-04-10 | 1 | 2763.922 |  |  | 0 | M304-CS-U2-008 | 2026-04-14 | 1 | 2763.922 | 2026-04-15 | 1 | 2763.922 | PAC | M304-027
15 | M304 | Shipment 2 Casing U2 | Shipment 2 | Casing U2 |  | 2026-04-01 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0328 | CS44B | (841 x 2910 x 8154) | 1 | 4588.92 | 4588.92 | [14 empty] | 4588.92 | 0 |  | 100% | 4588.92 | 2026-04-04 | 1 | 4588.92 | 2026-04-10 | 1 | 4588.92 |  |  | 0 | M304-CS-U2-013 | 2026-04-16 | 1 | 4588.92 | 2026-04-17 | 1 | 4588.92 | Truong An | M304-035
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0007 | CS02R | (871 x 2745 x 12630.5) | 1 | 3973.909 | 3973.909 | [14 empty] | 3973.909 | 0 |  | 100% | 3973.909 | 2026-06-09 | 1 | 3973.909 | 2026-06-10 | 1 | 3973.909 |  |  | 0 | M304-CS-U3-042 | 2026-06-18 | 1 | 3973.909 | 2026-06-22 | 1 | 3973.909 | PAC | M304-114
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0016 | CS03R | (871 x 2745 x 14162) | 1 | 4586.014 | 4586.014 | [14 empty] | 4586.014 | 0 |  | 100% | 4586.014 | 2026-05-26 | 1 | 4586.014 | 2026-06-03 | 1 | 4586.014 |  |  | 0 | M304-CS-U3-039 | 2026-06-12 | 1 | 4586.014 | 2026-06-15 | 1 | 4586.014 | PAC | M304-103
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0030 | CS05R | (921 x 3245 x 15850.5) | 1 | 5458.032 | 5458.032 | [14 empty] | 5458.032 | 0 |  | 100% | 5458.032 | 2026-05-27 | 1 | 5458.032 | 2026-06-02 | 1 | 5458.032 |  |  | 0 | M304-CS-U3-037 | 2026-06-11 | 1 | 5458.032 | 2026-07-13 | 1 | 5458.032 | PAC | M304-102
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0036 | CS06R | (921 x 3245 x 14162) | 1 | 5403.245 | 5403.245 | [14 empty] | 5403.245 | 0 |  | 100% | 5403.245 | 2026-05-26 | 1 | 5403.245 | 2026-05-27 | 1 | 5403.245 |  |  | 0 | M304-CS-U3-036 | 2026-06-11 | 1 | 5403.245 | 2026-07-13 | 1 | 5403.245 | PAC | M304-102
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0048 | CS08R | (771 x 3645 x 15990) | 1 | 5737.828 | 5737.828 | [14 empty] | 5737.828 | 0 |  | 100% | 5737.828 | 2026-06-09 | 1 | 5737.828 | 2026-06-18 | 1 | 5737.828 |  |  | 0 | M304-CS-U3-049 | 2026-06-28 | 1 | 5737.828 | 2026-07-05 | 1 | 5737.828 | PAC | M304-127
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0054 | CS09R | (771 x 3645 x 14022.5) | 1 | 5514.988 | 5514.988 | [14 empty] | 5514.988 | 0 |  | 100% | 5514.988 | 2026-05-27 | 1 | 5514.988 | 2026-06-02 | 1 | 5514.988 |  |  | 0 | M304-CS-U3-034 | 2026-06-09 | 1 | 5514.988 | 2026-06-15 | 1 | 5514.988 | PAC | M304-099
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0065 | CS11R | (746 x 3612.5 x 15990) | 1 | 5884.573 | 5884.573 | [14 empty] | 5884.573 | 0 |  | 100% | 5884.573 | 2026-05-28 | 1 | 5884.573 | 2026-06-04 | 1 | 5884.573 |  |  | 0 | M304-CS-U3-045 | 2026-06-22 | 1 | 5884.573 | 2026-06-24 | 1 | 5884.573 | PAC | M304-121
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0071 | CS12R | (746 x 3612.5 x 14032.5) | 1 | 5400.906 | 5400.906 | [14 empty] | 5400.906 | 0 |  | 100% | 5400.906 | 2026-05-30 | 1 | 5400.906 | 2026-06-09 | 1 | 5400.906 |  |  | 0 | M304-CS-U3-047 | 2026-06-24 | 1 | 5400.906 | 2026-06-30 | 1 | 5400.906 | PAC | M304-123
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0094 | CS15R | (657 x 3425 x 13847.5) | 1 | 4450.375 | 4450.375 | [14 empty] | 4450.375 | 0 |  | 100% | 4450.375 | 2026-05-25 | 1 | 4450.375 | 2026-05-27 | 1 | 4450.375 |  |  | 0 | M304-CS-U3-035 | 2026-06-10 | 1 | 4450.375 | 2026-06-15 | 1 | 4450.375 | PAC | M304-100
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0098 | CS16R | (657 x 3425 x 12100) | 1 | 4504.218 | 4504.218 | [14 empty] | 4504.218 | 0 |  | 100% | 4504.218 | 2026-06-08 | 1 | 4504.218 | 2026-06-11 | 1 | 4504.218 |  |  | 0 | M304-CS-U3-041 | 2026-06-17 | 1 | 4504.218 | 2026-06-22 | 1 | 4504.218 | PAC | M304-112
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0113 | CS18R | (507 x 2910 x 14228) | 1 | 4329.301 | 4329.301 | [14 empty] | 4329.301 | 0 |  | 100% | 4329.301 | 2026-06-13 | 1 | 4329.301 | 2026-06-15 | 1 | 4329.301 |  |  | 0 | M304-CS-U3-046 | 2026-06-22 | 1 | 4329.301 | 2026-06-24 | 1 | 4329.301 | PAC | M304-122
15 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0117 | CS19R | (507 x 2910 x 14191.5) | 1 | 4319.345 | 4319.345 | [14 empty] | 4319.345 | 0 |  | 100% | 4319.345 | 2026-05-29 | 1 | 4319.345 | 2026-06-11 | 1 | 4319.345 |  |  | 0 | M304-CS-U3-046 | 2026-06-22 | 1 | 4319.345 | 2026-06-24 | 1 | 4319.345 | PAC | M304-122
16 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0251 | CS21T | (1620 x 583 x 10816) | 1 | 5103.32 | 5103.32 | [14 empty] | 5103.32 | 0 |  | 100% | 5103.32 | 2026-05-04 | 1 | 5103.32 | 2026-05-09 | 1 | 5103.32 |  |  | 0 | M304-CS-U3-002 | 2026-05-09 | 1 | 5103.32 | 2026-05-18 | 1 | 5103.32 | PAC | M304-059
17 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0253 | CS22T | (1650 x 1018 x 10816) | 1 | 5577.73 | 5577.73 | [14 empty] | 5577.73 | 0 |  | 100% | 5577.73 | 2026-05-04 | 1 | 5577.73 | 2026-05-11 | 1 | 5577.73 |  |  | 0 | M304-CS-U3-013 | 2026-05-18 | 1 | 5577.73 | 2026-05-21 | 1 | 5577.73 | PAC | M304-082
18 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0257 | CS23T | (2086 x 585 x 10916) | 1 | 6924.928 | 6924.928 | [14 empty] | 6924.928 | 0 |  | 100% | 6924.928 | 2026-05-11 | 1 | 6924.928 | 2026-05-21 | 1 | 6924.928 |  |  | 0 | M304-CS-U3-038 | 2026-06-16 | 1 | 6924.928 | 2026-06-22 | 1 | 6924.928 | PAC | M304-108
19 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0259 | CS24T | (2020 x 996 x 10916) | 1 | 7299.26 | 7299.26 | [14 empty] | 7299.26 | 0 |  | 100% | 7299.26 | 2026-05-18 | 1 | 7299.26 | 2026-05-19 | 1 | 7299.26 |  |  | 0 | M304-CS-U3-040 | 2026-06-17 | 1 | 7299.26 | 2026-06-22 | 1 | 7299.26 | PAC | M304-111
19 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0262 | CS25T | (2020 x 820 x 10616) | 1 | 6835.794 | 6835.794 | [14 empty] | 6835.794 | 0 |  | 100% | 6835.794 | 2026-05-14 | 1 | 6835.794 | 2026-05-21 | 1 | 6835.794 |  |  | 0 | M304-CS-U3-018 | 2026-05-23 | 1 | 6835.794 | 2026-05-31 | 1 | 6835.794 | PAC | M304-085
19 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0264 | CS26T | (2040 x 820 x 10616) | 1 | 6906.524 | 6906.524 | [14 empty] | 6906.524 | 0 |  | 100% | 6906.524 | 2026-05-15 | 1 | 6906.524 | 2026-05-22 | 1 | 6906.524 |  |  | 0 | M304-CS-U3-018 | 2026-05-23 | 1 | 6906.524 | 2026-05-31 | 1 | 6906.524 | PAC | M304-085
19 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0267 | CS27T | (2020 x 585 x 10566) | 1 | 6758.544 | 6758.544 | [14 empty] | 6758.544 | 0 |  | 100% | 6758.544 | 2026-04-14 | 1 | 6758.544 | 2026-04-26 | 1 | 6758.544 |  |  | 0 | M304-CS-U3-007 | 2026-05-14 | 1 | 6758.544 | 2026-05-18 | 1 | 6758.544 | PAC | M304-065
19 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0269 | CS28T | (1461 x 2509 x 8454) | 1 | 3010.008 | 3010.008 | [14 empty] | 3010.008 | 0 |  | 100% | 3010.008 | 2026-05-08 | 1 | 3010.008 | 2026-05-11 | 1 | 3010.008 |  |  | 0 | M304-CS-U3-015 | 2026-05-18 | 1 | 3010.008 | 2026-05-20 | 1 | 3010.008 | Truong An | M304-083
19 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0273 | CS29T | (915 x 3619 x 8454) | 1 | 3930.556 | 3930.556 | [14 empty] | 3930.556 | 0 |  | 100% | 3930.556 | 2026-05-02 | 1 | 3930.556 | 2026-05-08 | 1 | 3930.556 |  |  | 0 | M304-CS-U3-006 | 2026-05-14 | 1 | 3930.556 | 2026-05-18 | 1 | 3930.556 | Truong An | M304-064
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0276 | CS30T | (846 x 4084 x 8154) | 1 | 4847.212 | 4847.212 | [14 empty] | 4847.212 | 0 |  | 100% | 4847.212 | 2026-05-08 | 1 | 4847.212 | 2026-05-13 | 1 | 4847.212 |  |  | 0 | M304-CS-U3-032 | 2026-06-07 | 1 | 4847.212 | 2026-06-16 | 1 | 4847.212 | Truong An | M304-096
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0281 | CS31B | (1098 x 475 x 8366) | 1 | 2498.5 | 2498.5 | [14 empty] | 2498.5 | 0 |  | 100% | 2498.5 | 2026-05-16 | 1 | 2498.5 | 2026-05-21 | 1 | 2498.5 |  |  | 0 | M304-CS-U3-019 | 2026-05-24 | 1 | 2498.5 | 2026-05-31 | 1 | 2498.5 | PAC | M304-086
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0283 | CS32B | (636 x 2465 x 8354) | 1 | 2159.476 | 2159.476 | [14 empty] | 2159.476 | 0 |  | 100% | 2159.476 | 2026-04-26 | 1 | 2159.476 | 2026-04-28 | 1 | 2159.476 |  |  | 0 | M304-CS-U3-022 | 2026-05-27 | 1 | 2159.476 | 2026-05-29 | 1 | 2159.476 | Truong An | M304-088
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0290 | CS33B | (1266 x 1023 x 8366) | 1 | 3022.746 | 3022.746 | [14 empty] | 3022.746 | 0 |  | 100% | 3022.746 | 2026-05-17 | 1 | 3022.746 | 2026-05-21 | 1 | 3022.746 |  |  | 0 | M304-CS-U3-034 | 2026-06-09 | 1 | 3022.746 | 2026-06-15 | 1 | 3022.746 | PAC | M304-099
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0293 | CS34B | (686 x 1603 x 8454) | 1 | 1416.26 | 1416.26 | [14 empty] | 1416.26 | 0 |  | 100% | 1416.26 | 2026-05-04 | 1 | 1416.26 | 2026-05-06 | 1 | 1416.26 |  |  | 0 | M304-CS-U3-010 | 2026-05-16 | 1 | 1416.26 | 2026-05-18 | 1 | 1416.26 | Truong An | M304-070
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0296 | CS35B | (686 x 3425 x 8454) | 1 | 2720.12 | 2720.12 | [14 empty] | 2720.12 | 0 |  | 100% | 2720.12 | 2026-04-23 | 1 | 2720.12 | 2026-04-25 | 1 | 2720.12 |  |  | 0 | M304-CS-U3-014 | 2026-05-16 | 1 | 2720.12 | 2026-05-29 | 1 | 2720.12 | Truong An | M304-071
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0299 | CS36B | (1448 x 475 x 8466) | 1 | 2876 | 2876 | [14 empty] | 2876 | 0 |  | 100% | 2876 | 2026-05-09 | 1 | 2876 | 2026-05-12 | 1 | 2876 |  |  | 0 | M304-CS-U3-019 | 2026-05-24 | 1 | 2876 | 2026-05-31 | 1 | 2876 | PAC | M304-086
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0301 | CS37B | (686 x 3245 x 8454) | 1 | 2357.264 | 2357.264 | [14 empty] | 2357.264 | 0 |  | 100% | 2357.264 | 2026-05-11 | 1 | 2357.264 | 2026-05-17 | 1 | 2357.264 |  |  | 0 | M304-CS-U3-024 | 2026-05-27 | 1 | 2357.264 | 2026-06-04 | 1 | 2357.264 | Truong An | M304-089
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0306 | CS38B | (1666 x 2254 x 8466) | 1 | 5971.224 | 5971.224 | [14 empty] | 5971.224 | 0 |  | 100% | 5971.224 | 2026-05-15 | 1 | 5971.224 | 2026-05-18 | 1 | 5971.224 |  |  | 0 | M304-CS-U3-026 | 2026-05-28 | 1 | 5971.224 | 2026-05-31 | 1 | 5971.224 | PAC | M304-090
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0310 | CS39B | (1491 x 617 x 8166) | 1 | 3030.756 | 3030.756 | [14 empty] | 3030.756 | 0 |  | 100% | 3030.756 | 2026-04-28 | 1 | 3030.756 | 2026-05-04 | 1 | 3030.756 |  |  | 0 | M304-CS-U3-029 | 2026-06-03 | 1 | 3030.756 | 2026-06-05 | 1 | 3030.756 | PAC | M304-093
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0313 | CS40B | (511 x 3645 x 8154) | 1 | 2362.776 | 2362.776 | [14 empty] | 2362.776 | 0 |  | 100% | 2362.776 | 2026-04-27 | 1 | 2362.776 | 2026-04-30 | 1 | 2362.776 |  |  | 0 | M304-CS-U3-023 | 2026-05-26 | 1 | 2362.776 | 2026-05-29 | 1 | 2362.776 | Truong An | M304-087
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0318 | CS41B | (1491 x 619 x 8166) | 1 | 2874.756 | 2874.756 | [14 empty] | 2874.756 | 0 |  | 100% | 2874.756 | 2026-04-28 | 1 | 2874.756 | 2026-05-22 | 1 | 2874.756 |  |  | 0 | M304-CS-U3-029 | 2026-06-03 | 1 | 2874.756 | 2026-06-05 | 1 | 2874.756 | PAC | M304-093
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0321 | CS42B | (500 x 3645 x 8166) | 1 | 2276.424 | 2276.424 | [14 empty] | 2276.424 | 0 |  | 100% | 2276.424 | 2026-04-23 | 1 | 2276.424 | 2026-04-27 | 1 | 2276.424 |  |  | 0 | M304-CS-U3-030 | 2026-06-03 | 1 | 2276.424 | 2026-06-04 | 1 | 2276.424 | Truong An | M304-094
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0326 | CS43B | (1448 x 475 x 8116) | 1 | 2763.922 | 2763.922 | [14 empty] | 2763.922 | 0 |  | 100% | 2763.922 | 2026-05-04 | 1 | 2763.922 | 2026-05-14 | 1 | 2763.922 |  |  | 0 | M304-CS-U3-025 | 2026-06-01 | 1 | 2763.922 | 2026-06-05 | 1 | 2763.922 | PAC | M304-092
20 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0328 | CS44B | (841 x 2910 x 8154) | 1 | 4588.92 | 4588.92 | [14 empty] | 4588.92 | 0 |  | 100% | 4588.92 | 2026-05-15 | 1 | 4588.92 | 2026-05-21 | 1 | 4588.92 |  |  | 0 | M304-CS-U3-027 | 2026-05-29 | 1 | 4588.92 | 2026-06-04 | 1 | 4588.92 | Truong An | M304-091
21 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0341 | CS51F | (939 x 1868 x 8354) | 1 | 2435.221 | 2435.221 | [14 empty] | 2435.221 | 0 |  | 100% | 2435.221 | 2026-04-28 | 1 | 2435.221 | 2026-05-09 | 1 | 2435.221 |  |  | 0 | M304-CS-U3-001 | 2026-05-09 | 1 | 2435.221 | 2026-05-13 | 1 | 2435.221 | Truong An | M304-060
22 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0348 | CS52F | (939 x 2422 x 8354) | 1 | 2649.092 | 2649.092 | [14 empty] | 2649.092 | 0 |  | 100% | 2649.092 | 2026-04-23 | 1 | 2649.092 | 2026-04-27 | 1 | 2649.092 |  |  | 0 | M304-CS-U3-012 | 2026-05-15 | 1 | 2649.092 | 2026-05-20 | 1 | 2649.092 | Truong An | M304-069
23 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0357 | CS53F | (640 x 1868 x 8454) | 1 | 2248.038 | 2248.038 | [14 empty] | 2248.038 | 0 |  | 100% | 2248.038 | 2026-04-24 | 1 | 2248.038 | 2026-04-30 | 1 | 2248.038 |  |  | 0 | M304-CS-U3-009 | 2026-05-15 | 1 | 2248.038 | 2026-05-18 | 1 | 2248.038 | Truong An | M304-067
24 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0363 | CS54F | (640 x 2288 x 8454) | 1 | 2557.24 | 2557.24 | [14 empty] | 2557.24 | 0 |  | 100% | 2557.24 | 2026-04-24 | 1 | 2557.24 | 2026-05-07 | 1 | 2557.24 |  |  | 0 | M304-CS-U3-009 | 2026-05-15 | 1 | 2557.24 | 2026-05-18 | 1 | 2557.24 | Truong An | M304-067
25 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0369 | CS55F | (929 x 2088 x 8454) | 1 | 2495.414 | 2495.414 | [14 empty] | 2495.414 | 0 |  | 100% | 2495.414 | 2026-05-06 | 1 | 2495.414 | 2026-05-11 | 1 | 2495.414 |  |  | 0 | M304-CS-U3-003 | 2026-05-11 | 1 | 2495.414 | 2026-05-13 | 1 | 2495.414 | Truong An | M304-060
25 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0375 | CS56F | (859 x 2422 x 8454) | 1 | 2535.307 | 2535.307 | [14 empty] | 2535.307 | 0 |  | 100% | 2535.307 | 2026-04-23 | 1 | 2535.307 | 2026-04-25 | 1 | 2535.307 |  |  | 0 | M304-CS-U3-011 | 2026-05-15 | 1 | 2535.307 | 2026-05-18 | 1 | 2535.307 | Truong An | M304-068
25 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0382 | CS57F | (642 x 2088 x 8394) | 1 | 2835.166 | 2835.166 | [14 empty] | 2835.166 | 0 |  | 100% | 2835.166 | 2026-04-27 | 1 | 2835.166 | 2026-05-04 | 1 | 2835.166 |  |  | 0 | M304-CS-U3-044 | 2026-06-22 | 1 | 2835.166 | 2026-06-24 | 1 | 2835.166 | Truong An | M304-120
25 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0387 | CS58F | (773 x 2088 x 8154) | 1 | 2332.36 | 2332.36 | [14 empty] | 2332.36 | 0 |  | 100% | 2332.36 | 2026-05-02 | 1 | 2332.36 | 2026-05-10 | 1 | 2332.36 |  |  | 0 | M304-CS-U3-008 | 2026-05-14 | 1 | 2332.36 | 2026-05-18 | 1 | 2332.36 | Truong An | M304-066
25 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0391 | CS59F | (970 x 2088 x 8104) | 1 | 2778.406 | 2778.406 | [14 empty] | 2778.406 | 0 |  | 100% | 2778.406 | 2026-04-23 | 1 | 2778.406 | 2026-04-29 | 1 | 2778.406 |  |  | 0 | M304-CS-U3-004 | 2026-05-13 | 1 | 2778.406 | 2026-05-18 | 1 | 2778.406 | Truong An | M304-063
25 | M304 | Shipment 4 Casing U3 | Shipment 4 | Casing U3 |  | 2026-04-16 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0396 | CS60F | (970 x 2422 x 8104) | 1 | 2924.7 | 2924.7 | [14 empty] | 2924.7 | 0 |  | 100% | 2924.7 | 2026-05-02 | 1 | 2924.7 | 2026-05-12 | 1 | 2924.7 |  |  | 0 | M304-CS-U3-016 | 2026-05-18 | 1 | 2924.7 | 2026-05-20 | 1 | 2924.7 | Truong An | M304-084
26 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0251 | CS21T | (1620 x 583 x 10816) | 1 | 5103.32 | 5103.32 | [14 empty] | 5103.32 | 0 |  | 100% | 5103.32 | 2026-07-18 | 1 | 5103.32 | 2026-07-26 | 1 | 5103.32 |  |  | 0 | M304-CS-U4-017 | 2026-08-10 | 1 | 5103.32 | 2026-08-11 | 1 | 5103.32 | Truong An | M304-148
27 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0253 | CS22T | (1650 x 1018 x 10816) | 1 | 5577.73 | 5577.73 | [14 empty] | 5577.73 | 0 |  | 100% | 5577.73 | 2026-05-17 | 1 | 5577.73 | 2026-05-29 | 1 | 5577.73 |  |  | 0 | M304-CS-U4-009 | 2026-08-05 | 1 | 5577.73 | 2026-08-08 | 1 | 5577.73 | PAC | M304-139
28 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0257 | CS23T | (2086 x 585 x 10916) | 1 | 6924.928 | 6924.928 | [14 empty] | 6924.928 | 0 |  | 100% | 6924.928 | 2026-05-20 | 1 | 6924.928 | 2026-06-21 | 1 | 6924.928 |  |  | 0 | M304-CS-U4-019 | 2026-08-11 | 1 | 6924.928 | 2026-08-14 | 1 | 6924.928 | PAC | M304-150
29 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0259 | CS24T | (2020 x 996 x 10916) | 1 | 7299.26 | 7299.26 | [14 empty] | 7299.26 | 0 |  | 100% | 7299.26 | 2026-07-29 | 1 | 7299.26 | 2026-08-03 | 1 | 7299.26 |  |  | 0 | M304-CS-U4-018 | 2026-08-10 | 1 | 7299.26 | 2026-08-11 | 1 | 7299.26 | Truong An | M304-148
29 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0262 | CS25T | (2020 x 820 x 10616) | 1 | 6835.794 | 6835.794 | [14 empty] | 6835.794 | 0 |  | 100% | 6835.794 | 2026-06-27 | 1 | 6835.794 | 2026-07-09 | 1 | 6835.794 |  |  | 0 | M304-CS-U4-007 | 2026-08-01 | 1 | 6835.794 | 2026-08-03 | 1 | 6835.794 | PAC | M304-136
29 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0264 | CS26T | (2040 x 820 x 10616) | 1 | 6906.524 | 6906.524 | [14 empty] | 6906.524 | 0 |  | 100% | 6906.524 | 2026-06-12 | 1 | 6906.524 | 2026-06-22 | 1 | 6906.524 |  |  | 0 | M304-CS-U4-002 | 2026-07-09 | 1 | 6906.524 | 2026-07-11 | 1 | 6906.524 | PAC | M304-129
29 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0267 | CS27T | (2020 x 585 x 10566) | 1 | 6758.544 | 6758.544 | [14 empty] | 6758.544 | 0 |  | 100% | 6758.544 | 2026-06-27 | 1 | 6758.544 | 2026-06-26 | 1 | 6758.544 |  |  | 0 | M304-CS-U4-001 | 2026-07-09 | 1 | 6758.544 | 2026-07-10 | 1 | 6758.544 | Truong An | M304-128
29 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0269 | CS28T | (1461 x 2509 x 8454) | 1 | 3010.008 | 3010.008 | [14 empty] | 3010.008 | 0 |  | 100% | 3010.008 | 2026-07-24 | 1 | 3010.008 | 2026-07-29 | 1 | 3010.008 |  |  | 0 | M304-CS-U4-004 | 2026-07-29 | 1 | 3010.008 | 2026-08-07 | 1 | 3010.008 | Truong An | M304-133
29 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0273 | CS29T | (915 x 3619 x 8454) | 1 | 3930.556 | 3930.556 | [14 empty] | 3930.556 | 0 |  | 100% | 3930.556 | 2026-06-17 | 1 | 3930.556 | 2026-06-23 | 1 | 3930.556 |  |  | 0 | M304-CS-U4-003 | 2026-07-11 | 1 | 3930.556 | 2026-08-07 | 1 | 3930.556 | Truong An | M304-130
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0276 | CS30T | (846 x 4084 x 8154) | 1 | 4847.212 | 4847.212 | [14 empty] | 4847.212 | 0 |  | 100% | 4847.212 | 2026-08-03 | 1 | 4847.212 | 2026-08-06 | 1 | 4847.212 |  |  | 0 | M304-CS-U4-022 | 2026-08-18 | 1 | 4847.212 | 2026-08-19 | 1 | 4847.212 | Truong An | M304-161
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0281 | CS31B | (1098 x 475 x 8366) | 1 | 2498.5 | 2498.5 | [14 empty] | 2498.5 | 0 |  | 100% | 2498.5 | 2026-07-16 | 1 | 2498.5 | 2026-07-23 | 1 | 2498.5 |  |  | 0 | M304-CS-U4-005 | 2026-08-03 | 1 | 2498.5 | 2026-08-07 | 1 | 2498.5 | PAC | M304-137
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0283 | CS32B | (636 x 2465 x 8354) | 1 | 2159.476 | 2159.476 | [14 empty] | 2159.476 | 0 |  | 100% | 2159.476 | 2026-07-30 | 1 | 2159.476 | 2026-08-03 | 1 | 2159.476 |  |  | 0 | M304-CS-U4-023 | 2026-08-18 | 1 | 2159.476 | 2026-08-20 | 1 | 2159.476 | Truong An | M304-160
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0290 | CS33B | (1266 x 1023 x 8366) | 1 | 3022.746 | 3022.746 | [14 empty] | 3022.746 | 0 |  | 100% | 3022.746 | 2026-07-28 | 1 | 3022.746 | 2026-08-01 | 1 | 3022.746 |  |  | 0 | M304-CS-U4-020 | 2026-08-11 | 1 | 3022.746 | 2026-08-14 | 1 | 3022.746 | PAC | M304-151
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0293 | CS34B | (686 x 1603 x 8454) | 1 | 1416.26 | 1416.26 | [14 empty] | 1416.26 | 0 |  | 100% | 1416.26 | 2026-08-06 | 1 | 1416.26 | 2026-08-07 | 1 | 1416.26 |  |  | 0 | M304-CS-U4-024 | 2026-08-19 | 1 | 1416.26 | 2026-08-22 | 1 | 1416.26 | Truong An | M304-161
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0296 | CS35B | (686 x 3425 x 8454) | 1 | 2720.12 | 2720.12 | [14 empty] | 2720.12 | 0 |  | 100% | 2720.12 | 2026-07-24 | 1 | 2720.12 | 2026-08-02 | 1 | 2720.12 |  |  | 0 | M304-CS-U4-024 | 2026-08-19 | 1 | 2720.12 | 2026-08-22 | 1 | 2720.12 | Truong An | M304-161
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0299 | CS36B | (1448 x 475 x 8466) | 1 | 2876 | 2876 | [14 empty] | 2876 | 0 |  | 100% | 2876 | 2026-07-18 | 1 | 2876 | 2026-07-25 | 1 | 2876 |  |  | 0 | M304-CS-U4-006 | 2026-08-03 | 1 | 2876 | 2026-08-07 | 1 | 2876 | PAC | M304-138
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0301 | CS37B | (686 x 3245 x 8454) | 1 | 2357.264 | 2357.264 | [14 empty] | 2357.264 | 0 |  | 100% | 2357.264 | 2026-07-30 | 1 | 2357.264 | 2026-08-05 | 1 | 2357.264 |  |  | 0 | M304-CS-U4-021 | 2026-08-15 | 1 | 2357.264 | 2026-08-17 | 1 | 2357.264 | Truong An | M304-159
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0306 | CS38B | (1666 x 2254 x 8466) | 1 | 5971.224 | 5971.224 | [14 empty] | 5971.224 | 0 |  | 100% | 5971.224 | 2026-07-22 | 1 | 5971.224 | 2026-07-25 | 1 | 5971.224 |  |  | 0 | M304-CS-U4-030 | 2026-09-03 | 1 | 5971.224 | 2026-09-08 | 1 | 5971.224 | PAC | M304-167
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0310 | CS39B | (1491 x 617 x 8166) | 1 | 3030.756 | 3030.756 | [14 empty] | 3030.756 | 0 |  | 100% | 3030.756 | 2026-07-23 | 1 | 3030.756 | 2026-07-25 | 1 | 3030.756 |  |  | 0 | M304-CS-U4-010 | 2026-08-06 | 1 | 3030.756 | 2026-08-08 | 1 | 3030.756 | PAC | M304-141
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0313 | CS40B | (511 x 3645 x 8154) | 1 | 2362.776 | 2362.776 | [14 empty] | 2362.776 | 0 |  | 100% | 2362.776 | 2026-08-03 | 1 | 2362.776 | 2026-08-06 | 1 | 2362.776 |  |  | 0 | M304-CS-U4-027 | 2026-08-24 | 1 | 2362.776 | 2026-08-26 | 1 | 2362.776 | Truong An | M304-166
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0318 | CS41B | (1491 x 619 x 8166) | 1 | 2874.756 | 2874.756 | [14 empty] | 2874.756 | 0 |  | 100% | 2874.756 | 2026-07-28 | 1 | 2874.756 | 2026-08-05 | 1 | 2874.756 |  |  | 0 | M304-CS-U4-015 | 2026-08-10 | 1 | 2874.756 | 2026-08-14 | 1 | 2874.756 | PAC | M304-147
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0321 | CS42B | (500 x 3645 x 8166) | 1 | 2276.424 | 2276.424 | [14 empty] | 2276.424 | 0 |  | 100% | 2276.424 | 2026-08-06 | 1 | 2276.424 | 2026-08-07 | 1 | 2276.424 |  |  | 0 | M304-CS-U4-014 | 2026-08-23 | 1 | 2276.424 | 2026-08-27 | 1 | 2276.424 | Truong An | M304-164
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0326 | CS43B | (1448 x 475 x 8116) | 1 | 2763.922 | 2763.922 | [14 empty] | 2763.922 | 0 |  | 100% | 2763.922 | 2026-07-24 | 1 | 2763.922 | 2026-07-30 | 1 | 2763.922 |  |  | 0 | M304-CS-U4-011 | 2026-08-07 | 1 | 2763.922 | 2026-08-14 | 1 | 2763.922 | PAC | M304-143
30 | M304 | Shipment 5 Casing U4 | Shipment 5 | Casing U4 |  | 2026-05-06 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0328 | CS44B | (841 x 2910 x 8154) | 1 | 4588.92 | 4588.92 | [14 empty] | 4588.92 | 0 |  | 100% | 4588.92 | 2026-07-24 | 1 | 4588.92 | 2026-07-30 | 1 | 4588.92 |  |  | 0 | M304-CS-U4-026 | 2026-08-22 | 1 | 4588.92 | 2026-08-26 | 1 | 4588.92 | Truong An | M304-165
31 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0251 | CS21T | (1620 x 583 x 10816) | 1 | 5103.32 | 5103.32 | [14 empty] | 0 | 5103.32 |  | 30% | 1530.996 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
32 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0253 | CS22T | (1650 x 1018 x 10816) | 1 | 5577.73 | 5577.73 | [14 empty] | 0 | 5577.73 |  | 30% | 1673.319 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
33 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0257 | CS23T | (2086 x 585 x 10916) | 1 | 6924.928 | 6924.928 | [14 empty] | 0 | 6924.928 |  | 30% | 2077.4784 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
34 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0259 | CS24T | (2020 x 996 x 10916) | 1 | 7299.26 | 7299.26 | [14 empty] | 0 | 7299.26 |  | 30% | 2189.778 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
34 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0262 | CS25T | (2020 x 820 x 10616) | 1 | 6835.794 | 6835.794 | [14 empty] | 0 | 6835.794 |  | 30% | 2050.7382 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
34 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0264 | CS26T | (2040 x 820 x 10616) | 1 | 6906.524 | 6906.524 | [14 empty] | 6906.524 | 0 |  | 30% | 2071.9572 | 2026-08-11 | 1 | 6906.524 | 2026-08-15 | 1 | 6906.524 |  |  | 0 | M304-CS-U5-002 | 2026-08-15 | 1 | 6906.524 | 2026-08-27 | 1 | 6906.524 | PAC | M304-158
34 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0267 | CS27T | (2020 x 585 x 10566) | 1 | 6758.544 | 6758.544 | [14 empty] | 6758.544 | 0 |  | 30% | 2027.5632 | 2026-08-11 | 1 | 6758.544 | 2026-08-11 | 1 | 6758.544 |  |  | 0 | M304-CS-U5-001 | 2026-08-11 | 1 | 6758.544 | 2026-08-13 | 1 | 6758.544 | Truong An | M304-152
34 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0269 | CS28T | (1461 x 2509 x 8454) | 1 | 3010.008 | 3010.008 | [14 empty] | 3010.008 | 0 |  | 30% | 903.0024 | 2026-08-11 | 1 | 3010.008 | 2026-08-15 | 1 | 3010.008 |  |  | 0 | M304-CS-U5-004 | 2026-09-21 | 1 | 3010.008 | 2026-09-24 | 1 | 3010.008 | Truong An | M304-185
34 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0273 | CS29T | (915 x 3619 x 8454) | 1 | 3930.556 | 3930.556 | [14 empty] | 3930.556 | 0 |  | 30% | 1179.1668 | 2026-08-12 | 1 | 3930.556 | 2026-08-17 | 1 | 3930.556 |  |  | 0 | M304-CS-U5-003 | 2026-09-17 | 1 | 3930.556 | 2026-09-17 | 1 | 3930.556 | Truong An | M304-182
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0276 | CS30T | (846 x 4084 x 8154) | 1 | 4847.212 | 4847.212 | [14 empty] | 0 | 4847.212 |  | 30% | 1454.1636 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0281 | CS31B | (1098 x 475 x 8366) | 1 | 2498.5 | 2498.5 | [14 empty] | 0 | 2498.5 |  | 30% | 749.55 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0283 | CS32B | (636 x 2465 x 8354) | 1 | 2159.476 | 2159.476 | [14 empty] | 0 | 2159.476 |  | 30% | 647.8428 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0290 | CS33B | (1266 x 1023 x 8366) | 1 | 3022.746 | 3022.746 | [14 empty] | 0 | 3022.746 |  | 30% | 906.8238 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0293 | CS34B | (686 x 1603 x 8454) | 1 | 1416.26 | 1416.26 | [14 empty] | 0 | 1416.26 |  | 30% | 424.878 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0296 | CS35B | (686 x 3425 x 8454) | 1 | 2720.12 | 2720.12 | [14 empty] | 0 | 2720.12 |  | 30% | 816.036 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0299 | CS36B | (1448 x 475 x 8466) | 1 | 2876 | 2876 | [14 empty] | 1438 | 1438 |  | 30% | 862.8 | 2026-07-22 | 1 | 2876 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0301 | CS37B | (686 x 3245 x 8454) | 1 | 2357.264 | 2357.264 | [14 empty] | 0 | 2357.264 |  | 30% | 707.1792 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0306 | CS38B | (1666 x 2254 x 8466) | 1 | 5971.224 | 5971.224 | [14 empty] | 0 | 5971.224 |  | 30% | 1791.3672 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0310 | CS39B | (1491 x 617 x 8166) | 1 | 3030.756 | 3030.756 | [14 empty] | 0 | 3030.756 |  | 30% | 909.2268 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0313 | CS40B | (511 x 3645 x 8154) | 1 | 2362.776 | 2362.776 | [14 empty] | 0 | 2362.776 |  | 30% | 708.8328 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0318 | CS41B | (1491 x 619 x 8166) | 1 | 2874.756 | 2874.756 | [14 empty] | 1437.378 | 1437.378 |  | 30% | 862.4268 | 2026-07-28 | 1 | 2874.756 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0321 | CS42B | (500 x 3645 x 8166) | 1 | 2276.424 | 2276.424 | [14 empty] | 0 | 2276.424 |  | 30% | 682.9272 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0326 | CS43B | (1448 x 475 x 8116) | 1 | 2763.922 | 2763.922 | [14 empty] | 0 | 2763.922 |  | 30% | 829.1766 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
35 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S1 | 25HG001-309-DD0-0C0328 | CS44B | (841 x 2910 x 8154) | 1 | 4588.92 | 4588.92 | [14 empty] | 0 | 4588.92 |  | 30% | 1376.676 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
36 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0341 | CS51F | (939 x 1868 x 8354) | 1 | 2435.221 | 2435.221 | [14 empty] | 0 | 2435.221 |  | 30% | 730.5663 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
37 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0348 | CS52F | (939 x 2422 x 8354) | 1 | 2649.092 | 2649.092 | [14 empty] | 0 | 2649.092 |  | 30% | 794.7276 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
38 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0357 | CS53F | (640 x 1868 x 8454) | 1 | 2248.038 | 2248.038 | [14 empty] | 0 | 2248.038 |  | 30% | 674.4114 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
39 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0363 | CS54F | (640 x 2288 x 8454) | 1 | 2557.24 | 2557.24 | [14 empty] | 0 | 2557.24 |  | 30% | 767.172 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
40 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0369 | CS55F | (929 x 2088 x 8454) | 1 | 2495.414 | 2495.414 | [14 empty] | 0 | 2495.414 |  | 30% | 748.6242 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
40 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0375 | CS56F | (859 x 2422 x 8454) | 1 | 2535.307 | 2535.307 | [14 empty] | 1267.6535 | 1267.6535 |  | 30% | 760.5921 | 2026-10-06 | 1 | 2535.307 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
40 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0382 | CS57F | (642 x 2088 x 8394) | 1 | 2835.166 | 2835.166 | [14 empty] | 0 | 2835.166 |  | 30% | 850.5498 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
40 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0387 | CS58F | (773 x 2088 x 8154) | 1 | 2332.36 | 2332.36 | [14 empty] | 0 | 2332.36 |  | 30% | 699.708 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
40 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0391 | CS59F | (970 x 2088 x 8104) | 1 | 2778.406 | 2778.406 | [14 empty] | 0 | 2778.406 |  | 30% | 833.5218 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
40 | M304 | Shipment 6 Casing U5 | Shipment 6 | Casing U5 |  | 2026-05-26 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0396 | CS60F | (970 x 2422 x 8104) | 1 | 2924.7 | 2924.7 | [14 empty] | 0 | 2924.7 |  | 30% | 877.41 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
41 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0251 | CS21T | (1620 x 583 x 10816) | 1 | 5103.32 | 5103.32 | [14 empty] | 0 | 5103.32 |  | 20% | 1020.664 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
42 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0253 | CS22T | (1650 x 1018 x 10816) | 1 | 5577.73 | 5577.73 | [14 empty] | 0 | 5577.73 |  | 20% | 1115.546 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
43 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0257 | CS23T | (2086 x 585 x 10916) | 1 | 6924.928 | 6924.928 | [14 empty] | 0 | 6924.928 |  | 20% | 1384.9856 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
44 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0259 | CS24T | (2020 x 996 x 10916) | 1 | 7299.26 | 7299.26 | [14 empty] | 0 | 7299.26 |  | 20% | 1459.852 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
44 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0262 | CS25T | (2020 x 820 x 10616) | 1 | 6835.794 | 6835.794 | [14 empty] | 0 | 6835.794 |  | 20% | 1367.1588 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
44 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0264 | CS26T | (2040 x 820 x 10616) | 1 | 6906.524 | 6906.524 | [14 empty] | 0 | 6906.524 |  | 20% | 1381.3048 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
44 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0267 | CS27T | (2020 x 585 x 10566) | 1 | 6758.544 | 6758.544 | [14 empty] | 0 | 6758.544 |  | 20% | 1351.7088 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
44 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0269 | CS28T | (1461 x 2509 x 8454) | 1 | 3010.008 | 3010.008 | [14 empty] | 0 | 3010.008 |  | 20% | 602.0016 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
44 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S2 | 25HG001-309-DD0-0C0273 | CS29T | (915 x 3619 x 8454) | 1 | 3930.556 | 3930.556 | [14 empty] | 0 | 3930.556 |  | 20% | 786.1112 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S4 | 25HG001-309-DD0-0C0276 | CS30T | (846 x 4084 x 8154) | 1 | 4847.212 | 4847.212 | [14 empty] | 0 | 4847.212 |  | 20% | 969.4424 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0281 | CS31B | (1098 x 475 x 8366) | 1 | 2498.5 | 2498.5 | [14 empty] | 0 | 2498.5 |  | 20% | 499.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0283 | CS32B | (636 x 2465 x 8354) | 1 | 2159.476 | 2159.476 | [14 empty] | 0 | 2159.476 |  | 20% | 431.8952 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0290 | CS33B | (1266 x 1023 x 8366) | 1 | 3022.746 | 3022.746 | [14 empty] | 0 | 3022.746 |  | 20% | 604.5492 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0293 | CS34B | (686 x 1603 x 8454) | 1 | 1416.26 | 1416.26 | [14 empty] | 0 | 1416.26 |  | 20% | 283.252 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0296 | CS35B | (686 x 3425 x 8454) | 1 | 2720.12 | 2720.12 | [14 empty] | 0 | 2720.12 |  | 20% | 544.024 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0299 | CS36B | (1448 x 475 x 8466) | 1 | 2876 | 2876 | [14 empty] | 0 | 2876 |  | 20% | 575.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0301 | CS37B | (686 x 3245 x 8454) | 1 | 2357.264 | 2357.264 | [14 empty] | 0 | 2357.264 |  | 20% | 471.4528 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0306 | CS38B | (1666 x 2254 x 8466) | 1 | 5971.224 | 5971.224 | [14 empty] | 0 | 5971.224 |  | 20% | 1194.2448 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0310 | CS39B | (1491 x 617 x 8166) | 1 | 3030.756 | 3030.756 | [14 empty] | 0 | 3030.756 |  | 20% | 606.1512 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0313 | CS40B | (511 x 3645 x 8154) | 1 | 2362.776 | 2362.776 | [14 empty] | 0 | 2362.776 |  | 20% | 472.5552 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0318 | CS41B | (1491 x 619 x 8166) | 1 | 2874.756 | 2874.756 | [14 empty] | 0 | 2874.756 |  | 20% | 574.9512 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0321 | CS42B | (500 x 3645 x 8166) | 1 | 2276.424 | 2276.424 | [14 empty] | 0 | 2276.424 |  | 20% | 455.2848 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0326 | CS43B | (1448 x 475 x 8116) | 1 | 2763.922 | 2763.922 | [14 empty] | 0 | 2763.922 |  | 20% | 552.7844 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | PAC
45 | M304 | Shipment 7 Casing U6 | Shipment 7 | Casing U6 |  | 2026-06-15 | HRSG | HSG01 | S3 | 25HG001-309-DD0-0C0328 | CS44B | (841 x 2910 x 8154) | 1 | 4588.92 | 4588.92 | [14 empty] | 0 | 4588.92 |  | 20% | 917.784 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
46 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06A | (1059 x 3997 x 4640) | 1 | 1930.27 | 1930.27 | [14 empty] | 1930.27 | 0 |  | 100% | 1930.27 | 2026-03-31 | 1 | 1930.27 | 2026-04-02 | 1 | 1930.27 |  |  | 0 | M304-STK-U1-001 | 2026-04-15 | 1 | 1930.27 | 2026-04-18 | 1 | 1930.27 | Truong An | M304-032
47 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06B | (1059 x 3997 x 4640) | 1 | 1930.27 | 1930.27 | [14 empty] | 1930.27 | 0 |  | 100% | 1930.27 | 2026-03-31 | 1 | 1930.27 | 2026-04-03 | 1 | 1930.27 |  |  | 0 | M304-STK-U1-002 | 2026-04-16 | 1 | 1930.27 | 2026-04-18 | 1 | 1930.27 | Truong An | M304-036
48 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07A | (1059 x 3997 x 4640) | 1 | 1928.96 | 1928.96 | [14 empty] | 1928.96 | 0 |  | 100% | 1928.96 | 2026-03-31 | 1 | 1928.96 | 2026-04-04 | 1 | 1928.96 |  |  | 0 | M304-STK-U1-001 | 2026-04-15 | 1 | 1928.96 | 2026-04-18 | 1 | 1928.96 | Truong An | M304-032
49 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07B | (1059 x 3997 x 4640) | 1 | 1928.96 | 1928.96 | [14 empty] | 1928.96 | 0 |  | 100% | 1928.96 | 2026-03-31 | 1 | 1928.96 | 2026-04-06 | 1 | 1928.96 |  |  | 0 | M304-STK-U1-001 | 2026-04-15 | 1 | 1928.96 | 2026-04-18 | 1 | 1928.96 | Truong An | M304-032
50 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG05 | S4 | 25HG001-312-DD0-0S0016 | SH08A | (2420 x 3927 x 6474) | 1 | 4387.655 | 4387.655 | [14 empty] | 4387.655 | 0 |  | 100% | 4387.655 | 2026-04-04 | 1 | 4387.655 | 2026-04-20 | 1 | 4387.655 |  |  | 0 | M304-STK-U1-008 | 2026-05-07 | 1 | 4387.655 | 2026-05-08 | 1 | 4387.655 | Truong An | M304-058
51 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG05 | S4 | 25HG001-312-DD0-0S0016 | SH08B | (2420 x 3927 x 6474) | 1 | 4494.755 | 4494.755 | [14 empty] | 4494.755 | 0 |  | 100% | 4494.755 | 2026-04-15 | 1 | 4494.755 | 2026-04-20 | 1 | 4494.755 |  |  | 0 | M304-STK-U1-008 | 2026-05-07 | 1 | 4494.755 | 2026-05-08 | 1 | 4494.755 | Truong An | M304-058
52 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG05 | S4 | 25HG001-312-DD0-0S0018 | SH09A | (3091 x 4100 x 6719) | 1 | 3840.31 | 3840.31 | [14 empty] | 3840.31 | 0 |  | 100% | 3840.31 | 2026-04-11 | 1 | 3840.31 | 2026-04-15 | 1 | 3840.31 |  |  | 0 | M304-STK-U1-003 | 2026-04-30 | 1 | 3840.31 | 2026-05-08 | 1 | 3840.31 | Truong An | M304-052
53 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG05 | S4 | 25HG001-312-DD0-0S0018 | SH09B | (3091 x 4100 x 6719) | 1 | 2805.17 | 2805.17 | [14 empty] | 2805.17 | 0 |  | 100% | 2805.17 | 2026-04-11 | 1 | 2805.17 | 2026-04-15 | 1 | 2805.17 |  |  | 0 | M304-STK-U1-003 | 2026-04-30 | 1 | 2805.17 | 2026-05-08 | 1 | 2805.17 | Truong An | M304-052
54 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG05 | S4 | 25HG001-312-DD0-0S0021 | SH10A | (3278 x 3468 x 6716) | 1 | 4227.66 | 4227.66 | [14 empty] | 4227.66 | 0 |  | 100% | 4227.66 | 2026-04-09 | 1 | 4227.66 | 2026-04-13 | 1 | 4227.66 |  |  | 0 | M304-STK-U1-006 | 2026-05-04 | 1 | 4227.66 | 2026-05-08 | 1 | 4227.66 | Truong An | M304-057
55 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG05 | S4 | 25HG001-312-DD0-0S0021 | SH10B | (3278 x 3358 x 6716) | 1 | 3438.66 | 3438.66 | [14 empty] | 3438.66 | 0 |  | 100% | 3438.66 | 2026-04-09 | 1 | 3438.66 | 2026-04-13 | 1 | 3438.66 |  |  | 0 | M304-STK-U1-006 | 2026-05-04 | 1 | 3438.66 | 2026-05-08 | 1 | 3438.66 | Truong An | M304-057
56 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 | Shipping Frame | 2026-03-27 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-1 | SFR-CV-1 | (6267x98x2941) | 4 | 128.46 | 513.84 | [14 empty] | 513.84 | 0 |  | 100% | 513.84 | 2026-04-28 | 4 | 513.84 | 2026-04-28 | 4 | 513.84 |  |  | 0 |  | 2026-04-28 | 4 | 513.84 | 2026-04-28 | 4 | 513.84 | Truong An | M304-Theo Stack
57 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 | Shipping Frame | 2026-03-27 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-2 | SFR-CV-2 | (5606x95x1723) | 4 | 103.68 | 414.72 | [14 empty] | 414.72 | 0 |  | 100% | 414.72 | 2026-04-28 | 4 | 414.72 | 2026-04-28 | 4 | 414.72 |  |  | 0 |  | 2026-04-28 | 4 | 414.72 | 2026-04-28 | 4 | 414.72 | Truong An | M304-Theo Stack
58 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 | Shipping Frame | 2026-03-27 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-4 | SFR-CV-4 | (4587x98x1006) | 2 | 46.43 | 92.86 | [14 empty] | 92.86 | 0 |  | 100% | 92.86 | 2026-04-28 | 2 | 92.86 | 2026-04-28 | 2 | 92.86 |  |  | 0 |  | 2026-04-28 | 2 | 92.86 | 2026-04-28 | 2 | 92.86 | Truong An | M304-Theo Stack
59 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 | Shipping Frame | 2026-03-27 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-5 | SFR-CV-5 | (6147x98x2520) | 4 | 121.9 | 487.6 | [14 empty] | 487.6 | 0 |  | 100% | 487.6 | 2026-04-28 | 4 | 487.6 | 2026-04-28 | 4 | 487.6 |  |  | 0 |  | 2026-04-28 | 4 | 487.6 | 2026-04-28 | 4 | 487.6 | Truong An | M304-Theo Stack
60 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 | Shipping Frame | 2026-03-27 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-9 | SFR-CV-9 | (2999x85x386) | 8 | 17.24 | 137.92 | [14 empty] | 137.92 | 0 |  | 100% | 137.92 | 2026-04-28 | 8 | 137.92 | 2026-04-28 | 8 | 137.92 |  |  | 0 |  | 2026-04-28 | 8 | 137.92 | 2026-04-28 | 8 | 137.92 | Truong An | M304-Theo Stack
61 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 | Shipping Frame | 2026-03-27 | HRSG | HSG07 | S4 | M304-AS-SFR-LUG-1 | SFR-LUG-1 | (300x250x350) | 30 | 36.32 | 1089.6 | [14 empty] | 1089.6 | 0 |  | 100% | 1089.6 | 2026-04-28 | 30 | 1089.6 | 2026-04-28 | 30 | 1089.6 |  |  | 0 |  | 2026-04-28 | 30 | 1089.6 | 2026-04-28 | 30 | 1089.6 | Truong An | M304-Theo Stack
61 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG12 | S2 | 25HG001-312-DD0-0S0102 | BD01 | BREECH DUCT | 1 | 5014.5 | 5014.5 | [14 empty] | 5014.5 | 0 |  | 100% | 5014.5 | 2026-04-15 | 1 | 5014.5 | 2026-04-20 | 1 | 5014.5 |  |  | 0 | M304-STK-U1-004 | 2026-05-02 | 1 | 5014.5 | 2026-05-04 | 1 | 5014.5 | Truong An | M304-054
61 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG12 | S1 | 25HG001-312-DD0-0S0104 | BD02 | BREECH DUCT | 1 | 4538.2 | 4538.2 | [14 empty] | 4538.2 | 0 |  | 100% | 4538.2 | 2026-04-15 | 1 | 4538.2 | 2026-04-25 | 1 | 4538.2 |  |  | 0 | M304-STK-U1-007 | 2026-05-03 | 1 | 4538.2 | 2026-05-08 | 1 | 4538.2 | Truong An | M304-055
62 | M304 | Shipment 1 Main Stack U1 | Shipment 1 | Main Stack U1 |  | 2026-03-27 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0106 | BD03 | BREECH DUCT | 1 | 5014.5 | 5014.5 | [14 empty] | 5014.5 | 0 |  | 100% | 5014.5 | 2026-04-16 | 1 | 5014.5 | 2026-04-21 | 1 | 5014.5 |  |  | 0 | M304-STK-U1-005 | 2026-05-04 | 1 | 5014.5 | 2026-05-08 | 1 | 5014.5 | Truong An | M304-056
63 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01A | SHELL | 1 | 6446.78 | 6446.78 | (2950 x 3418 x 6836) | [13 empty] | 6446.78 | 0 |  | 100% | 6446.78 | 2026-05-15 | 1 | 6446.78 | 2026-05-23 | 1 | 6446.78 |  |  | 0 | M304-STK-U2-012 | 2026-06-27 | 1 | 6446.78 | 2026-06-30 | 1 | 6446.78 | PAC | M304-125
64 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01B | SHELL | 1 | 6668.184 | 6668.184 | (2950 x 3418 x 6836) | [13 empty] | 6668.184 | 0 |  | 100% | 6668.184 | 2026-05-22 | 1 | 6668.184 | 2026-05-26 | 1 | 6668.184 |  |  | 0 | M304-STK-U2-012 | 2026-06-27 | 1 | 6668.184 | 2026-06-30 | 1 | 6668.184 | PAC | M304-125
65 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0006 | SH02A | SHELL | 1 | 5402.1 | 5402.1 | (2815 x 3468 x 6716) | [13 empty] | 5402.1 | 0 |  | 100% | 5402.1 | 2026-05-21 | 1 | 5402.1 | 2026-05-28 | 1 | 5402.1 |  |  | 0 | M304-STK-U2-001 | 2026-06-05 | 1 | 5402.1 | 2026-06-15 | 1 | 5402.1 | Truong An | M304-095
66 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0006 | SH02B | SHELL | 1 | 4496.3 | 4496.3 | (2815 x 3358 x 6716) | [13 empty] | 4496.3 | 0 |  | 100% | 4496.3 | 2026-05-23 | 1 | 4496.3 | 2026-06-01 | 1 | 4496.3 |  |  | 0 | M304-STK-U2-001 | 2026-06-05 | 1 | 4496.3 | 2026-06-15 | 1 | 4496.3 | Truong An | M304-095
67 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0008 | SH03A | SHELL | 1 | 4238.315 | 4238.315 | (3091 x 3097 x 6719) | [13 empty] | 4238.315 | 0 |  | 100% | 4238.315 | 2026-06-01 | 1 | 4238.315 | 2026-06-06 | 1 | 4238.315 |  |  | 0 | M304-STK-U2-006 | 2026-06-10 | 1 | 4238.315 | 2026-06-15 | 1 | 4238.315 | Truong An | M304-101
68 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0008 | SH03B | SHELL | 1 | 2935.855 | 2935.855 | (1598 x 3097 x 5513) | [13 empty] | 2935.855 | 0 |  | 100% | 2935.855 | 2026-06-02 | 1 | 2935.855 | 2026-06-09 | 1 | 2935.855 |  |  | 0 | M304-STK-U2-006 | 2026-06-10 | 1 | 2935.855 | 2026-06-15 | 1 | 2935.855 | Truong An | M304-101
69 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0010 | SH04A | SHELL | 1 | 3928.65 | 3928.65 | (2420 x 2907 x 6474) | [13 empty] | 3928.65 | 0 |  | 100% | 3928.65 | 2026-06-09 | 1 | 3928.65 | 2026-06-13 | 1 | 3928.65 |  |  | 0 | M304-STK-U2-009 | 2026-06-16 | 1 | 3928.65 | 2026-06-18 | 1 | 3928.65 | AMC GT-HTP | M304-109
70 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0010 | SH04B | SHELL | 1 | 3930.05 | 3930.05 | (2420 x 2907 x 6474) | [13 empty] | 3930.05 | 0 |  | 100% | 3930.05 | 2026-06-12 | 1 | 3930.05 | 2026-06-15 | 1 | 3930.05 |  |  | 0 | M304-STK-U2-009 | 2026-06-16 | 1 | 3930.05 | 2026-06-18 | 1 | 3930.05 | AMC GT-HTP | M304-109
71 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05A | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  | 100% | 2112.37 | 2026-06-04 | 1 | 2112.37 | 2026-06-08 | 1 | 2112.37 |  |  | 0 | M304-STK-U2-007 | 2026-06-13 | 1 | 2112.37 | 2026-06-17 | 1 | 2112.37 | AMC GT-HTP | M304-105
72 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05B | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  | 100% | 2112.37 | 2026-06-06 | 1 | 2112.37 | 2026-06-10 | 1 | 2112.37 |  |  | 0 | M304-STK-U2-007 | 2026-06-13 | 1 | 2112.37 | 2026-06-17 | 1 | 2112.37 | AMC GT-HTP | M304-105
73 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06A | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  | 100% | 1940.67 | 2026-05-21 | 1 | 1940.67 | 2026-05-21 | 1 | 1940.67 |  |  | 0 | M304-STK-U2-003 | 2026-06-07 | 1 | 1940.67 | 2026-06-11 | 1 | 1940.67 | Truong An | M304-097
74 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06B | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  | 100% | 1940.67 | 2026-05-21 | 1 | 1940.67 | 2026-05-21 | 1 | 1940.67 |  |  | 0 | M304-STK-U2-003 | 2026-06-07 | 1 | 1940.67 | 2026-06-11 | 1 | 1940.67 | Truong An | M304-097
75 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07A | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  | 100% | 1939.36 | 2026-05-21 | 1 | 1939.36 | 2026-05-21 | 1 | 1939.36 |  |  | 0 | M304-STK-U2-004 | 2026-06-07 | 1 | 1939.36 | 2026-06-11 | 1 | 1939.36 | Truong An | M304-098
76 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07B | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  | 100% | 1939.36 | 2026-05-21 | 1 | 1939.36 | 2026-05-29 | 1 | 1939.36 |  |  | 0 | M304-STK-U2-004 | 2026-06-07 | 1 | 1939.36 | 2026-06-11 | 1 | 1939.36 | Truong An | M304-098
77 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-1 | SFR-CV-1 | (6267x98x2941) | 6 | 128.46 | 770.64 | [14 empty] | 770.64 | 0 |  | 100% | 770.64 | 2026-06-06 | 6 | 770.64 | 2026-06-07 | 6 | 770.64 |  |  | 0 |  | 2026-06-18 | 6 | 770.64 | 2026-06-18 | 6 | 770.64 | Truong An | M304-Theo Stack
78 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-3 | SFR-CV-3 | (6267x98x2916) | 2 | 127.98 | 255.97 | [14 empty] | 255.97 | 0 |  | 100% | 255.97 | 2026-06-06 | 2 | 255.97 | 2026-06-07 | 2 | 255.97 |  |  | 0 |  | 2026-06-18 | 2 | 255.97 | 2026-06-18 | 2 | 255.97 | Truong An | M304-Theo Stack
79 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-5 | SFR-CV-5 | (6147x98x2520) | 2 | 121.9 | 243.72 | [14 empty] | 243.72 | 0 |  | 100% | 243.72 | 2026-06-06 | 2 | 243.72 | 2026-06-07 | 2 | 243.72 |  |  | 0 |  | 2026-06-18 | 2 | 243.72 | 2026-06-18 | 2 | 243.72 | Truong An | M304-Theo Stack
80 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-6 | SFR-CV-6 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 46.43 | 0 |  | 100% | 46.43 | 2026-06-06 | 1 | 46.43 | 2026-06-07 | 1 | 46.43 |  |  | 0 |  | 2026-06-18 | 1 | 46.43 | 2026-06-18 | 1 | 46.43 | Truong An | M304-Theo Stack
81 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-7 | SFR-CV-7 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 46.43 | 0 |  | 100% | 46.43 | 2026-06-06 | 1 | 46.43 | 2026-06-07 | 1 | 46.43 |  |  | 0 |  | 2026-06-18 | 1 | 46.43 | 2026-06-18 | 1 | 46.43 | Truong An | M304-Theo Stack
82 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-8 | SFR-CV-8 | (5596x95x1723) | 4 | 103.68 | 414.74 | [14 empty] | 414.74 | 0 |  | 100% | 414.74 | 2026-06-06 | 4 | 414.74 | 2026-06-07 | 4 | 414.74 |  |  | 0 |  | 2026-06-18 | 4 | 414.74 | 2026-06-18 | 4 | 414.74 | Truong An | M304-Theo Stack
83 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-9 | SFR-CV-9 | (2999x85x386) | 12 | 17.24 | 206.88 | [14 empty] | 206.88 | 0 |  | 100% | 206.88 | 2026-06-06 | 12 | 206.88 | 2026-06-07 | 12 | 206.88 |  |  | 0 |  | 2026-06-18 | 12 | 206.88 | 2026-06-18 | 12 | 206.88 | Truong An | M304-Theo Stack
84 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 | Shipping Frame | 2026-04-15 | HRSG | HSG07 | S4 | M304-AS-SFR-LUG-1 | SFR-LUG-1 | (300x250x350) | 42 | 36.32 | 1525.44 | [14 empty] | 1525.44 | 0 |  | 100% | 1525.44 | 2026-06-06 | 42 | 1525.44 | 2026-06-07 | 42 | 1525.44 |  |  | 0 |  | 2026-06-18 | 42 | 1525.44 | 2026-06-18 | 42 | 1525.44 | Truong An | M304-Theo Stack
84 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S2 | 25HG001-312-DD0-0S0108 | BD04 | BREECH DUCT | 1 | 4518.344 | 4518.344 | (1795 x 2762 x 11827) | [13 empty] | 4518.344 | 0 |  | 100% | 4518.344 | 2026-06-10 | 1 | 4518.344 | 2026-06-12 | 1 | 4518.344 |  |  | 0 | M304-STK-U2-010 | 2026-06-18 | 1 | 4518.344 | 2026-06-20 | 1 | 4518.344 | AMC GT-HTP | M304-115
84 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S3 | 25HG001-312-DD0-0S0110 | BD05 | BREECH DUCT | 1 | 2057.35 | 2057.35 | (706 x 2345 x 8616) | [13 empty] | 2057.35 | 0 |  | 100% | 2057.35 | 2026-06-08 | 1 | 2057.35 | 2026-06-10 | 1 | 2057.35 |  |  | 0 | M304-STK-U2-008 | 2026-06-15 | 1 | 2057.35 | 2026-06-17 | 1 | 2057.35 | AMC GT-HTP | M304-106
84 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S3 | 25HG001-312-DD0-0S0112 | BD06 | BREECH DUCT | 1 | 2078.65 | 2078.65 | (706 x 2345 x 8616) | [13 empty] | 2078.65 | 0 |  | 100% | 2078.65 | 2026-06-09 | 1 | 2078.65 | 2026-06-11 | 1 | 2078.65 |  |  | 0 | M304-STK-U2-008 | 2026-06-15 | 1 | 2078.65 | 2026-06-17 | 1 | 2078.65 | AMC GT-HTP | M304-106
85 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0113 | CC01 | CARBON CAPTURE | 1 | 1344.2 | 1344.2 | (404 x 1470 x 11750) | [13 empty] | 1344.2 | 0 |  | 100% | 1344.2 | 2026-06-08 | 1 | 1344.2 | 2026-06-12 | 1 | 1344.2 |  |  | 0 | M304-STK-U2-011 | 2026-06-20 | 1 | 1344.2 | 2026-06-24 | 1 | 1344.2 | AMC GT-HTP | M304-118
86 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0114 | CC02 | CARBON CAPTURE | 1 | 1344.2 | 1344.2 | (404 x 1470 x 11750) | [13 empty] | 1344.2 | 0 |  | 100% | 1344.2 | 2026-06-08 | 1 | 1344.2 | 2026-06-15 | 1 | 1344.2 |  |  | 0 | M304-STK-U2-011 | 2026-06-20 | 1 | 1344.2 | 2026-06-24 | 1 | 1344.2 | AMC GT-HTP | M304-118
87 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0116 | CC03 | CARBON CAPTURE | 1 | 549 | 549 | (281 x 1245 x 5554) | [13 empty] | 549 | 0 |  | 100% | 549 | 2026-06-13 | 1 | 549 | 2026-06-18 | 1 | 549 |  |  | 0 | M304-STK-U2-011 | 2026-06-20 | 1 | 549 | 2026-06-24 | 1 | 549 | AMC GT-HTP | M304-118
88 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0118 | CC04 | CARBON CAPTURE | 1 | 549 | 549 | (281 x 1245 x 5554) | [13 empty] | 549 | 0 |  | 100% | 549 | 2026-06-13 | 1 | 549 | 2026-06-18 | 1 | 549 |  |  | 0 | M304-STK-U2-011 | 2026-06-20 | 1 | 549 | 2026-06-24 | 1 | 549 | AMC GT-HTP | M304-118
89 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC05 | CARBON CAPTURE | 1 | 2090.9 | 2090.9 | (162 x 4132 x 5554) | [13 empty] | 2090.9 | 0 |  | 100% | 2090.9 | 2026-06-09 | 1 | 2090.9 | 2026-06-15 | 1 | 2090.9 |  |  | 0 | M304-STK-U2-015 | 2026-06-29 | 1 | 2090.9 | 2026-07-05 | 1 | 2090.9 | PAC | M304-126
90 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC06 | CARBON CAPTURE | 1 | 2005.6 | 2005.6 | (162 x 4000 x 5554) | [13 empty] | 2005.6 | 0 |  | 100% | 2005.6 | 2026-06-09 | 1 | 2005.6 | 2026-06-15 | 1 | 2005.6 |  |  | 0 | M304-STK-U2-015 | 2026-06-29 | 1 | 2005.6 | 2026-07-05 | 1 | 2005.6 | PAC | M304-126
91 | M304 | Shipment 3 Main Stack U2 | Shipment 3 | Main Stack U2 |  | 2026-04-15 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC07 | CARBON CAPTURE | 1 | 2014.7 | 2014.7 | (162 x 4132 x 5554) | [13 empty] | 2014.7 | 0 |  | 100% | 2014.7 | 2026-06-10 | 1 | 2014.7 | 2026-06-18 | 1 | 2014.7 |  |  | 0 | M304-STK-U2-015 | 2026-06-29 | 1 | 2014.7 | 2026-07-05 | 1 | 2014.7 | PAC | M304-126
92 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01A | SHELL | 1 | 6446.78 | 6446.78 | (2950 x 3418 x 6836) | [13 empty] | 6446.78 | 0 |  |  | 0 | 2026-06-11 | 1 | 6446.78 | 2026-06-17 | 1 | 6446.78 |  |  | 0 | M304-STK-U3-004 | 2026-07-30 | 1 | 6446.78 | 2026-08-01 | 1 | 6446.78 | Truong An | M304-134
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01B | SHELL | 1 | 6668.184 | 6668.184 | (2950 x 3418 x 6836) | [13 empty] | 6668.184 | 0 |  |  | 0 | 2026-06-17 | 1 | 6668.184 | 2026-06-19 | 1 | 6668.184 |  |  | 0 | M304-STK-U3-004 | 2026-07-30 | 1 | 6668.184 | 2026-08-01 | 1 | 6668.184 | Truong An | M304-134
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0006 | SH02A | SHELL | 1 | 5402.1 | 5402.1 | (2815 x 3468 x 6716) | [13 empty] | 5402.1 | 0 |  |  | 0 | 2026-07-06 | 1 | 5402.1 | 2026-07-21 | 1 | 5402.1 |  |  | 0 | M304-STK-U3-007 | 2026-07-30 | 1 | 5402.1 | 2026-07-31 | 1 | 5402.1 | Truong An | M304-135
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0006 | SH02B | SHELL | 1 | 4496.3 | 4496.3 | (2815 x 3358 x 6716) | [13 empty] | 4496.3 | 0 |  |  | 0 | 2026-07-07 | 1 | 4496.3 | 2026-07-26 | 1 | 4496.3 |  |  | 0 | M304-STK-U3-007 | 2026-07-30 | 1 | 4496.3 | 2026-07-31 | 1 | 4496.3 | Truong An | M304-135
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0008 | SH03A | SHELL | 1 | 4238.315 | 4238.315 | (3091 x 3097 x 6719) | [13 empty] | 4238.315 | 0 |  |  | 0 | 2026-07-02 | 1 | 4238.315 | 2026-07-09 | 1 | 4238.315 |  |  | 0 | M304-STK-U3-009 | 2026-08-05 | 1 | 4238.315 | 2026-08-08 | 1 | 4238.315 | Truong An | M304-140
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0008 | SH03B | SHELL | 1 | 2935.855 | 2935.855 | (1598 x 3097 x 5513) | [13 empty] | 2935.855 | 0 |  |  | 0 | 2026-07-28 | 1 | 2935.855 | 2026-07-31 | 1 | 2935.855 |  |  | 0 | M304-STK-U3-009 | 2026-08-05 | 1 | 2935.855 | 2026-08-08 | 1 | 2935.855 | Truong An | M304-140
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0010 | SH04A | SHELL | 1 | 3928.65 | 3928.65 | (2420 x 2907 x 6474) | [13 empty] | 3928.65 | 0 |  |  | 0 | 2026-06-24 | 1 | 3928.65 | 2026-07-07 | 1 | 3928.65 |  |  | 0 | M304-STK-U3-008 | 2026-08-07 | 1 | 3928.65 | 2026-08-08 | 1 | 3928.65 | AMC GT-HTP | M304-142
93 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0010 | SH04B | SHELL | 1 | 3930.05 | 3930.05 | (2420 x 2907 x 6474) | [13 empty] | 3930.05 | 0 |  |  | 0 | 2026-07-28 | 1 | 3930.05 | 2026-08-01 | 1 | 3930.05 |  |  | 0 | M304-STK-U3-008 | 2026-08-07 | 1 | 3930.05 | 2026-08-08 | 1 | 3930.05 | AMC GT-HTP | M304-142
94 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05A | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  |  | 0 | 2026-06-18 | 1 | 2112.37 | 2026-06-22 | 1 | 2112.37 |  |  | 0 | M304-STK-U3-001 | 2026-07-18 | 1 | 2112.37 | 2026-07-20 | 1 | 2112.37 | Truong An | M304-131
95 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05B | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  |  | 0 | 2026-06-18 | 1 | 2112.37 | 2026-07-10 | 1 | 2112.37 |  |  | 0 | M304-STK-U3-001 | 2026-07-18 | 1 | 2112.37 | 2026-07-20 | 1 | 2112.37 | Truong An | M304-131
96 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06A | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  |  | 0 | 2026-07-20 | 1 | 1940.67 | 2026-07-20 | 1 | 1940.67 |  |  | 0 | M304-STK-U3-002 | 2026-07-20 | 1 | 1940.67 | 2026-07-21 | 1 | 1940.67 | Truong An | M304-132
97 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06B | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  |  | 0 | 2026-06-23 | 1 | 1940.67 | 2026-07-20 | 1 | 1940.67 |  |  | 0 | M304-STK-U3-002 | 2026-07-20 | 1 | 1940.67 | 2026-07-21 | 1 | 1940.67 | Truong An | M304-132
98 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07A | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  |  | 0 | 2026-07-16 | 1 | 1939.36 | 2026-07-20 | 1 | 1939.36 |  |  | 0 | M304-STK-U3-002 | 2026-07-20 | 1 | 1939.36 | 2026-07-21 | 1 | 1939.36 | Truong An | M304-132
99 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 |  | 2026-05-05 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07B | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  |  | 0 | 2026-07-16 | 1 | 1939.36 | 2026-07-20 | 1 | 1939.36 |  |  | 0 | M304-STK-U3-002 | 2026-07-20 | 1 | 1939.36 | 2026-07-21 | 1 | 1939.36 | Truong An | M304-132
100 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-1 | SFR-CV-1 | (6267x98x2941) | 6 | 128.46 | 770.64 | [14 empty] | 770.64 | 0 |  |  | 0 | 2026-07-16 | 6 | 770.64 | 2026-07-16 | 6 | 770.64 |  |  | 0 |  | 2026-08-14 | 6 | 770.64 | 2026-08-14 | 6 | 770.64 | Truong An | M304-Theo Stack
101 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-3 | SFR-CV-3 | (6267x98x2916) | 2 | 127.98 | 255.97 | [14 empty] | 255.97 | 0 |  |  | 0 | 2026-07-16 | 2 | 255.97 | 2026-07-16 | 2 | 255.97 |  |  | 0 |  | 2026-08-14 | 2 | 255.97 | 2026-08-14 | 2 | 255.97 | Truong An | M304-Theo Stack
102 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-5 | SFR-CV-5 | (6147x98x2520) | 2 | 121.9 | 243.72 | [14 empty] | 243.72 | 0 |  |  | 0 | 2026-07-16 | 2 | 243.72 | 2026-07-16 | 2 | 243.72 |  |  | 0 |  | 2026-08-14 | 2 | 243.72 | 2026-08-14 | 2 | 243.72 | Truong An | M304-Theo Stack
103 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-6 | SFR-CV-6 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 46.43 | 0 |  |  | 0 | 2026-07-16 | 1 | 46.43 | 2026-07-16 | 1 | 46.43 |  |  | 0 |  | 2026-08-14 | 1 | 46.43 | 2026-08-14 | 1 | 46.43 | Truong An | M304-Theo Stack
104 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-7 | SFR-CV-7 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 46.43 | 0 |  |  | 0 | 2026-07-16 | 1 | 46.43 | 2026-07-16 | 1 | 46.43 |  |  | 0 |  | 2026-08-14 | 1 | 46.43 | 2026-08-14 | 1 | 46.43 | Truong An | M304-Theo Stack
105 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-8 | SFR-CV-8 | (5596x95x1723) | 4 | 103.68 | 414.74 | [14 empty] | 414.74 | 0 |  |  | 0 | 2026-07-16 | 4 | 414.74 | 2026-07-16 | 4 | 414.74 |  |  | 0 |  | 2026-08-14 | 4 | 414.74 | 2026-08-14 | 4 | 414.74 | Truong An | M304-Theo Stack
106 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-9 | SFR-CV-9 | (2999x85x386) | 12 | 17.24 | 206.88 | [14 empty] | 206.88 | 0 |  |  | 0 | 2026-07-16 | 12 | 206.88 | 2026-07-16 | 12 | 206.88 |  |  | 0 |  | 2026-08-14 | 12 | 206.88 | 2026-08-14 | 12 | 206.88 | Truong An | M304-Theo Stack
107 | M304 | Shipment 5 Main Stack U3 | Shipment 5 | Main Stack U3 | Shipping Frame | 2026-05-05 | HRSG | HSG07 | S4 | M304-AS-SFR-LUG-1 | SFR-LUG-1 | (300x250x350) | 42 | 36.32 | 1525.44 | [14 empty] | 1525.44 | 0 |  |  | 0 | 2026-07-16 | 42 | 1525.44 | 2026-07-16 | 42 | 1525.44 |  |  | 0 |  | 2026-08-14 | 42 | 1525.44 | 2026-08-14 | 42 | 1525.44 | Truong An | M304-Theo Stack
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0003 | SH01A | SHELL | 1 | 6446.78 | 6446.78 | (2950 x 3418 x 6836) | [13 empty] | 6446.78 | 0 |  |  | 0 | 2026-08-15 | 1 | 6446.78 | 2026-08-18 | 1 | 6446.78 |  |  | 0 | M304-STK-U4-018 | 2026-09-09 | 1 | 6446.78 | 2026-09-11 | 1 | 6446.78 | Truong An | M304-177
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0003 | SH01B | SHELL | 1 | 6668.184 | 6668.184 | (2950 x 3418 x 6836) | [13 empty] | 6668.184 | 0 |  |  | 0 | 2026-08-15 | 1 | 6668.184 | 2026-08-21 | 1 | 6668.184 |  |  | 0 | M304-STK-U4-018 | 2026-09-09 | 1 | 6668.184 | 2026-09-11 | 1 | 6668.184 | Truong An | M304-177
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0006 | SH02A | SHELL | 1 | 5402.1 | 5402.1 | (2815 x 3468 x 6716) | [13 empty] | 5402.1 | 0 |  |  | 0 | 2026-08-17 | 1 | 5402.1 | 2026-08-20 | 1 | 5402.1 |  |  | 0 | M304-STK-U4-008 | 2026-09-03 | 1 | 5402.1 | 2026-09-05 | 1 | 5402.1 | Truong An | M304-168
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0006 | SH02B | SHELL | 1 | 4496.3 | 4496.3 | (2815 x 3358 x 6716) | [13 empty] | 4496.3 | 0 |  |  | 0 | 2026-08-20 | 1 | 4496.3 | 2026-08-23 | 1 | 4496.3 |  |  | 0 | M304-STK-U4-008 | 2026-09-03 | 1 | 4496.3 | 2026-09-05 | 1 | 4496.3 | Truong An | M304-168
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0008 | SH03A | SHELL | 1 | 4238.315 | 4238.315 | (3091 x 3097 x 6719) | [13 empty] | 4238.315 | 0 |  |  | 0 | 2026-08-21 | 1 | 4238.315 | 2026-08-29 | 1 | 4238.315 |  |  | 0 | M304-STK-U4-018 | 2026-09-09 | 1 | 4238.315 | 2026-09-11 | 1 | 4238.315 | Truong An | M304-177
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0008 | SH03B | SHELL | 1 | 2935.855 | 2935.855 | (1598 x 3097 x 5513) | [13 empty] | 2935.855 | 0 |  |  | 0 | 2026-08-25 | 1 | 2935.855 | 2026-09-02 | 1 | 2935.855 |  |  | 0 | M304-STK-U4-018 | 2026-09-09 | 1 | 2935.855 | 2026-09-11 | 1 | 2935.855 | Truong An | M304-177
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0010 | SH04A | SHELL | 1 | 3928.65 | 3928.65 | (2420 x 2907 x 6474) | [13 empty] | 3928.65 | 0 |  |  | 0 | 2026-08-31 | 1 | 3928.65 | 2026-09-09 | 1 | 3928.65 |  |  | 0 | M304-STK-U4-023 | 2026-09-12 | 1 | 3928.65 | 2026-09-13 | 1 | 3928.65 | Truong An | M304-179
107 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S1 | 25HG001-312-DD0-0S0010 | SH04B | SHELL | 1 | 3930.05 | 3930.05 | (2420 x 2907 x 6474) | [13 empty] | 3930.05 | 0 |  |  | 0 | 2026-09-03 | 1 | 3930.05 | 2026-09-09 | 1 | 3930.05 |  |  | 0 | M304-STK-U4-023 | 2026-09-12 | 1 | 3930.05 | 2026-09-13 | 1 | 3930.05 | Truong An | M304-179
108 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05A | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  |  | 0 | 2026-07-31 | 1 | 2112.37 | 2026-08-04 | 1 | 2112.37 |  |  | 0 | M304-STK-U4-006 | 2026-08-21 | 1 | 2112.37 | 2026-08-22 | 1 | 2112.37 | Truong An | M304-163
109 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05B | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  |  | 0 | 2026-07-31 | 1 | 2112.37 | 2026-08-05 | 1 | 2112.37 |  |  | 0 | M304-STK-U4-006 | 2026-08-21 | 1 | 2112.37 | 2026-08-22 | 1 | 2112.37 | Truong An | M304-163
110 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06A | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  |  | 0 | 2026-08-08 | 1 | 1940.67 | 2026-08-14 | 1 | 1940.67 |  |  | 0 | M304-STK-U4-001 | 2026-08-14 | 1 | 1940.67 | 2026-08-16 | 1 | 1940.67 | Truong An | M304-157
111 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06B | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  |  | 0 | 2026-08-14 | 1 | 1940.67 | 2026-08-14 | 1 | 1940.67 |  |  | 0 | M304-STK-U4-001 | 2026-08-14 | 1 | 1940.67 | 2026-08-16 | 1 | 1940.67 | Truong An | M304-157
112 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07A | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  |  | 0 | 2026-08-14 | 1 | 1939.36 | 2026-08-14 | 1 | 1939.36 |  |  | 0 | M304-STK-U4-001 | 2026-08-14 | 1 | 1939.36 | 2026-08-16 | 1 | 1939.36 | Truong An | M304-157
113 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07B | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  |  | 0 | 2026-08-20 | 1 | 1939.36 | 2026-08-20 | 1 | 1939.36 |  |  | 0 | M304-STK-U4-005 | 2026-08-20 | 1 | 1939.36 | 2026-08-22 | 1 | 1939.36 | Truong An | M304-163
114 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-1 | SFR-CV-1 | (6267x98x2941) | 6 | 128.46 | 770.64 | [14 empty] | 770.64 | 0 |  |  | 0 | 2026-08-21 | 6 | 770.64 | 2026-08-31 | 6 | 770.64 |  |  | 0 |  | 2026-09-10 | 6 | 770.64 | 2026-09-10 | 6 | 770.64 | Truong An | M304-Theo Stack
115 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-3 | SFR-CV-3 | (6267x98x2916) | 2 | 127.98 | 255.97 | [14 empty] | 255.97 | 0 |  |  | 0 | 2026-08-21 | 2 | 255.97 | 2026-08-31 | 2 | 255.97 |  |  | 0 |  | 2026-09-10 | 2 | 255.97 | 2026-09-10 | 2 | 255.97 | Truong An | M304-Theo Stack
116 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-5 | SFR-CV-5 | (6147x98x2520) | 2 | 121.9 | 243.72 | [14 empty] | 243.72 | 0 |  |  | 0 | 2026-08-21 | 2 | 243.72 | 2026-08-31 | 2 | 243.72 |  |  | 0 |  | 2026-09-10 | 2 | 243.72 | 2026-09-10 | 2 | 243.72 | Truong An | M304-Theo Stack
117 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-6 | SFR-CV-6 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 46.43 | 0 |  |  | 0 | 2026-08-21 | 1 | 46.43 | 2026-08-31 | 1 | 46.43 |  |  | 0 |  | 2026-09-10 | 1 | 46.43 | 2026-09-10 | 1 | 46.43 | Truong An | M304-Theo Stack
118 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-7 | SFR-CV-7 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 46.43 | 0 |  |  | 0 | 2026-08-21 | 1 | 46.43 | 2026-08-31 | 1 | 46.43 |  |  | 0 |  | 2026-09-10 | 1 | 46.43 | 2026-09-10 | 1 | 46.43 | Truong An | M304-Theo Stack
119 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-8 | SFR-CV-8 | (5596x95x1723) | 4 | 103.68 | 414.74 | [14 empty] | 414.74 | 0 |  |  | 0 | 2026-08-21 | 4 | 414.74 | 2026-08-31 | 4 | 414.74 |  |  | 0 |  | 2026-09-10 | 4 | 414.74 | 2026-09-10 | 4 | 414.74 | Truong An | M304-Theo Stack
120 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-9 | SFR-CV-9 | (2999x85x386) | 12 | 17.24 | 206.88 | [14 empty] | 206.88 | 0 |  |  | 0 | 2026-08-21 | 12 | 206.88 | 2026-08-31 | 12 | 206.88 |  |  | 0 |  | 2026-09-10 | 12 | 206.88 | 2026-09-10 | 12 | 206.88 | Truong An | M304-Theo Stack
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 | Shipping Frame | 2026-05-26 | HRSG | HSG07 | S4 | M304-AS-SFR-LUG-1 | SFR-LUG-1 | (300x250x350) | 42 | 36.32 | 1525.44 | [14 empty] | 1525.44 | 0 |  |  | 0 | 2026-08-21 | 42 | 1525.44 | 2026-08-31 | 42 | 1525.44 |  |  | 0 |  | 2026-09-10 | 42 | 1525.44 | 2026-09-10 | 42 | 1525.44 | Truong An | M304-Theo Stack
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S2 | 25HG001-312-DD0-0S0102 | BD01 | BREECH DUCT | 1 | 5014.5 | 5014.5 | (1795 x 2762 x 13577) | [13 empty] | 5014.5 | 0 |  |  | 0 | 2026-08-29 | 1 | 5014.5 | 2026-08-31 | 1 | 5014.5 |  |  | 0 | M304-STK-U4-024 | 2026-09-11 | 1 | 5014.5 | 2026-09-13 | 1 | 5014.5 | Truong An | M304-178
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S2 | 25HG001-312-DD0-0S0104 | BD02 | BREECH DUCT | 1 | 4538.444 | 4538.444 | (1795 x 2762 x 11827) | [13 empty] | 4538.444 | 0 |  |  | 0 | 2026-09-01 | 1 | 4538.444 | 2026-09-05 | 1 | 4538.444 |  |  | 0 | M304-STK-U4-025 | 2026-09-16 | 1 | 4538.444 | 2026-09-17 | 1 | 4538.444 | Truong An | M304-180
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S2 | 25HG001-312-DD0-0S0106 | BD03 | BREECH DUCT | 1 | 5014.5 | 5014.5 | (1795 x 2762 x 13577) | [13 empty] | 5014.5 | 0 |  |  | 0 | 2026-09-04 | 1 | 5014.5 | 2026-09-08 | 1 | 5014.5 |  |  | 0 | M304-STK-U4-024 | 2026-09-11 | 1 | 5014.5 | 2026-09-13 | 1 | 5014.5 | Truong An | M304-178
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S3 | 25HG001-312-DD0-0S0108 | BD04 | BREECH DUCT | 1 | 4518.344 | 4518.344 | (1795 x 2762 x 11827) | [13 empty] | 4518.344 | 0 |  |  | 0 | 2026-08-23 | 1 | 4518.344 | 2026-08-26 | 1 | 4518.344 |  |  | 0 | M304-STK-U4-026 | 2026-09-18 | 1 | 4518.344 |  |  | 0 | Truong An
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S3 | 25HG001-312-DD0-0S0110 | BD05 | BREECH DUCT | 1 | 2057.35 | 2057.35 | (706 x 2345 x 8616) | [13 empty] | 2057.35 | 0 |  |  | 0 | 2026-08-24 | 1 | 2057.35 | 2026-09-05 | 1 | 2057.35 |  |  | 0 | M304-STK-U4-001-1 | 2026-08-07 | 1 | 2057.35 | 2026-09-08 | 1 | 2057.35 | Truong An | M304-KO SỐ
121 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S3 | 25HG001-312-DD0-0S0112 | BD06 | BREECH DUCT | 1 | 2078.65 | 2078.65 | (706 x 2345 x 8616) | [13 empty] | 2078.65 | 0 |  |  | 0 | 2026-08-31 | 1 | 2078.65 | 2026-09-06 | 1 | 2078.65 |  |  | 0 | M304-STK-U4-001-1 | 2026-08-07 | 1 | 2078.65 | 2026-09-08 | 1 | 2078.65 | Truong An | M304-KO SỐ
122 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0113 | CC01 | CARBON CAPTURE | 1 | 1344.2 | 1344.2 | (404 x 1470 x 11750) | [13 empty] | 1344.2 | 0 |  |  | 0 | 2026-08-25 | 1 | 1344.2 | 2026-08-31 | 1 | 1344.2 |  |  | 0 | M304-STK-U4-017 | 2026-09-09 | 1 | 1344.2 | 2026-09-11 | 1 | 1344.2 | Truong An | M304-176
123 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0114 | CC02 | CARBON CAPTURE | 1 | 1344.2 | 1344.2 | (404 x 1470 x 11750) | [13 empty] | 1344.2 | 0 |  |  | 0 | 2026-08-26 | 1 | 1344.2 | 2026-09-08 | 1 | 1344.2 |  |  | 0 | M304-STK-U4-017 | 2026-09-09 | 1 | 1344.2 | 2026-09-11 | 1 | 1344.2 | Truong An | M304-176
124 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0116 | CC03 | CARBON CAPTURE | 1 | 549 | 549 | (281 x 1245 x 5554) | [13 empty] | 549 | 0 |  |  | 0 | 2026-08-23 | 1 | 549 | 2026-09-08 | 1 | 549 |  |  | 0 | M304-STK-U4-017 | 2026-09-09 | 1 | 549 | 2026-09-11 | 1 | 549 | Truong An | M304-176
125 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0118 | CC04 | CARBON CAPTURE | 1 | 549 | 549 | (281 x 1245 x 5554) | [13 empty] | 549 | 0 |  |  | 0 | 2026-08-24 | 1 | 549 | 2026-09-08 | 1 | 549 |  |  | 0 | M304-STK-U4-017 | 2026-09-09 | 1 | 549 | 2026-09-11 | 1 | 549 | Truong An | M304-176
126 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC05 | CARBON CAPTURE | 1 | 2090.9 | 2090.9 | (162 x 4132 x 5554) | [13 empty] | 2090.9 | 0 |  |  | 0 | 2026-09-04 | 1 | 2090.9 | 2026-09-05 | 1 | 2090.9 |  |  | 0 | M304-STK-U4-011 | 2026-09-05 | 1 | 2090.9 | 2026-09-09 | 1 | 2090.9 | Truong An | M304-170
127 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC06 | CARBON CAPTURE | 1 | 2005.6 | 2005.6 | (162 x 4000 x 5554) | [13 empty] | 2005.6 | 0 |  |  | 0 | 2026-09-01 | 1 | 2005.6 | 2026-09-05 | 1 | 2005.6 |  |  | 0 | M304-STK-U4-015 | 2026-09-08 | 1 | 2005.6 | 2026-09-09 | 1 | 2005.6 | Truong An | M304-171
128 | M304 | Shipment 6 Main Stack U4 | Shipment 6 | Main Stack U4 |  | 2026-05-26 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC07 | CARBON CAPTURE | 1 | 2014.7 | 2014.7 | (162 x 4132 x 5554) | [13 empty] | 2014.7 | 0 |  |  | 0 | 2026-09-02 | 1 | 2014.7 | 2026-09-05 | 1 | 2014.7 |  |  | 0 | M304-STK-U4-015 | 2026-09-08 | 1 | 2014.7 | 2026-09-09 | 1 | 2014.7 | Truong An | M304-171
129 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01A | SHELL | 1 | 6446.78 | 6446.78 | (2950 x 3418 x 6836) | [13 empty] | 3223.39 | 3223.39 |  |  | 0 | 2026-10-05 | 1 | 6446.78 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
130 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01B | SHELL | 1 | 6668.184 | 6668.184 | (2950 x 3418 x 6836) | [13 empty] | 3334.092 | 3334.092 |  |  | 0 | 2026-10-06 | 1 | 6668.184 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
131 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0006 | SH02A | SHELL | 1 | 5402.1 | 5402.1 | (2815 x 3468 x 6716) | [13 empty] | 4861.89 | 540.21 |  |  | 0 | 2026-09-18 | 1 | 5402.1 | 2026-09-23 | 1 | 5402.1 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
132 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0006 | SH02B | SHELL | 1 | 4496.3 | 4496.3 | (2815 x 3358 x 6716) | [13 empty] | 4046.67 | 449.63 |  |  | 0 | 2026-09-18 | 1 | 4496.3 | 2026-09-30 | 1 | 4496.3 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
133 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0008 | SH03A | SHELL | 1 | 4238.315 | 4238.315 | (3091 x 3097 x 6719) | [13 empty] | 3814.4835 | 423.8315 |  |  | 0 | 2026-09-19 | 1 | 4238.315 | 2026-10-03 | 1 | 4238.315 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
134 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0008 | SH03B | SHELL | 1 | 2935.855 | 2935.855 | (1598 x 3097 x 5513) | [13 empty] | 2642.2695 | 293.5855 |  |  | 0 | 2026-09-22 | 1 | 2935.855 | 2026-10-03 | 1 | 2935.855 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
135 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0010 | SH04A | SHELL | 1 | 3928.65 | 3928.65 | (2420 x 2907 x 6474) | [13 empty] | 3928.65 | 0 |  |  | 0 | 2026-09-05 | 1 | 3928.65 | 2026-09-10 | 1 | 3928.65 |  |  | 0 | M304-STK-U5-003 | 2026-09-20 | 1 | 3928.65 | 2026-09-29 | 1 | 3928.65 | Truong An | M304-184
136 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0010 | SH04B | SHELL | 1 | 3930.05 | 3930.05 | (2420 x 2907 x 6474) | [13 empty] | 3930.05 | 0 |  |  | 0 | 2026-09-09 | 1 | 3930.05 | 2026-09-16 | 1 | 3930.05 |  |  | 0 | M304-STK-U5-003 | 2026-09-20 | 1 | 3930.05 | 2026-09-29 | 1 | 3930.05 | Truong An | M304-184
137 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05A | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  |  | 0 | 2026-09-09 | 1 | 2112.37 | 2026-09-16 | 1 | 2112.37 |  |  | 0 | M304-STK-U5-002 | 2026-09-19 | 1 | 2112.37 | 2026-09-24 | 1 | 2112.37 | Truong An | M304-183
138 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05B | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 2112.37 | 0 |  |  | 0 | 2026-09-09 | 1 | 2112.37 | 2026-09-16 | 1 | 2112.37 |  |  | 0 | M304-STK-U5-002 | 2026-09-19 | 1 | 2112.37 | 2026-09-24 | 1 | 2112.37 | Truong An | M304-183
139 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06A | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  |  | 0 | 2026-09-14 | 1 | 1940.67 | 2026-09-16 | 1 | 1940.67 |  |  | 0 | M304-STK-U5-001 | 2026-09-16 | 1 | 1940.67 | 2026-09-24 | 1 | 1940.67 | Truong An | M304-181
140 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06B | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1940.67 | 0 |  |  | 0 | 2026-09-14 | 1 | 1940.67 | 2026-09-23 | 1 | 1940.67 |  |  | 0 | M304-STK-U5-004 | 2026-09-23 | 1 | 1940.67 | 2026-09-24 | 1 | 1940.67 | Truong An | M304-186
141 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07A | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  |  | 0 | 2026-09-12 | 1 | 1939.36 | 2026-09-23 | 1 | 1939.36 |  |  | 0 | M304-STK-U5-005 | 2026-09-23 | 1 | 1939.36 | 2026-09-24 | 1 | 1939.36 | Truong An | M304-186
142 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 |  | 2026-06-15 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07B | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 1939.36 | 0 |  |  | 0 | 2026-09-12 | 1 | 1939.36 | 2026-09-16 | 1 | 1939.36 |  |  | 0 | M304-STK-U5-001 | 2026-09-16 | 1 | 1939.36 | 2026-09-24 | 1 | 1939.36 | Truong An | M304-181
143 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-1 | SFR-CV-1 | (6267x98x2941) | 6 | 128.46 | 770.64 | [14 empty] | 693.576 | 77.064 |  |  | 0 | 2026-09-16 | 6 | 770.64 | 2026-09-22 | 6 | 770.64 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
144 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-3 | SFR-CV-3 | (6267x98x2916) | 2 | 127.98 | 255.97 | [14 empty] | 230.373 | 25.597 |  |  | 0 | 2026-09-16 | 2 | 255.97 | 2026-09-22 | 2 | 255.97 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
145 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-5 | SFR-CV-5 | (6147x98x2520) | 2 | 121.9 | 243.72 | [14 empty] | 219.348 | 24.372 |  |  | 0 | 2026-09-16 | 2 | 243.72 | 2026-09-22 | 2 | 243.72 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
146 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-6 | SFR-CV-6 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 41.787 | 4.643 |  |  | 0 | 2026-09-16 | 1 | 46.43 | 2026-09-22 | 1 | 46.43 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
147 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-7 | SFR-CV-7 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 41.787 | 4.643 |  |  | 0 | 2026-09-16 | 1 | 46.43 | 2026-09-22 | 1 | 46.43 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
148 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-8 | SFR-CV-8 | (5596x95x1723) | 4 | 103.68 | 414.74 | [14 empty] | 373.266 | 41.474 |  |  | 0 | 2026-09-16 | 4 | 414.74 | 2026-09-22 | 4 | 414.74 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
149 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-9 | SFR-CV-9 | (2999x85x386) | 12 | 17.24 | 206.88 | [14 empty] | 186.192 | 20.688 |  |  | 0 | 2026-09-16 | 12 | 206.88 | 2026-09-22 | 12 | 206.88 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
150 | M304 | Shipment 7 Main Stack U5 | Shipment 7 | Main Stack U5 | Shipping Frame | 2026-06-15 | HRSG | HSG07 | S4 | M304-AS-SFR-LUG-1 | SFR-LUG-1 | (300x250x350) | 42 | 36.32 | 1525.44 | [14 empty] | 1372.896 | 152.544 |  |  | 0 | 2026-09-16 | 42 | 1525.44 | 2026-09-22 | 42 | 1525.44 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
151 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01A | SHELL | 1 | 6446.78 | 6446.78 | (2950 x 3418 x 6836) | [13 empty] | 0 | 6446.78 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
152 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0003 | SH01B | SHELL | 1 | 6668.184 | 6668.184 | (2950 x 3418 x 6836) | [13 empty] | 0 | 6668.184 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
153 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0006 | SH02A | SHELL | 1 | 5402.1 | 5402.1 | (2815 x 3468 x 6716) | [13 empty] | 0 | 5402.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
154 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0006 | SH02B | SHELL | 1 | 4496.3 | 4496.3 | (2815 x 3358 x 6716) | [13 empty] | 0 | 4496.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
155 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0008 | SH03A | SHELL | 1 | 4238.315 | 4238.315 | (3091 x 3097 x 6719) | [13 empty] | 0 | 4238.315 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
156 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0008 | SH03B | SHELL | 1 | 2935.855 | 2935.855 | (1598 x 3097 x 5513) | [13 empty] | 0 | 2935.855 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
157 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0010 | SH04A | SHELL | 1 | 3928.65 | 3928.65 | (2420 x 2907 x 6474) | [13 empty] | 0 | 3928.65 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
158 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0010 | SH04B | SHELL | 1 | 3930.05 | 3930.05 | (2420 x 2907 x 6474) | [13 empty] | 0 | 3930.05 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
159 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05A | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 0 | 2112.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
160 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0011 | SH05B | SHELL | 1 | 2112.37 | 2112.37 | (1060 x 3747 x 4640) | [13 empty] | 0 | 2112.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
161 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06A | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1746.603 | 194.067 |  |  | 0 | 2026-07-24 | 1 | 1940.67 | 2026-08-03 | 1 | 1940.67 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
162 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0012 | SH06B | SHELL | 1 | 1940.67 | 1940.67 | (1059 x 3997 x 4640) | [13 empty] | 1746.603 | 194.067 |  |  | 0 | 2026-07-24 | 1 | 1940.67 | 2026-10-03 | 1 | 1940.67 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
163 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07A | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 0 | 1939.36 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
164 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG07 | S4 | 25HG001-312-DD0-0S0013 | SH07B | SHELL | 1 | 1939.36 | 1939.36 | (1059 x 3997 x 4640) | [13 empty] | 0 | 1939.36 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
165 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-1 | SFR-CV-1 | (6267x98x2941) | 6 | 128.46 | 770.64 | [14 empty] | 0 | 770.64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
166 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-3 | SFR-CV-3 | (6267x98x2916) | 2 | 127.98 | 255.97 | [14 empty] | 0 | 255.97 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
167 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-5 | SFR-CV-5 | (6147x98x2520) | 2 | 121.9 | 243.72 | [14 empty] | 0 | 243.72 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
168 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-6 | SFR-CV-6 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 0 | 46.43 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
169 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-7 | SFR-CV-7 | (4587x83x1006) | 1 | 46.43 | 46.43 | [14 empty] | 0 | 46.43 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
170 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-8 | SFR-CV-8 | (5596x95x1723) | 4 | 103.68 | 414.74 | [14 empty] | 0 | 414.74 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
171 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-CV-9 | SFR-CV-9 | (2999x85x386) | 12 | 17.24 | 206.88 | [14 empty] | 0 | 206.88 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
172 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 | Shipping Frame | 2026-07-09 | HRSG | HSG07 | S4 | M304-AS-SFR-LUG-1 | SFR-LUG-1 | (300x250x350) | 42 | 36.32 | 1525.44 | [14 empty] | 0 | 1525.44 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
173 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0102 | BD01 | BREECH DUCT | 1 | 5014.5 | 5014.5 | (1795 x 2762 x 13577) | [13 empty] | 0 | 5014.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
174 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0104 | BD02 | BREECH DUCT | 1 | 4538.444 | 4538.444 | (1795 x 2762 x 11827) | [13 empty] | 0 | 4538.444 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
175 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0106 | BD03 | BREECH DUCT | 1 | 5014.5 | 5014.5 | (1795 x 2762 x 13577) | [13 empty] | 0 | 5014.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
176 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0108 | BD04 | BREECH DUCT | 1 | 4518.344 | 4518.344 | (1795 x 2762 x 11827) | [13 empty] | 0 | 4518.344 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
177 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0110 | BD05 | BREECH DUCT | 1 | 2057.35 | 2057.35 | (706 x 2345 x 8616) | [13 empty] | 0 | 2057.35 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
178 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0112 | BD06 | BREECH DUCT | 1 | 2078.65 | 2078.65 | (706 x 2345 x 8616) | [13 empty] | 0 | 2078.65 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
179 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0113 | CC01 | CARBON CAPTURE | 1 | 1344.2 | 1344.2 | (404 x 1470 x 11750) | [13 empty] | 0 | 1344.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
180 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0114 | CC02 | CARBON CAPTURE | 1 | 1344.2 | 1344.2 | (404 x 1470 x 11750) | [13 empty] | 0 | 1344.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
181 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0116 | CC03 | CARBON CAPTURE | 1 | 549 | 549 | (281 x 1245 x 5554) | [13 empty] | 0 | 549 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
182 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0118 | CC04 | CARBON CAPTURE | 1 | 549 | 549 | (281 x 1245 x 5554) | [13 empty] | 0 | 549 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
183 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC05 | CARBON CAPTURE | 1 | 2090.9 | 2090.9 | (162 x 4132 x 5554) | [13 empty] | 0 | 2090.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
184 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC06 | CARBON CAPTURE | 1 | 2005.6 | 2005.6 | (162 x 4000 x 5554) | [13 empty] | 0 | 2005.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 8 Main Stack U6 | Shipment 8 | Main Stack U6 |  | 2026-07-09 | HRSG | HSG12 | S4 | 25HG001-312-DD0-0S0120 | CC07 | CARBON CAPTURE | 1 | 2014.7 | 2014.7 | (162 x 4132 x 5554) | [13 empty] | 0 | 2014.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM001 | ONE-BEAM-228-001-2BM001 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(1/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(2/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(3/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(4/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(5/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(1/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(2/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(3/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(4/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(5/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM004 | ONE-BEAM-228-001-2BM004 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-04-17 | 1 | 54.1 | 2026-04-21 | 1 | 54.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 54.1 | 2026-04-25 | 1 | 54.1 | Truong An | M304-045 |  | 2BM004
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM005 | ONE-BEAM-228-001-2BM005 | 1 | 66.4 | 66.4 |  |  | Stair Tower | [11 empty] | 66.4 | 0 |  | 100% | 66.4 | 2026-04-17 | 1 | 66.4 | 2026-04-21 | 1 | 66.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 66.4 | 2026-04-25 | 1 | 66.4 | Truong An | M304-045 |  | 2BM005
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(1/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(2/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(3/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(4/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(5/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(6/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(1/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-21 | 1 | 27.2 | 2026-04-21 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(2/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-21 | 1 | 27.2 | 2026-04-21 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(3/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-21 | 1 | 27.2 | 2026-04-21 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(4/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-21 | 1 | 27.2 | 2026-04-21 | 1 | 27.2 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 27.2 | 2026-05-13 | 1 | 27.2 | Truong An | M304-062 | #VALUE! | 2BM007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(5/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-21 | 1 | 27.2 | 2026-04-21 | 1 | 27.2 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 27.2 | 2026-05-13 | 1 | 27.2 | Truong An | M304-062 | #VALUE! | 2BM007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(6/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-21 | 1 | 27.2 | 2026-04-21 | 1 | 27.2 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 27.2 | 2026-05-13 | 1 | 27.2 | Truong An | M304-062 | #VALUE! | 2BM007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(1/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(2/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(3/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM009 | ONE-BEAM-228-002-2BM009 | 1 | 25.1 | 25.1 |  |  | Stair Tower | [11 empty] | 25.1 | 0 |  | 100% | 25.1 | 2026-04-16 | 1 | 25.1 | 2026-04-17 | 1 | 25.1 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 25.1 | 2026-04-25 | 1 | 25.1 | Truong An | M304-045 |  | 2BM009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(1/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 30.3 | 0 |  | 100% | 30.3 | 2026-04-16 | 1 | 30.3 | 2026-04-17 | 1 | 30.3 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 30.3 | 2026-04-25 | 1 | 30.3 | Truong An | M304-045 |  | 2BM010
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(2/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 30.3 | 0 |  | 100% | 30.3 | 2026-04-16 | 1 | 30.3 | 2026-04-17 | 1 | 30.3 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 30.3 | 2026-04-25 | 1 | 30.3 | Truong An | M304-045 |  | 2BM010
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM011 | ONE-BEAM-228-002-2BM011 | 1 | 27 | 27 |  |  | Stair Tower | [11 empty] | 27 | 0 |  | 100% | 27 | 2026-04-16 | 1 | 27 | 2026-04-17 | 1 | 27 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27 | 2026-04-25 | 1 | 27 | Truong An | M304-045 |  | 2BM011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(1/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(2/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(3/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(1/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(2/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(3/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(4/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(5/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(6/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-04-16 | 1 | 27.2 | 2026-04-17 | 1 | 27.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 27.2 | 2026-04-25 | 1 | 27.2 | Truong An | M304-045 |  | 2BM013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM014 | ONE-BEAM-228-003-2BM014 | 1 | 70.8 | 70.8 |  |  | Stair Tower | [11 empty] | 70.8 | 0 |  | 100% | 70.8 | 2026-04-21 | 1 | 70.8 | 2026-04-21 | 1 | 70.8 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 70.8 | 2026-04-25 | 1 | 70.8 | Truong An | M304-045 |  | 2BM014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM015 | ONE-BEAM-228-003-2BM015 | 1 | 15.3 | 15.3 |  |  | Stair Tower | [11 empty] | 15.3 | 0 |  | 100% | 15.3 | 2026-04-16 | 1 | 15.3 | 2026-04-17 | 1 | 15.3 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.3 | 2026-04-25 | 1 | 15.3 | Truong An | M304-045 |  | 2BM015
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(1/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(2/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(3/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(4/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(5/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(6/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(7/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(8/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(9/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(10/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(11/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(12/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-04-16 | 1 | 15.4 | 2026-04-17 | 1 | 15.4 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 15.4 | 2026-04-25 | 1 | 15.4 | Truong An | M304-045 |  | 2BM016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(1/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-21 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(2/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-21 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(3/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-21 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(4/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-21 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(5/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-21 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(6/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-21 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(1/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-16 | 1 | 101.2 | 2026-04-17 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM018
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(2/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-16 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM018
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(3/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-16 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM018
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(4/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-17 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM018
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(5/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-04-17 | 1 | 101.2 | 2026-04-21 | 1 | 101.2 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 101.2 | 2026-04-25 | 1 | 101.2 | Truong An | M304-045 |  | 2BM018
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM019 | ONE-BEAM-228-004-2BM019 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 36.6 | 0 |  | 100% | 36.6 | 2026-04-16 | 1 | 36.6 | 2026-04-21 | 1 | 36.6 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 36.6 | 2026-04-25 | 1 | 36.6 | Truong An | M304-045 |  | 2BM019
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM020 | ONE-BEAM-228-004-2BM020 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 36.6 | 0 |  | 100% | 36.6 | 2026-04-16 | 1 | 36.6 | 2026-04-21 | 1 | 36.6 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 36.6 | 2026-04-25 | 1 | 36.6 | Truong An | M304-045 |  | 2BM020
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM021 | ONE-BEAM-228-004-2BM021 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 30.5 | 0 |  | 100% | 30.5 | 2026-04-16 | 1 | 30.5 | 2026-04-21 | 1 | 30.5 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 30.5 | 2026-04-25 | 1 | 30.5 | Truong An | M304-045 |  | 2BM021
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM022 | ONE-BEAM-228-004-2BM022 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 30.5 | 0 |  | 100% | 30.5 | 2026-04-16 | 1 | 30.5 | 2026-04-21 | 1 | 30.5 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 30.5 | 2026-04-25 | 1 | 30.5 | Truong An | M304-045 |  | 2BM022
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM023 | ONE-BEAM-228-004-2BM023 | 1 | 97 | 97 |  |  | Stair Tower | [11 empty] | 97 | 0 |  | 100% | 97 | 2026-04-16 | 1 | 97 | 2026-04-21 | 1 | 97 |  |  | 0 | M304-STR-U1-002 | 2026-04-21 | 1 | 97 | 2026-04-25 | 1 | 97 | Truong An | M304-045 |  | 2BM023
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-002 | 2CL001 | ONE-COLUMN-228-001-2CL001 | 1 | 2989.3 | 2989.3 |  |  | Stair Tower | [11 empty] | 2989.3 | 0 |  | 100% | 2989.3 | 2026-04-30 | 1 | 2989.3 | 2026-05-01 | 1 | 2989.3 |  |  | 0 | M304-STR-U1-009 | 2026-05-01 | 1 | 2989.3 | 2026-05-13 | 1 | 2989.3 | Truong An | M304-053 | #VALUE! | 2CL001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-004 | 2CL002 | ONE-COLUMN-228-003-2CL002 | 1 | 2181.2 | 2181.2 |  |  | Stair Tower | [11 empty] | 2181.2 | 0 |  | 100% | 2181.2 | 2026-04-21 | 1 | 2181.2 | 2026-04-23 | 1 | 2181.2 |  |  | 0 | M304-STR-U1-007 | 2026-04-28 | 1 | 2181.2 | 2026-05-13 | 1 | 2181.2 | Truong An | M304-050 | #VALUE! | 2CL002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-006 | 2CL003 | ONE-COLUMN-228-005-2CL003 | 1 | 2995.1 | 2995.1 |  |  | Stair Tower | [11 empty] | 2995.1 | 0 |  | 100% | 2995.1 | 2026-04-30 | 1 | 2995.1 | 2026-05-01 | 1 | 2995.1 |  |  | 0 | M304-STR-U1-009 | 2026-05-01 | 1 | 2995.1 | 2026-05-13 | 1 | 2995.1 | Truong An | M304-053 | #VALUE! | 2CL003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-008 | 2CL004 | ONE-COLUMN-228-007-2CL004 | 1 | 2603.9 | 2603.9 |  |  | Stair Tower | [11 empty] | 2603.9 | 0 |  | 100% | 2603.9 | 2026-04-23 | 1 | 2603.9 | 2026-04-25 | 1 | 2603.9 |  |  | 0 | M304-STR-U1-006 | 2026-04-25 | 1 | 2603.9 | 2026-05-13 | 1 | 2603.9 | Truong An | M304-061 | #VALUE! | 2CL004
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-010 | 2CL005 | ONE-COLUMN-228-009-2CL005 | 1 | 2672.5 | 2672.5 |  |  | Stair Tower | [11 empty] | 2672.5 | 0 |  | 100% | 2672.5 | 2026-04-23 | 1 | 2672.5 | 2026-04-24 | 1 | 2672.5 |  |  | 0 | M304-STR-U1-005 | 2026-04-24 | 1 | 2672.5 | 2026-05-13 | 1 | 2672.5 | Truong An | M304-048 | #VALUE! | 2CL005
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-012 | 2CL006 | ONE-COLUMN-228-011-2CL006 | 1 | 2246.4 | 2246.4 |  |  | Stair Tower | [11 empty] | 2246.4 | 0 |  | 100% | 2246.4 | 2026-04-23 | 1 | 2246.4 | 2026-04-24 | 1 | 2246.4 |  |  | 0 | M304-STR-U1-005 | 2026-04-24 | 1 | 2246.4 | 2026-05-13 | 1 | 2246.4 | Truong An | M304-048 | #VALUE! | 2CL006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR001 | ONE-GIRDER-228-001-2GR001 | 1 | 290.8 | 290.8 |  |  | Stair Tower | [11 empty] | 290.8 | 0 |  | 100% | 290.8 | 2026-04-29 | 1 | 290.8 | 2026-04-29 | 1 | 290.8 |  |  | 0 | M304-STR-U1-008 | 2026-04-29 | 1 | 290.8 | 2026-05-13 | 1 | 290.8 | Truong An | M304-051 |  | 2GR001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR002 | ONE-GIRDER-228-001-2GR002 | 1 | 301.3 | 301.3 |  |  | Stair Tower | [11 empty] | 301.3 | 0 |  | 100% | 301.3 | 2026-04-16 | 1 | 301.3 | 2026-05-02 | 1 | 301.3 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 301.3 | 2026-05-13 | 1 | 301.3 | Truong An | M304-062 | #VALUE! | 2GR002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR003 | ONE-GIRDER-228-001-2GR003 | 1 | 276.4 | 276.4 |  |  | Stair Tower | [11 empty] | 276.4 | 0 |  | 100% | 276.4 | 2026-04-29 | 1 | 276.4 | 2026-04-29 | 1 | 276.4 |  |  | 0 | M304-STR-U1-008 | 2026-04-29 | 1 | 276.4 | 2026-05-13 | 1 | 276.4 | Truong An | M304-051 |  | 2GR003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR004 | ONE-GIRDER-228-002-2GR004 | 1 | 280.3 | 280.3 |  |  | Stair Tower | [11 empty] | 280.3 | 0 |  | 100% | 280.3 | 2026-04-16 | 1 | 280.3 | 2026-05-02 | 1 | 280.3 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 280.3 | 2026-05-13 | 1 | 280.3 | Truong An | M304-062 | #VALUE! | 2GR004
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR005 | ONE-GIRDER-228-002-2GR005 | 1 | 280.1 | 280.1 |  |  | Stair Tower | [11 empty] | 280.1 | 0 |  | 100% | 280.1 | 2026-04-16 | 1 | 280.1 | 2026-05-02 | 1 | 280.1 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 280.1 | 2026-05-13 | 1 | 280.1 | Truong An | M304-062 | #VALUE! | 2GR005
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR006 | ONE-GIRDER-228-002-2GR006 | 1 | 279.3 | 279.3 |  |  | Stair Tower | [11 empty] | 279.3 | 0 |  | 100% | 279.3 | 2026-04-16 | 1 | 279.3 | 2026-04-24 | 1 | 279.3 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 279.3 | 2026-04-25 | 1 | 279.3 | Truong An | M304-047 |  | 2GR006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR007 | ONE-GIRDER-228-003-2GR007 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 279.7 | 0 |  | 100% | 279.7 | 2026-04-16 | 1 | 279.7 | 2026-04-29 | 1 | 279.7 |  |  | 0 | M304-STR-U1-008 | 2026-04-29 | 1 | 279.7 | 2026-05-13 | 1 | 279.7 | Truong An | M304-051 |  | 2GR007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR008 | ONE-GIRDER-228-003-2GR008 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 279.7 | 0 |  | 100% | 279.7 | 2026-04-16 | 1 | 279.7 | 2026-04-24 | 1 | 279.7 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 279.7 | 2026-04-25 | 1 | 279.7 | Truong An | M304-047 |  | 2GR008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(1/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  | 100% | 275 | 2026-04-16 | 1 | 275 | 2026-04-24 | 1 | 275 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275 | 2026-04-25 | 1 | 275 | Truong An | M304-047 |  | 2GR009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(2/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  | 100% | 275 | 2026-04-16 | 1 | 275 | 2026-04-24 | 1 | 275 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275 | 2026-04-25 | 1 | 275 | Truong An | M304-047 |  | 2GR009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(3/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  | 100% | 275 | 2026-04-16 | 1 | 275 | 2026-04-24 | 1 | 275 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275 | 2026-04-25 | 1 | 275 | Truong An | M304-047 |  | 2GR009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR010 | ONE-GIRDER-228-004-2GR010 | 1 | 294.2 | 294.2 | Rev thêm mã cấp rời vào site |  | Stair Tower | [11 empty] | 294.2 | 0 |  | 100% | 294.2 | 2026-04-16 | 1 | 294.2 | 2026-05-02 | 1 | 294.2 |  |  | 0 | M304-STR-U1-010 | 2026-05-12 | 1 | 294.2 | 2026-05-13 | 1 | 294.2 | Truong An | M304-062 | #VALUE! | 2GR010
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(1/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-16 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(2/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-16 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(3/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-16 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(4/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-16 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(5/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-16 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(6/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 | Rev giảm nhưng đã chuyển site |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-16 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(1/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-24 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(2/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-24 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(3/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-24 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(4/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-24 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(5/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-04-24 | 1 | 275.4 | 2026-04-24 | 1 | 275.4 |  |  | 0 | M304-STR-U1-004 | 2026-04-24 | 1 | 275.4 | 2026-04-25 | 1 | 275.4 | Truong An | M304-047 |  | 2GR012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR013 | ONE-GIRDER-228-004-2GR013 | 1 | 272.8 | 272.8 |  |  | Stair Tower | [11 empty] | 272.8 | 0 |  | 100% | 272.8 | 2026-04-29 | 1 | 272.8 | 2026-04-29 | 1 | 272.8 |  |  | 0 | M304-STR-U1-008 | 2026-04-29 | 1 | 272.8 | 2026-05-13 | 1 | 272.8 | Truong An | M304-051 |  | 2GR013
|  | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-2GR014 | 2GR014 | ONE-GIRDER-228-2GR014 | 1 | 294.2 | 294.2 | ADD, lấy từ phôi 2GR011(6/6) nhưng do đã chuyển công trường |  | Stair Tower | [11 empty] | 0 | 294.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT001 | ONE-POST-228-001-2PT001 | 1 | 112.8 | 112.8 |  |  | Stair Tower | [11 empty] | 112.8 | 0 |  | 100% | 112.8 | 2026-04-17 | 1 | 112.8 | 2026-04-21 | 1 | 112.8 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 112.8 | 2026-04-25 | 1 | 112.8 | Truong An | M304-046 |  | 2PT001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT003 | ONE-POST-228-001-2PT003 | 1 | 107 | 107 |  |  | Stair Tower | [11 empty] | 107 | 0 |  | 100% | 107 | 2026-04-17 | 1 | 107 | 2026-04-21 | 1 | 107 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 107 | 2026-04-25 | 1 | 107 | Truong An | M304-046 |  | 2PT003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT004 | ONE-POST-228-001-2PT004 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 104.7 | 0 |  | 100% | 104.7 | 2026-04-17 | 1 | 104.7 | 2026-04-21 | 1 | 104.7 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.7 | 2026-04-25 | 1 | 104.7 | Truong An | M304-046 |  | 2PT004
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT005 | ONE-POST-228-001-2PT005 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 104.7 | 0 |  | 100% | 104.7 | 2026-04-17 | 1 | 104.7 | 2026-04-21 | 1 | 104.7 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.7 | 2026-04-25 | 1 | 104.7 | Truong An | M304-046 |  | 2PT005
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(1/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-04-17 | 1 | 104.2 | 2026-04-21 | 1 | 104.2 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.2 | 2026-04-25 | 1 | 104.2 | Truong An | M304-046 |  | 2PT007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(2/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-04-17 | 1 | 104.2 | 2026-04-21 | 1 | 104.2 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.2 | 2026-04-25 | 1 | 104.2 | Truong An | M304-046 |  | 2PT007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(3/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-04-17 | 1 | 104.2 | 2026-04-21 | 1 | 104.2 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.2 | 2026-04-25 | 1 | 104.2 | Truong An | M304-046 |  | 2PT007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT008 | ONE-POST-228-002-2PT008 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-04-17 | 1 | 104.2 | 2026-04-21 | 1 | 104.2 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.2 | 2026-04-25 | 1 | 104.2 | Truong An | M304-046 |  | 2PT008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT009 | ONE-POST-228-002-2PT009 | 1 | 110.9 | 110.9 |  |  | Stair Tower | [11 empty] | 110.9 | 0 |  | 100% | 110.9 | 2026-04-29 | 1 | 110.9 | 2026-04-29 | 1 | 110.9 |  |  | 0 | M304-STR-U1-008 | 2026-04-29 | 1 | 110.9 | 2026-05-13 | 1 | 110.9 | Truong An | M304-051 |  | 2PT009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT010 | ONE-POST-228-002-2PT010 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-04-21 | 1 | 104.2 | 2026-04-21 | 1 | 104.2 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 104.2 | 2026-04-25 | 1 | 104.2 | Truong An | M304-046 |  | 2PT010
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB001 | ONE-VBRACE-228-001-2VB001 | 1 | 25.7 | 25.7 |  |  | Stair Tower | [11 empty] | 25.7 | 0 |  | 100% | 25.7 | 2026-04-18 | 1 | 25.7 | 2026-04-21 | 1 | 25.7 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 25.7 | 2026-04-25 | 1 | 25.7 | Truong An | M304-046 |  | 2VB001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB002 | ONE-VBRACE-228-001-2VB002 | 1 | 27.7 | 27.7 |  |  | Stair Tower | [11 empty] | 27.7 | 0 |  | 100% | 27.7 | 2026-04-18 | 1 | 27.7 | 2026-04-21 | 1 | 27.7 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 27.7 | 2026-04-25 | 1 | 27.7 | Truong An | M304-046 |  | 2VB002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB003 | ONE-VBRACE-228-001-2VB003 | 1 | 20.1 | 20.1 |  |  | Stair Tower | [11 empty] | 20.1 | 0 |  | 100% | 20.1 | 2026-04-18 | 1 | 20.1 | 2026-04-21 | 1 | 20.1 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 20.1 | 2026-04-25 | 1 | 20.1 | Truong An | M304-046 |  | 2VB003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB004 | ONE-VBRACE-228-001-2VB004 | 1 | 20.3 | 20.3 |  |  | Stair Tower | [11 empty] | 20.3 | 0 |  | 100% | 20.3 | 2026-04-18 | 1 | 20.3 | 2026-04-21 | 1 | 20.3 |  |  | 0 | M304-STR-U1-003 | 2026-04-21 | 1 | 20.3 | 2026-04-25 | 1 | 20.3 | Truong An | M304-046 |  | 2VB004
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB005 | ONE-VBRACE-228-001-2VB005 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-18 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB005
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB006 | ONE-VBRACE-228-001-2VB006 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-18 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB006
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(1/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(2/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(3/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(4/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(5/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(6/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(7/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(8/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(9/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(10/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB007
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(1/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(2/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(3/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(4/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(5/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(6/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(7/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(8/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-18 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(9/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(10/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(11/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(12/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(13/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(14/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-04-17 | 1 | 64 | 2026-04-20 | 1 | 64 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 64 | 2026-04-25 | 1 | 64 | Truong An | M304-044 |  | 2VB008
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(1/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-04-17 | 1 | 48.6 | 2026-04-20 | 1 | 48.6 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 48.6 | 2026-04-25 | 1 | 48.6 | Truong An | M304-044 |  | 2VB009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(2/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-04-17 | 1 | 48.6 | 2026-04-20 | 1 | 48.6 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 48.6 | 2026-04-25 | 1 | 48.6 | Truong An | M304-044 |  | 2VB009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(3/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-04-17 | 1 | 48.6 | 2026-04-20 | 1 | 48.6 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 48.6 | 2026-04-25 | 1 | 48.6 | Truong An | M304-044 |  | 2VB009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(4/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-04-17 | 1 | 48.6 | 2026-04-20 | 1 | 48.6 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 48.6 | 2026-04-25 | 1 | 48.6 | Truong An | M304-044 |  | 2VB009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(5/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-04-17 | 1 | 48.6 | 2026-04-20 | 1 | 48.6 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 48.6 | 2026-04-25 | 1 | 48.6 | Truong An | M304-044 |  | 2VB009
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB010 | ONE-VBRACE-228-002-2VB010 | 1 | 49.3 | 49.3 |  |  | Stair Tower | [11 empty] | 49.3 | 0 |  | 100% | 49.3 | 2026-04-17 | 1 | 49.3 | 2026-04-20 | 1 | 49.3 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 49.3 | 2026-04-25 | 1 | 49.3 | Truong An | M304-044 |  | 2VB010
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB011 | ONE-VBRACE-228-002-2VB011 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 60 | 0 |  | 100% | 60 | 2026-04-17 | 1 | 60 | 2026-04-20 | 1 | 60 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 60 | 2026-04-25 | 1 | 60 | Truong An | M304-044 |  | 2VB011
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB012 | ONE-VBRACE-228-002-2VB012 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 60 | 0 |  | 100% | 60 | 2026-04-17 | 1 | 60 | 2026-04-20 | 1 | 60 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 60 | 2026-04-25 | 1 | 60 | Truong An | M304-044 |  | 2VB012
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(1/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(2/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB013
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(1/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(2/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(3/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(4/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(5/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(6/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-04-17 | 1 | 84 | 2026-04-20 | 1 | 84 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 84 | 2026-04-25 | 1 | 84 | Truong An | M304-044 |  | 2VB014
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(1/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-04-17 | 1 | 92 | 2026-04-20 | 1 | 92 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 92 | 2026-04-25 | 1 | 92 | Truong An | M304-044 |  | 2VB015
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(2/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-04-17 | 1 | 92 | 2026-04-20 | 1 | 92 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 92 | 2026-04-25 | 1 | 92 | Truong An | M304-044 |  | 2VB015
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(1/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-04-17 | 1 | 92 | 2026-04-20 | 1 | 92 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 92 | 2026-04-25 | 1 | 92 | Truong An | M304-044 |  | 2VB016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(2/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-04-17 | 1 | 92 | 2026-04-20 | 1 | 92 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 92 | 2026-04-25 | 1 | 92 | Truong An | M304-044 |  | 2VB016
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(1/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  | 100% | 63.3 | 2026-04-17 | 1 | 63.3 | 2026-04-20 | 1 | 63.3 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 63.3 | 2026-04-25 | 1 | 63.3 | Truong An | M304-044 |  | 2VB017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(2/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  | 100% | 63.3 | 2026-04-17 | 1 | 63.3 | 2026-04-20 | 1 | 63.3 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 63.3 | 2026-04-25 | 1 | 63.3 | Truong An | M304-044 |  | 2VB017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(3/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  | 100% | 63.3 | 2026-04-17 | 1 | 63.3 | 2026-04-20 | 1 | 63.3 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 63.3 | 2026-04-25 | 1 | 63.3 | Truong An | M304-044 |  | 2VB017
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB018 | ONE-VBRACE-228-003-2VB018 | 1 | 66.2 | 66.2 |  |  | Stair Tower | [11 empty] | 66.2 | 0 |  | 100% | 66.2 | 2026-04-17 | 1 | 66.2 | 2026-04-20 | 1 | 66.2 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 66.2 | 2026-04-25 | 1 | 66.2 | Truong An | M304-044 |  | 2VB018
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB019 | ONE-VBRACE-228-003-2VB019 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 77.2 | 0 |  | 100% | 77.2 | 2026-04-17 | 1 | 77.2 | 2026-04-20 | 1 | 77.2 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 77.2 | 2026-04-25 | 1 | 77.2 | Truong An | M304-044 |  | 2VB019
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB020 | ONE-VBRACE-228-003-2VB020 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 77.2 | 0 |  | 100% | 77.2 | 2026-04-17 | 1 | 77.2 | 2026-04-20 | 1 | 77.2 |  |  | 0 | M304-STR-U1-001 | 2026-04-20 | 1 | 77.2 | 2026-04-25 | 1 | 77.2 | Truong An | M304-044 |  | 2VB020
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(1/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 | ADD |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3GR001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(2/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 | ADD |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3GR001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(1/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 | ADD |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U1-012 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-172 |  | 3GR002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(2/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 | ADD |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U1-012 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-172 |  | 3GR002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(3/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 | ADD |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U1-012 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-172 |  | 3GR002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR003 | 3GR003 | ONE-GIRDER-228-3GR003 | 1 | 79.3 | 79.3 | ADD |  | Stair Tower | [11 empty] | 79.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 79.3 | 2026-09-08 | 1 | 79.3 |  |  | 0 | M304-STR-U1-012 | 2026-09-08 | 1 | 79.3 | 2026-09-17 | 1 | 79.3 | Truong An | M304-172 |  | 3GR003
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT001 | 3PT001 | ONE-POST-228-3PT001 | 1 | 248.5 | 248.5 | ADD |  | Stair Tower | [11 empty] | 0 | 248.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PT001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT002 | 3PT002 | ONE-POST-228-3PT002 | 1 | 211.9 | 211.9 | ADD |  | Stair Tower | [11 empty] | 0 | 211.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PT002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB001 | 3VB001 | ONE-VBRACE-228-3VB001 | 1 | 65 | 65 | ADD |  | Stair Tower | [11 empty] | 65 | 0 |  |  | 0 | 2026-09-08 | 1 | 65 | 2026-09-08 | 1 | 65 |  |  | 0 | M304-STR-U1-012 | 2026-09-08 | 1 | 65 | 2026-09-17 | 1 | 65 | Truong An | M304-172 |  | 3VB001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB002 | 3VB002 | ONE-VBRACE-228-3VB002 | 1 | 64 | 64 | ADD |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-09-08 | 1 | 64 | 2026-09-08 | 1 | 64 |  |  | 0 | M304-STR-U1-012 | 2026-09-08 | 1 | 64 | 2026-09-17 | 1 | 64 | Truong An | M304-172 |  | 3VB002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(1/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 | ADD |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(2/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 | ADD |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(3/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 | ADD |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(1/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 | ADD |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL002
185 | M304 | Shipment 1 Steel Structure U1 | Shipment 1 | Steel Structure U1 | Stair Tower | 2026-03-27 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(2/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 | ADD |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM001 | ONE-BEAM-228-001-2BM001 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(1/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(2/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(3/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(4/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(5/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(1/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(2/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(3/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(4/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(5/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM004 | ONE-BEAM-228-001-2BM004 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  | 100% | 54.1 | 2026-06-17 | 1 | 54.1 | 2026-06-17 | 1 | 54.1 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 54.1 | 2026-06-27 | 1 | 54.1 | Truong An | M304-113 |  | 2BM004
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM005 | ONE-BEAM-228-001-2BM005 | 1 | 66.4 | 66.4 |  |  | Stair Tower | [11 empty] | 66.4 | 0 |  | 100% | 66.4 | 2026-06-17 | 1 | 66.4 | 2026-06-17 | 1 | 66.4 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 66.4 | 2026-06-27 | 1 | 66.4 | Truong An | M304-113 |  | 2BM005
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(1/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(2/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(3/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(4/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(5/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(6/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(1/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(2/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(3/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(4/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(5/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(6/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(1/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(2/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(3/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM009 | ONE-BEAM-228-002-2BM009 | 1 | 25.1 | 25.1 |  |  | Stair Tower | [11 empty] | 25.1 | 0 |  | 100% | 25.1 | 2026-06-18 | 1 | 25.1 | 2026-06-18 | 1 | 25.1 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 25.1 | 2026-06-27 | 1 | 25.1 | Truong An | M304-116 |  | 2BM009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(1/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 30.3 | 0 |  | 100% | 30.3 | 2026-06-18 | 1 | 30.3 | 2026-06-18 | 1 | 30.3 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 30.3 | 2026-06-27 | 1 | 30.3 | Truong An | M304-116 |  | 2BM010
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(2/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 30.3 | 0 |  | 100% | 30.3 | 2026-06-18 | 1 | 30.3 | 2026-06-18 | 1 | 30.3 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 30.3 | 2026-06-27 | 1 | 30.3 | Truong An | M304-116 |  | 2BM010
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM011 | ONE-BEAM-228-002-2BM011 | 1 | 27 | 27 |  |  | Stair Tower | [11 empty] | 27 | 0 |  | 100% | 27 | 2026-06-18 | 1 | 27 | 2026-06-18 | 1 | 27 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27 | 2026-06-27 | 1 | 27 | Truong An | M304-116 |  | 2BM011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(1/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(2/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(3/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(1/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(2/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(3/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(4/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(5/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(6/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  | 100% | 27.2 | 2026-06-18 | 1 | 27.2 | 2026-06-18 | 1 | 27.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.2 | 2026-06-27 | 1 | 27.2 | Truong An | M304-116 |  | 2BM013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM014 | ONE-BEAM-228-003-2BM014 | 1 | 70.8 | 70.8 |  |  | Stair Tower | [11 empty] | 70.8 | 0 |  | 100% | 70.8 | 2026-06-17 | 1 | 70.8 | 2026-06-17 | 1 | 70.8 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 70.8 | 2026-06-27 | 1 | 70.8 | Truong An | M304-113 |  | 2BM014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM015 | ONE-BEAM-228-003-2BM015 | 1 | 15.3 | 15.3 |  |  | Stair Tower | [11 empty] | 15.3 | 0 |  | 100% | 15.3 | 2026-06-18 | 1 | 15.3 | 2026-06-18 | 1 | 15.3 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.3 | 2026-06-27 | 1 | 15.3 | Truong An | M304-116 |  | 2BM015
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(1/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(2/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(3/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(4/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(5/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(6/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(7/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(8/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(9/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(10/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(11/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(12/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  | 100% | 15.4 | 2026-06-18 | 1 | 15.4 | 2026-06-18 | 1 | 15.4 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 15.4 | 2026-06-27 | 1 | 15.4 | Truong An | M304-116 |  | 2BM016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(1/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(2/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(3/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(4/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(5/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(6/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(1/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM018
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(2/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM018
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(3/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM018
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(4/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM018
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(5/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  | 100% | 101.2 | 2026-06-15 | 1 | 101.2 | 2026-06-17 | 1 | 101.2 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 101.2 | 2026-06-27 | 1 | 101.2 | Truong An | M304-113 |  | 2BM018
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM019 | ONE-BEAM-228-004-2BM019 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 36.6 | 0 |  | 100% | 36.6 | 2026-06-15 | 1 | 36.6 | 2026-06-18 | 1 | 36.6 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 36.6 | 2026-06-27 | 1 | 36.6 | Truong An | M304-116 |  | 2BM019
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM020 | ONE-BEAM-228-004-2BM020 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 36.6 | 0 |  | 100% | 36.6 | 2026-06-15 | 1 | 36.6 | 2026-06-18 | 1 | 36.6 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 36.6 | 2026-06-27 | 1 | 36.6 | Truong An | M304-116 |  | 2BM020
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM021 | ONE-BEAM-228-004-2BM021 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 30.5 | 0 |  | 100% | 30.5 | 2026-06-15 | 1 | 30.5 | 2026-06-18 | 1 | 30.5 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 30.5 | 2026-06-27 | 1 | 30.5 | Truong An | M304-116 |  | 2BM021
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM022 | ONE-BEAM-228-004-2BM022 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 30.5 | 0 |  | 100% | 30.5 | 2026-06-15 | 1 | 30.5 | 2026-06-18 | 1 | 30.5 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 30.5 | 2026-06-27 | 1 | 30.5 | Truong An | M304-116 |  | 2BM022
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM023 | ONE-BEAM-228-004-2BM023 | 1 | 97 | 97 |  |  | Stair Tower | [11 empty] | 97 | 0 |  | 100% | 97 | 2026-06-15 | 1 | 97 | 2026-06-17 | 1 | 97 |  |  | 0 | M304-STR-U2-004 | 2026-06-17 | 1 | 97 | 2026-06-27 | 1 | 97 | Truong An | M304-113 |  | 2BM023
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-002 | 2CL001 | ONE-COLUMN-228-001-2CL001 | 1 | 2989.3 | 2989.3 |  |  | Stair Tower | [11 empty] | 2989.3 | 0 |  | 100% | 2989.3 | 2026-06-13 | 1 | 2989.3 | 2026-06-18 | 1 | 2989.3 |  |  | 0 | M304-STR-U2-006 | 2026-06-19 | 1 | 2989.3 | 2026-06-27 | 1 | 2989.3 | Truong An | M304-117 | #VALUE! | 2CL001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-004 | 2CL002 | ONE-COLUMN-228-003-2CL002 | 1 | 2181.2 | 2181.2 |  |  | Stair Tower | [11 empty] | 2181.2 | 0 |  | 100% | 2181.2 | 2026-06-09 | 1 | 2181.2 | 2026-06-13 | 1 | 2181.2 |  |  | 0 | M304-STR-U2-001-1 | 2026-06-13 | 1 | 2181.2 | 2026-06-27 | 1 | 2181.2 | Truong An | M304-124 |  | 2CL002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-006 | 2CL003 | ONE-COLUMN-228-005-2CL003 | 1 | 2995.1 | 2995.1 |  |  | Stair Tower | [11 empty] | 2995.1 | 0 |  | 100% | 2995.1 | 2026-06-13 | 1 | 2995.1 | 2026-06-17 | 1 | 2995.1 |  |  | 0 | M304-STR-U2-006 | 2026-06-19 | 1 | 2995.1 | 2026-06-27 | 1 | 2995.1 | Truong An | M304-117 | #VALUE! | 2CL003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-008 | 2CL004 | ONE-COLUMN-228-007-2CL004 | 1 | 2603.9 | 2603.9 |  |  | Stair Tower | [11 empty] | 2603.9 | 0 |  | 100% | 2603.9 | 2026-06-15 | 1 | 2603.9 | 2026-06-18 | 1 | 2603.9 |  |  | 0 | M304-STR-U2-007 | 2026-06-21 | 1 | 2603.9 | 2026-06-27 | 1 | 2603.9 | Truong An | M304-119 | #VALUE! | 2CL004
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-010 | 2CL005 | ONE-COLUMN-228-009-2CL005 | 1 | 2672.5 | 2672.5 |  |  | Stair Tower | [11 empty] | 2672.5 | 0 |  | 100% | 2672.5 | 2026-06-11 | 1 | 2672.5 | 2026-06-18 | 1 | 2672.5 |  |  | 0 | M304-STR-U2-007 | 2026-06-21 | 1 | 2672.5 | 2026-06-27 | 1 | 2672.5 | Truong An | M304-119 | #VALUE! | 2CL005
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-012 | 2CL006 | ONE-COLUMN-228-011-2CL006 | 1 | 2246.4 | 2246.4 |  |  | Stair Tower | [11 empty] | 2246.4 | 0 |  | 100% | 2246.4 | 2026-06-10 | 1 | 2246.4 | 2026-06-12 | 1 | 2246.4 |  |  | 0 | M304-STR-U2-002-1 | 2026-06-15 | 1 | 2246.4 | 2026-06-27 | 1 | 2246.4 | Truong An | M304-124 |  | 2CL006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR001 | ONE-GIRDER-228-001-2GR001 | 1 | 290.8 | 290.8 |  |  | Stair Tower | [11 empty] | 290.8 | 0 |  | 100% | 290.8 | 2026-06-13 | 1 | 290.8 | 2026-06-15 | 1 | 290.8 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 290.8 | 2026-06-27 | 1 | 290.8 | Truong An | M304-107 |  | 2GR001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR002 | ONE-GIRDER-228-001-2GR002 | 1 | 301.3 | 301.3 |  |  | Stair Tower | [11 empty] | 301.3 | 0 |  | 100% | 301.3 | 2026-06-13 | 1 | 301.3 | 2026-06-16 | 1 | 301.3 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 301.3 | 2026-06-27 | 1 | 301.3 | Truong An | M304-110 |  | 2GR002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR003 | ONE-GIRDER-228-001-2GR003 | 1 | 276.4 | 276.4 |  |  | Stair Tower | [11 empty] | 276.4 | 0 |  | 100% | 276.4 | 2026-06-13 | 1 | 276.4 | 2026-06-16 | 1 | 276.4 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 276.4 | 2026-06-27 | 1 | 276.4 | Truong An | M304-110 |  | 2GR003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR004 | ONE-GIRDER-228-002-2GR004 | 1 | 280.3 | 280.3 |  |  | Stair Tower | [11 empty] | 280.3 | 0 |  | 100% | 280.3 | 2026-06-13 | 1 | 280.3 | 2026-06-16 | 1 | 280.3 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 280.3 | 2026-06-27 | 1 | 280.3 | Truong An | M304-110 |  | 2GR004
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR005 | ONE-GIRDER-228-002-2GR005 | 1 | 280.1 | 280.1 |  |  | Stair Tower | [11 empty] | 280.1 | 0 |  | 100% | 280.1 | 2026-06-13 | 1 | 280.1 | 2026-06-15 | 1 | 280.1 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 280.1 | 2026-06-27 | 1 | 280.1 | Truong An | M304-107 |  | 2GR005
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR006 | ONE-GIRDER-228-002-2GR006 | 1 | 279.3 | 279.3 |  |  | Stair Tower | [11 empty] | 279.3 | 0 |  | 100% | 279.3 | 2026-06-10 | 1 | 279.3 | 2026-06-15 | 1 | 279.3 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 279.3 | 2026-06-27 | 1 | 279.3 | Truong An | M304-107 |  | 2GR006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR007 | ONE-GIRDER-228-003-2GR007 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 279.7 | 0 |  | 100% | 279.7 | 2026-06-15 | 1 | 279.7 | 2026-06-15 | 1 | 279.7 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 279.7 | 2026-06-27 | 1 | 279.7 | Truong An | M304-107 |  | 2GR007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR008 | ONE-GIRDER-228-003-2GR008 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 279.7 | 0 |  | 100% | 279.7 | 2026-06-10 | 1 | 279.7 | 2026-06-16 | 1 | 279.7 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 279.7 | 2026-06-27 | 1 | 279.7 | Truong An | M304-110 |  | 2GR008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(1/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  | 100% | 275 | 2026-06-10 | 1 | 275 | 2026-06-15 | 1 | 275 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275 | 2026-06-27 | 1 | 275 | Truong An | M304-107 |  | 2GR009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(2/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  | 100% | 275 | 2026-06-10 | 1 | 275 | 2026-06-15 | 1 | 275 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275 | 2026-06-27 | 1 | 275 | Truong An | M304-107 |  | 2GR009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(3/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  | 100% | 275 | 2026-06-10 | 1 | 275 | 2026-06-15 | 1 | 275 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275 | 2026-06-27 | 1 | 275 | Truong An | M304-107 |  | 2GR009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR010 | ONE-GIRDER-228-004-2GR010 | 1 | 294.2 | 294.2 | Thêm mã sửa ở Shop |  | Stair Tower | [11 empty] | 294.2 | 0 |  | 100% | 294.2 | 2026-06-10 | 1 | 294.2 | 2026-06-15 | 1 | 294.2 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 294.2 | 2026-06-27 | 1 | 294.2 | Truong An | M304-107 |  | 2GR010
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(1/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-10 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(2/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-10 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(3/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-10 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-110 |  | 2GR011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(4/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-10 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-110 |  | 2GR011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(5/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-10 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-110 |  | 2GR011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(6/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 | Rev chuyển về 2GR-014 |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-10 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-110 |  | 2GR011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(1/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-12 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(2/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-12 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(3/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-12 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(4/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-12 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(5/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  | 100% | 275.4 | 2026-06-12 | 1 | 275.4 | 2026-06-15 | 1 | 275.4 |  |  | 0 | M304-STR-U2-002 | 2026-06-15 | 1 | 275.4 | 2026-06-27 | 1 | 275.4 | Truong An | M304-107 |  | 2GR012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR013 | ONE-GIRDER-228-004-2GR013 | 1 | 272.8 | 272.8 |  |  | Stair Tower | [11 empty] | 272.8 | 0 |  | 100% | 272.8 | 2026-06-12 | 1 | 272.8 | 2026-06-16 | 1 | 272.8 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 272.8 | 2026-06-27 | 1 | 272.8 | Truong An | M304-110 |  | 2GR013
|  | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-2GR014 | 2GR014 | ONE-GIRDER-228-2GR014 | 1 | 294.2 | 294.2 | ADD, lấy từ phôi 2GR011(6/6) nhưng do đã chuyển công trường |  | Stair Tower | [11 empty] | 0 | 294.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT001 | ONE-POST-228-001-2PT001 | 1 | 112.8 | 112.8 |  |  | Stair Tower | [11 empty] | 112.8 | 0 |  | 100% | 112.8 | 2026-06-12 | 1 | 112.8 | 2026-06-18 | 1 | 112.8 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 112.8 | 2026-06-27 | 1 | 112.8 | Truong An | M304-116 |  | 2PT001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT003 | ONE-POST-228-001-2PT003 | 1 | 107 | 107 |  |  | Stair Tower | [11 empty] | 107 | 0 |  | 100% | 107 | 2026-06-12 | 1 | 107 | 2026-06-18 | 1 | 107 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 107 | 2026-06-27 | 1 | 107 | Truong An | M304-116 |  | 2PT003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT004 | ONE-POST-228-001-2PT004 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 104.7 | 0 |  | 100% | 104.7 | 2026-06-12 | 1 | 104.7 | 2026-06-18 | 1 | 104.7 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.7 | 2026-06-27 | 1 | 104.7 | Truong An | M304-116 |  | 2PT004
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT005 | ONE-POST-228-001-2PT005 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 104.7 | 0 |  | 100% | 104.7 | 2026-06-18 | 1 | 104.7 | 2026-06-18 | 1 | 104.7 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.7 | 2026-06-27 | 1 | 104.7 | Truong An | M304-116 |  | 2PT005
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(1/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-06-18 | 1 | 104.2 | 2026-06-18 | 1 | 104.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.2 | 2026-06-27 | 1 | 104.2 | Truong An | M304-116 |  | 2PT007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(2/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-06-18 | 1 | 104.2 | 2026-06-18 | 1 | 104.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.2 | 2026-06-27 | 1 | 104.2 | Truong An | M304-116 |  | 2PT007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(3/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-06-18 | 1 | 104.2 | 2026-06-18 | 1 | 104.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.2 | 2026-06-27 | 1 | 104.2 | Truong An | M304-116 |  | 2PT007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT008 | ONE-POST-228-002-2PT008 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-06-18 | 1 | 104.2 | 2026-06-18 | 1 | 104.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.2 | 2026-06-27 | 1 | 104.2 | Truong An | M304-116 |  | 2PT008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT009 | ONE-POST-228-002-2PT009 | 1 | 110.9 | 110.9 |  |  | Stair Tower | [11 empty] | 110.9 | 0 |  | 100% | 110.9 | 2026-06-18 | 1 | 110.9 | 2026-06-18 | 1 | 110.9 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 110.9 | 2026-06-27 | 1 | 110.9 | Truong An | M304-116 |  | 2PT009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT010 | ONE-POST-228-002-2PT010 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  | 100% | 104.2 | 2026-06-18 | 1 | 104.2 | 2026-06-18 | 1 | 104.2 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 104.2 | 2026-06-27 | 1 | 104.2 | Truong An | M304-116 |  | 2PT010
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB001 | ONE-VBRACE-228-001-2VB001 | 1 | 25.7 | 25.7 |  |  | Stair Tower | [11 empty] | 25.7 | 0 |  | 100% | 25.7 | 2026-06-18 | 1 | 25.7 | 2026-06-18 | 1 | 25.7 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 25.7 | 2026-06-27 | 1 | 25.7 | Truong An | M304-116 |  | 2VB001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB002 | ONE-VBRACE-228-001-2VB002 | 1 | 27.7 | 27.7 |  |  | Stair Tower | [11 empty] | 27.7 | 0 |  | 100% | 27.7 | 2026-06-18 | 1 | 27.7 | 2026-06-18 | 1 | 27.7 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 27.7 | 2026-06-27 | 1 | 27.7 | Truong An | M304-116 |  | 2VB002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB003 | ONE-VBRACE-228-001-2VB003 | 1 | 20.1 | 20.1 |  |  | Stair Tower | [11 empty] | 20.1 | 0 |  | 100% | 20.1 | 2026-06-18 | 1 | 20.1 | 2026-06-18 | 1 | 20.1 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 20.1 | 2026-06-27 | 1 | 20.1 | Truong An | M304-116 |  | 2VB003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB004 | ONE-VBRACE-228-001-2VB004 | 1 | 20.3 | 20.3 |  |  | Stair Tower | [11 empty] | 20.3 | 0 |  | 100% | 20.3 | 2026-06-18 | 1 | 20.3 | 2026-06-18 | 1 | 20.3 |  |  | 0 | M304-STR-U2-005 | 2026-06-18 | 1 | 20.3 | 2026-06-27 | 1 | 20.3 | Truong An | M304-116 |  | 2VB004
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB005 | ONE-VBRACE-228-001-2VB005 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB005
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB006 | ONE-VBRACE-228-001-2VB006 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB006
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(1/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(2/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(3/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(4/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(5/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(6/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(7/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(8/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(9/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(10/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB007
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(1/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(2/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(3/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(4/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(5/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(6/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(7/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(8/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(9/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-10 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(10/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-12 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(11/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-12 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(12/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-12 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(13/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-12 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(14/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  | 100% | 64 | 2026-06-12 | 1 | 64 | 2026-06-13 | 1 | 64 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 64 | 2026-06-27 | 1 | 64 | Truong An | M304-104 |  | 2VB008
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(1/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-06-12 | 1 | 48.6 | 2026-06-13 | 1 | 48.6 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 48.6 | 2026-06-27 | 1 | 48.6 | Truong An | M304-104 |  | 2VB009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(2/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-06-12 | 1 | 48.6 | 2026-06-13 | 1 | 48.6 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 48.6 | 2026-06-27 | 1 | 48.6 | Truong An | M304-104 |  | 2VB009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(3/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-06-12 | 1 | 48.6 | 2026-06-13 | 1 | 48.6 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 48.6 | 2026-06-27 | 1 | 48.6 | Truong An | M304-104 |  | 2VB009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(4/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-06-12 | 1 | 48.6 | 2026-06-13 | 1 | 48.6 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 48.6 | 2026-06-27 | 1 | 48.6 | Truong An | M304-104 |  | 2VB009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(5/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  | 100% | 48.6 | 2026-06-12 | 1 | 48.6 | 2026-06-13 | 1 | 48.6 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 48.6 | 2026-06-27 | 1 | 48.6 | Truong An | M304-104 |  | 2VB009
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB010 | ONE-VBRACE-228-002-2VB010 | 1 | 49.3 | 49.3 |  |  | Stair Tower | [11 empty] | 49.3 | 0 |  | 100% | 49.3 | 2026-06-12 | 1 | 49.3 | 2026-06-13 | 1 | 49.3 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 49.3 | 2026-06-27 | 1 | 49.3 | Truong An | M304-104 |  | 2VB010
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB011 | ONE-VBRACE-228-002-2VB011 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 60 | 0 |  | 100% | 60 | 2026-06-12 | 1 | 60 | 2026-06-13 | 1 | 60 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 60 | 2026-06-27 | 1 | 60 | Truong An | M304-104 |  | 2VB011
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB012 | ONE-VBRACE-228-002-2VB012 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 60 | 0 |  | 100% | 60 | 2026-06-12 | 1 | 60 | 2026-06-13 | 1 | 60 |  |  | 0 | M304-STR-U2-001 | 2026-06-13 | 1 | 60 | 2026-06-27 | 1 | 60 | Truong An | M304-104 |  | 2VB012
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(1/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(2/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB013
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(1/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(2/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(3/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(4/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(5/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(6/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  | 100% | 84 | 2026-06-12 | 1 | 84 | 2026-06-16 | 1 | 84 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 84 | 2026-06-27 | 1 | 84 | Truong An | M304-110 |  | 2VB014
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(1/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-06-12 | 1 | 92 | 2026-06-16 | 1 | 92 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 92 | 2026-06-27 | 1 | 92 | Truong An | M304-110 |  | 2VB015
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(2/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-06-12 | 1 | 92 | 2026-06-16 | 1 | 92 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 92 | 2026-06-27 | 1 | 92 | Truong An | M304-110 |  | 2VB015
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(1/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-06-12 | 1 | 92 | 2026-06-16 | 1 | 92 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 92 | 2026-06-27 | 1 | 92 | Truong An | M304-110 |  | 2VB016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(2/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  | 100% | 92 | 2026-06-12 | 1 | 92 | 2026-06-16 | 1 | 92 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 92 | 2026-06-27 | 1 | 92 | Truong An | M304-110 |  | 2VB016
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(1/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  | 100% | 63.3 | 2026-06-12 | 1 | 63.3 | 2026-06-16 | 1 | 63.3 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 63.3 | 2026-06-27 | 1 | 63.3 | Truong An | M304-110 |  | 2VB017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(2/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  | 100% | 63.3 | 2026-06-12 | 1 | 63.3 | 2026-06-16 | 1 | 63.3 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 63.3 | 2026-06-27 | 1 | 63.3 | Truong An | M304-110 |  | 2VB017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(3/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  | 100% | 63.3 | 2026-06-12 | 1 | 63.3 | 2026-06-16 | 1 | 63.3 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 63.3 | 2026-06-27 | 1 | 63.3 | Truong An | M304-110 |  | 2VB017
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB018 | ONE-VBRACE-228-003-2VB018 | 1 | 66.2 | 66.2 |  |  | Stair Tower | [11 empty] | 66.2 | 0 |  | 100% | 66.2 | 2026-06-12 | 1 | 66.2 | 2026-06-16 | 1 | 66.2 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 66.2 | 2026-06-27 | 1 | 66.2 | Truong An | M304-110 |  | 2VB018
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB019 | ONE-VBRACE-228-003-2VB019 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 77.2 | 0 |  | 100% | 77.2 | 2026-06-12 | 1 | 77.2 | 2026-06-16 | 1 | 77.2 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 77.2 | 2026-06-27 | 1 | 77.2 | Truong An | M304-110 |  | 2VB019
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB020 | ONE-VBRACE-228-003-2VB020 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 77.2 | 0 |  | 100% | 77.2 | 2026-06-12 | 1 | 77.2 | 2026-06-16 | 1 | 77.2 |  |  | 0 | M304-STR-U2-003 | 2026-06-16 | 1 | 77.2 | 2026-06-27 | 1 | 77.2 | Truong An | M304-110 |  | 2VB020
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(1/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 |  |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3GR001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(2/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 |  |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3GR001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(1/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U2-009 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-173 |  | 3GR002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(2/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U2-009 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-173 |  | 3GR002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(3/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U2-009 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-173 |  | 3GR002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR003 | 3GR003 | ONE-GIRDER-228-3GR003 | 1 | 79.3 | 79.3 |  |  | Stair Tower | [11 empty] | 79.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 79.3 | 2026-09-08 | 1 | 79.3 |  |  | 0 | M304-STR-U2-009 | 2026-09-08 | 1 | 79.3 | 2026-09-17 | 1 | 79.3 | Truong An | M304-173 |  | 3GR003
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT001 | 3PT001 | ONE-POST-228-3PT001 | 1 | 248.5 | 248.5 |  |  | Stair Tower | [11 empty] | 0 | 248.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PT001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT002 | 3PT002 | ONE-POST-228-3PT002 | 1 | 211.9 | 211.9 |  |  | Stair Tower | [11 empty] | 0 | 211.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PT002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB001 | 3VB001 | ONE-VBRACE-228-3VB001 | 1 | 65 | 65 |  |  | Stair Tower | [11 empty] | 65 | 0 |  |  | 0 | 2026-09-08 | 1 | 65 | 2026-09-08 | 1 | 65 |  |  | 0 | M304-STR-U2-009 | 2026-09-08 | 1 | 65 | 2026-09-17 | 1 | 65 | Truong An | M304-173 |  | 3VB001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB002 | 3VB002 | ONE-VBRACE-228-3VB002 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-09-08 | 1 | 64 | 2026-09-08 | 1 | 64 |  |  | 0 | M304-STR-U2-009 | 2026-09-08 | 1 | 64 | 2026-09-17 | 1 | 64 | Truong An | M304-173 |  | 3VB002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(1/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(2/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(3/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(1/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL002
185 | M304 | Shipment 3 Steel Structure U2 | Shipment 3 | Steel Structure U2 | Stair Tower | 2026-04-15 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(2/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM001 | ONE-BEAM-228-001-2BM001 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(1/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(2/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(3/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(4/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(5/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(1/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(2/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(3/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(4/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(5/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM004 | ONE-BEAM-228-001-2BM004 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 54.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 54.1 | 2026-08-10 | 1 | 54.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 54.1 | 2026-08-19 | 1 | 54.1 | Truong An | M304-156 |  | 2BM004
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM005 | ONE-BEAM-228-001-2BM005 | 1 | 66.4 | 66.4 |  |  | Stair Tower | [11 empty] | 66.4 | 0 |  |  | 0 | 2026-08-07 | 1 | 66.4 | 2026-08-10 | 1 | 66.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 66.4 | 2026-08-19 | 1 | 66.4 | Truong An | M304-156 |  | 2BM005
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(1/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(2/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(3/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(4/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(5/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(6/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(1/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(2/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(3/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(4/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(5/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(6/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(1/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(2/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(3/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM009 | ONE-BEAM-228-002-2BM009 | 1 | 25.1 | 25.1 |  |  | Stair Tower | [11 empty] | 25.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 25.1 | 2026-08-10 | 1 | 25.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 25.1 | 2026-08-19 | 1 | 25.1 | Truong An | M304-156 |  | 2BM009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(1/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 30.3 | 0 |  |  | 0 | 2026-08-07 | 1 | 30.3 | 2026-08-10 | 1 | 30.3 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 30.3 | 2026-08-19 | 1 | 30.3 | Truong An | M304-156 |  | 2BM010
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(2/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 30.3 | 0 |  |  | 0 | 2026-08-07 | 1 | 30.3 | 2026-08-10 | 1 | 30.3 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 30.3 | 2026-08-19 | 1 | 30.3 | Truong An | M304-156 |  | 2BM010
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM011 | ONE-BEAM-228-002-2BM011 | 1 | 27 | 27 |  |  | Stair Tower | [11 empty] | 27 | 0 |  |  | 0 | 2026-08-07 | 1 | 27 | 2026-08-10 | 1 | 27 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27 | 2026-08-19 | 1 | 27 | Truong An | M304-156 |  | 2BM011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(1/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(2/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(3/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(1/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(2/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(3/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(4/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(5/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-10 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(6/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 27.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.2 | 2026-08-13 | 1 | 27.2 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.2 | 2026-08-19 | 1 | 27.2 | Truong An | M304-156 |  | 2BM013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM014 | ONE-BEAM-228-003-2BM014 | 1 | 70.8 | 70.8 |  |  | Stair Tower | [11 empty] | 70.8 | 0 |  |  | 0 | 2026-08-12 | 1 | 70.8 | 2026-08-13 | 1 | 70.8 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 70.8 | 2026-08-19 | 1 | 70.8 | Truong An | M304-156 |  | 2BM014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM015 | ONE-BEAM-228-003-2BM015 | 1 | 15.3 | 15.3 |  |  | Stair Tower | [11 empty] | 15.3 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.3 | 2026-08-13 | 1 | 15.3 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.3 | 2026-08-19 | 1 | 15.3 | Truong An | M304-156 |  | 2BM015
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(1/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(2/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(3/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(4/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(5/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(6/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(7/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(8/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(9/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(10/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(11/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(12/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 15.4 | 0 |  |  | 0 | 2026-08-12 | 1 | 15.4 | 2026-08-13 | 1 | 15.4 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 15.4 | 2026-08-19 | 1 | 15.4 | Truong An | M304-156 |  | 2BM016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(1/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(2/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(3/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(4/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(5/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(6/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(1/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM018
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(2/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM018
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(3/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM018
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(4/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM018
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(5/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 101.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 101.2 | 2026-08-06 | 1 | 101.2 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 101.2 | 2026-08-13 | 1 | 101.2 | Truong An | M304-144 |  | 2BM018
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM019 | ONE-BEAM-228-004-2BM019 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 36.6 | 0 |  |  | 0 | 2026-08-05 | 1 | 36.6 | 2026-08-06 | 1 | 36.6 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 36.6 | 2026-08-19 | 1 | 36.6 | Truong An | M304-155 |  | 2BM019
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM020 | ONE-BEAM-228-004-2BM020 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 36.6 | 0 |  |  | 0 | 2026-08-05 | 1 | 36.6 | 2026-08-06 | 1 | 36.6 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 36.6 | 2026-08-19 | 1 | 36.6 | Truong An | M304-155 |  | 2BM020
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM021 | ONE-BEAM-228-004-2BM021 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 30.5 | 0 |  |  | 0 | 2026-08-05 | 1 | 30.5 | 2026-08-06 | 1 | 30.5 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 30.5 | 2026-08-19 | 1 | 30.5 | Truong An | M304-155 |  | 2BM021
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM022 | ONE-BEAM-228-004-2BM022 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 30.5 | 0 |  |  | 0 | 2026-08-05 | 1 | 30.5 | 2026-08-06 | 1 | 30.5 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 30.5 | 2026-08-19 | 1 | 30.5 | Truong An | M304-155 |  | 2BM022
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM023 | ONE-BEAM-228-004-2BM023 | 1 | 97 | 97 |  |  | Stair Tower | [11 empty] | 97 | 0 |  |  | 0 | 2026-08-05 | 1 | 97 | 2026-08-06 | 1 | 97 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 97 | 2026-08-19 | 1 | 97 | Truong An | M304-155 |  | 2BM023
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-002 | 2CL001 | ONE-COLUMN-228-001-2CL001 | 1 | 2989.3 | 2989.3 |  |  | Stair Tower | [11 empty] | 2989.3 | 0 |  |  | 0 | 2026-08-06 | 1 | 2989.3 | 2026-08-10 | 1 | 2989.3 |  |  | 0 | M304-STR-U3-005 | 2026-08-10 | 1 | 2989.3 | 2026-08-16 | 1 | 2989.3 | Truong An | M304-149 | #VALUE! | 2CL001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-004 | 2CL002 | ONE-COLUMN-228-003-2CL002 | 1 | 2181.2 | 2181.2 |  |  | Stair Tower | [11 empty] | 2181.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 2181.2 | 2026-08-08 | 1 | 2181.2 |  |  | 0 | M304-STR-U3-002 | 2026-08-08 | 1 | 2181.2 | 2026-08-16 | 1 | 2181.2 | Truong An | M304-145 | #VALUE! | 2CL002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-006 | 2CL003 | ONE-COLUMN-228-005-2CL003 | 1 | 2995.1 | 2995.1 |  |  | Stair Tower | [11 empty] | 2995.1 | 0 |  |  | 0 | 2026-08-08 | 1 | 2995.1 | 2026-08-10 | 1 | 2995.1 |  |  | 0 | M304-STR-U3-005 | 2026-08-10 | 1 | 2995.1 | 2026-08-16 | 1 | 2995.1 | Truong An | M304-149 | #VALUE! | 2CL003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-008 | 2CL004 | ONE-COLUMN-228-007-2CL004 | 1 | 2603.9 | 2603.9 |  |  | Stair Tower | [11 empty] | 2603.9 | 0 |  |  | 0 | 2026-08-08 | 1 | 2603.9 | 2026-08-11 | 1 | 2603.9 |  |  | 0 | M304-STR-U3-006 | 2026-08-11 | 1 | 2603.9 | 2026-08-16 | 1 | 2603.9 | Truong An | M304-153 | #VALUE! | 2CL004
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-010 | 2CL005 | ONE-COLUMN-228-009-2CL005 | 1 | 2672.5 | 2672.5 |  |  | Stair Tower | [11 empty] | 2672.5 | 0 |  |  | 0 | 2026-08-06 | 1 | 2672.5 | 2026-08-07 | 1 | 2672.5 |  |  | 0 | M304-STR-U3-006 | 2026-08-11 | 1 | 2672.5 | 2026-08-16 | 1 | 2672.5 | Truong An | M304-153 | #VALUE! | 2CL005
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-012 | 2CL006 | ONE-COLUMN-228-011-2CL006 | 1 | 2246.4 | 2246.4 |  |  | Stair Tower | [11 empty] | 2246.4 | 0 |  |  | 0 | 2026-08-05 | 1 | 2246.4 | 2026-08-06 | 1 | 2246.4 |  |  | 0 | M304-STR-U3-002 | 2026-08-08 | 1 | 2246.4 | 2026-08-16 | 1 | 2246.4 | Truong An | M304-145 | #VALUE! | 2CL006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR001 | ONE-GIRDER-228-001-2GR001 | 1 | 290.8 | 290.8 |  |  | Stair Tower | [11 empty] | 290.8 | 0 |  |  | 0 | 2026-08-08 | 1 | 290.8 | 2026-08-08 | 1 | 290.8 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 290.8 | 2026-08-13 | 1 | 290.8 | Truong An | M304-146 |  | 2GR001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR002 | ONE-GIRDER-228-001-2GR002 | 1 | 301.3 | 301.3 |  |  | Stair Tower | [11 empty] | 301.3 | 0 |  |  | 0 | 2026-08-08 | 1 | 301.3 | 2026-08-08 | 1 | 301.3 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 301.3 | 2026-08-13 | 1 | 301.3 | Truong An | M304-146 |  | 2GR002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR003 | ONE-GIRDER-228-001-2GR003 | 1 | 276.4 | 276.4 |  |  | Stair Tower | [11 empty] | 276.4 | 0 |  |  | 0 | 2026-08-05 | 1 | 276.4 | 2026-08-07 | 1 | 276.4 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 276.4 | 2026-08-13 | 1 | 276.4 | Truong An | M304-144 |  | 2GR003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR004 | ONE-GIRDER-228-002-2GR004 | 1 | 280.3 | 280.3 |  |  | Stair Tower | [11 empty] | 280.3 | 0 |  |  | 0 | 2026-08-05 | 1 | 280.3 | 2026-08-07 | 1 | 280.3 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 280.3 | 2026-08-13 | 1 | 280.3 | Truong An | M304-144 |  | 2GR004
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR005 | ONE-GIRDER-228-002-2GR005 | 1 | 280.1 | 280.1 |  |  | Stair Tower | [11 empty] | 280.1 | 0 |  |  | 0 | 2026-08-08 | 1 | 280.1 | 2026-08-08 | 1 | 280.1 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 280.1 | 2026-08-13 | 1 | 280.1 | Truong An | M304-146 |  | 2GR005
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR006 | ONE-GIRDER-228-002-2GR006 | 1 | 279.3 | 279.3 |  |  | Stair Tower | [11 empty] | 279.3 | 0 |  |  | 0 | 2026-08-05 | 1 | 279.3 | 2026-08-07 | 1 | 279.3 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 279.3 | 2026-08-13 | 1 | 279.3 | Truong An | M304-144 |  | 2GR006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR007 | ONE-GIRDER-228-003-2GR007 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 279.7 | 0 |  |  | 0 | 2026-08-05 | 1 | 279.7 | 2026-08-07 | 1 | 279.7 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 279.7 | 2026-08-13 | 1 | 279.7 | Truong An | M304-144 |  | 2GR007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR008 | ONE-GIRDER-228-003-2GR008 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 279.7 | 0 |  |  | 0 | 2026-08-07 | 1 | 279.7 | 2026-08-07 | 1 | 279.7 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 279.7 | 2026-08-13 | 1 | 279.7 | Truong An | M304-144 |  | 2GR008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(1/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  |  | 0 | 2026-08-08 | 1 | 275 | 2026-08-08 | 1 | 275 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275 | 2026-08-13 | 1 | 275 | Truong An | M304-146 |  | 2GR009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(2/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  |  | 0 | 2026-08-08 | 1 | 275 | 2026-08-08 | 1 | 275 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275 | 2026-08-13 | 1 | 275 | Truong An | M304-146 |  | 2GR009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(3/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 275 | 0 |  |  | 0 | 2026-08-08 | 1 | 275 | 2026-08-08 | 1 | 275 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275 | 2026-08-13 | 1 | 275 | Truong An | M304-146 |  | 2GR009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR010 | ONE-GIRDER-228-004-2GR010 | 1 | 294.2 | 294.2 | Thêm mã sửa ở Shop |  | Stair Tower | [11 empty] | 294.2 | 0 |  |  | 0 | 2026-08-05 | 1 | 294.2 | 2026-08-14 | 1 | 294.2 |  |  | 0 | M304-STR-U3-011 | 2026-09-03 | 1 | 294.2 | 2026-09-08 | 1 | 294.2 | Truong An | M304-169 | #VALUE! | 2GR010
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(1/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-05 | 1 | 275.4 | 2026-08-07 | 1 | 275.4 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-144 |  | 2GR011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(2/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-05 | 1 | 275.4 | 2026-08-07 | 1 | 275.4 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-144 |  | 2GR011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(3/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-05 | 1 | 275.4 | 2026-08-07 | 1 | 275.4 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-144 |  | 2GR011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(4/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-05 | 1 | 275.4 | 2026-08-07 | 1 | 275.4 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-144 |  | 2GR011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(5/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-07 | 1 | 275.4 | 2026-08-07 | 1 | 275.4 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-144 |  | 2GR011
|  | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(6/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 | Delete |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(1/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-08 | 1 | 275.4 | 2026-08-08 | 1 | 275.4 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-146 |  | 2GR012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(2/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-08 | 1 | 275.4 | 2026-08-08 | 1 | 275.4 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-146 |  | 2GR012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(3/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-08 | 1 | 275.4 | 2026-08-08 | 1 | 275.4 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-146 |  | 2GR012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(4/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-08 | 1 | 275.4 | 2026-08-08 | 1 | 275.4 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-146 |  | 2GR012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(5/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 275.4 | 0 |  |  | 0 | 2026-08-08 | 1 | 275.4 | 2026-08-08 | 1 | 275.4 |  |  | 0 | M304-STR-U3-003 | 2026-08-08 | 1 | 275.4 | 2026-08-13 | 1 | 275.4 | Truong An | M304-146 |  | 2GR012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR013 | ONE-GIRDER-228-004-2GR013 | 1 | 272.8 | 272.8 |  |  | Stair Tower | [11 empty] | 272.8 | 0 |  |  | 0 | 2026-08-05 | 1 | 272.8 | 2026-08-07 | 1 | 272.8 |  |  | 0 | M304-STR-U3-001 | 2026-08-07 | 1 | 272.8 | 2026-08-13 | 1 | 272.8 | Truong An | M304-144 |  | 2GR013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-2GR014 | 2GR014 | ONE-GIRDER-228-2GR014 | 1 | 294.2 | 294.2 |  |  | Stair Tower | [11 empty] | 294.2 | 0 |  |  | 0 | 2026-08-14 | 1 | 294.2 | 2026-08-14 | 1 | 294.2 |  |  | 0 | M304-STR-U3-011 | 2026-09-03 | 1 | 294.2 | 2026-09-08 | 1 | 294.2 | Truong An | M304-169 | #VALUE! | 2GR014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT001 | ONE-POST-228-001-2PT001 | 1 | 112.8 | 112.8 |  |  | Stair Tower | [11 empty] | 112.8 | 0 |  |  | 0 | 2026-08-07 | 1 | 112.8 | 2026-08-12 | 1 | 112.8 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 112.8 | 2026-08-19 | 1 | 112.8 | Truong An | M304-155 |  | 2PT001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT003 | ONE-POST-228-001-2PT003 | 1 | 107 | 107 |  |  | Stair Tower | [11 empty] | 107 | 0 |  |  | 0 | 2026-08-07 | 1 | 107 | 2026-08-12 | 1 | 107 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 107 | 2026-08-19 | 1 | 107 | Truong An | M304-155 |  | 2PT003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT004 | ONE-POST-228-001-2PT004 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 104.7 | 0 |  |  | 0 | 2026-08-07 | 1 | 104.7 | 2026-08-12 | 1 | 104.7 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.7 | 2026-08-19 | 1 | 104.7 | Truong An | M304-155 |  | 2PT004
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT005 | ONE-POST-228-001-2PT005 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 104.7 | 0 |  |  | 0 | 2026-08-07 | 1 | 104.7 | 2026-08-12 | 1 | 104.7 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.7 | 2026-08-19 | 1 | 104.7 | Truong An | M304-155 |  | 2PT005
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(1/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  |  | 0 | 2026-08-12 | 1 | 104.2 | 2026-08-12 | 1 | 104.2 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.2 | 2026-08-19 | 1 | 104.2 | Truong An | M304-155 |  | 2PT007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(2/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  |  | 0 | 2026-08-12 | 1 | 104.2 | 2026-08-12 | 1 | 104.2 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.2 | 2026-08-19 | 1 | 104.2 | Truong An | M304-155 |  | 2PT007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(3/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  |  | 0 | 2026-08-12 | 1 | 104.2 | 2026-08-12 | 1 | 104.2 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.2 | 2026-08-19 | 1 | 104.2 | Truong An | M304-155 |  | 2PT007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT008 | ONE-POST-228-002-2PT008 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 104.2 | 2026-08-10 | 1 | 104.2 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.2 | 2026-08-19 | 1 | 104.2 | Truong An | M304-155 |  | 2PT008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT009 | ONE-POST-228-002-2PT009 | 1 | 110.9 | 110.9 |  |  | Stair Tower | [11 empty] | 110.9 | 0 |  |  | 0 | 2026-08-07 | 1 | 110.9 | 2026-08-10 | 1 | 110.9 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 110.9 | 2026-08-19 | 1 | 110.9 | Truong An | M304-155 |  | 2PT009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT010 | ONE-POST-228-002-2PT010 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 104.2 | 0 |  |  | 0 | 2026-08-07 | 1 | 104.2 | 2026-08-10 | 1 | 104.2 |  |  | 0 | M304-STR-U3-009 | 2026-08-12 | 1 | 104.2 | 2026-08-19 | 1 | 104.2 | Truong An | M304-155 |  | 2PT010
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB001 | ONE-VBRACE-228-001-2VB001 | 1 | 25.7 | 25.7 |  |  | Stair Tower | [11 empty] | 25.7 | 0 |  |  | 0 | 2026-08-07 | 1 | 25.7 | 2026-08-10 | 1 | 25.7 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 25.7 | 2026-08-19 | 1 | 25.7 | Truong An | M304-156 |  | 2VB001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB002 | ONE-VBRACE-228-001-2VB002 | 1 | 27.7 | 27.7 |  |  | Stair Tower | [11 empty] | 27.7 | 0 |  |  | 0 | 2026-08-07 | 1 | 27.7 | 2026-08-10 | 1 | 27.7 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 27.7 | 2026-08-19 | 1 | 27.7 | Truong An | M304-156 |  | 2VB002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB003 | ONE-VBRACE-228-001-2VB003 | 1 | 20.1 | 20.1 |  |  | Stair Tower | [11 empty] | 20.1 | 0 |  |  | 0 | 2026-08-07 | 1 | 20.1 | 2026-08-10 | 1 | 20.1 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 20.1 | 2026-08-19 | 1 | 20.1 | Truong An | M304-156 |  | 2VB003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB004 | ONE-VBRACE-228-001-2VB004 | 1 | 20.3 | 20.3 |  |  | Stair Tower | [11 empty] | 20.3 | 0 |  |  | 0 | 2026-08-07 | 1 | 20.3 | 2026-08-10 | 1 | 20.3 |  |  | 0 | M304-STR-U3-010 | 2026-08-13 | 1 | 20.3 | 2026-08-19 | 1 | 20.3 | Truong An | M304-156 |  | 2VB004
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB005 | ONE-VBRACE-228-001-2VB005 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB005
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB006 | ONE-VBRACE-228-001-2VB006 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB006
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(1/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(2/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(3/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(4/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(5/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(6/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(7/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(8/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(9/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(10/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB007
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(1/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(2/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(3/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(4/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(5/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(6/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(7/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(8/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(9/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(10/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(11/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(12/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(13/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(14/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-08-03 | 1 | 64 | 2026-08-07 | 1 | 64 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 64 | 2026-08-13 | 1 | 64 | Truong An | M304-154 |  | 2VB008
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(1/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  |  | 0 | 2026-08-03 | 1 | 48.6 | 2026-08-07 | 1 | 48.6 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 48.6 | 2026-08-13 | 1 | 48.6 | Truong An | M304-154 |  | 2VB009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(2/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  |  | 0 | 2026-08-03 | 1 | 48.6 | 2026-08-07 | 1 | 48.6 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 48.6 | 2026-08-13 | 1 | 48.6 | Truong An | M304-154 |  | 2VB009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(3/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  |  | 0 | 2026-08-03 | 1 | 48.6 | 2026-08-07 | 1 | 48.6 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 48.6 | 2026-08-13 | 1 | 48.6 | Truong An | M304-154 |  | 2VB009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(4/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  |  | 0 | 2026-08-03 | 1 | 48.6 | 2026-08-07 | 1 | 48.6 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 48.6 | 2026-08-13 | 1 | 48.6 | Truong An | M304-154 |  | 2VB009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(5/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 48.6 | 0 |  |  | 0 | 2026-08-03 | 1 | 48.6 | 2026-08-07 | 1 | 48.6 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 48.6 | 2026-08-13 | 1 | 48.6 | Truong An | M304-154 |  | 2VB009
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB010 | ONE-VBRACE-228-002-2VB010 | 1 | 49.3 | 49.3 |  |  | Stair Tower | [11 empty] | 49.3 | 0 |  |  | 0 | 2026-08-03 | 1 | 49.3 | 2026-08-07 | 1 | 49.3 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 49.3 | 2026-08-13 | 1 | 49.3 | Truong An | M304-154 |  | 2VB010
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB011 | ONE-VBRACE-228-002-2VB011 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 60 | 0 |  |  | 0 | 2026-08-03 | 1 | 60 | 2026-08-07 | 1 | 60 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 60 | 2026-08-13 | 1 | 60 | Truong An | M304-154 |  | 2VB011
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB012 | ONE-VBRACE-228-002-2VB012 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 60 | 0 |  |  | 0 | 2026-08-03 | 1 | 60 | 2026-08-07 | 1 | 60 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 60 | 2026-08-13 | 1 | 60 | Truong An | M304-154 |  | 2VB012
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(1/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-07 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(2/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-07 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB013
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(1/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-07 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(2/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-07 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(3/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-09 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(4/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-09 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(5/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-09 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(6/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 84 | 0 |  |  | 0 | 2026-08-03 | 1 | 84 | 2026-08-09 | 1 | 84 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 84 | 2026-08-13 | 1 | 84 | Truong An | M304-154 |  | 2VB014
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(1/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  |  | 0 | 2026-08-03 | 1 | 92 | 2026-08-09 | 1 | 92 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 92 | 2026-08-13 | 1 | 92 | Truong An | M304-154 |  | 2VB015
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(2/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  |  | 0 | 2026-08-03 | 1 | 92 | 2026-08-09 | 1 | 92 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 92 | 2026-08-13 | 1 | 92 | Truong An | M304-154 |  | 2VB015
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(1/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  |  | 0 | 2026-08-03 | 1 | 92 | 2026-08-09 | 1 | 92 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 92 | 2026-08-13 | 1 | 92 | Truong An | M304-154 |  | 2VB016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(2/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 92 | 0 |  |  | 0 | 2026-08-03 | 1 | 92 | 2026-08-09 | 1 | 92 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 92 | 2026-08-13 | 1 | 92 | Truong An | M304-154 |  | 2VB016
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(1/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  |  | 0 | 2026-08-03 | 1 | 63.3 | 2026-08-09 | 1 | 63.3 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 63.3 | 2026-08-13 | 1 | 63.3 | Truong An | M304-154 |  | 2VB017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(2/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  |  | 0 | 2026-08-03 | 1 | 63.3 | 2026-08-09 | 1 | 63.3 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 63.3 | 2026-08-13 | 1 | 63.3 | Truong An | M304-154 |  | 2VB017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(3/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 63.3 | 0 |  |  | 0 | 2026-08-03 | 1 | 63.3 | 2026-08-09 | 1 | 63.3 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 63.3 | 2026-08-13 | 1 | 63.3 | Truong An | M304-154 |  | 2VB017
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB018 | ONE-VBRACE-228-003-2VB018 | 1 | 66.2 | 66.2 |  |  | Stair Tower | [11 empty] | 66.2 | 0 |  |  | 0 | 2026-08-03 | 1 | 66.2 | 2026-08-09 | 1 | 66.2 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 66.2 | 2026-08-13 | 1 | 66.2 | Truong An | M304-154 |  | 2VB018
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB019 | ONE-VBRACE-228-003-2VB019 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 77.2 | 0 |  |  | 0 | 2026-08-03 | 1 | 77.2 | 2026-08-09 | 1 | 77.2 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 77.2 | 2026-08-13 | 1 | 77.2 | Truong An | M304-154 |  | 2VB019
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB020 | ONE-VBRACE-228-003-2VB020 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 77.2 | 0 |  |  | 0 | 2026-08-03 | 1 | 77.2 | 2026-08-09 | 1 | 77.2 |  |  | 0 | M304-STR-U3-007 | 2026-08-11 | 1 | 77.2 | 2026-08-13 | 1 | 77.2 | Truong An | M304-154 |  | 2VB020
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(1/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 |  |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3GR001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(2/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 |  |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3GR001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(1/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U3-013 | 2026-09-08 | 1 | 35.3 | 2026-09-20 | 1 | 35.3 | Truong An | M304-174 | #VALUE! | 3GR002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(2/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U3-013 | 2026-09-08 | 1 | 35.3 | 2026-09-20 | 1 | 35.3 | Truong An | M304-174 | #VALUE! | 3GR002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(3/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U3-013 | 2026-09-08 | 1 | 35.3 | 2026-09-20 | 1 | 35.3 | Truong An | M304-174 | #VALUE! | 3GR002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR003 | 3GR003 | ONE-GIRDER-228-3GR003 | 1 | 79.3 | 79.3 |  |  | Stair Tower | [11 empty] | 79.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 79.3 | 2026-09-08 | 1 | 79.3 |  |  | 0 | M304-STR-U3-013 | 2026-09-08 | 1 | 79.3 | 2026-09-20 | 1 | 79.3 | Truong An | M304-174 | #VALUE! | 3GR003
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT001 | 3PT001 | ONE-POST-228-3PT001 | 1 | 248.5 | 248.5 |  |  | Stair Tower | [11 empty] | 0 | 248.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PT001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT002 | 3PT002 | ONE-POST-228-3PT002 | 1 | 211.9 | 211.9 |  |  | Stair Tower | [11 empty] | 0 | 211.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PT002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB001 | 3VB001 | ONE-VBRACE-228-3VB001 | 1 | 65 | 65 |  |  | Stair Tower | [11 empty] | 65 | 0 |  |  | 0 | 2026-09-08 | 1 | 65 | 2026-09-08 | 1 | 65 |  |  | 0 | M304-STR-U3-013 | 2026-09-08 | 1 | 65 | 2026-09-20 | 1 | 65 | Truong An | M304-174 | #VALUE! | 3VB001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB002 | 3VB002 | ONE-VBRACE-228-3VB002 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-09-08 | 1 | 64 | 2026-09-08 | 1 | 64 |  |  | 0 | M304-STR-U3-013 | 2026-09-08 | 1 | 64 | 2026-09-20 | 1 | 64 | Truong An | M304-174 | #VALUE! | 3VB002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(1/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PL001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(2/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PL001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(3/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PL001
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(1/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PL002
185 | M304 | Shipment 5 Steel Structure U3 | Shipment 5 | Steel Structure U3 | Stair Tower | 2026-05-05 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(2/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  | #VALUE! | 3PL002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM001 | ONE-BEAM-228-001-2BM001 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(1/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(2/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(3/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(4/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM002(5/5) | 5-BEAMS-228-001-2BM002 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(1/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(2/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(3/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(4/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM003(5/5) | 5-BEAMS-228-001-2BM003 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM004 | ONE-BEAM-228-001-2BM004 | 1 | 54.1 | 54.1 |  |  | Stair Tower | [11 empty] | 0 | 54.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM004
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM005 | ONE-BEAM-228-001-2BM005 | 1 | 66.4 | 66.4 |  |  | Stair Tower | [11 empty] | 0 | 66.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM005
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(1/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(2/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(3/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(4/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(5/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-001 | 2BM006(6/6) | 6-BEAMS-228-001-2BM006 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(1/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(2/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(3/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(4/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(5/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM007(6/6) | 6-BEAMS-228-002-2BM007 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(1/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(2/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM008(3/3) | 3-BEAMS-228-002-2BM008 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM009 | ONE-BEAM-228-002-2BM009 | 1 | 25.1 | 25.1 |  |  | Stair Tower | [11 empty] | 0 | 25.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(1/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 0 | 30.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM010
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM010(2/2) | 2-BEAMS-228-002-2BM010 | 1 | 30.3 | 30.3 |  |  | Stair Tower | [11 empty] | 0 | 30.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM010
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM011 | ONE-BEAM-228-002-2BM011 | 1 | 27 | 27 |  |  | Stair Tower | [11 empty] | 0 | 27 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(1/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(2/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM012(3/3) | 3-BEAMS-228-002-2BM012 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(1/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(2/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(3/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(4/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(5/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-002 | 2BM013(6/6) | 6-BEAMS-228-002-2BM013 | 1 | 27.2 | 27.2 |  |  | Stair Tower | [11 empty] | 0 | 27.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM014 | ONE-BEAM-228-003-2BM014 | 1 | 70.8 | 70.8 |  |  | Stair Tower | [11 empty] | 0 | 70.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM015 | ONE-BEAM-228-003-2BM015 | 1 | 15.3 | 15.3 |  |  | Stair Tower | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM015
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(1/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(2/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(3/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(4/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(5/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(6/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(7/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(8/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(9/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(10/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(11/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM016(12/12) | 12-BEAMS-228-003-2BM016 | 1 | 15.4 | 15.4 |  |  | Stair Tower | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(1/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(2/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(3/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(4/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(5/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM017(6/6) | 6-BEAMS-228-003-2BM017 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(1/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM018
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(2/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM018
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(3/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM018
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(4/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM018
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-003 | 2BM018(5/5) | 5-BEAMS-228-003-2BM018 | 1 | 101.2 | 101.2 |  |  | Stair Tower | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM018
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM019 | ONE-BEAM-228-004-2BM019 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 0 | 36.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM019
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM020 | ONE-BEAM-228-004-2BM020 | 1 | 36.6 | 36.6 |  |  | Stair Tower | [11 empty] | 0 | 36.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM020
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM021 | ONE-BEAM-228-004-2BM021 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 0 | 30.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM021
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM022 | ONE-BEAM-228-004-2BM022 | 1 | 30.5 | 30.5 |  |  | Stair Tower | [11 empty] | 0 | 30.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM022
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1BM-004 | 2BM023 | ONE-BEAM-228-004-2BM023 | 1 | 97 | 97 |  |  | Stair Tower | [11 empty] | 0 | 97 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2BM023
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-002 | 2CL001 | ONE-COLUMN-228-001-2CL001 | 1 | 2989.3 | 2989.3 |  |  | Stair Tower | [11 empty] | 0 | 2989.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2CL001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-004 | 2CL002 | ONE-COLUMN-228-003-2CL002 | 1 | 2181.2 | 2181.2 |  |  | Stair Tower | [11 empty] | 0 | 2181.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2CL002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-006 | 2CL003 | ONE-COLUMN-228-005-2CL003 | 1 | 2995.1 | 2995.1 |  |  | Stair Tower | [11 empty] | 0 | 2995.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2CL003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-008 | 2CL004 | ONE-COLUMN-228-007-2CL004 | 1 | 2603.9 | 2603.9 |  |  | Stair Tower | [11 empty] | 0 | 2603.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2CL004
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-010 | 2CL005 | ONE-COLUMN-228-009-2CL005 | 1 | 2672.5 | 2672.5 |  |  | Stair Tower | [11 empty] | 0 | 2672.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2CL005
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-228-1CL-012 | 2CL006 | ONE-COLUMN-228-011-2CL006 | 1 | 2246.4 | 2246.4 |  |  | Stair Tower | [11 empty] | 0 | 2246.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2CL006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR001 | ONE-GIRDER-228-001-2GR001 | 1 | 290.8 | 290.8 |  |  | Stair Tower | [11 empty] | 0 | 290.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR002 | ONE-GIRDER-228-001-2GR002 | 1 | 301.3 | 301.3 |  |  | Stair Tower | [11 empty] | 0 | 301.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-001 | 2GR003 | ONE-GIRDER-228-001-2GR003 | 1 | 276.4 | 276.4 |  |  | Stair Tower | [11 empty] | 0 | 276.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR004 | ONE-GIRDER-228-002-2GR004 | 1 | 280.3 | 280.3 |  |  | Stair Tower | [11 empty] | 0 | 280.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR004
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR005 | ONE-GIRDER-228-002-2GR005 | 1 | 280.1 | 280.1 |  |  | Stair Tower | [11 empty] | 0 | 280.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR005
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-002 | 2GR006 | ONE-GIRDER-228-002-2GR006 | 1 | 279.3 | 279.3 |  |  | Stair Tower | [11 empty] | 0 | 279.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR007 | ONE-GIRDER-228-003-2GR007 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 0 | 279.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR008 | ONE-GIRDER-228-003-2GR008 | 1 | 279.7 | 279.7 |  |  | Stair Tower | [11 empty] | 0 | 279.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(1/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 0 | 275 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(2/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 0 | 275 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-003 | 2GR009(3/3) | 3-GIRDERS-228-003-2GR009 | 1 | 275 | 275 |  |  | Stair Tower | [11 empty] | 0 | 275 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR010 | ONE-GIRDER-228-004-2GR010 | 1 | 294.2 | 294.2 | Thêm mã sửa ở Shop |  | Stair Tower | [11 empty] | 0 | 294.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR010
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(1/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(2/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(3/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(4/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(5/5) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR011
|  | Shipment 6 Steel Structure U4 | Shipment 6 | Steel Structure U4 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR011(6/6) | 6-GIRDERS-228-004-2GR011 | 1 | 275.4 | 275.4 | Delete |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | AMC GT-HTP |  |  | 2GR011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(1/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(2/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(3/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(4/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR012(5/5) | 5-GIRDERS-228-004-2GR012 | 1 | 275.4 | 275.4 |  |  | Stair Tower | [11 empty] | 0 | 275.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1GR-004 | 2GR013 | ONE-GIRDER-228-004-2GR013 | 1 | 272.8 | 272.8 |  |  | Stair Tower | [11 empty] | 0 | 272.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-2GR014 | 2GR014 | ONE-GIRDER-228-2GR014 | 1 | 294.2 | 294.2 | ADD |  | Stair Tower | [11 empty] | 0 | 294.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2GR014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT001 | ONE-POST-228-001-2PT001 | 1 | 112.8 | 112.8 |  |  | Stair Tower | [11 empty] | 0 | 112.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT003 | ONE-POST-228-001-2PT003 | 1 | 107 | 107 |  |  | Stair Tower | [11 empty] | 0 | 107 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT004 | ONE-POST-228-001-2PT004 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 0 | 104.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT004
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-001 | 2PT005 | ONE-POST-228-001-2PT005 | 1 | 104.7 | 104.7 |  |  | Stair Tower | [11 empty] | 0 | 104.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT005
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(1/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 0 | 104.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(2/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 0 | 104.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT007(3/3) | 3-POSTS-228-002-2PT007 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 0 | 104.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT008 | ONE-POST-228-002-2PT008 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 0 | 104.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT009 | ONE-POST-228-002-2PT009 | 1 | 110.9 | 110.9 |  |  | Stair Tower | [11 empty] | 0 | 110.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1PT-002 | 2PT010 | ONE-POST-228-002-2PT010 | 1 | 104.2 | 104.2 |  |  | Stair Tower | [11 empty] | 0 | 104.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2PT010
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB001 | ONE-VBRACE-228-001-2VB001 | 1 | 25.7 | 25.7 |  |  | Stair Tower | [11 empty] | 0 | 25.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB002 | ONE-VBRACE-228-001-2VB002 | 1 | 27.7 | 27.7 |  |  | Stair Tower | [11 empty] | 0 | 27.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB003 | ONE-VBRACE-228-001-2VB003 | 1 | 20.1 | 20.1 |  |  | Stair Tower | [11 empty] | 0 | 20.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB004 | ONE-VBRACE-228-001-2VB004 | 1 | 20.3 | 20.3 |  |  | Stair Tower | [11 empty] | 0 | 20.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB004
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB005 | ONE-VBRACE-228-001-2VB005 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB005
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB006 | ONE-VBRACE-228-001-2VB006 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB006
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(1/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(2/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(3/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(4/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(5/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(6/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(7/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(8/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(9/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB007(10/10) | 10-VBRACES-228-001-2VB007 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB007
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(1/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(2/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(3/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(4/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(5/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(6/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(7/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(8/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(9/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(10/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(11/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(12/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(13/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-001 | 2VB008(14/14) | 14-VBRACES-228-001-2VB008 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 0 | 64 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB008
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(1/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 0 | 48.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(2/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 0 | 48.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(3/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 0 | 48.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(4/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 0 | 48.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB009(5/5) | 5-VBRACES-228-002-2VB009 | 1 | 48.6 | 48.6 |  |  | Stair Tower | [11 empty] | 0 | 48.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB009
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB010 | ONE-VBRACE-228-002-2VB010 | 1 | 49.3 | 49.3 |  |  | Stair Tower | [11 empty] | 0 | 49.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB010
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB011 | ONE-VBRACE-228-002-2VB011 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 0 | 60 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB011
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB012 | ONE-VBRACE-228-002-2VB012 | 1 | 60 | 60 |  |  | Stair Tower | [11 empty] | 0 | 60 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB012
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(1/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-002 | 2VB013(2/2) | 2-VBRACES-228-002-2VB013 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB013
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(1/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(2/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(3/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(4/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(5/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB014(6/6) | 6-VBRACES-228-003-2VB014 | 1 | 84 | 84 |  |  | Stair Tower | [11 empty] | 0 | 84 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB014
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(1/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 0 | 92 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB015
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB015(2/2) | 2-VBRACES-228-003-2VB015 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 0 | 92 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB015
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(1/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 0 | 92 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB016(2/2) | 2-VBRACES-228-003-2VB016 | 1 | 92 | 92 |  |  | Stair Tower | [11 empty] | 0 | 92 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB016
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(1/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 0 | 63.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(2/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 0 | 63.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB017(3/3) | 3-VBRACES-228-003-2VB017 | 1 | 63.3 | 63.3 |  |  | Stair Tower | [11 empty] | 0 | 63.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB017
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB018 | ONE-VBRACE-228-003-2VB018 | 1 | 66.2 | 66.2 |  |  | Stair Tower | [11 empty] | 0 | 66.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB018
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB019 | ONE-VBRACE-228-003-2VB019 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 0 | 77.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB019
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-1VB-003 | 2VB020 | ONE-VBRACE-228-003-2VB020 | 1 | 77.2 | 77.2 |  |  | Stair Tower | [11 empty] | 0 | 77.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 2VB020
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(1/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 |  |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3GR001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR001 | 3GR001(2/2) | 2-GIRDERS-228-3GR001 | 1 | 151.6 | 151.6 |  |  | Stair Tower | [11 empty] | 0 | 151.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3GR001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(1/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U5-001 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-175 |  | 3GR002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(2/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U5-001 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-175 |  | 3GR002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR002 | 3GR002(3/3) | 3-GIRDERS-228-3GR002 | 1 | 35.3 | 35.3 |  |  | Stair Tower | [11 empty] | 35.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 35.3 | 2026-09-08 | 1 | 35.3 |  |  | 0 | M304-STR-U5-001 | 2026-09-08 | 1 | 35.3 | 2026-09-17 | 1 | 35.3 | Truong An | M304-175 |  | 3GR002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3GR003 | 3GR003 | ONE-GIRDER-228-3GR003 | 1 | 79.3 | 79.3 |  |  | Stair Tower | [11 empty] | 79.3 | 0 |  |  | 0 | 2026-09-08 | 1 | 79.3 | 2026-09-08 | 1 | 79.3 |  |  | 0 | M304-STR-U5-001 | 2026-09-08 | 1 | 79.3 | 2026-09-17 | 1 | 79.3 | Truong An | M304-175 |  | 3GR003
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT001 | 3PT001 | ONE-POST-228-3PT001 | 1 | 248.5 | 248.5 |  |  | Stair Tower | [11 empty] | 0 | 248.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PT001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PT002 | 3PT002 | ONE-POST-228-3PT002 | 1 | 211.9 | 211.9 |  |  | Stair Tower | [11 empty] | 0 | 211.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PT002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB001 | 3VB001 | ONE-VBRACE-228-3VB001 | 1 | 65 | 65 |  |  | Stair Tower | [11 empty] | 65 | 0 |  |  | 0 | 2026-09-08 | 1 | 65 | 2026-09-08 | 1 | 65 |  |  | 0 | M304-STR-U5-001 | 2026-09-08 | 1 | 65 | 2026-09-17 | 1 | 65 | Truong An | M304-175 |  | 3VB001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3VB002 | 3VB002 | ONE-VBRACE-228-3VB002 | 1 | 64 | 64 |  |  | Stair Tower | [11 empty] | 64 | 0 |  |  | 0 | 2026-09-08 | 1 | 64 | 2026-09-08 | 1 | 64 |  |  | 0 | M304-STR-U5-001 | 2026-09-08 | 1 | 64 | 2026-09-17 | 1 | 64 | Truong An | M304-175 |  | 3VB002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(1/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(2/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL001 | 3PL001(3/3) | 3-PLATES-228-3PL001 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL001
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(1/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Stair Tower | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-3PL002 | 3PL002(2/2) | 2-PLATES-228-3PL002 | 1 | 1.4 | 1.4 |  |  | Stair Tower | [11 empty] | 0 | 1.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An |  |  | 3PL002
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM001 | ONE-BEAM-228-001-0BM001 | 1 | 116.4 | 116.4 |  |  | Steel Structure | [11 empty] | 0 | 116.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM002 | ONE-BEAM-228-001-0BM002 | 1 | 269.1 | 269.1 |  |  | Steel Structure | [11 empty] | 0 | 269.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM003(1/2) | 8-BEAMS-228-001-0BM003 | 1 | 47.1 | 47.1 |  |  | Steel Structure | [11 empty] | 0 | 47.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM003(2/2) | 8-BEAMS-228-001-0BM003 | 1 | 47.1 | 47.1 |  |  | Steel Structure | [11 empty] | 0 | 47.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM004 | ONE-BEAM-228-001-0BM004 | 1 | 164.7 | 164.7 |  |  | Steel Structure | [11 empty] | 0 | 164.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM292(1/6) | 6-BEAMS-228-001-0BM292 | 1 | 46 | 46 |  |  | Steel Structure | [11 empty] | 0 | 46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM292(2/6) | 6-BEAMS-228-001-0BM292 | 1 | 46 | 46 |  |  | Steel Structure | [11 empty] | 0 | 46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM292(3/6) | 6-BEAMS-228-001-0BM292 | 1 | 46 | 46 |  |  | Steel Structure | [11 empty] | 0 | 46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM292(4/6) | 6-BEAMS-228-001-0BM292 | 1 | 46 | 46 |  |  | Steel Structure | [11 empty] | 0 | 46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM292(5/6) | 6-BEAMS-228-001-0BM292 | 1 | 46 | 46 |  |  | Steel Structure | [11 empty] | 0 | 46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-001 | 0BM292(6/6) | 6-BEAMS-228-001-0BM292 | 1 | 46 | 46 |  |  | Steel Structure | [11 empty] | 0 | 46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-002 | 0BM005 | ONE-BEAM-228-002-0BM005 | 1 | 470.3 | 470.3 |  |  | Steel Structure | [11 empty] | 0 | 470.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-002 | 0BM006 | ONE-BEAM-228-002-0BM006 | 1 | 257.1 | 257.1 |  |  | Steel Structure | [11 empty] | 0 | 257.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
185 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM-002 | 0BM007 | ONE-BEAM-228-002-0BM007 | 1 | 118 | 118 |  |  | Steel Structure | [11 empty] | 0 | 118 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
186 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR001(1/2) | 2-GIRDERS-228-001-0GR001 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
187 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR001(2/2) | 2-GIRDERS-228-001-0GR001 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
188 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR002(1/2) | 2-GIRDERS-228-001-0GR002 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
189 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR002(2/2) | 2-GIRDERS-228-001-0GR002 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
190 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR003(1/2) | 2-GIRDERS-228-001-0GR003 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
191 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR003(2/2) | 2-GIRDERS-228-001-0GR003 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
192 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR004(1/2) | 2-GIRDERS-228-001-0GR004 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
193 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-001 | 0GR004(2/2) | 2-GIRDERS-228-001-0GR004 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
194 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR005 | ONE-GIRDER-228-002-0GR005 | 1 | 110.1 | 110.1 |  |  | Steel Structure | [11 empty] | 0 | 110.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
195 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR006 | ONE-GIRDER-228-002-0GR006 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
196 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR007 | ONE-GIRDER-228-002-0GR007 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
197 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR008 | ONE-GIRDER-228-002-0GR008 | 1 | 88 | 88 |  |  | Steel Structure | [11 empty] | 0 | 88 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
198 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR009 | ONE-GIRDER-228-002-0GR009 | 1 | 76.1 | 76.1 |  |  | Steel Structure | [11 empty] | 0 | 76.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
199 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR010 | ONE-GIRDER-228-002-0GR010 | 1 | 76.1 | 76.1 |  |  | Steel Structure | [11 empty] | 0 | 76.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
200 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-002 | 0GR011 | ONE-GIRDER-228-002-0GR011 | 1 | 81.6 | 81.6 |  |  | Steel Structure | [11 empty] | 0 | 81.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
201 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR012 | ONE-GIRDER-228-003-0GR012 | 1 | 73.9 | 73.9 |  |  | Steel Structure | [11 empty] | 0 | 73.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
202 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR013 | ONE-GIRDER-228-003-0GR013 | 1 | 73.9 | 73.9 |  |  | Steel Structure | [11 empty] | 0 | 73.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
203 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR014 | ONE-GIRDER-228-003-0GR014 | 1 | 117.8 | 117.8 |  |  | Steel Structure | [11 empty] | 0 | 117.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
204 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR015(1/2) | 2-GIRDERS-228-003-0GR015 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
205 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR015(2/2) | 2-GIRDERS-228-003-0GR015 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
206 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR016 | ONE-GIRDER-228-003-0GR016 | 1 | 110.1 | 110.1 |  |  | Steel Structure | [11 empty] | 0 | 110.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
207 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-003 | 0GR017 | ONE-GIRDER-228-003-0GR017 | 1 | 110.1 | 110.1 |  |  | Steel Structure | [11 empty] | 0 | 110.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
208 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-004 | 0GR025 | ONE-GIRDER-228-004-0GR025 | 1 | 99.8 | 99.8 |  |  | Steel Structure | [11 empty] | 0 | 99.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
209 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-004 | 0GR026 | ONE-GIRDER-228-004-0GR026 | 1 | 78 | 78 |  |  | Steel Structure | [11 empty] | 0 | 78 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
210 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-004 | 0GR027 | ONE-GIRDER-228-004-0GR027 | 1 | 93.2 | 93.2 |  |  | Steel Structure | [11 empty] | 0 | 93.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
211 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR018(1/2) | 2-GIRDERS-228-005-0GR018 | 1 | 80.5 | 80.5 |  |  | Steel Structure | [11 empty] | 0 | 80.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
212 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR018(2/2) | 2-GIRDERS-228-005-0GR018 | 1 | 80.5 | 80.5 |  |  | Steel Structure | [11 empty] | 0 | 80.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
213 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR019 | ONE-GIRDER-228-005-0GR019 | 1 | 128 | 128 |  |  | Steel Structure | [11 empty] | 0 | 128 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
214 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR020 | ONE-GIRDER-228-005-0GR020 | 1 | 130.2 | 130.2 |  |  | Steel Structure | [11 empty] | 0 | 130.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
215 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR021 | ONE-GIRDER-228-005-0GR021 | 1 | 78.8 | 78.8 |  |  | Steel Structure | [11 empty] | 0 | 78.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
216 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR022 | ONE-GIRDER-228-005-0GR022 | 1 | 82.7 | 82.7 |  |  | Steel Structure | [11 empty] | 0 | 82.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
217 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR023 | ONE-GIRDER-228-005-0GR023 | 1 | 80.5 | 80.5 |  |  | Steel Structure | [11 empty] | 0 | 80.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
218 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-005 | 0GR024 | ONE-GIRDER-228-005-0GR024 | 1 | 82.1 | 82.1 |  |  | Steel Structure | [11 empty] | 0 | 82.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
219 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR028(1/2) | 2-GIRDERS-228-006-0GR028 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
220 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR028(2/2) | 2-GIRDERS-228-006-0GR028 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
221 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR029(1/2) | 2-GIRDERS-228-006-0GR029 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
222 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR029(2/2) | 2-GIRDERS-228-006-0GR029 | 1 | 116.7 | 116.7 |  |  | Steel Structure | [11 empty] | 0 | 116.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
223 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR030(1/2) | 2-GIRDERS-228-006-0GR030 | 1 | 77.7 | 77.7 |  |  | Steel Structure | [11 empty] | 0 | 77.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
224 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR030(2/2) | 2-GIRDERS-228-006-0GR030 | 1 | 77.7 | 77.7 |  |  | Steel Structure | [11 empty] | 0 | 77.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
225 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR031 | ONE-GIRDER-228-006-0GR031 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
226 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-006 | 0GR032 | ONE-GIRDER-228-006-0GR032 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
227 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-007 | 0GR033 | ONE-GIRDER-228-007-0GR033 | 1 | 211.9 | 211.9 |  |  | Steel Structure | [11 empty] | 0 | 211.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
228 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-007 | 0GR034 | ONE-GIRDER-228-007-0GR034 | 1 | 296.5 | 296.5 |  |  | Steel Structure | [11 empty] | 0 | 296.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
229 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-007 | 0GR035 | ONE-GIRDER-228-007-0GR035 | 1 | 209.7 | 209.7 |  |  | Steel Structure | [11 empty] | 0 | 209.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
230 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-008 | 0GR036 | ONE-GIRDER-228-008-0GR036 | 1 | 96.8 | 96.8 |  |  | Steel Structure | [11 empty] | 0 | 96.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
231 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-008 | 0GR037 | ONE-GIRDER-228-008-0GR037 | 1 | 90.2 | 90.2 |  |  | Steel Structure | [11 empty] | 0 | 90.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
232 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-008 | 0GR038 | ONE-GIRDER-228-008-0GR038 | 1 | 161.5 | 161.5 |  |  | Steel Structure | [11 empty] | 0 | 161.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
233 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-008 | 0GR039 | ONE-GIRDER-228-008-0GR039 | 1 | 121.2 | 121.2 |  |  | Steel Structure | [11 empty] | 0 | 121.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
234 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-008 | 0GR040 | ONE-GIRDER-228-008-0GR040 | 1 | 95.4 | 95.4 |  |  | Steel Structure | [11 empty] | 0 | 95.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
235 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-008 | 0GR041 | ONE-GIRDER-228-008-0GR041 | 1 | 93.2 | 93.2 |  |  | Steel Structure | [11 empty] | 0 | 93.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
236 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-009 | 0GR042 | ONE-GIRDER-228-009-0GR042 | 1 | 143.2 | 143.2 |  |  | Steel Structure | [11 empty] | 0 | 143.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
237 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-009 | 0GR043 | ONE-GIRDER-228-009-0GR043 | 1 | 145.4 | 145.4 |  |  | Steel Structure | [11 empty] | 0 | 145.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
238 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-009 | 0GR044 | ONE-GIRDER-228-009-0GR044 | 1 | 116.4 | 116.4 |  |  | Steel Structure | [11 empty] | 0 | 116.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
239 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-009 | 0GR045 | ONE-GIRDER-228-009-0GR045 | 1 | 149.4 | 149.4 |  |  | Steel Structure | [11 empty] | 0 | 149.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
240 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-010 | 0GR046 | ONE-GIRDER-228-010-0GR046 | 1 | 123 | 123 |  |  | Steel Structure | [11 empty] | 0 | 123 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
241 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-010 | 0GR047 | ONE-GIRDER-228-010-0GR047 | 1 | 123 | 123 |  |  | Steel Structure | [11 empty] | 0 | 123 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
242 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-010 | 0GR048 | ONE-GIRDER-228-010-0GR048 | 1 | 81 | 81 |  |  | Steel Structure | [11 empty] | 0 | 81 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
243 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-010 | 0GR049 | ONE-GIRDER-228-010-0GR049 | 1 | 123.6 | 123.6 |  |  | Steel Structure | [11 empty] | 0 | 123.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
244 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-010 | 0GR050 | ONE-GIRDER-228-010-0GR050 | 1 | 88.8 | 88.8 |  |  | Steel Structure | [11 empty] | 0 | 88.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
245 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-010 | 0GR051 | ONE-GIRDER-228-010-0GR051 | 1 | 88.8 | 88.8 |  |  | Steel Structure | [11 empty] | 0 | 88.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
246 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-011 | 0GR052 | ONE-GIRDER-228-011-0GR052 | 1 | 121.9 | 121.9 |  |  | Steel Structure | [11 empty] | 0 | 121.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
247 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-011 | 0GR053 | ONE-GIRDER-228-011-0GR053 | 1 | 120.8 | 120.8 |  |  | Steel Structure | [11 empty] | 0 | 120.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
248 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-011 | 0GR054 | ONE-GIRDER-228-011-0GR054 | 1 | 120.8 | 120.8 |  |  | Steel Structure | [11 empty] | 0 | 120.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
249 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-011 | 0GR055 | ONE-GIRDER-228-011-0GR055 | 1 | 116.4 | 116.4 |  |  | Steel Structure | [11 empty] | 0 | 116.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
250 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-011 | 0GR056 | ONE-GIRDER-228-011-0GR056 | 1 | 116.4 | 116.4 |  |  | Steel Structure | [11 empty] | 0 | 116.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
251 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-012 | 0GR057 | ONE-GIRDER-228-012-0GR057 | 1 | 106.4 | 106.4 |  |  | Steel Structure | [11 empty] | 0 | 106.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
252 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-012 | 0GR058 | ONE-GIRDER-228-012-0GR058 | 1 | 106.4 | 106.4 |  |  | Steel Structure | [11 empty] | 0 | 106.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
253 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-012 | 0GR059 | ONE-GIRDER-228-012-0GR059 | 1 | 79.9 | 79.9 |  |  | Steel Structure | [11 empty] | 0 | 79.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
254 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-012 | 0GR060 | ONE-GIRDER-228-012-0GR060 | 1 | 79.9 | 79.9 |  |  | Steel Structure | [11 empty] | 0 | 79.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
255 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-012 | 0GR061 | ONE-GIRDER-228-012-0GR061 | 1 | 99 | 99 |  |  | Steel Structure | [11 empty] | 0 | 99 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
256 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-012 | 0GR062 | ONE-GIRDER-228-012-0GR062 | 1 | 106.4 | 106.4 |  |  | Steel Structure | [11 empty] | 0 | 106.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
257 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-013 | 0GR063 | ONE-GIRDER-228-013-0GR063 | 1 | 99 | 99 |  |  | Steel Structure | [11 empty] | 0 | 99 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
258 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-013 | 0GR064 | ONE-GIRDER-228-013-0GR064 | 1 | 91.2 | 91.2 |  |  | Steel Structure | [11 empty] | 0 | 91.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
259 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-013 | 0GR065 | ONE-GIRDER-228-013-0GR065 | 1 | 94 | 94 |  |  | Steel Structure | [11 empty] | 0 | 94 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
260 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-013 | 0GR066 | ONE-GIRDER-228-013-0GR066 | 1 | 157.9 | 157.9 |  |  | Steel Structure | [11 empty] | 0 | 157.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
261 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-013 | 0GR067 | ONE-GIRDER-228-013-0GR067 | 1 | 157.9 | 157.9 |  |  | Steel Structure | [11 empty] | 0 | 157.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
262 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-013 | 0GR068 | ONE-GIRDER-228-013-0GR068 | 1 | 112.3 | 112.3 |  |  | Steel Structure | [11 empty] | 0 | 112.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
263 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-014 | 0GR072 | ONE-GIRDER-228-014-0GR072 | 1 | 160.5 | 160.5 |  |  | Steel Structure | [11 empty] | 0 | 160.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
264 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-014 | 0GR073 | ONE-GIRDER-228-014-0GR073 | 1 | 160.5 | 160.5 |  |  | Steel Structure | [11 empty] | 0 | 160.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
265 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-014 | 0GR074 | ONE-GIRDER-228-014-0GR074 | 1 | 176 | 176 |  |  | Steel Structure | [11 empty] | 0 | 176 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
266 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR-014 | 0GR075 | ONE-GIRDER-228-014-0GR075 | 1 | 176 | 176 |  |  | Steel Structure | [11 empty] | 0 | 176 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
267 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB001(1/2) | 2-HBRACES-228-001-0HB001 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
268 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB001(2/2) | 2-HBRACES-228-001-0HB001 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
269 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB002 | ONE-HBRACE-228-001-0HB002 | 1 | 18.9 | 18.9 |  |  | Steel Structure | [11 empty] | 0 | 18.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
270 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB003 | ONE-HBRACE-228-001-0HB003 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
271 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB004 | 2-HBRACES-228-001-0HB004 | 1 | 23.6 | 23.6 |  |  | Steel Structure | [11 empty] | 0 | 23.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
272 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB005 | ONE-HBRACE-228-001-0HB005 | 1 | 22.5 | 22.5 |  |  | Steel Structure | [11 empty] | 0 | 22.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
273 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB006 | ONE-HBRACE-228-001-0HB006 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
274 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB007 | ONE-HBRACE-228-001-0HB007 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB-001 | 0HB112 | ONE-HBRACE-228-001-0HB112 | 1 | 26 | 26 |  |  | Steel Structure | [11 empty] | 0 | 26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM008 | 0BM008 | ONE-BEAM-228-0BM008 | 1 | 261.2 | 261.2 |  |  | Steel Structure | [11 empty] | 0 | 261.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM009 | 0BM009 | ONE-BEAM-228-0BM009 | 1 | 163.9 | 163.9 |  |  | Steel Structure | [11 empty] | 0 | 163.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM010 | 0BM010 | ONE-BEAM-228-0BM010 | 1 | 102.6 | 102.6 |  |  | Steel Structure | [11 empty] | 0 | 102.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM011 | 0BM011 | ONE-BEAM-228-0BM011 | 1 | 103.5 | 103.5 |  |  | Steel Structure | [11 empty] | 0 | 103.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM012 | 0BM012(1/3) | 3-BEAMS-228-0BM012 | 1 | 15.4 | 15.4 |  |  | Steel Structure | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM012 | 0BM012(2/3) | 3-BEAMS-228-0BM012 | 1 | 15.4 | 15.4 |  |  | Steel Structure | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM012 | 0BM012(3/3) | 3-BEAMS-228-0BM012 | 1 | 15.4 | 15.4 |  |  | Steel Structure | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM013 | 0BM013 | ONE-BEAM-228-0BM013 | 1 | 32.9 | 32.9 |  |  | Steel Structure | [11 empty] | 0 | 32.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM014 | 0BM014(1/2) | 2-BEAMS-228-0BM014 | 1 | 23.3 | 23.3 |  |  | Steel Structure | [11 empty] | 0 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM014 | 0BM014(2/2) | 2-BEAMS-228-0BM014 | 1 | 23.3 | 23.3 |  |  | Steel Structure | [11 empty] | 0 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM015 | 0BM015 | 2-BEAMS-228-0BM015 | 1 | 105.2 | 105.2 |  |  | Steel Structure | [11 empty] | 0 | 105.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM016 | 0BM016 | ONE-BEAM-228-0BM016 | 1 | 108.9 | 108.9 |  |  | Steel Structure | [11 empty] | 0 | 108.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM017 | 0BM017 | ONE-BEAM-228-0BM017 | 1 | 160.2 | 160.2 |  |  | Steel Structure | [11 empty] | 0 | 160.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM018 | 0BM018 | ONE-BEAM-228-0BM018 | 1 | 14.1 | 14.1 |  |  | Steel Structure | [11 empty] | 0 | 14.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM019 | 0BM019 | ONE-BEAM-228-0BM019 | 1 | 49.4 | 49.4 |  |  | Steel Structure | [11 empty] | 0 | 49.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM020 | 0BM020 | ONE-BEAM-228-0BM020 | 1 | 56.9 | 56.9 |  |  | Steel Structure | [11 empty] | 0 | 56.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM021 | 0BM021 | ONE-BEAM-228-0BM021 | 1 | 20.3 | 20.3 |  |  | Steel Structure | [11 empty] | 0 | 20.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM022 | 0BM022 | ONE-BEAM-228-0BM022 | 1 | 12.7 | 12.7 |  |  | Steel Structure | [11 empty] | 0 | 12.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM023 | 0BM023 | ONE-BEAM-228-0BM023 | 1 | 115 | 115 |  |  | Steel Structure | [11 empty] | 0 | 115 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM024 | 0BM024 | ONE-BEAM-228-0BM024 | 1 | 108.3 | 108.3 |  |  | Steel Structure | [11 empty] | 0 | 108.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM025 | 0BM025 | ONE-BEAM-228-0BM025 | 1 | 101.9 | 101.9 |  |  | Steel Structure | [11 empty] | 0 | 101.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM026 | 0BM026 | ONE-BEAM-228-0BM026 | 1 | 101.9 | 101.9 |  |  | Steel Structure | [11 empty] | 0 | 101.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM027 | 0BM027 | ONE-BEAM-228-0BM027 | 1 | 101.9 | 101.9 |  |  | Steel Structure | [11 empty] | 0 | 101.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM028 | 0BM028 | ONE-BEAM-228-0BM028 | 1 | 92.1 | 92.1 |  |  | Steel Structure | [11 empty] | 0 | 92.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM029 | 0BM029 | ONE-BEAM-228-0BM029 | 1 | 254.5 | 254.5 |  |  | Steel Structure | [11 empty] | 0 | 254.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM030 | 0BM030(1/2) | 2-BEAMS-228-0BM030 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM030 | 0BM030(2/2) | 2-BEAMS-228-0BM030 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM031 | 0BM031(1/2) | 2-BEAMS-228-0BM031 | 1 | 89.4 | 89.4 |  |  | Steel Structure | [11 empty] | 0 | 89.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM031 | 0BM031(2/2) | 2-BEAMS-228-0BM031 | 1 | 89.4 | 89.4 |  |  | Steel Structure | [11 empty] | 0 | 89.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM032 | 0BM032 | ONE-BEAM-228-0BM032 | 1 | 18.5 | 18.5 |  |  | Steel Structure | [11 empty] | 0 | 18.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM033 | 0BM033 | ONE-BEAM-228-0BM033 | 1 | 22.4 | 22.4 |  |  | Steel Structure | [11 empty] | 0 | 22.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM034 | 0BM034 | ONE-BEAM-228-0BM034 | 1 | 13.6 | 13.6 |  |  | Steel Structure | [11 empty] | 0 | 13.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM035 | 0BM035 | ONE-BEAM-228-0BM035 | 1 | 24.5 | 24.5 |  |  | Steel Structure | [11 empty] | 0 | 24.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM036 | 0BM036 | ONE-BEAM-228-0BM036 | 1 | 96.4 | 96.4 |  |  | Steel Structure | [11 empty] | 0 | 96.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM037 | 0BM037 | ONE-BEAM-228-0BM037 | 1 | 201.3 | 201.3 |  |  | Steel Structure | [11 empty] | 0 | 201.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM038 | 0BM038 | ONE-BEAM-228-0BM038 | 1 | 103.6 | 103.6 |  |  | Steel Structure | [11 empty] | 0 | 103.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM039 | 0BM039 | ONE-BEAM-228-0BM039 | 1 | 113.3 | 113.3 |  |  | Steel Structure | [11 empty] | 0 | 113.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM040 | 0BM040(1/3) | 3-BEAMS-228-0BM040 | 1 | 13 | 13 |  |  | Steel Structure | [11 empty] | 0 | 13 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM040 | 0BM040(2/3) | 3-BEAMS-228-0BM040 | 1 | 13 | 13 |  |  | Steel Structure | [11 empty] | 0 | 13 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM040 | 0BM040(3/3) | 3-BEAMS-228-0BM040 | 1 | 13 | 13 |  |  | Steel Structure | [11 empty] | 0 | 13 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM041 | 0BM041(1/3) | 3-BEAMS-228-0BM041 | 1 | 13 | 13 |  |  | Steel Structure | [11 empty] | 0 | 13 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM041 | 0BM041(2/3) | 3-BEAMS-228-0BM041 | 1 | 13 | 13 |  |  | Steel Structure | [11 empty] | 0 | 13 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM041 | 0BM041(3/3) | 3-BEAMS-228-0BM041 | 1 | 13 | 13 |  |  | Steel Structure | [11 empty] | 0 | 13 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM042 | 0BM042 | ONE-BEAM-228-0BM042 | 1 | 144.4 | 144.4 |  |  | Steel Structure | [11 empty] | 0 | 144.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM043 | 0BM043 | ONE-BEAM-228-0BM043 | 1 | 144.4 | 144.4 |  |  | Steel Structure | [11 empty] | 0 | 144.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM044 | 0BM044(1/5) | 5-BEAMS-228-0BM044 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM044 | 0BM044(2/5) | 5-BEAMS-228-0BM044 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM044 | 0BM044(3/5) | 5-BEAMS-228-0BM044 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM044 | 0BM044(4/5) | 5-BEAMS-228-0BM044 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM044 | 0BM044(5/5) | 5-BEAMS-228-0BM044 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM045 | 0BM045 | ONE-BEAM-228-0BM045 | 1 | 92.1 | 92.1 |  |  | Steel Structure | [11 empty] | 0 | 92.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM046 | 0BM046(1/3) | 3-BEAMS-228-0BM046 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM046 | 0BM046(2/3) | 3-BEAMS-228-0BM046 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM046 | 0BM046(3/3) | 3-BEAMS-228-0BM046 | 1 | 15.3 | 15.3 |  |  | Steel Structure | [11 empty] | 0 | 15.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM047 | 0BM047 | ONE-BEAM-228-0BM047 | 1 | 673.6 | 673.6 |  |  | Steel Structure | [11 empty] | 0 | 673.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM048 | 0BM048 | ONE-BEAM-228-0BM048 | 1 | 116 | 116 |  |  | Steel Structure | [11 empty] | 0 | 116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM049 | 0BM049 | ONE-BEAM-228-0BM049 | 1 | 116 | 116 |  |  | Steel Structure | [11 empty] | 0 | 116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM050 | 0BM050 | ONE-BEAM-228-0BM050 | 1 | 30.6 | 30.6 |  |  | Steel Structure | [11 empty] | 0 | 30.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM051 | 0BM051 | ONE-BEAM-228-0BM051 | 1 | 30.6 | 30.6 |  |  | Steel Structure | [11 empty] | 0 | 30.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM052 | 0BM052 | ONE-BEAM-228-0BM052 | 1 | 70.1 | 70.1 |  |  | Steel Structure | [11 empty] | 0 | 70.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM053 | 0BM053(1/2) | 2-BEAMS-228-0BM053 | 1 | 63.2 | 63.2 |  |  | Steel Structure | [11 empty] | 0 | 63.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM053 | 0BM053(2/2) | 2-BEAMS-228-0BM053 | 1 | 63.2 | 63.2 |  |  | Steel Structure | [11 empty] | 0 | 63.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM054 | 0BM054 | ONE-BEAM-228-0BM054 | 1 | 234.4 | 234.4 |  |  | Steel Structure | [11 empty] | 0 | 234.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM055 | 0BM055 | ONE-BEAM-228-0BM055 | 1 | 59.4 | 59.4 |  |  | Steel Structure | [11 empty] | 0 | 59.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM056 | 0BM056 | ONE-BEAM-228-0BM056 | 1 | 25.3 | 25.3 |  |  | Steel Structure | [11 empty] | 0 | 25.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM057 | 0BM057 | ONE-BEAM-228-0BM057 | 1 | 15.8 | 15.8 |  |  | Steel Structure | [11 empty] | 0 | 15.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM058 | 0BM058 | ONE-BEAM-228-0BM058 | 1 | 35.4 | 35.4 |  |  | Steel Structure | [11 empty] | 0 | 35.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM059 | 0BM059 | ONE-BEAM-228-0BM059 | 1 | 117 | 117 |  |  | Steel Structure | [11 empty] | 0 | 117 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM060 | 0BM060 | ONE-BEAM-228-0BM060 | 1 | 138.5 | 138.5 |  |  | Steel Structure | [11 empty] | 0 | 138.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM061 | 0BM061 | ONE-BEAM-228-0BM061 | 1 | 117 | 117 |  |  | Steel Structure | [11 empty] | 0 | 117 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM062 | 0BM062 | ONE-BEAM-228-0BM062 | 1 | 58.3 | 58.3 |  |  | Steel Structure | [11 empty] | 0 | 58.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM063 | 0BM063 | ONE-BEAM-228-0BM063 | 1 | 61.7 | 61.7 |  |  | Steel Structure | [11 empty] | 0 | 61.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM064 | 0BM064 | ONE-BEAM-228-0BM064 | 1 | 41.9 | 41.9 |  |  | Steel Structure | [11 empty] | 0 | 41.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM065 | 0BM065(1/6) | 6-BEAMS-228-0BM065 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM065 | 0BM065(2/6) | 6-BEAMS-228-0BM065 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM065 | 0BM065(3/6) | 6-BEAMS-228-0BM065 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM065 | 0BM065(4/6) | 6-BEAMS-228-0BM065 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM065 | 0BM065(5/6) | 6-BEAMS-228-0BM065 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM065 | 0BM065(6/6) | 6-BEAMS-228-0BM065 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM066 | 0BM066(1/3) | 3-BEAMS-228-0BM066 | 1 | 21.1 | 21.1 |  |  | Steel Structure | [11 empty] | 0 | 21.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM066 | 0BM066(2/3) | 3-BEAMS-228-0BM066 | 1 | 21.1 | 21.1 |  |  | Steel Structure | [11 empty] | 0 | 21.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM066 | 0BM066(3/3) | 3-BEAMS-228-0BM066 | 1 | 21.1 | 21.1 |  |  | Steel Structure | [11 empty] | 0 | 21.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM067 | 0BM067 | ONE-BEAM-228-0BM067 | 1 | 26.7 | 26.7 |  |  | Steel Structure | [11 empty] | 0 | 26.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM068 | 0BM068(1/2) | 2-BEAMS-228-0BM068 | 1 | 166.5 | 166.5 |  |  | Steel Structure | [11 empty] | 0 | 166.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM068 | 0BM068(2/2) | 2-BEAMS-228-0BM068 | 1 | 166.5 | 166.5 |  |  | Steel Structure | [11 empty] | 0 | 166.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM069 | 0BM069 | ONE-BEAM-228-0BM069 | 1 | 153.9 | 153.9 |  |  | Steel Structure | [11 empty] | 0 | 153.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM070 | 0BM070(1/6) | 6-BEAMS-228-0BM070 | 1 | 8 | 8 |  |  | Steel Structure | [11 empty] | 0 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM070 | 0BM070(2/6) | 6-BEAMS-228-0BM070 | 1 | 8 | 8 |  |  | Steel Structure | [11 empty] | 0 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM070 | 0BM070(3/6) | 6-BEAMS-228-0BM070 | 1 | 8 | 8 |  |  | Steel Structure | [11 empty] | 0 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM070 | 0BM070(4/6) | 6-BEAMS-228-0BM070 | 1 | 8 | 8 |  |  | Steel Structure | [11 empty] | 0 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM070 | 0BM070(5/6) | 6-BEAMS-228-0BM070 | 1 | 8 | 8 |  |  | Steel Structure | [11 empty] | 0 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM070 | 0BM070(6/6) | 6-BEAMS-228-0BM070 | 1 | 8 | 8 |  |  | Steel Structure | [11 empty] | 0 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM071 | 0BM071 | ONE-BEAM-228-0BM071 | 1 | 103 | 103 |  |  | Steel Structure | [11 empty] | 0 | 103 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM072 | 0BM072 | ONE-BEAM-228-0BM072 | 1 | 134.9 | 134.9 |  |  | Steel Structure | [11 empty] | 0 | 134.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM073 | 0BM073 | ONE-BEAM-228-0BM073 | 1 | 134.9 | 134.9 |  |  | Steel Structure | [11 empty] | 0 | 134.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM074 | 0BM074(1/2) | 2-BEAMS-228-0BM074 | 1 | 40.4 | 40.4 |  |  | Steel Structure | [11 empty] | 0 | 40.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM074 | 0BM074(2/2) | 2-BEAMS-228-0BM074 | 1 | 40.4 | 40.4 |  |  | Steel Structure | [11 empty] | 0 | 40.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM075 | 0BM075(1/4) | 4-BEAMS-228-0BM075 | 1 | 62.4 | 62.4 |  |  | Steel Structure | [11 empty] | 0 | 62.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM075 | 0BM075(2/4) | 4-BEAMS-228-0BM075 | 1 | 62.4 | 62.4 |  |  | Steel Structure | [11 empty] | 0 | 62.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM075 | 0BM075(3/4) | 4-BEAMS-228-0BM075 | 1 | 62.4 | 62.4 |  |  | Steel Structure | [11 empty] | 0 | 62.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM075 | 0BM075(4/4) | 4-BEAMS-228-0BM075 | 1 | 62.4 | 62.4 |  |  | Steel Structure | [11 empty] | 0 | 62.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM076 | 0BM076 | ONE-BEAM-228-0BM076 | 1 | 50.4 | 50.4 |  |  | Steel Structure | [11 empty] | 0 | 50.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM077 | 0BM077 | ONE-BEAM-228-0BM077 | 1 | 47.4 | 47.4 |  |  | Steel Structure | [11 empty] | 0 | 47.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM078 | 0BM078(1/2) | 2-BEAMS-228-0BM078 | 1 | 51.2 | 51.2 |  |  | Steel Structure | [11 empty] | 0 | 51.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM078 | 0BM078(2/2) | 2-BEAMS-228-0BM078 | 1 | 51.2 | 51.2 |  |  | Steel Structure | [11 empty] | 0 | 51.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM079 | 0BM079 | ONE-BEAM-228-0BM079 | 1 | 47.4 | 47.4 |  |  | Steel Structure | [11 empty] | 0 | 47.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM080 | 0BM080 | ONE-BEAM-228-0BM080 | 1 | 70.4 | 70.4 |  |  | Steel Structure | [11 empty] | 0 | 70.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM081 | 0BM081(1/2) | 2-BEAMS-228-0BM081 | 1 | 6.1 | 6.1 |  |  | Steel Structure | [11 empty] | 0 | 6.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM081 | 0BM081(2/2) | 2-BEAMS-228-0BM081 | 1 | 6.1 | 6.1 |  |  | Steel Structure | [11 empty] | 0 | 6.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM082 | 0BM082 | ONE-BEAM-228-0BM082 | 1 | 145.4 | 145.4 |  |  | Steel Structure | [11 empty] | 0 | 145.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM083 | 0BM083 | ONE-BEAM-228-0BM083 | 1 | 37.8 | 37.8 |  |  | Steel Structure | [11 empty] | 0 | 37.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM084 | 0BM084(1/2) | 2-BEAMS-228-0BM084 | 1 | 18.2 | 18.2 |  |  | Steel Structure | [11 empty] | 0 | 18.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM084 | 0BM084(2/2) | 2-BEAMS-228-0BM084 | 1 | 18.2 | 18.2 |  |  | Steel Structure | [11 empty] | 0 | 18.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM085 | 0BM085 | ONE-BEAM-228-0BM085 | 1 | 90 | 90 |  |  | Steel Structure | [11 empty] | 0 | 90 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM086 | 0BM086 | ONE-BEAM-228-0BM086 | 1 | 89.9 | 89.9 |  |  | Steel Structure | [11 empty] | 0 | 89.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM087 | 0BM087 | ONE-BEAM-228-0BM087 | 1 | 159.5 | 159.5 |  |  | Steel Structure | [11 empty] | 0 | 159.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM088 | 0BM088 | ONE-BEAM-228-0BM088 | 1 | 27.6 | 27.6 |  |  | Steel Structure | [11 empty] | 0 | 27.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM089 | 0BM089(1/2) | 2-BEAMS-228-0BM089 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM089 | 0BM089(2/2) | 2-BEAMS-228-0BM089 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM090 | 0BM090 | ONE-BEAM-228-0BM090 | 1 | 20.5 | 20.5 |  |  | Steel Structure | [11 empty] | 0 | 20.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM091 | 0BM091 | ONE-BEAM-228-0BM091 | 1 | 20.5 | 20.5 |  |  | Steel Structure | [11 empty] | 0 | 20.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM092 | 0BM092 | ONE-BEAM-228-0BM092 | 1 | 163.7 | 163.7 |  |  | Steel Structure | [11 empty] | 0 | 163.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM093 | 0BM093 | ONE-BEAM-228-0BM093 | 1 | 176.8 | 176.8 |  |  | Steel Structure | [11 empty] | 0 | 176.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM094 | 0BM094 | ONE-BEAM-228-0BM094 | 1 | 165 | 165 |  |  | Steel Structure | [11 empty] | 0 | 165 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM095 | 0BM095 | ONE-BEAM-228-0BM095 | 1 | 49.5 | 49.5 |  |  | Steel Structure | [11 empty] | 0 | 49.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM096 | 0BM096 | ONE-BEAM-228-0BM096 | 1 | 165.2 | 165.2 |  |  | Steel Structure | [11 empty] | 0 | 165.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM097 | 0BM097 | ONE-BEAM-228-0BM097 | 1 | 163.1 | 163.1 |  |  | Steel Structure | [11 empty] | 0 | 163.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM098 | 0BM098(1/6) | 6-BEAMS-228-0BM098 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM098 | 0BM098(2/6) | 6-BEAMS-228-0BM098 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM098 | 0BM098(3/6) | 6-BEAMS-228-0BM098 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM098 | 0BM098(4/6) | 6-BEAMS-228-0BM098 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM098 | 0BM098(5/6) | 6-BEAMS-228-0BM098 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM098 | 0BM098(6/6) | 6-BEAMS-228-0BM098 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM099 | 0BM099 | ONE-BEAM-228-0BM099 | 1 | 101.5 | 101.5 |  |  | Steel Structure | [11 empty] | 0 | 101.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM100 | 0BM100(1/2) | 2-CHANNELS-228-0BM100 | 1 | 8.9 | 8.9 |  |  | Steel Structure | [11 empty] | 0 | 8.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM100 | 0BM100(2/2) | 2-CHANNELS-228-0BM100 | 1 | 8.9 | 8.9 |  |  | Steel Structure | [11 empty] | 0 | 8.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM101 | 0BM101(1/4) | 4-BEAMS-228-0BM101 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM101 | 0BM101(2/4) | 4-BEAMS-228-0BM101 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM101 | 0BM101(3/4) | 4-BEAMS-228-0BM101 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM101 | 0BM101(4/4) | 4-BEAMS-228-0BM101 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM102 | 0BM102 | ONE-BEAM-228-0BM102 | 1 | 81.2 | 81.2 |  |  | Steel Structure | [11 empty] | 0 | 81.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM103 | 0BM103(1/4) | 4-BEAMS-228-0BM103 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM103 | 0BM103(2/4) | 4-BEAMS-228-0BM103 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM103 | 0BM103(3/4) | 4-BEAMS-228-0BM103 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM103 | 0BM103(4/4) | 4-BEAMS-228-0BM103 | 1 | 32.8 | 32.8 |  |  | Steel Structure | [11 empty] | 0 | 32.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM104 | 0BM104(1/4) | 4-BEAMS-228-0BM104 | 1 | 34.2 | 34.2 |  |  | Steel Structure | [11 empty] | 0 | 34.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM104 | 0BM104(2/4) | 4-BEAMS-228-0BM104 | 1 | 34.2 | 34.2 |  |  | Steel Structure | [11 empty] | 0 | 34.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM104 | 0BM104(3/4) | 4-BEAMS-228-0BM104 | 1 | 34.2 | 34.2 |  |  | Steel Structure | [11 empty] | 0 | 34.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM104 | 0BM104(4/4) | 4-BEAMS-228-0BM104 | 1 | 34.2 | 34.2 |  |  | Steel Structure | [11 empty] | 0 | 34.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM105 | 0BM105(1/4) | 4-BEAMS-228-0BM105 | 1 | 47.8 | 47.8 |  |  | Steel Structure | [11 empty] | 0 | 47.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM105 | 0BM105(2/4) | 4-BEAMS-228-0BM105 | 1 | 47.8 | 47.8 |  |  | Steel Structure | [11 empty] | 0 | 47.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM105 | 0BM105(3/4) | 4-BEAMS-228-0BM105 | 1 | 47.8 | 47.8 |  |  | Steel Structure | [11 empty] | 0 | 47.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM105 | 0BM105(4/4) | 4-BEAMS-228-0BM105 | 1 | 47.8 | 47.8 |  |  | Steel Structure | [11 empty] | 0 | 47.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM106 | 0BM106 | ONE-BEAM-228-0BM106 | 1 | 64.9 | 64.9 |  |  | Steel Structure | [11 empty] | 0 | 64.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM107 | 0BM107 | ONE-BEAM-228-0BM107 | 1 | 64.9 | 64.9 |  |  | Steel Structure | [11 empty] | 0 | 64.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM108 | 0BM108 | ONE-BEAM-228-0BM108 | 1 | 81.2 | 81.2 |  |  | Steel Structure | [11 empty] | 0 | 81.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM109 | 0BM109 | ONE-BEAM-228-0BM109 | 1 | 78.8 | 78.8 |  |  | Steel Structure | [11 empty] | 0 | 78.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM110 | 0BM110 | ONE-BEAM-228-0BM110 | 1 | 162.4 | 162.4 |  |  | Steel Structure | [11 empty] | 0 | 162.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM111 | 0BM111 | ONE-BEAM-228-0BM111 | 1 | 120.9 | 120.9 |  |  | Steel Structure | [11 empty] | 0 | 120.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM112 | 0BM112 | ONE-BEAM-228-0BM112 | 1 | 32.2 | 32.2 |  |  | Steel Structure | [11 empty] | 0 | 32.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM113 | 0BM113 | ONE-BEAM-228-0BM113 | 1 | 17.4 | 17.4 |  |  | Steel Structure | [11 empty] | 0 | 17.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM114 | 0BM114 | ONE-BEAM-228-0BM114 | 1 | 17.4 | 17.4 |  |  | Steel Structure | [11 empty] | 0 | 17.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM115 | 0BM115 | ONE-BEAM-228-0BM115 | 1 | 17.4 | 17.4 |  |  | Steel Structure | [11 empty] | 0 | 17.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM116 | 0BM116(1/2) | 2-BEAMS-228-0BM116 | 1 | 18.3 | 18.3 |  |  | Steel Structure | [11 empty] | 0 | 18.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM116 | 0BM116(2/2) | 2-BEAMS-228-0BM116 | 1 | 18.3 | 18.3 |  |  | Steel Structure | [11 empty] | 0 | 18.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM117 | 0BM117 | ONE-BEAM-228-0BM117 | 1 | 68.8 | 68.8 |  |  | Steel Structure | [11 empty] | 0 | 68.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM118 | 0BM118 | ONE-BEAM-228-0BM118 | 1 | 172.5 | 172.5 |  |  | Steel Structure | [11 empty] | 0 | 172.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM119 | 0BM119 | ONE-BEAM-228-0BM119 | 1 | 169.5 | 169.5 |  |  | Steel Structure | [11 empty] | 0 | 169.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM120 | 0BM120 | ONE-BEAM-228-0BM120 | 1 | 182.7 | 182.7 |  |  | Steel Structure | [11 empty] | 0 | 182.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM121 | 0BM121 | ONE-BEAM-228-0BM121 | 1 | 137.5 | 137.5 |  |  | Steel Structure | [11 empty] | 0 | 137.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM122 | 0BM122 | ONE-BEAM-228-0BM122 | 1 | 341.6 | 341.6 |  |  | Steel Structure | [11 empty] | 0 | 341.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(1/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(2/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(3/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(4/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(5/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(6/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(7/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(8/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM123 | 0BM123(9/9) | 9-BEAMS-228-0BM123 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM124 | 0BM124(1/2) | 2-BEAMS-228-0BM124 | 1 | 47.5 | 47.5 |  |  | Steel Structure | [11 empty] | 0 | 47.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM124 | 0BM124(2/2) | 2-BEAMS-228-0BM124 | 1 | 47.5 | 47.5 |  |  | Steel Structure | [11 empty] | 0 | 47.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM125 | 0BM125(1/3) | 3-BEAMS-228-0BM125 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM125 | 0BM125(2/3) | 3-BEAMS-228-0BM125 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM125 | 0BM125(3/3) | 3-BEAMS-228-0BM125 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM126 | 0BM126(1/2) | 2-BEAMS-228-0BM126 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM126 | 0BM126(2/2) | 2-BEAMS-228-0BM126 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM127 | 0BM127(1/2) | 2-BEAMS-228-0BM127 | 1 | 17.4 | 17.4 |  |  | Steel Structure | [11 empty] | 0 | 17.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM127 | 0BM127(2/2) | 2-BEAMS-228-0BM127 | 1 | 17.4 | 17.4 |  |  | Steel Structure | [11 empty] | 0 | 17.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM128 | 0BM128 | ONE-BEAM-228-0BM128 | 1 | 117.8 | 117.8 |  |  | Steel Structure | [11 empty] | 0 | 117.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM129 | 0BM129 | ONE-BEAM-228-0BM129 | 1 | 144.9 | 144.9 |  |  | Steel Structure | [11 empty] | 0 | 144.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM130 | 0BM130 | ONE-BEAM-228-0BM130 | 1 | 147.1 | 147.1 |  |  | Steel Structure | [11 empty] | 0 | 147.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM131 | 0BM131 | ONE-BEAM-228-0BM131 | 1 | 136.9 | 136.9 |  |  | Steel Structure | [11 empty] | 0 | 136.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM132 | 0BM132 | ONE-BEAM-228-0BM132 | 1 | 191.4 | 191.4 |  |  | Steel Structure | [11 empty] | 0 | 191.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM133 | 0BM133(1/2) | 2-BEAMS-228-0BM133 | 1 | 53.2 | 53.2 |  |  | Steel Structure | [11 empty] | 0 | 53.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM133 | 0BM133(2/2) | 2-BEAMS-228-0BM133 | 1 | 53.2 | 53.2 |  |  | Steel Structure | [11 empty] | 0 | 53.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM134 | 0BM134 | ONE-BEAM-228-0BM134 | 1 | 162.6 | 162.6 |  |  | Steel Structure | [11 empty] | 0 | 162.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(1/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(2/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(3/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(4/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(5/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(6/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(7/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(8/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(9/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM135 | 0BM135(10/10) | 10-BEAMS-228-0BM135 | 1 | 11.6 | 11.6 |  |  | Steel Structure | [11 empty] | 0 | 11.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM136 | 0BM136 | ONE-BEAM-228-0BM136 | 1 | 15.5 | 15.5 |  |  | Steel Structure | [11 empty] | 0 | 15.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM137 | 0BM137(1/2) | 2-BEAMS-228-0BM137 | 1 | 17.2 | 17.2 |  |  | Steel Structure | [11 empty] | 0 | 17.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM137 | 0BM137(2/2) | 2-BEAMS-228-0BM137 | 1 | 17.2 | 17.2 |  |  | Steel Structure | [11 empty] | 0 | 17.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM138 | 0BM138 | ONE-BEAM-228-0BM138 | 1 | 117.3 | 117.3 |  |  | Steel Structure | [11 empty] | 0 | 117.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM139 | 0BM139 | ONE-BEAM-228-0BM139 | 1 | 40.2 | 40.2 |  |  | Steel Structure | [11 empty] | 0 | 40.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM140 | 0BM140 | ONE-BEAM-228-0BM140 | 1 | 145.1 | 145.1 |  |  | Steel Structure | [11 empty] | 0 | 145.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM141 | 0BM141(1/2) | ONE-BEAM-228-0BM141 | 1 | 33.4 | 33.4 |  |  | Steel Structure | [11 empty] | 0 | 33.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM141 | 0BM141(2/2) | ONE-BEAM-228-0BM141 | 1 | 33.4 | 33.4 |  |  | Steel Structure | [11 empty] | 0 | 33.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM142 | 0BM142 | ONE-BEAM-228-0BM142 | 1 | 120.2 | 120.2 |  |  | Steel Structure | [11 empty] | 0 | 120.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM143 | 0BM143 | ONE-BEAM-228-0BM143 | 1 | 19.8 | 19.8 |  |  | Steel Structure | [11 empty] | 0 | 19.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM144 | 0BM144 | ONE-BEAM-228-0BM144 | 1 | 42.4 | 42.4 |  |  | Steel Structure | [11 empty] | 0 | 42.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM145 | 0BM145 | ONE-BEAM-228-0BM145 | 1 | 101.9 | 101.9 |  |  | Steel Structure | [11 empty] | 0 | 101.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM146 | 0BM146 | ONE-BEAM-228-0BM146 | 1 | 54 | 54 |  |  | Steel Structure | [11 empty] | 0 | 54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(1/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(2/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(3/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(4/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(5/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(6/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(7/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(8/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM147 | 0BM147(9/9) | 9-BEAMS-228-0BM147 | 1 | 18.7 | 18.7 |  |  | Steel Structure | [11 empty] | 0 | 18.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM148 | 0BM148 | ONE-BEAM-228-0BM148 | 1 | 35.6 | 35.6 |  |  | Steel Structure | [11 empty] | 0 | 35.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM149 | 0BM149 | ONE-BEAM-228-0BM149 | 1 | 2235.3 | 2235.3 |  |  | Steel Structure | [11 empty] | 0 | 2235.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM150 | 0BM150(1/4) | 4-BEAMS-228-0BM150 | 1 | 15.2 | 15.2 |  |  | Steel Structure | [11 empty] | 0 | 15.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM150 | 0BM150(2/4) | 4-BEAMS-228-0BM150 | 1 | 15.2 | 15.2 |  |  | Steel Structure | [11 empty] | 0 | 15.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM150 | 0BM150(3/4) | 4-BEAMS-228-0BM150 | 1 | 15.2 | 15.2 |  |  | Steel Structure | [11 empty] | 0 | 15.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM150 | 0BM150(4/4) | 4-BEAMS-228-0BM150 | 1 | 15.2 | 15.2 |  |  | Steel Structure | [11 empty] | 0 | 15.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM151 | 0BM151 | ONE-BEAM-228-0BM151 | 1 | 2451.3 | 2451.3 |  |  | Steel Structure | [11 empty] | 0 | 2451.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM152 | 0BM152(1/4) | 4-BEAMS-228-0BM152 | 1 | 17.8 | 17.8 |  |  | Steel Structure | [11 empty] | 0 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM152 | 0BM152(2/4) | 4-BEAMS-228-0BM152 | 1 | 17.8 | 17.8 |  |  | Steel Structure | [11 empty] | 0 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM152 | 0BM152(3/4) | 4-BEAMS-228-0BM152 | 1 | 17.8 | 17.8 |  |  | Steel Structure | [11 empty] | 0 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM152 | 0BM152(4/4) | 4-BEAMS-228-0BM152 | 1 | 17.8 | 17.8 |  |  | Steel Structure | [11 empty] | 0 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM153 | 0BM153 | ONE-BEAM-228-0BM153 | 1 | 17.7 | 17.7 |  |  | Steel Structure | [11 empty] | 0 | 17.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM154 | 0BM154(1/2) | 2-BEAMS-228-0BM154 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM154 | 0BM154(2/2) | 2-BEAMS-228-0BM154 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM155 | 0BM155 | ONE-BEAM-228-0BM155 | 1 | 80.4 | 80.4 |  |  | Steel Structure | [11 empty] | 0 | 80.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM156 | 0BM156(1/2) | 2-BEAMS-228-0BM156 | 1 | 66.8 | 66.8 |  |  | Steel Structure | [11 empty] | 0 | 66.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM156 | 0BM156(2/2) | 2-BEAMS-228-0BM156 | 1 | 66.8 | 66.8 |  |  | Steel Structure | [11 empty] | 0 | 66.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM157 | 0BM157 | ONE-BEAM-228-0BM157 | 1 | 80.4 | 80.4 |  |  | Steel Structure | [11 empty] | 0 | 80.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM158 | 0BM158 | ONE-BEAM-228-0BM158 | 1 | 78.9 | 78.9 |  |  | Steel Structure | [11 empty] | 0 | 78.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM159 | 0BM159 | ONE-BEAM-228-0BM159 | 1 | 80.6 | 80.6 |  |  | Steel Structure | [11 empty] | 0 | 80.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM160 | 0BM160 | ONE-BEAM-228-0BM160 | 1 | 72.9 | 72.9 |  |  | Steel Structure | [11 empty] | 0 | 72.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM161 | 0BM161 | ONE-BEAM-228-0BM161 | 1 | 32.1 | 32.1 |  |  | Steel Structure | [11 empty] | 0 | 32.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM162 | 0BM162 | ONE-BEAM-228-0BM162 | 1 | 1787 | 1787 |  |  | Steel Structure | [11 empty] | 0 | 1787 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM163 | 0BM163 | ONE-BEAM-228-0BM163 | 1 | 145.5 | 145.5 |  |  | Steel Structure | [11 empty] | 0 | 145.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM164 | 0BM164(1/3) | 3-BEAMS-228-0BM164 | 1 | 17.7 | 17.7 |  |  | Steel Structure | [11 empty] | 0 | 17.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM164 | 0BM164(2/3) | 3-BEAMS-228-0BM164 | 1 | 17.7 | 17.7 |  |  | Steel Structure | [11 empty] | 0 | 17.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM164 | 0BM164(3/3) | 3-BEAMS-228-0BM164 | 1 | 17.7 | 17.7 |  |  | Steel Structure | [11 empty] | 0 | 17.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM165 | 0BM165 | ONE-BEAM-228-0BM165 | 1 | 44.4 | 44.4 |  |  | Steel Structure | [11 empty] | 0 | 44.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM166 | 0BM166 | ONE-BEAM-228-0BM166 | 1 | 59.3 | 59.3 |  |  | Steel Structure | [11 empty] | 0 | 59.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM167 | 0BM167 | ONE-BEAM-228-0BM167 | 1 | 98.7 | 98.7 |  |  | Steel Structure | [11 empty] | 0 | 98.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM168 | 0BM168 | ONE-BEAM-228-0BM168 | 1 | 150.4 | 150.4 |  |  | Steel Structure | [11 empty] | 0 | 150.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM169 | 0BM169 | ONE-BEAM-228-0BM169 | 1 | 145.9 | 145.9 |  |  | Steel Structure | [11 empty] | 0 | 145.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM170 | 0BM170 | ONE-BEAM-228-0BM170 | 1 | 59.3 | 59.3 |  |  | Steel Structure | [11 empty] | 0 | 59.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM171 | 0BM171 | ONE-BEAM-228-0BM171 | 1 | 64.5 | 64.5 |  |  | Steel Structure | [11 empty] | 0 | 64.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM172 | 0BM172 | ONE-BEAM-228-0BM172 | 1 | 48.3 | 48.3 |  |  | Steel Structure | [11 empty] | 0 | 48.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM173 | 0BM173 | ONE-BEAM-228-0BM173 | 1 | 62 | 62 |  |  | Steel Structure | [11 empty] | 0 | 62 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM174 | 0BM174 | ONE-BEAM-228-0BM174 | 1 | 150 | 150 |  |  | Steel Structure | [11 empty] | 0 | 150 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM175 | 0BM175 | ONE-BEAM-228-0BM175 | 1 | 1787 | 1787 |  |  | Steel Structure | [11 empty] | 0 | 1787 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM176 | 0BM176 | ONE-BEAM-228-0BM176 | 1 | 32.1 | 32.1 |  |  | Steel Structure | [11 empty] | 0 | 32.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM177 | 0BM177 | ONE-BEAM-228-0BM177 | 1 | 64.8 | 64.8 |  |  | Steel Structure | [11 empty] | 0 | 64.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM178 | 0BM178 | ONE-BEAM-228-0BM178 | 1 | 78.9 | 78.9 |  |  | Steel Structure | [11 empty] | 0 | 78.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM179 | 0BM179 | ONE-BEAM-228-0BM179 | 1 | 84.2 | 84.2 |  |  | Steel Structure | [11 empty] | 0 | 84.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM180 | 0BM180 | ONE-BEAM-228-0BM180 | 1 | 80.4 | 80.4 |  |  | Steel Structure | [11 empty] | 0 | 80.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM181 | 0BM181 | ONE-BEAM-228-0BM181 | 1 | 93.5 | 93.5 |  |  | Steel Structure | [11 empty] | 0 | 93.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM182 | 0BM182 | ONE-BEAM-228-0BM182 | 1 | 2451.3 | 2451.3 |  |  | Steel Structure | [11 empty] | 0 | 2451.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM183 | 0BM183 | ONE-BEAM-228-0BM183 | 1 | 2235.3 | 2235.3 |  |  | Steel Structure | [11 empty] | 0 | 2235.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM184 | 0BM184 | ONE-BEAM-228-0BM184 | 1 | 48.2 | 48.2 |  |  | Steel Structure | [11 empty] | 0 | 48.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM185 | 0BM185(1/2) | 2-BEAMS-228-0BM185 | 1 | 15.9 | 15.9 |  |  | Steel Structure | [11 empty] | 0 | 15.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM185 | 0BM185(2/2) | 2-BEAMS-228-0BM185 | 1 | 15.9 | 15.9 |  |  | Steel Structure | [11 empty] | 0 | 15.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM186 | 0BM186 | ONE-BEAM-228-0BM186 | 1 | 32.5 | 32.5 |  |  | Steel Structure | [11 empty] | 0 | 32.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM187 | 0BM187 | ONE-BEAM-228-0BM187 | 1 | 101.9 | 101.9 |  |  | Steel Structure | [11 empty] | 0 | 101.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM188 | 0BM188 | ONE-BEAM-228-0BM188 | 1 | 19.8 | 19.8 |  |  | Steel Structure | [11 empty] | 0 | 19.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM189 | 0BM189 | ONE-BEAM-228-0BM189 | 1 | 117.3 | 117.3 |  |  | Steel Structure | [11 empty] | 0 | 117.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM190 | 0BM190 | ONE-BEAM-228-0BM190 | 1 | 144.5 | 144.5 |  |  | Steel Structure | [11 empty] | 0 | 144.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM191 | 0BM191 | ONE-BEAM-228-0BM191 | 1 | 115 | 115 |  |  | Steel Structure | [11 empty] | 0 | 115 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM192 | 0BM192 | ONE-BEAM-228-0BM192 | 1 | 119.8 | 119.8 |  |  | Steel Structure | [11 empty] | 0 | 119.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM193 | 0BM193(1/2) | 2-BEAMS-228-0BM193 | 1 | 17.2 | 17.2 |  |  | Steel Structure | [11 empty] | 0 | 17.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM193 | 0BM193(2/2) | 2-BEAMS-228-0BM193 | 1 | 17.2 | 17.2 |  |  | Steel Structure | [11 empty] | 0 | 17.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM194 | 0BM194 | ONE-BEAM-228-0BM194 | 1 | 11.7 | 11.7 |  |  | Steel Structure | [11 empty] | 0 | 11.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM195 | 0BM195(1/2) | 2-BEAMS-228-0BM195 | 1 | 20.6 | 20.6 |  |  | Steel Structure | [11 empty] | 0 | 20.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM195 | 0BM195(2/2) | 2-BEAMS-228-0BM195 | 1 | 20.6 | 20.6 |  |  | Steel Structure | [11 empty] | 0 | 20.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM196 | 0BM196 | ONE-BEAM-228-0BM196 | 1 | 171.3 | 171.3 |  |  | Steel Structure | [11 empty] | 0 | 171.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM197 | 0BM197 | ONE-BEAM-228-0BM197 | 1 | 144.9 | 144.9 |  |  | Steel Structure | [11 empty] | 0 | 144.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM198 | 0BM198 | ONE-BEAM-228-0BM198 | 1 | 157.3 | 157.3 |  |  | Steel Structure | [11 empty] | 0 | 157.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM199 | 0BM199 | ONE-BEAM-228-0BM199 | 1 | 138 | 138 |  |  | Steel Structure | [11 empty] | 0 | 138 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM200 | 0BM200 | ONE-BEAM-228-0BM200 | 1 | 190.1 | 190.1 |  |  | Steel Structure | [11 empty] | 0 | 190.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM201 | 0BM201 | ONE-BEAM-228-0BM201 | 1 | 325.9 | 325.9 |  |  | Steel Structure | [11 empty] | 0 | 325.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM202 | 0BM202(1/4) | 4-BEAMS-228-0BM202 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM202 | 0BM202(2/4) | 4-BEAMS-228-0BM202 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM202 | 0BM202(3/4) | 4-BEAMS-228-0BM202 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM202 | 0BM202(4/4) | 4-BEAMS-228-0BM202 | 1 | 24.8 | 24.8 |  |  | Steel Structure | [11 empty] | 0 | 24.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM203 | 0BM203 | ONE-BEAM-228-0BM203 | 1 | 75.8 | 75.8 |  |  | Steel Structure | [11 empty] | 0 | 75.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM204 | 0BM204 | ONE-BEAM-228-0BM204 | 1 | 142.5 | 142.5 |  |  | Steel Structure | [11 empty] | 0 | 142.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM205 | 0BM205 | ONE-BEAM-228-0BM205 | 1 | 174.1 | 174.1 |  |  | Steel Structure | [11 empty] | 0 | 174.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM206 | 0BM206 | ONE-BEAM-228-0BM206 | 1 | 143.9 | 143.9 |  |  | Steel Structure | [11 empty] | 0 | 143.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM207 | 0BM207 | ONE-BEAM-228-0BM207 | 1 | 134.1 | 134.1 |  |  | Steel Structure | [11 empty] | 0 | 134.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM208 | 0BM208 | ONE-BEAM-228-0BM208 | 1 | 122.7 | 122.7 |  |  | Steel Structure | [11 empty] | 0 | 122.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM209 | 0BM209 | ONE-BEAM-228-0BM209 | 1 | 137 | 137 |  |  | Steel Structure | [11 empty] | 0 | 137 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM210 | 0BM210 | ONE-BEAM-228-0BM210 | 1 | 45.3 | 45.3 |  |  | Steel Structure | [11 empty] | 0 | 45.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM211 | 0BM211 | ONE-BEAM-228-0BM211 | 1 | 34.9 | 34.9 |  |  | Steel Structure | [11 empty] | 0 | 34.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM212 | 0BM212 | ONE-BEAM-228-0BM212 | 1 | 29 | 29 |  |  | Steel Structure | [11 empty] | 0 | 29 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM213 | 0BM213 | ONE-BEAM-228-0BM213 | 1 | 30.8 | 30.8 |  |  | Steel Structure | [11 empty] | 0 | 30.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM214 | 0BM214 | ONE-BEAM-228-0BM214 | 1 | 24.2 | 24.2 |  |  | Steel Structure | [11 empty] | 0 | 24.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM215 | 0BM215(1/2) | 2-BEAMS-228-0BM215 | 1 | 15.4 | 15.4 |  |  | Steel Structure | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM215 | 0BM215(2/2) | 2-BEAMS-228-0BM215 | 1 | 15.4 | 15.4 |  |  | Steel Structure | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM216 | 0BM216 | ONE-BEAM-228-0BM216 | 1 | 102.5 | 102.5 |  |  | Steel Structure | [11 empty] | 0 | 102.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM217 | 0BM217 | ONE-BEAM-228-0BM217 | 1 | 101.1 | 101.1 |  |  | Steel Structure | [11 empty] | 0 | 101.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM218 | 0BM218 | ONE-BEAM-228-0BM218 | 1 | 20.3 | 20.3 |  |  | Steel Structure | [11 empty] | 0 | 20.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM219 | 0BM219 | ONE-BEAM-228-0BM219 | 1 | 18.9 | 18.9 |  |  | Steel Structure | [11 empty] | 0 | 18.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM220 | 0BM220 | ONE-BEAM-228-0BM220 | 1 | 24.3 | 24.3 |  |  | Steel Structure | [11 empty] | 0 | 24.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM221 | 0BM221 | ONE-BEAM-228-0BM221 | 1 | 45.4 | 45.4 |  |  | Steel Structure | [11 empty] | 0 | 45.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM222 | 0BM222 | ONE-BEAM-228-0BM222 | 1 | 120.9 | 120.9 |  |  | Steel Structure | [11 empty] | 0 | 120.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM223 | 0BM223 | ONE-BEAM-228-0BM223 | 1 | 122.9 | 122.9 |  |  | Steel Structure | [11 empty] | 0 | 122.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM224 | 0BM224(1/3) | 3-BEAMS-228-0BM224 | 1 | 17.3 | 17.3 |  |  | Steel Structure | [11 empty] | 0 | 17.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM224 | 0BM224(2/3) | 3-BEAMS-228-0BM224 | 1 | 17.3 | 17.3 |  |  | Steel Structure | [11 empty] | 0 | 17.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM224 | 0BM224(3/3) | 3-BEAMS-228-0BM224 | 1 | 17.3 | 17.3 |  |  | Steel Structure | [11 empty] | 0 | 17.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM225 | 0BM225 | ONE-BEAM-228-0BM225 | 1 | 140 | 140 |  |  | Steel Structure | [11 empty] | 0 | 140 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM226 | 0BM226(1/3) | 3-BEAMS-228-0BM226 | 1 | 33.9 | 33.9 |  |  | Steel Structure | [11 empty] | 0 | 33.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM226 | 0BM226(2/3) | 3-BEAMS-228-0BM226 | 1 | 33.9 | 33.9 |  |  | Steel Structure | [11 empty] | 0 | 33.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM226 | 0BM226(3/3) | 3-BEAMS-228-0BM226 | 1 | 33.9 | 33.9 |  |  | Steel Structure | [11 empty] | 0 | 33.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM227 | 0BM227 | ONE-BEAM-228-0BM227 | 1 | 103.6 | 103.6 |  |  | Steel Structure | [11 empty] | 0 | 103.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM228 | 0BM228(1/3) | 3-BEAMS-228-0BM228 | 1 | 41 | 41 |  |  | Steel Structure | [11 empty] | 0 | 41 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM228 | 0BM228(2/3) | 3-BEAMS-228-0BM228 | 1 | 41 | 41 |  |  | Steel Structure | [11 empty] | 0 | 41 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM228 | 0BM228(3/3) | 3-BEAMS-228-0BM228 | 1 | 41 | 41 |  |  | Steel Structure | [11 empty] | 0 | 41 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM229 | 0BM229 | ONE-BEAM-228-0BM229 | 1 | 145.1 | 145.1 |  |  | Steel Structure | [11 empty] | 0 | 145.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM230 | 0BM230 | ONE-BEAM-228-0BM230 | 1 | 105.2 | 105.2 |  |  | Steel Structure | [11 empty] | 0 | 105.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM231 | 0BM231 | ONE-BEAM-229-0BM231 | 1 | 63.5 | 63.5 |  |  | Steel Structure | [11 empty] | 0 | 63.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM232 | 0BM232(1/2) | 2-BEAMS-229-0BM232 | 1 | 60.1 | 60.1 |  |  | Steel Structure | [11 empty] | 0 | 60.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM232 | 0BM232(2/2) | 2-BEAMS-229-0BM232 | 1 | 60.1 | 60.1 |  |  | Steel Structure | [11 empty] | 0 | 60.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM233 | 0BM233 | ONE-BEAM-229-0BM233 | 1 | 66.3 | 66.3 |  |  | Steel Structure | [11 empty] | 0 | 66.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM234 | 0BM234 | ONE-BEAM-229-0BM234 | 1 | 136.7 | 136.7 |  |  | Steel Structure | [11 empty] | 0 | 136.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM235 | 0BM235 | ONE-BEAM-229-0BM235 | 1 | 115.1 | 115.1 |  |  | Steel Structure | [11 empty] | 0 | 115.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM236 | 0BM236 | ONE-BEAM-229-0BM236 | 1 | 200 | 200 |  |  | Steel Structure | [11 empty] | 0 | 200 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM237 | 0BM237 | ONE-BEAM-229-0BM237 | 1 | 162.4 | 162.4 |  |  | Steel Structure | [11 empty] | 0 | 162.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM238 | 0BM238(1/2) | 2-BEAMS-229-0BM238 | 1 | 63.2 | 63.2 |  |  | Steel Structure | [11 empty] | 0 | 63.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM238 | 0BM238(2/2) | 2-BEAMS-229-0BM238 | 1 | 63.2 | 63.2 |  |  | Steel Structure | [11 empty] | 0 | 63.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM239 | 0BM239(1/5) | 5-BEAMS-229-0BM239 | 1 | 57.1 | 57.1 |  |  | Steel Structure | [11 empty] | 0 | 57.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM239 | 0BM239(2/5) | 5-BEAMS-229-0BM239 | 1 | 57.1 | 57.1 |  |  | Steel Structure | [11 empty] | 0 | 57.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM239 | 0BM239(3/5) | 5-BEAMS-229-0BM239 | 1 | 57.1 | 57.1 |  |  | Steel Structure | [11 empty] | 0 | 57.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM239 | 0BM239(4/5) | 5-BEAMS-229-0BM239 | 1 | 57.1 | 57.1 |  |  | Steel Structure | [11 empty] | 0 | 57.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM239 | 0BM239(5/5) | 5-BEAMS-229-0BM239 | 1 | 57.1 | 57.1 |  |  | Steel Structure | [11 empty] | 0 | 57.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM240 | 0BM240(1/4) | 4-BEAMS-229-0BM240 | 1 | 64.7 | 64.7 |  |  | Steel Structure | [11 empty] | 0 | 64.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM240 | 0BM240(2/4) | 4-BEAMS-229-0BM240 | 1 | 64.7 | 64.7 |  |  | Steel Structure | [11 empty] | 0 | 64.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM240 | 0BM240(3/4) | 4-BEAMS-229-0BM240 | 1 | 64.7 | 64.7 |  |  | Steel Structure | [11 empty] | 0 | 64.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM240 | 0BM240(4/4) | 4-BEAMS-229-0BM240 | 1 | 64.7 | 64.7 |  |  | Steel Structure | [11 empty] | 0 | 64.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM241 | 0BM241(1/2) | 2-BEAMS-229-0BM241 | 1 | 70.9 | 70.9 |  |  | Steel Structure | [11 empty] | 0 | 70.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM241 | 0BM241(2/2) | 2-BEAMS-229-0BM241 | 1 | 70.9 | 70.9 |  |  | Steel Structure | [11 empty] | 0 | 70.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM242 | 0BM242 | ONE-BEAM-229-0BM242 | 1 | 140.7 | 140.7 |  |  | Steel Structure | [11 empty] | 0 | 140.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM243 | 0BM243 | ONE-BEAM-229-0BM243 | 1 | 115.1 | 115.1 |  |  | Steel Structure | [11 empty] | 0 | 115.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM244 | 0BM244 | ONE-BEAM-229-0BM244 | 1 | 200 | 200 |  |  | Steel Structure | [11 empty] | 0 | 200 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM245 | 0BM245 | ONE-BEAM-229-0BM245 | 1 | 164.3 | 164.3 |  |  | Steel Structure | [11 empty] | 0 | 164.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM246 | 0BM246 | ONE-BEAM-229-0BM246 | 1 | 171 | 171 |  |  | Steel Structure | [11 empty] | 0 | 171 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM247 | 0BM247(1/3) | 3-BEAMS-229-0BM247 | 1 | 52.5 | 52.5 |  |  | Steel Structure | [11 empty] | 0 | 52.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM247 | 0BM247(2/3) | 3-BEAMS-229-0BM247 | 1 | 52.5 | 52.5 |  |  | Steel Structure | [11 empty] | 0 | 52.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM247 | 0BM247(3/3) | 3-BEAMS-229-0BM247 | 1 | 52.5 | 52.5 |  |  | Steel Structure | [11 empty] | 0 | 52.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM248 | 0BM248 | ONE-BEAM-229-0BM248 | 1 | 60.1 | 60.1 |  |  | Steel Structure | [11 empty] | 0 | 60.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM249 | 0BM249 | ONE-BEAM-229-0BM249 | 1 | 148.6 | 148.6 |  |  | Steel Structure | [11 empty] | 0 | 148.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM250 | 0BM250 | ONE-BEAM-229-0BM250 | 1 | 50.7 | 50.7 |  |  | Steel Structure | [11 empty] | 0 | 50.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM251 | 0BM251 | ONE-BEAM-229-0BM251 | 1 | 75.6 | 75.6 |  |  | Steel Structure | [11 empty] | 0 | 75.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM252 | 0BM252 | ONE-BEAM-229-0BM252 | 1 | 55.5 | 55.5 |  |  | Steel Structure | [11 empty] | 0 | 55.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM253 | 0BM253(1/2) | 2-BEAMS-229-0BM253 | 1 | 61.7 | 61.7 |  |  | Steel Structure | [11 empty] | 0 | 61.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM253 | 0BM253(2/2) | 2-BEAMS-229-0BM253 | 1 | 61.7 | 61.7 |  |  | Steel Structure | [11 empty] | 0 | 61.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM254 | 0BM254(1/3) | 3-BEAMS-229-0BM254 | 1 | 49.4 | 49.4 |  |  | Steel Structure | [11 empty] | 0 | 49.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM254 | 0BM254(2/3) | 3-BEAMS-229-0BM254 | 1 | 49.4 | 49.4 |  |  | Steel Structure | [11 empty] | 0 | 49.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM254 | 0BM254(3/3) | 3-BEAMS-229-0BM254 | 1 | 49.4 | 49.4 |  |  | Steel Structure | [11 empty] | 0 | 49.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM255 | 0BM255 | ONE-BEAM-229-0BM255 | 1 | 163.1 | 163.1 |  |  | Steel Structure | [11 empty] | 0 | 163.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM256 | 0BM256 | ONE-BEAM-229-0BM256 | 1 | 139.5 | 139.5 |  |  | Steel Structure | [11 empty] | 0 | 139.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM257 | 0BM257 | ONE-BEAM-229-0BM257 | 1 | 157.3 | 157.3 |  |  | Steel Structure | [11 empty] | 0 | 157.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM258 | 0BM258(1/2) | 2-BEAMS-229-0BM258 | 1 | 54 | 54 |  |  | Steel Structure | [11 empty] | 0 | 54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM258 | 0BM258(2/2) | 2-BEAMS-229-0BM258 | 1 | 54 | 54 |  |  | Steel Structure | [11 empty] | 0 | 54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM259 | 0BM259 | ONE-BEAM-229-0BM259 | 1 | 155.9 | 155.9 |  |  | Steel Structure | [11 empty] | 0 | 155.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM260 | 0BM260 | ONE-BEAM-229-0BM260 | 1 | 183.4 | 183.4 |  |  | Steel Structure | [11 empty] | 0 | 183.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM261 | 0BM261 | ONE-BEAM-229-0BM261 | 1 | 190.8 | 190.8 |  |  | Steel Structure | [11 empty] | 0 | 190.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM262 | 0BM262 | ONE-BEAM-229-0BM262 | 1 | 114.6 | 114.6 |  |  | Steel Structure | [11 empty] | 0 | 114.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-229-0BM263 | 0BM263 | ONE-BEAM-229-0BM263 | 1 | 112.6 | 112.6 |  |  | Steel Structure | [11 empty] | 0 | 112.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM264 | 0BM264 | ONE-BEAM-418-0BM264 | 1 | 58.9 | 58.9 |  |  | Steel Structure | [11 empty] | 0 | 58.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM265 | 0BM265 | ONE-BEAM-418-0BM265 | 1 | 58.9 | 58.9 |  |  | Steel Structure | [11 empty] | 0 | 58.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM266 | 0BM266 | ONE-BEAM-418-0BM266 | 1 | 68.7 | 68.7 |  |  | Steel Structure | [11 empty] | 0 | 68.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM267 | 0BM267 | ONE-BEAM-418-0BM267 | 1 | 68.7 | 68.7 |  |  | Steel Structure | [11 empty] | 0 | 68.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM268 | 0BM268 | ONE-BEAM-418-0BM268 | 1 | 73.2 | 73.2 |  |  | Steel Structure | [11 empty] | 0 | 73.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM269 | 0BM269 | ONE-BEAM-418-0BM269 | 1 | 138.4 | 138.4 |  |  | Steel Structure | [11 empty] | 0 | 138.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM270 | 0BM270 | ONE-BEAM-418-0BM270 | 1 | 118.9 | 118.9 |  |  | Steel Structure | [11 empty] | 0 | 118.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM271 | 0BM271 | ONE-BEAM-418-0BM271 | 1 | 104.5 | 104.5 |  |  | Steel Structure | [11 empty] | 0 | 104.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM272 | 0BM272 | ONE-BEAM-418-0BM272 | 1 | 76.5 | 76.5 |  |  | Steel Structure | [11 empty] | 0 | 76.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM273 | 0BM273 | ONE-BEAM-418-0BM273 | 1 | 76.5 | 76.5 |  |  | Steel Structure | [11 empty] | 0 | 76.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM274 | 0BM274 | ONE-BEAM-418-0BM274 | 1 | 79.2 | 79.2 |  |  | Steel Structure | [11 empty] | 0 | 79.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM275 | 0BM275 | ONE-BEAM-418-0BM275 | 1 | 79.2 | 79.2 |  |  | Steel Structure | [11 empty] | 0 | 79.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM276 | 0BM276 | ONE-BEAM-418-0BM276 | 1 | 57.4 | 57.4 |  |  | Steel Structure | [11 empty] | 0 | 57.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM277 | 0BM277 | ONE-BEAM-418-0BM277 | 1 | 57.4 | 57.4 |  |  | Steel Structure | [11 empty] | 0 | 57.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM278 | 0BM278 | ONE-BEAM-418-0BM278 | 1 | 204 | 204 |  |  | Steel Structure | [11 empty] | 0 | 204 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM279 | 0BM279 | ONE-BEAM-418-0BM279 | 1 | 60.9 | 60.9 |  |  | Steel Structure | [11 empty] | 0 | 60.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM280 | 0BM280 | ONE-BEAM-418-0BM280 | 1 | 60.9 | 60.9 |  |  | Steel Structure | [11 empty] | 0 | 60.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM281 | 0BM281 | ONE-BEAM-418-0BM281 | 1 | 200.5 | 200.5 |  |  | Steel Structure | [11 empty] | 0 | 200.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM282 | 0BM282 | ONE-BEAM-418-0BM282 | 1 | 103.7 | 103.7 |  |  | Steel Structure | [11 empty] | 0 | 103.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM283 | 0BM283 | ONE-BEAM-418-0BM283 | 1 | 129.8 | 129.8 |  |  | Steel Structure | [11 empty] | 0 | 129.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM284 | 0BM284 | ONE-BEAM-418-0BM284 | 1 | 134.4 | 134.4 |  |  | Steel Structure | [11 empty] | 0 | 134.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM285 | 0BM285 | ONE-BEAM-418-0BM285 | 1 | 101.6 | 101.6 |  |  | Steel Structure | [11 empty] | 0 | 101.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-418-0BM286 | 0BM286 | ONE-BEAM-418-0BM286 | 1 | 75.5 | 75.5 |  |  | Steel Structure | [11 empty] | 0 | 75.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM287 | 0BM287 | ONE-BEAM-228-0BM287 | 1 | 50.5 | 50.5 |  |  | Steel Structure | [11 empty] | 0 | 50.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM288 | 0BM288 | ONE-BEAM-228-0BM288 | 1 | 50.5 | 50.5 |  |  | Steel Structure | [11 empty] | 0 | 50.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM289 | 0BM289 | ONE-BEAM-228-0BM289 | 1 | 59.7 | 59.7 |  |  | Steel Structure | [11 empty] | 0 | 59.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM290 | 0BM290 | ONE-BEAM-228-0BM290 | 1 | 22 | 22 |  |  | Steel Structure | [11 empty] | 0 | 22 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
275 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S3 | 25HG001-351-DD0-228-0BM291 | 0BM291 | ONE-BEAM-228-0BM291 | 1 | 45.4 | 45.4 |  |  | Steel Structure | [11 empty] | 0 | 45.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
276 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR069 | 0GR069(1/2) | 2-GIRDERS-228-0GR069 | 1 | 170.1 | 170.1 |  |  | Steel Structure | [11 empty] | 0 | 170.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
277 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR069 | 0GR069(2/2) | 2-GIRDERS-228-0GR069 | 1 | 170.1 | 170.1 |  |  | Steel Structure | [11 empty] | 0 | 170.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
278 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR070 | 0GR070(1/4) | 4-GIRDERS-228-0GR070 | 1 | 118.1 | 118.1 |  |  | Steel Structure | [11 empty] | 0 | 118.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
279 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR070 | 0GR070(2/4) | 4-GIRDERS-228-0GR070 | 1 | 118.1 | 118.1 |  |  | Steel Structure | [11 empty] | 0 | 118.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
280 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR070 | 0GR070(3/4) | 4-GIRDERS-228-0GR070 | 1 | 118.1 | 118.1 |  |  | Steel Structure | [11 empty] | 0 | 118.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
281 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR070 | 0GR070(4/4) | 4-GIRDERS-228-0GR070 | 1 | 118.1 | 118.1 |  |  | Steel Structure | [11 empty] | 0 | 118.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
282 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR071 | 0GR071 | ONE-GIRDER-228-0GR071 | 1 | 642.7 | 642.7 |  |  | Steel Structure | [11 empty] | 0 | 642.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
283 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR076 | 0GR076 | ONE-GIRDER-228-0GR076 | 1 | 118 | 118 |  |  | Steel Structure | [11 empty] | 0 | 118 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
284 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR077 | 0GR077 | ONE-GIRDER-228-0GR077 | 1 | 139.2 | 139.2 |  |  | Steel Structure | [11 empty] | 0 | 139.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
285 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR078 | 0GR078 | ONE-GIRDER-228-0GR078 | 1 | 120.9 | 120.9 |  |  | Steel Structure | [11 empty] | 0 | 120.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
286 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR079 | 0GR079 | ONE-GIRDER-228-0GR079 | 1 | 223.8 | 223.8 |  |  | Steel Structure | [11 empty] | 0 | 223.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
287 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR080 | 0GR080 | ONE-GIRDER-228-0GR080 | 1 | 176.6 | 176.6 |  |  | Steel Structure | [11 empty] | 0 | 176.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
288 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR081 | 0GR081 | ONE-GIRDER-228-0GR081 | 1 | 169.2 | 169.2 |  |  | Steel Structure | [11 empty] | 0 | 169.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
289 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR082 | 0GR082 | ONE-GIRDER-228-0GR082 | 1 | 186.2 | 186.2 |  |  | Steel Structure | [11 empty] | 0 | 186.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
290 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR083 | 0GR083 | ONE-GIRDER-228-0GR083 | 1 | 173.5 | 173.5 |  |  | Steel Structure | [11 empty] | 0 | 173.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
291 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR084 | 0GR084 | ONE-GIRDER-228-0GR084 | 1 | 138.7 | 138.7 |  |  | Steel Structure | [11 empty] | 0 | 138.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
292 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR085 | 0GR085 | ONE-GIRDER-228-0GR085 | 1 | 124 | 124 |  |  | Steel Structure | [11 empty] | 0 | 124 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
293 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR086 | 0GR086 | ONE-GIRDER-228-0GR086 | 1 | 111.8 | 111.8 |  |  | Steel Structure | [11 empty] | 0 | 111.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
294 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR087 | 0GR087 | ONE-GIRDER-228-0GR087 | 1 | 125.7 | 125.7 |  |  | Steel Structure | [11 empty] | 0 | 125.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
295 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR088 | 0GR088 | ONE-GIRDER-228-0GR088 | 1 | 134.2 | 134.2 |  |  | Steel Structure | [11 empty] | 0 | 134.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
296 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR089 | 0GR089 | ONE-GIRDER-228-0GR089 | 1 | 133.4 | 133.4 |  |  | Steel Structure | [11 empty] | 0 | 133.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
297 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR090 | 0GR090 | ONE-GIRDER-228-0GR090 | 1 | 114.6 | 114.6 |  |  | Steel Structure | [11 empty] | 0 | 114.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
298 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR091 | 0GR091 | ONE-GIRDER-228-0GR091 | 1 | 128.4 | 128.4 |  |  | Steel Structure | [11 empty] | 0 | 128.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
299 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR092 | 0GR092 | ONE-GIRDER-228-0GR092 | 1 | 96.6 | 96.6 |  |  | Steel Structure | [11 empty] | 0 | 96.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
300 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR093 | 0GR093 | ONE-GIRDER-228-0GR093 | 1 | 72 | 72 |  |  | Steel Structure | [11 empty] | 0 | 72 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
301 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR094 | 0GR094 | ONE-GIRDER-228-0GR094 | 1 | 55.9 | 55.9 |  |  | Steel Structure | [11 empty] | 0 | 55.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
302 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR095 | 0GR095 | ONE-GIRDER-228-0GR095 | 1 | 135.4 | 135.4 |  |  | Steel Structure | [11 empty] | 0 | 135.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
303 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR096 | 0GR096(1/3) | 3-GIRDERS-228-0GR096 | 1 | 90.3 | 90.3 |  |  | Steel Structure | [11 empty] | 0 | 90.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
304 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR096 | 0GR096(2/3) | 3-GIRDERS-228-0GR096 | 1 | 90.3 | 90.3 |  |  | Steel Structure | [11 empty] | 0 | 90.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
305 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR096 | 0GR096(3/3) | 3-GIRDERS-228-0GR096 | 1 | 90.3 | 90.3 |  |  | Steel Structure | [11 empty] | 0 | 90.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
306 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR097 | 0GR097 | ONE-GIRDER-228-0GR097 | 1 | 58.1 | 58.1 |  |  | Steel Structure | [11 empty] | 0 | 58.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
307 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR098 | 0GR098(1/2) | 2-GIRDERS-228-0GR098 | 1 | 50.4 | 50.4 |  |  | Steel Structure | [11 empty] | 0 | 50.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
308 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR098 | 0GR098(2/2) | 2-GIRDERS-228-0GR098 | 1 | 50.4 | 50.4 |  |  | Steel Structure | [11 empty] | 0 | 50.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
309 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR099 | 0GR099 | ONE-GIRDER-228-0GR099 | 1 | 127.5 | 127.5 |  |  | Steel Structure | [11 empty] | 0 | 127.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
310 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR100 | 0GR100 | ONE-GIRDER-228-0GR100 | 1 | 54.5 | 54.5 |  |  | Steel Structure | [11 empty] | 0 | 54.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
311 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR101 | 0GR101 | ONE-GIRDER-228-0GR101 | 1 | 135.4 | 135.4 |  |  | Steel Structure | [11 empty] | 0 | 135.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
312 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR102 | 0GR102 | ONE-GIRDER-228-0GR102 | 1 | 56 | 56 |  |  | Steel Structure | [11 empty] | 0 | 56 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
313 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR103 | 0GR103 | ONE-GIRDER-228-0GR103 | 1 | 119.4 | 119.4 |  |  | Steel Structure | [11 empty] | 0 | 119.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
314 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR104 | 0GR104 | ONE-GIRDER-228-0GR104 | 1 | 138.4 | 138.4 |  |  | Steel Structure | [11 empty] | 0 | 138.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
315 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR105 | 0GR105 | ONE-GIRDER-228-0GR105 | 1 | 104.7 | 104.7 |  |  | Steel Structure | [11 empty] | 0 | 104.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
316 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR106 | 0GR106 | ONE-GIRDER-228-0GR106 | 1 | 194 | 194 |  |  | Steel Structure | [11 empty] | 0 | 194 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
317 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR107 | 0GR107 | ONE-GIRDER-228-0GR107 | 1 | 123.4 | 123.4 |  |  | Steel Structure | [11 empty] | 0 | 123.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
318 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR108 | 0GR108 | ONE-GIRDER-228-0GR108 | 1 | 157.8 | 157.8 |  |  | Steel Structure | [11 empty] | 0 | 157.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
319 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR109 | 0GR109 | ONE-GIRDER-228-0GR109 | 1 | 44.3 | 44.3 |  |  | Steel Structure | [11 empty] | 0 | 44.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
320 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR110 | 0GR110 | ONE-GIRDER-228-0GR110 | 1 | 92.4 | 92.4 |  |  | Steel Structure | [11 empty] | 0 | 92.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
321 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR111 | 0GR111 | ONE-GIRDER-228-0GR111 | 1 | 86.9 | 86.9 |  |  | Steel Structure | [11 empty] | 0 | 86.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
322 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR112 | 0GR112 | ONE-GIRDER-228-0GR112 | 1 | 108.4 | 108.4 |  |  | Steel Structure | [11 empty] | 0 | 108.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
323 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR113 | 0GR113 | ONE-GIRDER-228-0GR113 | 1 | 99.3 | 99.3 |  |  | Steel Structure | [11 empty] | 0 | 99.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
324 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR114 | 0GR114 | ONE-GIRDER-228-0GR114 | 1 | 28.1 | 28.1 |  |  | Steel Structure | [11 empty] | 0 | 28.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
325 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR115 | 0GR115(1/3) | 3-GIRDERS-228-0GR115 | 1 | 91.4 | 91.4 |  |  | Steel Structure | [11 empty] | 0 | 91.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
326 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR115 | 0GR115(2/3) | 3-GIRDERS-228-0GR115 | 1 | 91.4 | 91.4 |  |  | Steel Structure | [11 empty] | 0 | 91.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
327 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR115 | 0GR115(3/3) | 3-GIRDERS-228-0GR115 | 1 | 91.4 | 91.4 |  |  | Steel Structure | [11 empty] | 0 | 91.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
328 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR116 | 0GR116 | ONE-GIRDER-228-0GR116 | 1 | 95.7 | 95.7 |  |  | Steel Structure | [11 empty] | 0 | 95.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
329 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR117 | 0GR117 | ONE-GIRDER-228-0GR117 | 1 | 53.7 | 53.7 |  |  | Steel Structure | [11 empty] | 0 | 53.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
330 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR118 | 0GR118(1/2) | 2-GIRDERS-228-0GR118 | 1 | 111.5 | 111.5 |  |  | Steel Structure | [11 empty] | 0 | 111.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
331 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR118 | 0GR118(2/2) | 2-GIRDERS-228-0GR118 | 1 | 111.5 | 111.5 |  |  | Steel Structure | [11 empty] | 0 | 111.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
332 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR119 | 0GR119(1/3) | 3-GIRDERS-228-0GR119 | 1 | 28.7 | 28.7 |  |  | Steel Structure | [11 empty] | 0 | 28.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
333 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR119 | 0GR119(2/3) | 3-GIRDERS-228-0GR119 | 1 | 28.7 | 28.7 |  |  | Steel Structure | [11 empty] | 0 | 28.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
334 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR119 | 0GR119(3/3) | 3-GIRDERS-228-0GR119 | 1 | 28.7 | 28.7 |  |  | Steel Structure | [11 empty] | 0 | 28.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
335 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR120 | 0GR120 | ONE-GIRDER-228-0GR120 | 1 | 49.1 | 49.1 |  |  | Steel Structure | [11 empty] | 0 | 49.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
336 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR121 | 0GR121 | ONE-GIRDER-228-0GR121 | 1 | 50.8 | 50.8 |  |  | Steel Structure | [11 empty] | 0 | 50.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
337 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR122 | 0GR122 | ONE-GIRDER-228-0GR122 | 1 | 50.8 | 50.8 |  |  | Steel Structure | [11 empty] | 0 | 50.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
338 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR123 | 0GR123 | ONE-GIRDER-228-0GR123 | 1 | 53.7 | 53.7 |  |  | Steel Structure | [11 empty] | 0 | 53.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
339 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR124 | 0GR124 | ONE-GIRDER-228-0GR124 | 1 | 101.2 | 101.2 |  |  | Steel Structure | [11 empty] | 0 | 101.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
340 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR125 | 0GR125 | ONE-GIRDER-228-0GR125 | 1 | 95.4 | 95.4 |  |  | Steel Structure | [11 empty] | 0 | 95.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
341 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR126 | 0GR126 | ONE-GIRDER-228-0GR126 | 1 | 197.6 | 197.6 |  |  | Steel Structure | [11 empty] | 0 | 197.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
342 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR127 | 0GR127 | ONE-GIRDER-228-0GR127 | 1 | 93 | 93 |  |  | Steel Structure | [11 empty] | 0 | 93 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
343 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR128 | 0GR128 | ONE-GIRDER-228-0GR128 | 1 | 28.1 | 28.1 |  |  | Steel Structure | [11 empty] | 0 | 28.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
344 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR129 | 0GR129 | ONE-GIRDER-228-0GR129 | 1 | 65.9 | 65.9 |  |  | Steel Structure | [11 empty] | 0 | 65.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
345 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR130 | 0GR130 | ONE-GIRDER-228-0GR130 | 1 | 72 | 72 |  |  | Steel Structure | [11 empty] | 0 | 72 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
346 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR131 | 0GR131 | ONE-GIRDER-228-0GR131 | 1 | 92.4 | 92.4 |  |  | Steel Structure | [11 empty] | 0 | 92.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
347 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR132 | 0GR132 | ONE-GIRDER-228-0GR132 | 1 | 239.7 | 239.7 |  |  | Steel Structure | [11 empty] | 0 | 239.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
348 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR133 | 0GR133 | ONE-GIRDER-228-0GR133 | 1 | 182.5 | 182.5 |  |  | Steel Structure | [11 empty] | 0 | 182.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
349 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR134 | 0GR134 | ONE-GIRDER-228-0GR134 | 1 | 189.1 | 189.1 |  |  | Steel Structure | [11 empty] | 0 | 189.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
350 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR135 | 0GR135 | ONE-GIRDER-228-0GR135 | 1 | 204.4 | 204.4 |  |  | Steel Structure | [11 empty] | 0 | 204.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
351 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR136 | 0GR136 | ONE-GIRDER-228-0GR136 | 1 | 184.6 | 184.6 |  |  | Steel Structure | [11 empty] | 0 | 184.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
352 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR137 | 0GR137 | ONE-GIRDER-228-0GR137 | 1 | 153.9 | 153.9 |  |  | Steel Structure | [11 empty] | 0 | 153.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
353 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR138 | 0GR138 | ONE-GIRDER-228-0GR138 | 1 | 78.5 | 78.5 |  |  | Steel Structure | [11 empty] | 0 | 78.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
354 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR139 | 0GR139 | ONE-GIRDER-228-0GR139 | 1 | 147.8 | 147.8 |  |  | Steel Structure | [11 empty] | 0 | 147.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
355 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR140 | 0GR140(1/2) | 2-GIRDERS-228-0GR140 | 1 | 118.5 | 118.5 |  |  | Steel Structure | [11 empty] | 0 | 118.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
356 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR140 | 0GR140(2/2) | 2-GIRDERS-228-0GR140 | 1 | 118.5 | 118.5 |  |  | Steel Structure | [11 empty] | 0 | 118.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
357 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR141 | 0GR141 | ONE-GIRDER-228-0GR141 | 1 | 546.7 | 546.7 |  |  | Steel Structure | [11 empty] | 0 | 546.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
358 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR142 | 0GR142 | ONE-GIRDER-228-0GR142 | 1 | 107.7 | 107.7 |  |  | Steel Structure | [11 empty] | 0 | 107.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
359 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR144 | 0GR144 | ONE-GIRDER-228-0GR144 | 1 | 32.4 | 32.4 |  |  | Steel Structure | [11 empty] | 0 | 32.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
360 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR145 | 0GR145 | ONE-GIRDER-228-0GR145 | 1 | 28.9 | 28.9 |  |  | Steel Structure | [11 empty] | 0 | 28.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
361 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR146 | 0GR146 | ONE-GIRDER-228-0GR146 | 1 | 251.1 | 251.1 |  |  | Steel Structure | [11 empty] | 0 | 251.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
362 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR147 | 0GR147 | ONE-GIRDER-228-0GR147 | 1 | 53.4 | 53.4 |  |  | Steel Structure | [11 empty] | 0 | 53.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
363 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR148 | 0GR148 | ONE-GIRDER-228-0GR148 | 1 | 77.9 | 77.9 |  |  | Steel Structure | [11 empty] | 0 | 77.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
364 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR149 | 0GR149 | ONE-GIRDER-228-0GR149 | 1 | 272 | 272 |  |  | Steel Structure | [11 empty] | 0 | 272 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
365 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR150 | 0GR150 | ONE-GIRDER-228-0GR150 | 1 | 55 | 55 |  |  | Steel Structure | [11 empty] | 0 | 55 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
366 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR151 | 0GR151 | ONE-GIRDER-228-0GR151 | 1 | 49.9 | 49.9 |  |  | Steel Structure | [11 empty] | 0 | 49.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
367 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR153 | 0GR153 | ONE-GIRDER-228-0GR153 | 1 | 67.3 | 67.3 |  |  | Steel Structure | [11 empty] | 0 | 67.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
368 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR154 | 0GR154 | ONE-GIRDER-228-0GR154 | 1 | 97.6 | 97.6 |  |  | Steel Structure | [11 empty] | 0 | 97.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
369 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR155 | 0GR155 | ONE-GIRDER-228-0GR155 | 1 | 49.9 | 49.9 |  |  | Steel Structure | [11 empty] | 0 | 49.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
370 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR156 | 0GR156 | ONE-GIRDER-228-0GR156 | 1 | 53.5 | 53.5 |  |  | Steel Structure | [11 empty] | 0 | 53.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
371 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR157 | 0GR157 | ONE-GIRDER-228-0GR157 | 1 | 100.6 | 100.6 |  |  | Steel Structure | [11 empty] | 0 | 100.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
372 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR158 | 0GR158 | ONE-GIRDER-228-0GR158 | 1 | 277.6 | 277.6 |  |  | Steel Structure | [11 empty] | 0 | 277.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
373 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR159 | 0GR159 | ONE-GIRDER-228-0GR159 | 1 | 53.4 | 53.4 |  |  | Steel Structure | [11 empty] | 0 | 53.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
374 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR160 | 0GR160 | ONE-GIRDER-228-0GR160 | 1 | 251.1 | 251.1 |  |  | Steel Structure | [11 empty] | 0 | 251.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
375 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR161 | 0GR161 | ONE-GIRDER-228-0GR161 | 1 | 145.1 | 145.1 |  |  | Steel Structure | [11 empty] | 0 | 145.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
376 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR162 | 0GR162 | ONE-GIRDER-228-0GR162 | 1 | 83.1 | 83.1 |  |  | Steel Structure | [11 empty] | 0 | 83.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
377 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR163 | 0GR163 | ONE-GIRDER-228-0GR163 | 1 | 148 | 148 |  |  | Steel Structure | [11 empty] | 0 | 148 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
378 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR164 | 0GR164 | ONE-GIRDER-228-0GR164 | 1 | 540.1 | 540.1 |  |  | Steel Structure | [11 empty] | 0 | 540.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
379 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR166 | 0GR166 | ONE-GIRDER-228-0GR166 | 1 | 122.5 | 122.5 |  |  | Steel Structure | [11 empty] | 0 | 122.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
380 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR167 | 0GR167 | ONE-GIRDER-228-0GR167 | 1 | 152.9 | 152.9 |  |  | Steel Structure | [11 empty] | 0 | 152.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
381 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR168 | 0GR168 | ONE-GIRDER-228-0GR168 | 1 | 191.9 | 191.9 |  |  | Steel Structure | [11 empty] | 0 | 191.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
382 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR169 | 0GR169 | ONE-GIRDER-228-0GR169 | 1 | 163.1 | 163.1 |  |  | Steel Structure | [11 empty] | 0 | 163.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
383 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR170 | 0GR170 | ONE-GIRDER-228-0GR170 | 1 | 160.3 | 160.3 |  |  | Steel Structure | [11 empty] | 0 | 160.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
384 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR171 | 0GR171 | ONE-GIRDER-228-0GR171 | 1 | 168.6 | 168.6 |  |  | Steel Structure | [11 empty] | 0 | 168.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
385 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR172 | 0GR172 | ONE-GIRDER-228-0GR172 | 1 | 52.9 | 52.9 |  |  | Steel Structure | [11 empty] | 0 | 52.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
386 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR173 | 0GR173 | ONE-GIRDER-228-0GR173 | 1 | 52.9 | 52.9 |  |  | Steel Structure | [11 empty] | 0 | 52.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
387 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR174 | 0GR174 | ONE-GIRDER-228-0GR174 | 1 | 120.4 | 120.4 |  |  | Steel Structure | [11 empty] | 0 | 120.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
388 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR175 | 0GR175 | ONE-GIRDER-228-0GR175 | 1 | 127 | 127 |  |  | Steel Structure | [11 empty] | 0 | 127 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
389 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR176 | 0GR176 | ONE-GIRDER-228-0GR176 | 1 | 118.9 | 118.9 |  |  | Steel Structure | [11 empty] | 0 | 118.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
390 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR177 | 0GR177 | ONE-GIRDER-228-0GR177 | 1 | 30.8 | 30.8 |  |  | Steel Structure | [11 empty] | 0 | 30.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
391 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR178 | 0GR178 | ONE-GIRDER-228-0GR178 | 1 | 73 | 73 |  |  | Steel Structure | [11 empty] | 0 | 73 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
392 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR179 | 0GR179 | ONE-GIRDER-228-0GR179 | 1 | 74.6 | 74.6 |  |  | Steel Structure | [11 empty] | 0 | 74.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
393 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR180 | 0GR180 | 2-GIRDERS-228-0GR180 | 1 | 200.1 | 200.1 |  |  | Steel Structure | [11 empty] | 0 | 200.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
394 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR181 | 0GR181 | ONE-GIRDER-228-0GR181 | 1 | 200 | 200 |  |  | Steel Structure | [11 empty] | 0 | 200 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
395 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR182 | 0GR182(1/2) | 2-GIRDERS-228-0GR182 | 1 | 163.5 | 163.5 |  |  | Steel Structure | [11 empty] | 0 | 163.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
396 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR182 | 0GR182(2/2) | 2-GIRDERS-228-0GR182 | 1 | 163.5 | 163.5 |  |  | Steel Structure | [11 empty] | 0 | 163.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
397 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR183 | 0GR183 | ONE-GIRDER-228-0GR183 | 1 | 202.5 | 202.5 |  |  | Steel Structure | [11 empty] | 0 | 202.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
398 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR184 | 0GR184 | ONE-GIRDER-228-0GR184 | 1 | 111.7 | 111.7 |  |  | Steel Structure | [11 empty] | 0 | 111.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
399 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR185 | 0GR185(1/2) | 2-GIRDERS-228-0GR185 | 1 | 93.3 | 93.3 |  |  | Steel Structure | [11 empty] | 0 | 93.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
400 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR185 | 0GR185(2/2) | 2-GIRDERS-228-0GR185 | 1 | 93.3 | 93.3 |  |  | Steel Structure | [11 empty] | 0 | 93.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
401 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR186 | 0GR186 | ONE-GIRDER-228-0GR186 | 1 | 117.8 | 117.8 |  |  | Steel Structure | [11 empty] | 0 | 117.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
402 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR187 | 0GR187 | ONE-GIRDER-228-0GR187 | 1 | 130.4 | 130.4 |  |  | Steel Structure | [11 empty] | 0 | 130.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
403 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR188 | 0GR188 | ONE-GIRDER-228-0GR188 | 1 | 136.2 | 136.2 |  |  | Steel Structure | [11 empty] | 0 | 136.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
404 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR189 | 0GR189 | ONE-GIRDER-228-0GR189 | 1 | 82.4 | 82.4 |  |  | Steel Structure | [11 empty] | 0 | 82.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
405 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR190 | 0GR190 | ONE-GIRDER-228-0GR190 | 1 | 133.1 | 133.1 |  |  | Steel Structure | [11 empty] | 0 | 133.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
406 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR191 | 0GR191 | ONE-GIRDER-228-0GR191 | 1 | 78.9 | 78.9 |  |  | Steel Structure | [11 empty] | 0 | 78.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
407 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR192 | 0GR192 | ONE-GIRDER-228-0GR192 | 1 | 40.2 | 40.2 |  |  | Steel Structure | [11 empty] | 0 | 40.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
408 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR193 | 0GR193 | ONE-GIRDER-228-0GR193 | 1 | 37 | 37 |  |  | Steel Structure | [11 empty] | 0 | 37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
409 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR194 | 0GR194 | ONE-GIRDER-228-0GR194 | 1 | 64.8 | 64.8 |  |  | Steel Structure | [11 empty] | 0 | 64.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
410 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0GR267 | 0GR267 | ONE-GIRDER-228-0GR267 | 1 | 75.3 | 75.3 |  |  | Steel Structure | [11 empty] | 0 | 75.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
411 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR195 | 0GR195 | ONE-GIRDER-229-0GR195 | 1 | 104.3 | 104.3 |  |  | Steel Structure | [11 empty] | 0 | 104.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
412 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR196 | 0GR196 | ONE-GIRDER-229-0GR196 | 1 | 242.3 | 242.3 |  |  | Steel Structure | [11 empty] | 0 | 242.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
413 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR197 | 0GR197 | ONE-GIRDER-229-0GR197 | 1 | 212.1 | 212.1 |  |  | Steel Structure | [11 empty] | 0 | 212.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
414 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR198 | 0GR198 | ONE-GIRDER-229-0GR198 | 1 | 273 | 273 |  |  | Steel Structure | [11 empty] | 0 | 273 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
415 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR199 | 0GR199 | ONE-GIRDER-229-0GR199 | 1 | 201.7 | 201.7 |  |  | Steel Structure | [11 empty] | 0 | 201.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
416 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR200 | 0GR200 | ONE-GIRDER-229-0GR200 | 1 | 222.9 | 222.9 |  |  | Steel Structure | [11 empty] | 0 | 222.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
417 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR201 | 0GR201 | ONE-GIRDER-229-0GR201 | 1 | 209 | 209 |  |  | Steel Structure | [11 empty] | 0 | 209 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
418 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR202 | 0GR202 | ONE-GIRDER-229-0GR202 | 1 | 223 | 223 |  |  | Steel Structure | [11 empty] | 0 | 223 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
419 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR203 | 0GR203 | ONE-GIRDER-229-0GR203 | 1 | 209 | 209 |  |  | Steel Structure | [11 empty] | 0 | 209 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
420 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR204 | 0GR204 | ONE-GIRDER-229-0GR204 | 1 | 218 | 218 |  |  | Steel Structure | [11 empty] | 0 | 218 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
421 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR205 | 0GR205 | ONE-GIRDER-229-0GR205 | 1 | 195.8 | 195.8 |  |  | Steel Structure | [11 empty] | 0 | 195.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
422 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR206 | 0GR206 | ONE-GIRDER-229-0GR206 | 1 | 198.5 | 198.5 |  |  | Steel Structure | [11 empty] | 0 | 198.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
423 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR207 | 0GR207 | ONE-GIRDER-229-0GR207 | 1 | 249.2 | 249.2 |  |  | Steel Structure | [11 empty] | 0 | 249.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
424 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR208 | 0GR208 | ONE-GIRDER-229-0GR208 | 1 | 177.4 | 177.4 |  |  | Steel Structure | [11 empty] | 0 | 177.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
425 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR209 | 0GR209 | ONE-GIRDER-229-0GR209 | 1 | 206.5 | 206.5 |  |  | Steel Structure | [11 empty] | 0 | 206.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
426 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR210 | 0GR210 | ONE-GIRDER-229-0GR210 | 1 | 220.5 | 220.5 |  |  | Steel Structure | [11 empty] | 0 | 220.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
427 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR211 | 0GR211 | ONE-GIRDER-229-0GR211 | 1 | 206.5 | 206.5 |  |  | Steel Structure | [11 empty] | 0 | 206.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
428 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR212 | 0GR212 | ONE-GIRDER-229-0GR212 | 1 | 218 | 218 |  |  | Steel Structure | [11 empty] | 0 | 218 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
429 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR213 | 0GR213 | ONE-GIRDER-229-0GR213 | 1 | 187.6 | 187.6 |  |  | Steel Structure | [11 empty] | 0 | 187.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
430 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR214 | 0GR214 | ONE-GIRDER-229-0GR214 | 1 | 188.1 | 188.1 |  |  | Steel Structure | [11 empty] | 0 | 188.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
431 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR215 | 0GR215 | ONE-GIRDER-229-0GR215 | 1 | 193.3 | 193.3 |  |  | Steel Structure | [11 empty] | 0 | 193.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
432 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR216 | 0GR216 | ONE-GIRDER-229-0GR216 | 1 | 238.8 | 238.8 |  |  | Steel Structure | [11 empty] | 0 | 238.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
433 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR217 | 0GR217 | ONE-GIRDER-229-0GR217 | 1 | 161.6 | 161.6 |  |  | Steel Structure | [11 empty] | 0 | 161.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
434 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR218 | 0GR218 | ONE-GIRDER-229-0GR218 | 1 | 168.3 | 168.3 |  |  | Steel Structure | [11 empty] | 0 | 168.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
435 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR219 | 0GR219 | ONE-GIRDER-229-0GR219 | 1 | 172.1 | 172.1 |  |  | Steel Structure | [11 empty] | 0 | 172.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
436 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR220 | 0GR220 | ONE-GIRDER-229-0GR220 | 1 | 140.8 | 140.8 |  |  | Steel Structure | [11 empty] | 0 | 140.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
437 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR221 | 0GR221 | ONE-GIRDER-229-0GR221 | 1 | 70.8 | 70.8 |  |  | Steel Structure | [11 empty] | 0 | 70.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
438 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR222 | 0GR222 | ONE-GIRDER-229-0GR222 | 1 | 70.8 | 70.8 |  |  | Steel Structure | [11 empty] | 0 | 70.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
439 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR223 | 0GR223 | ONE-GIRDER-229-0GR223 | 1 | 216.1 | 216.1 |  |  | Steel Structure | [11 empty] | 0 | 216.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
440 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR224 | 0GR224 | ONE-GIRDER-229-0GR224 | 1 | 205.5 | 205.5 |  |  | Steel Structure | [11 empty] | 0 | 205.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
441 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR225 | 0GR225 | ONE-GIRDER-229-0GR225 | 1 | 189.7 | 189.7 |  |  | Steel Structure | [11 empty] | 0 | 189.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
442 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR226 | 0GR226 | ONE-GIRDER-229-0GR226 | 1 | 202.4 | 202.4 |  |  | Steel Structure | [11 empty] | 0 | 202.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
443 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR227 | 0GR227(1/2) | 2-GIRDERS-229-0GR227 | 1 | 189.7 | 189.7 |  |  | Steel Structure | [11 empty] | 0 | 189.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
444 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR227 | 0GR227(2/2) | 2-GIRDERS-229-0GR227 | 1 | 189.7 | 189.7 |  |  | Steel Structure | [11 empty] | 0 | 189.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
445 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR228 | 0GR228 | ONE-GIRDER-229-0GR228 | 1 | 233 | 233 |  |  | Steel Structure | [11 empty] | 0 | 233 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
446 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR229 | 0GR229 | ONE-GIRDER-229-0GR229 | 1 | 224.4 | 224.4 |  |  | Steel Structure | [11 empty] | 0 | 224.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
447 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR230 | 0GR230 | ONE-GIRDER-229-0GR230 | 1 | 201.3 | 201.3 |  |  | Steel Structure | [11 empty] | 0 | 201.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
448 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR231 | 0GR231 | ONE-GIRDER-229-0GR231 | 1 | 192.1 | 192.1 |  |  | Steel Structure | [11 empty] | 0 | 192.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
449 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR232 | 0GR232 | ONE-GIRDER-229-0GR232 | 1 | 235.5 | 235.5 |  |  | Steel Structure | [11 empty] | 0 | 235.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
450 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR233 | 0GR233 | ONE-GIRDER-229-0GR233 | 1 | 226 | 226 |  |  | Steel Structure | [11 empty] | 0 | 226 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
451 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR234 | 0GR234 | ONE-GIRDER-229-0GR234 | 1 | 248.1 | 248.1 |  |  | Steel Structure | [11 empty] | 0 | 248.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
452 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR235 | 0GR235 | ONE-GIRDER-229-0GR235 | 1 | 234.1 | 234.1 |  |  | Steel Structure | [11 empty] | 0 | 234.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
453 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR236 | 0GR236 | ONE-GIRDER-229-0GR236 | 1 | 236.5 | 236.5 |  |  | Steel Structure | [11 empty] | 0 | 236.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
454 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR237 | 0GR237 | ONE-GIRDER-229-0GR237 | 1 | 229.6 | 229.6 |  |  | Steel Structure | [11 empty] | 0 | 229.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
455 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR238 | 0GR238 | ONE-GIRDER-229-0GR238 | 1 | 226.6 | 226.6 |  |  | Steel Structure | [11 empty] | 0 | 226.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
456 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR239 | 0GR239 | ONE-GIRDER-229-0GR239 | 1 | 154.8 | 154.8 |  |  | Steel Structure | [11 empty] | 0 | 154.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
457 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR240 | 0GR240 | ONE-GIRDER-229-0GR240 | 1 | 183.8 | 183.8 |  |  | Steel Structure | [11 empty] | 0 | 183.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
458 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR241 | 0GR241 | ONE-GIRDER-229-0GR241 | 1 | 152.8 | 152.8 |  |  | Steel Structure | [11 empty] | 0 | 152.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
459 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR242 | 0GR242 | ONE-GIRDER-229-0GR242 | 1 | 212.6 | 212.6 |  |  | Steel Structure | [11 empty] | 0 | 212.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
460 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0GR243 | 0GR243 | ONE-GIRDER-229-0GR243 | 1 | 212.6 | 212.6 |  |  | Steel Structure | [11 empty] | 0 | 212.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
461 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR244 | 0GR244 | ONE-GIRDER-418-0GR244 | 1 | 115.7 | 115.7 |  |  | Steel Structure | [11 empty] | 0 | 115.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
462 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR245 | 0GR245 | ONE-GIRDER-418-0GR245 | 1 | 204 | 204 |  |  | Steel Structure | [11 empty] | 0 | 204 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
463 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR246 | 0GR246 | ONE-GIRDER-418-0GR246 | 1 | 104.5 | 104.5 |  |  | Steel Structure | [11 empty] | 0 | 104.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
464 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR247 | 0GR247 | ONE-GIRDER-418-0GR247 | 1 | 118.9 | 118.9 |  |  | Steel Structure | [11 empty] | 0 | 118.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
465 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR248 | 0GR248 | ONE-GIRDER-418-0GR248 | 1 | 129 | 129 |  |  | Steel Structure | [11 empty] | 0 | 129 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
466 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR249 | 0GR249 | ONE-GIRDER-418-0GR249 | 1 | 148.6 | 148.6 |  |  | Steel Structure | [11 empty] | 0 | 148.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
467 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR250 | 0GR250 | ONE-GIRDER-418-0GR250 | 1 | 153.4 | 153.4 |  |  | Steel Structure | [11 empty] | 0 | 153.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
468 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR251 | 0GR251 | ONE-GIRDER-418-0GR251 | 1 | 173.1 | 173.1 |  |  | Steel Structure | [11 empty] | 0 | 173.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
469 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR252 | 0GR252 | ONE-GIRDER-418-0GR252 | 1 | 246.7 | 246.7 |  |  | Steel Structure | [11 empty] | 0 | 246.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
470 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR253 | 0GR253 | ONE-GIRDER-418-0GR253 | 1 | 262.1 | 262.1 |  |  | Steel Structure | [11 empty] | 0 | 262.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
471 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR254 | 0GR254 | ONE-GIRDER-418-0GR254 | 1 | 113.1 | 113.1 |  |  | Steel Structure | [11 empty] | 0 | 113.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
472 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR255 | 0GR255 | ONE-GIRDER-418-0GR255 | 1 | 118.3 | 118.3 |  |  | Steel Structure | [11 empty] | 0 | 118.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
473 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR256 | 0GR256 | ONE-GIRDER-418-0GR256 | 1 | 99.7 | 99.7 |  |  | Steel Structure | [11 empty] | 0 | 99.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
474 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR257 | 0GR257 | ONE-GIRDER-418-0GR257 | 1 | 121.5 | 121.5 |  |  | Steel Structure | [11 empty] | 0 | 121.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
475 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR258 | 0GR258 | ONE-GIRDER-418-0GR258 | 1 | 121.5 | 121.5 |  |  | Steel Structure | [11 empty] | 0 | 121.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
476 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR259 | 0GR259 | ONE-GIRDER-418-0GR259 | 1 | 115.7 | 115.7 |  |  | Steel Structure | [11 empty] | 0 | 115.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
477 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR260 | 0GR260 | ONE-GIRDER-418-0GR260 | 1 | 129.6 | 129.6 |  |  | Steel Structure | [11 empty] | 0 | 129.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
478 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR261 | 0GR261 | ONE-GIRDER-418-0GR261 | 1 | 197.9 | 197.9 |  |  | Steel Structure | [11 empty] | 0 | 197.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
479 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR262 | 0GR262 | ONE-GIRDER-418-0GR262 | 1 | 259 | 259 |  |  | Steel Structure | [11 empty] | 0 | 259 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
480 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR263 | 0GR263 | ONE-GIRDER-418-0GR263 | 1 | 290.8 | 290.8 |  |  | Steel Structure | [11 empty] | 0 | 290.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
481 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR264 | 0GR264 | ONE-GIRDER-418-0GR264 | 1 | 246.7 | 246.7 |  |  | Steel Structure | [11 empty] | 0 | 246.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
482 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR265 | 0GR265 | ONE-GIRDER-418-0GR265 | 1 | 200.5 | 200.5 |  |  | Steel Structure | [11 empty] | 0 | 200.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
483 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0GR266 | 0GR266 | ONE-GIRDER-418-0GR266 | 1 | 134.4 | 134.4 |  |  | Steel Structure | [11 empty] | 0 | 134.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
484 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB008 | 0HB008 | ONE-HBRACE-228-0HB008 | 1 | 21 | 21 |  |  | Steel Structure | [11 empty] | 0 | 21 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
485 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB009 | 0HB009 | ONE-HBRACE-228-0HB009 | 1 | 20.9 | 20.9 |  |  | Steel Structure | [11 empty] | 0 | 20.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
486 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB010 | 0HB010 | ONE-HBRACE-228-0HB010 | 1 | 21.7 | 21.7 |  |  | Steel Structure | [11 empty] | 0 | 21.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
487 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB011 | 0HB011 | ONE-HBRACE-228-0HB011 | 1 | 16.9 | 16.9 |  |  | Steel Structure | [11 empty] | 0 | 16.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
488 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB012 | 0HB012(1/6) | 6-HBRACES-228-0HB012 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
489 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB012 | 0HB012(2/6) | 6-HBRACES-228-0HB012 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
490 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB012 | 0HB012(3/6) | 6-HBRACES-228-0HB012 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
491 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB012 | 0HB012(4/6) | 6-HBRACES-228-0HB012 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
492 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB012 | 0HB012(5/6) | 6-HBRACES-228-0HB012 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
493 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB012 | 0HB012(6/6) | 6-HBRACES-228-0HB012 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
494 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB013 | 0HB013(1/2) | 2-HBRACES-228-0HB013 | 1 | 12.6 | 12.6 |  |  | Steel Structure | [11 empty] | 0 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
495 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB013 | 0HB013(2/2) | 2-HBRACES-228-0HB013 | 1 | 12.6 | 12.6 |  |  | Steel Structure | [11 empty] | 0 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
496 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB014 | 0HB014(1/2) | 2-HBRACES-228-0HB014 | 1 | 12.6 | 12.6 |  |  | Steel Structure | [11 empty] | 0 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
497 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB014 | 0HB014(2/2) | 2-HBRACES-228-0HB014 | 1 | 12.6 | 12.6 |  |  | Steel Structure | [11 empty] | 0 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
498 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB015 | 0HB015(1/2) | 2-HBRACES-228-0HB015 | 1 | 14.5 | 14.5 |  |  | Steel Structure | [11 empty] | 0 | 14.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
499 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB015 | 0HB015(2/2) | 2-HBRACES-228-0HB015 | 1 | 14.5 | 14.5 |  |  | Steel Structure | [11 empty] | 0 | 14.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
500 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB016 | 0HB016(1/4) | 4-HBRACES-228-0HB016 | 1 | 16.8 | 16.8 |  |  | Steel Structure | [11 empty] | 0 | 16.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
501 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB016 | 0HB016(2/4) | 4-HBRACES-228-0HB016 | 1 | 16.8 | 16.8 |  |  | Steel Structure | [11 empty] | 0 | 16.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
502 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB016 | 0HB016(3/4) | 4-HBRACES-228-0HB016 | 1 | 16.8 | 16.8 |  |  | Steel Structure | [11 empty] | 0 | 16.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
503 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB016 | 0HB016(4/4) | 4-HBRACES-228-0HB016 | 1 | 16.8 | 16.8 |  |  | Steel Structure | [11 empty] | 0 | 16.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
504 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB017 | 0HB017(1/2) | 2-HBRACES-228-0HB017 | 1 | 14.3 | 14.3 |  |  | Steel Structure | [11 empty] | 0 | 14.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
505 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB017 | 0HB017(2/2) | 2-HBRACES-228-0HB017 | 1 | 14.3 | 14.3 |  |  | Steel Structure | [11 empty] | 0 | 14.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
506 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB018 | 0HB018(1/2) | 2-HBRACES-228-0HB018 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
507 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB018 | 0HB018(2/2) | 2-HBRACES-228-0HB018 | 1 | 19.3 | 19.3 |  |  | Steel Structure | [11 empty] | 0 | 19.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
508 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB019 | 0HB019 | ONE-HBRACE-228-0HB019 | 1 | 17.7 | 17.7 |  |  | Steel Structure | [11 empty] | 0 | 17.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
509 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB020 | 0HB020 | ONE-HBRACE-228-0HB020 | 1 | 17.7 | 17.7 |  |  | Steel Structure | [11 empty] | 0 | 17.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
510 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB021 | 0HB021 | ONE-HBRACE-228-0HB021 | 1 | 20.6 | 20.6 |  |  | Steel Structure | [11 empty] | 0 | 20.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
511 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB022 | 0HB022 | ONE-HBRACE-228-0HB022 | 1 | 19.8 | 19.8 |  |  | Steel Structure | [11 empty] | 0 | 19.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
512 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB023 | 0HB023 | ONE-HBRACE-228-0HB023 | 1 | 30.7 | 30.7 |  |  | Steel Structure | [11 empty] | 0 | 30.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
513 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB024 | 0HB024 | ONE-HBRACE-228-0HB024 | 1 | 30.7 | 30.7 |  |  | Steel Structure | [11 empty] | 0 | 30.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
514 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB025 | 0HB025 | ONE-HBRACE-228-0HB025 | 1 | 25.5 | 25.5 |  |  | Steel Structure | [11 empty] | 0 | 25.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
515 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB026 | 0HB026 | ONE-HBRACE-228-0HB026 | 1 | 25.5 | 25.5 |  |  | Steel Structure | [11 empty] | 0 | 25.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
516 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB027 | 0HB027 | ONE-HBRACE-228-0HB027 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
517 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB028 | 0HB028(1/2) | 2-HBRACES-228-0HB028 | 1 | 18.8 | 18.8 |  |  | Steel Structure | [11 empty] | 0 | 18.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
518 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB028 | 0HB028(2/2) | 2-HBRACES-228-0HB028 | 1 | 18.8 | 18.8 |  |  | Steel Structure | [11 empty] | 0 | 18.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
519 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB029 | 0HB029(1/2) | 2-HBRACES-228-0HB029 | 1 | 20.9 | 20.9 |  |  | Steel Structure | [11 empty] | 0 | 20.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
520 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB029 | 0HB029(2/2) | 2-HBRACES-228-0HB029 | 1 | 20.9 | 20.9 |  |  | Steel Structure | [11 empty] | 0 | 20.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
521 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB030 | 0HB030(1/2) | 2-HBRACES-228-0HB030 | 1 | 28.2 | 28.2 |  |  | Steel Structure | [11 empty] | 0 | 28.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
522 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB030 | 0HB030(2/2) | 2-HBRACES-228-0HB030 | 1 | 28.2 | 28.2 |  |  | Steel Structure | [11 empty] | 0 | 28.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
523 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB031 | 0HB031(1/2) | 2-HBRACES-228-0HB031 | 1 | 28.8 | 28.8 |  |  | Steel Structure | [11 empty] | 0 | 28.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
524 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB031 | 0HB031(2/2) | 2-HBRACES-228-0HB031 | 1 | 28.8 | 28.8 |  |  | Steel Structure | [11 empty] | 0 | 28.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
525 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB032 | 0HB032(1/2) | 2-HBRACES-228-0HB032 | 1 | 29.1 | 29.1 |  |  | Steel Structure | [11 empty] | 0 | 29.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
526 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB032 | 0HB032(2/2) | 2-HBRACES-228-0HB032 | 1 | 29.1 | 29.1 |  |  | Steel Structure | [11 empty] | 0 | 29.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
527 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB033 | 0HB033(1/2) | 2-HBRACES-228-0HB033 | 1 | 28.2 | 28.2 |  |  | Steel Structure | [11 empty] | 0 | 28.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
528 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB033 | 0HB033(2/2) | 2-HBRACES-228-0HB033 | 1 | 28.2 | 28.2 |  |  | Steel Structure | [11 empty] | 0 | 28.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
529 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB034 | 0HB034 | ONE-HBRACE-228-0HB034 | 1 | 26.1 | 26.1 |  |  | Steel Structure | [11 empty] | 0 | 26.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
530 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB035 | 0HB035 | ONE-HBRACE-228-0HB035 | 1 | 21.7 | 21.7 |  |  | Steel Structure | [11 empty] | 0 | 21.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
531 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB036 | 0HB036 | ONE-HBRACE-228-0HB036 | 1 | 76.6 | 76.6 |  |  | Steel Structure | [11 empty] | 0 | 76.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
532 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB037 | 0HB037 | ONE-HBRACE-228-0HB037 | 1 | 23.6 | 23.6 |  |  | Steel Structure | [11 empty] | 0 | 23.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
533 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB038 | 0HB038 | ONE-HBRACE-228-0HB038 | 1 | 31 | 31 |  |  | Steel Structure | [11 empty] | 0 | 31 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
534 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB039 | 0HB039 | ONE-HBRACE-228-0HB039 | 1 | 31.6 | 31.6 |  |  | Steel Structure | [11 empty] | 0 | 31.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
535 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB040 | 0HB040 | ONE-HBRACE-228-0HB040 | 1 | 24 | 24 |  |  | Steel Structure | [11 empty] | 0 | 24 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
536 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB041 | 0HB041 | ONE-HBRACE-228-0HB041 | 1 | 21.7 | 21.7 |  |  | Steel Structure | [11 empty] | 0 | 21.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
537 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB042 | 0HB042 | ONE-HBRACE-228-0HB042 | 1 | 26.2 | 26.2 |  |  | Steel Structure | [11 empty] | 0 | 26.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
538 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB043 | 0HB043 | ONE-HBRACE-228-0HB043 | 1 | 25 | 25 |  |  | Steel Structure | [11 empty] | 0 | 25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
539 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB044 | 0HB044 | ONE-HBRACE-228-0HB044 | 1 | 10.8 | 10.8 |  |  | Steel Structure | [11 empty] | 0 | 10.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
540 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB045 | 0HB045 | ONE-HBRACE-228-0HB045 | 1 | 19.9 | 19.9 |  |  | Steel Structure | [11 empty] | 0 | 19.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
541 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB046 | 0HB046 | ONE-HBRACE-228-0HB046 | 1 | 22.5 | 22.5 |  |  | Steel Structure | [11 empty] | 0 | 22.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
542 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB047 | 0HB047 | ONE-HBRACE-228-0HB047 | 1 | 22.4 | 22.4 |  |  | Steel Structure | [11 empty] | 0 | 22.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
543 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB048 | 0HB048 | ONE-HBRACE-228-0HB048 | 1 | 29.5 | 29.5 |  |  | Steel Structure | [11 empty] | 0 | 29.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
544 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB049 | 0HB049 | ONE-HBRACE-228-0HB049 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
545 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB050 | 0HB050 | ONE-HBRACE-228-0HB050 | 1 | 22.3 | 22.3 |  |  | Steel Structure | [11 empty] | 0 | 22.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
546 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB051 | 0HB051(1/2) | 2-HBRACES-228-0HB051 | 1 | 18 | 18 |  |  | Steel Structure | [11 empty] | 0 | 18 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
547 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB051 | 0HB051(2/2) | 2-HBRACES-228-0HB051 | 1 | 18 | 18 |  |  | Steel Structure | [11 empty] | 0 | 18 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
548 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB052 | 0HB052 | ONE-HBRACE-228-0HB052 | 1 | 17 | 17 |  |  | Steel Structure | [11 empty] | 0 | 17 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
549 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB053 | 0HB053 | ONE-HBRACE-228-0HB053 | 1 | 16.9 | 16.9 |  |  | Steel Structure | [11 empty] | 0 | 16.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
550 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB054 | 0HB054 | ONE-HBRACE-228-0HB054 | 1 | 16.2 | 16.2 |  |  | Steel Structure | [11 empty] | 0 | 16.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
551 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB055 | 0HB055 | ONE-HBRACE-228-0HB055 | 1 | 14.3 | 14.3 |  |  | Steel Structure | [11 empty] | 0 | 14.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
552 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB056 | 0HB056 | ONE-HBRACE-228-0HB056 | 1 | 15.8 | 15.8 |  |  | Steel Structure | [11 empty] | 0 | 15.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
553 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB057 | 0HB057 | ONE-HBRACE-228-0HB057 | 1 | 17.8 | 17.8 |  |  | Steel Structure | [11 empty] | 0 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
554 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB058 | 0HB058 | ONE-HBRACE-228-0HB058 | 1 | 10.8 | 10.8 |  |  | Steel Structure | [11 empty] | 0 | 10.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
555 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB059 | 0HB059(1/2) | 2-HBRACES-228-0HB059 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
556 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB059 | 0HB059(2/2) | 2-HBRACES-228-0HB059 | 1 | 17.9 | 17.9 |  |  | Steel Structure | [11 empty] | 0 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
557 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB060 | 0HB060 | ONE-HBRACE-228-0HB060 | 1 | 23.3 | 23.3 |  |  | Steel Structure | [11 empty] | 0 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
558 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB061 | 0HB061 | ONE-HBRACE-228-0HB061 | 1 | 12.3 | 12.3 |  |  | Steel Structure | [11 empty] | 0 | 12.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
559 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB062 | 0HB062 | ONE-HBRACE-228-0HB062 | 1 | 16.6 | 16.6 |  |  | Steel Structure | [11 empty] | 0 | 16.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
560 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB063 | 0HB063 | ONE-HBRACE-228-0HB063 | 1 | 13.1 | 13.1 |  |  | Steel Structure | [11 empty] | 0 | 13.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
561 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB064 | 0HB064 | ONE-HBRACE-228-0HB064 | 1 | 23.1 | 23.1 |  |  | Steel Structure | [11 empty] | 0 | 23.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
562 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB065 | 0HB065(1/2) | 2-HBRACES-228-0HB065 | 1 | 13.2 | 13.2 |  |  | Steel Structure | [11 empty] | 0 | 13.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
563 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB065 | 0HB065(2/2) | 2-HBRACES-228-0HB065 | 1 | 13.2 | 13.2 |  |  | Steel Structure | [11 empty] | 0 | 13.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
564 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB066 | 0HB066 | ONE-HBRACE-228-0HB066 | 1 | 23 | 23 |  |  | Steel Structure | [11 empty] | 0 | 23 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
565 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB067 | 0HB067 | ONE-HBRACE-228-0HB067 | 1 | 23.1 | 23.1 |  |  | Steel Structure | [11 empty] | 0 | 23.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
566 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB068 | 0HB068 | ONE-HBRACE-228-0HB068 | 1 | 12.8 | 12.8 |  |  | Steel Structure | [11 empty] | 0 | 12.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
567 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB069 | 0HB069 | ONE-HBRACE-228-0HB069 | 1 | 19 | 19 |  |  | Steel Structure | [11 empty] | 0 | 19 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
568 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB070 | 0HB070 | ONE-HBRACE-228-0HB070 | 1 | 16.6 | 16.6 |  |  | Steel Structure | [11 empty] | 0 | 16.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
569 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB071 | 0HB071 | ONE-HBRACE-228-0HB071 | 1 | 13.6 | 13.6 |  |  | Steel Structure | [11 empty] | 0 | 13.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
570 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB072 | 0HB072 | ONE-HBRACE-228-0HB072 | 1 | 15.5 | 15.5 |  |  | Steel Structure | [11 empty] | 0 | 15.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
571 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB073 | 0HB073 | ONE-HBRACE-228-0HB073 | 1 | 13.4 | 13.4 |  |  | Steel Structure | [11 empty] | 0 | 13.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
572 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB074 | 0HB074 | ONE-HBRACE-228-0HB074 | 1 | 23.6 | 23.6 |  |  | Steel Structure | [11 empty] | 0 | 23.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
573 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB075 | 0HB075 | ONE-HBRACE-228-0HB075 | 1 | 11.1 | 11.1 |  |  | Steel Structure | [11 empty] | 0 | 11.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
574 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB076 | 0HB076 | ONE-HBRACE-228-0HB076 | 1 | 19.2 | 19.2 |  |  | Steel Structure | [11 empty] | 0 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
575 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB077 | 0HB077 | ONE-HBRACE-228-0HB077 | 1 | 29.6 | 29.6 |  |  | Steel Structure | [11 empty] | 0 | 29.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
576 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB078 | 0HB078 | ONE-HBRACE-228-0HB078 | 1 | 21.7 | 21.7 |  |  | Steel Structure | [11 empty] | 0 | 21.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
577 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB079 | 0HB079 | ONE-HBRACE-228-0HB079 | 1 | 20.7 | 20.7 |  |  | Steel Structure | [11 empty] | 0 | 20.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
578 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB080 | 0HB080 | ONE-HBRACE-228-0HB080 | 1 | 21.3 | 21.3 |  |  | Steel Structure | [11 empty] | 0 | 21.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
579 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB081 | 0HB081 | ONE-HBRACE-228-0HB081 | 1 | 19.8 | 19.8 |  |  | Steel Structure | [11 empty] | 0 | 19.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
580 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB082 | 0HB082(1/2) | 2-HBRACES-228-0HB082 | 1 | 22.4 | 22.4 |  |  | Steel Structure | [11 empty] | 0 | 22.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
581 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB082 | 0HB082(2/2) | 2-HBRACES-228-0HB082 | 1 | 22.4 | 22.4 |  |  | Steel Structure | [11 empty] | 0 | 22.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
582 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB083 | 0HB083 | ONE-HBRACE-228-0HB083 | 1 | 19.5 | 19.5 |  |  | Steel Structure | [11 empty] | 0 | 19.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
583 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB084 | 0HB084 | ONE-HBRACE-228-0HB084 | 1 | 19.9 | 19.9 |  |  | Steel Structure | [11 empty] | 0 | 19.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
584 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB085 | 0HB085 | ONE-HBRACE-228-0HB085 | 1 | 21.7 | 21.7 |  |  | Steel Structure | [11 empty] | 0 | 21.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
585 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB086 | 0HB086 | ONE-HBRACE-228-0HB086 | 1 | 19.8 | 19.8 |  |  | Steel Structure | [11 empty] | 0 | 19.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
586 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB087 | 0HB087 | ONE-HBRACE-228-0HB087 | 1 | 10.5 | 10.5 |  |  | Steel Structure | [11 empty] | 0 | 10.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
587 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB088 | 0HB088 | ONE-HBRACE-228-0HB088 | 1 | 23.7 | 23.7 |  |  | Steel Structure | [11 empty] | 0 | 23.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
588 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB089 | 0HB089 | ONE-HBRACE-228-0HB089 | 1 | 22 | 22 |  |  | Steel Structure | [11 empty] | 0 | 22 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
589 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB090 | 0HB090 | ONE-HBRACE-228-0HB090 | 1 | 78.5 | 78.5 |  |  | Steel Structure | [11 empty] | 0 | 78.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
590 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB091 | 0HB091 | ONE-HBRACE-228-0HB091 | 1 | 86.5 | 86.5 |  |  | Steel Structure | [11 empty] | 0 | 86.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
591 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB092 | 0HB092 | ONE-HBRACE-228-0HB092 | 1 | 74.9 | 74.9 |  |  | Steel Structure | [11 empty] | 0 | 74.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
592 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB093 | 0HB093 | ONE-HBRACE-228-0HB093 | 1 | 86.3 | 86.3 |  |  | Steel Structure | [11 empty] | 0 | 86.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
593 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB094 | 0HB094 | ONE-HBRACE-228-0HB094 | 1 | 81.3 | 81.3 |  |  | Steel Structure | [11 empty] | 0 | 81.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
594 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB095 | 0HB095 | ONE-HBRACE-228-0HB095 | 1 | 90.7 | 90.7 |  |  | Steel Structure | [11 empty] | 0 | 90.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
595 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB096 | 0HB096 | ONE-HBRACE-228-0HB096 | 1 | 81.9 | 81.9 |  |  | Steel Structure | [11 empty] | 0 | 81.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
596 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB097 | 0HB097 | ONE-HBRACE-228-0HB097 | 1 | 73.9 | 73.9 |  |  | Steel Structure | [11 empty] | 0 | 73.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
597 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB098 | 0HB098(1/2) | 2-HBRACES-228-0HB098 | 1 | 73.7 | 73.7 |  |  | Steel Structure | [11 empty] | 0 | 73.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
598 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB098 | 0HB098(2/2) | 2-HBRACES-228-0HB098 | 1 | 73.7 | 73.7 |  |  | Steel Structure | [11 empty] | 0 | 73.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
599 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB099 | 0HB099(1/2) | 2-HBRACES-228-0HB099 | 1 | 59.1 | 59.1 |  |  | Steel Structure | [11 empty] | 0 | 59.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
600 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB099 | 0HB099(2/2) | 2-HBRACES-228-0HB099 | 1 | 59.1 | 59.1 |  |  | Steel Structure | [11 empty] | 0 | 59.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
601 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB100 | 0HB100 | ONE-HBRACE-228-0HB100 | 1 | 59.3 | 59.3 |  |  | Steel Structure | [11 empty] | 0 | 59.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
602 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB101 | 0HB101 | ONE-HBRACE-228-0HB101 | 1 | 60.1 | 60.1 |  |  | Steel Structure | [11 empty] | 0 | 60.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
603 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB102 | 0HB102 | ONE-HBRACE-228-0HB102 | 1 | 80.9 | 80.9 |  |  | Steel Structure | [11 empty] | 0 | 80.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
604 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB103 | 0HB103(1/2) | 2-HBRACES-228-0HB103 | 1 | 74.1 | 74.1 |  |  | Steel Structure | [11 empty] | 0 | 74.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
605 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB103 | 0HB103(2/2) | 2-HBRACES-228-0HB103 | 1 | 74.1 | 74.1 |  |  | Steel Structure | [11 empty] | 0 | 74.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
606 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB104 | 0HB104 | ONE-HBRACE-228-0HB104 | 1 | 76.9 | 76.9 |  |  | Steel Structure | [11 empty] | 0 | 76.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
607 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB105 | 0HB105 | ONE-HBRACE-228-0HB105 | 1 | 73.7 | 73.7 |  |  | Steel Structure | [11 empty] | 0 | 73.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
608 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB106 | 0HB106 | ONE-HBRACE-228-0HB106 | 1 | 78.5 | 78.5 |  |  | Steel Structure | [11 empty] | 0 | 78.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
609 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB107 | 0HB107 | ONE-HBRACE-228-0HB107 | 1 | 82.1 | 82.1 |  |  | Steel Structure | [11 empty] | 0 | 82.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
610 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB108 | 0HB108 | ONE-HBRACE-228-0HB108 | 1 | 86.5 | 86.5 |  |  | Steel Structure | [11 empty] | 0 | 86.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
611 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB109 | 0HB109 | ONE-HBRACE-228-0HB109 | 1 | 91.5 | 91.5 |  |  | Steel Structure | [11 empty] | 0 | 91.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
612 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB110 | 0HB110 | ONE-HBRACE-228-0HB110 | 1 | 87.1 | 87.1 |  |  | Steel Structure | [11 empty] | 0 | 87.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
613 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-228-0HB111 | 0HB111 | ONE-HBRACE-228-0HB111 | 1 | 67.2 | 67.2 |  |  | Steel Structure | [11 empty] | 0 | 67.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
614 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT040 | 0PT040 | ONE-POST-229-0PT040 | 1 | 44.8 | 44.8 |  |  | Steel Structure | [11 empty] | 0 | 44.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
615 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT041 | 0PT041 | ONE-POST-229-0PT041 | 1 | 50.1 | 50.1 |  |  | Steel Structure | [11 empty] | 0 | 50.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
616 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT042 | 0PT042 | ONE-POST-229-0PT042 | 1 | 50.1 | 50.1 |  |  | Steel Structure | [11 empty] | 0 | 50.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
617 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT043 | 0PT043 | ONE-POST-229-0PT043 | 1 | 41.4 | 41.4 |  |  | Steel Structure | [11 empty] | 0 | 41.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
618 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT044 | 0PT044 | ONE-POST-229-0PT044 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
619 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT045 | 0PT045 | ONE-POST-229-0PT045 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
620 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT046 | 0PT046 | ONE-POST-229-0PT046 | 1 | 37.9 | 37.9 |  |  | Steel Structure | [11 empty] | 0 | 37.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
621 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT047 | 0PT047 | ONE-POST-229-0PT047 | 1 | 43.2 | 43.2 |  |  | Steel Structure | [11 empty] | 0 | 43.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
622 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT048 | 0PT048 | ONE-POST-229-0PT048 | 1 | 43.2 | 43.2 |  |  | Steel Structure | [11 empty] | 0 | 43.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
623 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT049 | 0PT049 | ONE-POST-229-0PT049 | 1 | 34.7 | 34.7 |  |  | Steel Structure | [11 empty] | 0 | 34.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
624 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT050 | 0PT050 | ONE-POST-229-0PT050 | 1 | 40 | 40 |  |  | Steel Structure | [11 empty] | 0 | 40 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
625 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT051 | 0PT051 | ONE-POST-229-0PT051 | 1 | 40 | 40 |  |  | Steel Structure | [11 empty] | 0 | 40 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
626 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT052 | 0PT052(1/2) | 2-POSTS-229-0PT052 | 1 | 45 | 45 |  |  | Steel Structure | [11 empty] | 0 | 45 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
627 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT052 | 0PT052(2/2) | 2-POSTS-229-0PT052 | 1 | 45 | 45 |  |  | Steel Structure | [11 empty] | 0 | 45 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
628 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT053 | 0PT053(1/2) | 2-POSTS-229-0PT053 | 1 | 41.6 | 41.6 |  |  | Steel Structure | [11 empty] | 0 | 41.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
629 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT053 | 0PT053(2/2) | 2-POSTS-229-0PT053 | 1 | 41.6 | 41.6 |  |  | Steel Structure | [11 empty] | 0 | 41.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
630 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT054 | 0PT054(1/2) | 2-POSTS-229-0PT054 | 1 | 38.1 | 38.1 |  |  | Steel Structure | [11 empty] | 0 | 38.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
631 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT054 | 0PT054(2/2) | 2-POSTS-229-0PT054 | 1 | 38.1 | 38.1 |  |  | Steel Structure | [11 empty] | 0 | 38.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
632 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT055 | 0PT055(1/2) | 2-POSTS-229-0PT055 | 1 | 34.8 | 34.8 |  |  | Steel Structure | [11 empty] | 0 | 34.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0PT055 | 0PT055(2/2) | 2-POSTS-229-0PT055 | 1 | 34.8 | 34.8 |  |  | Steel Structure | [11 empty] | 0 | 34.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL001 | 0CL001 | ONE-COLUMN-231-0CL001 | 1 | 1212.2 | 1212.2 |  |  | Steel Structure | [11 empty] | 0 | 1212.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL002 | 0CL002 | ONE-COLUMN-231-0CL002 | 1 | 1201.3 | 1201.3 |  |  | Steel Structure | [11 empty] | 0 | 1201.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL003 | 0CL003 | ONE-COLUMN-231-0CL003 | 1 | 1178.6 | 1178.6 |  |  | Steel Structure | [11 empty] | 0 | 1178.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL004 | 0CL004 | ONE-COLUMN-231-0CL004 | 1 | 1176.2 | 1176.2 |  |  | Steel Structure | [11 empty] | 0 | 1176.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL005 | 0CL005 | ONE-COLUMN-231-0CL005 | 1 | 1231.4 | 1231.4 |  |  | Steel Structure | [11 empty] | 0 | 1231.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL006 | 0CL006 | ONE-COLUMN-231-0CL006 | 1 | 1204.6 | 1204.6 |  |  | Steel Structure | [11 empty] | 0 | 1204.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL007 | 0CL007 | ONE-COLUMN-231-0CL007 | 1 | 267.7 | 267.7 |  |  | Steel Structure | [11 empty] | 0 | 267.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL008 | 0CL008 | ONE-COLUMN-231-0CL008 | 1 | 1309.7 | 1309.7 |  |  | Steel Structure | [11 empty] | 0 | 1309.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL009 | 0CL009 | ONE-COLUMN-231-0CL009 | 1 | 1114.4 | 1114.4 |  |  | Steel Structure | [11 empty] | 0 | 1114.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL010 | 0CL010 | ONE-COLUMN-231-0CL010 | 1 | 287 | 287 |  |  | Steel Structure | [11 empty] | 0 | 287 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL011 | 0CL011 | ONE-COLUMN-231-0CL011 | 1 | 266.7 | 266.7 |  |  | Steel Structure | [11 empty] | 0 | 266.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL012 | 0CL012 | ONE-COLUMN-231-0CL012 | 1 | 271.3 | 271.3 |  |  | Steel Structure | [11 empty] | 0 | 271.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL013 | 0CL013 | ONE-COLUMN-231-0CL013 | 1 | 454.2 | 454.2 |  |  | Steel Structure | [11 empty] | 0 | 454.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL014 | 0CL014 | ONE-COLUMN-231-0CL014 | 1 | 1200 | 1200 |  |  | Steel Structure | [11 empty] | 0 | 1200 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL015 | 0CL015 | ONE-COLUMN-231-0CL015 | 1 | 252.3 | 252.3 |  |  | Steel Structure | [11 empty] | 0 | 252.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL016 | 0CL016 | ONE-COLUMN-231-0CL016 | 1 | 271.1 | 271.1 |  |  | Steel Structure | [11 empty] | 0 | 271.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL017 | 0CL017 | ONE-COLUMN-231-0CL017 | 1 | 379.6 | 379.6 |  |  | Steel Structure | [11 empty] | 0 | 379.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL018 | 0CL018 | ONE-COLUMN-231-0CL018 | 1 | 355.5 | 355.5 |  |  | Steel Structure | [11 empty] | 0 | 355.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL019 | 0CL019 | ONE-COLUMN-231-0CL019 | 1 | 400.8 | 400.8 |  |  | Steel Structure | [11 empty] | 0 | 400.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL020 | 0CL020 | ONE-COLUMN-231-0CL020 | 1 | 371.8 | 371.8 |  |  | Steel Structure | [11 empty] | 0 | 371.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL021 | 0CL021 | ONE-COLUMN-231-0CL021 | 1 | 336.9 | 336.9 |  |  | Steel Structure | [11 empty] | 0 | 336.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL022 | 0CL022 | ONE-COLUMN-231-0CL022 | 1 | 278.1 | 278.1 |  |  | Steel Structure | [11 empty] | 0 | 278.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL023 | 0CL023 | ONE-COLUMN-231-0CL023 | 1 | 273.1 | 273.1 |  |  | Steel Structure | [11 empty] | 0 | 273.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL024 | 0CL024 | ONE-COLUMN-231-0CL024 | 1 | 273.1 | 273.1 |  |  | Steel Structure | [11 empty] | 0 | 273.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL025 | 0CL025 | ONE-COLUMN-231-0CL025 | 1 | 315.8 | 315.8 |  |  | Steel Structure | [11 empty] | 0 | 315.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL026 | 0CL026 | ONE-COLUMN-231-0CL026 | 1 | 431.3 | 431.3 |  |  | Steel Structure | [11 empty] | 0 | 431.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL027 | 0CL027 | ONE-COLUMN-231-0CL027 | 1 | 1134.2 | 1134.2 |  |  | Steel Structure | [11 empty] | 0 | 1134.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL028 | 0CL028 | ONE-COLUMN-231-0CL028 | 1 | 1162.3 | 1162.3 |  |  | Steel Structure | [11 empty] | 0 | 1162.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL029 | 0CL029 | ONE-COLUMN-231-0CL029 | 1 | 1262.6 | 1262.6 |  |  | Steel Structure | [11 empty] | 0 | 1262.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL030 | 0CL030 | ONE-COLUMN-231-0CL030 | 1 | 1227.8 | 1227.8 |  |  | Steel Structure | [11 empty] | 0 | 1227.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL031 | 0CL031 | ONE-COLUMN-231-0CL031 | 1 | 1173 | 1173 |  |  | Steel Structure | [11 empty] | 0 | 1173 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL032 | 0CL032 | ONE-COLUMN-231-0CL032 | 1 | 1131.9 | 1131.9 |  |  | Steel Structure | [11 empty] | 0 | 1131.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
633 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG15 | S3 | 25HG001-351-DD0-231-0CL033 | 0CL033 | ONE-COLUMN-231-0CL033 | 1 | 166.7 | 166.7 |  |  | Steel Structure | [11 empty] | 0 | 166.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
634 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT019 | 0PT019 | ONE-POST-231-0PT019 | 1 | 126 | 126 |  |  | Steel Structure | [11 empty] | 0 | 126 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
635 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT020 | 0PT020 | ONE-POST-231-0PT020 | 1 | 143.7 | 143.7 |  |  | Steel Structure | [11 empty] | 0 | 143.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
636 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT021 | 0PT021(1/2) | 2-POSTS-231-0PT021 | 1 | 131.5 | 131.5 |  |  | Steel Structure | [11 empty] | 0 | 131.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
637 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT021 | 0PT021(2/2) | 2-POSTS-231-0PT021 | 1 | 131.5 | 131.5 |  |  | Steel Structure | [11 empty] | 0 | 131.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
638 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT022 | 0PT022 | ONE-POST-231-0PT022 | 1 | 194.7 | 194.7 |  |  | Steel Structure | [11 empty] | 0 | 194.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
639 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT023 | 0PT023 | ONE-POST-231-0PT023 | 1 | 169.5 | 169.5 |  |  | Steel Structure | [11 empty] | 0 | 169.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
640 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT024 | 0PT024 | ONE-POST-231-0PT024 | 1 | 108.5 | 108.5 |  |  | Steel Structure | [11 empty] | 0 | 108.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
641 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT025 | 0PT025 | ONE-POST-231-0PT025 | 1 | 269.6 | 269.6 |  |  | Steel Structure | [11 empty] | 0 | 269.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
642 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT026 | 0PT026 | ONE-POST-231-0PT026 | 1 | 266.9 | 266.9 |  |  | Steel Structure | [11 empty] | 0 | 266.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
643 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT027 | 0PT027 | ONE-POST-231-0PT027 | 1 | 65.4 | 65.4 |  |  | Steel Structure | [11 empty] | 0 | 65.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
644 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT028 | 0PT028 | ONE-POST-231-0PT028 | 1 | 27.6 | 27.6 |  |  | Steel Structure | [11 empty] | 0 | 27.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
645 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT029 | 0PT029 | ONE-POST-231-0PT029 | 1 | 124.6 | 124.6 |  |  | Steel Structure | [11 empty] | 0 | 124.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
646 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT030 | 0PT030 | ONE-POST-231-0PT030 | 1 | 127.6 | 127.6 |  |  | Steel Structure | [11 empty] | 0 | 127.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
647 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT031 | 0PT031 | ONE-POST-231-0PT031 | 1 | 27.6 | 27.6 |  |  | Steel Structure | [11 empty] | 0 | 27.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
648 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT032 | 0PT032(1/3) | 3-POSTS-231-0PT032 | 1 | 36.2 | 36.2 |  |  | Steel Structure | [11 empty] | 0 | 36.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
649 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT032 | 0PT032(2/3) | 3-POSTS-231-0PT032 | 1 | 36.2 | 36.2 |  |  | Steel Structure | [11 empty] | 0 | 36.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
650 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT032 | 0PT032(3/3) | 3-POSTS-231-0PT032 | 1 | 36.2 | 36.2 |  |  | Steel Structure | [11 empty] | 0 | 36.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
651 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT033 | 0PT033 | ONE-POST-231-0PT033 | 1 | 162.8 | 162.8 |  |  | Steel Structure | [11 empty] | 0 | 162.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
652 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT034 | 0PT034 | ONE-POST-231-0PT034 | 1 | 124.5 | 124.5 |  |  | Steel Structure | [11 empty] | 0 | 124.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
653 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT035 | 0PT035(1/2) | 2-POSTS-231-0PT035 | 1 | 36.8 | 36.8 |  |  | Steel Structure | [11 empty] | 0 | 36.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
654 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT035 | 0PT035(2/2) | 2-POSTS-231-0PT035 | 1 | 36.8 | 36.8 |  |  | Steel Structure | [11 empty] | 0 | 36.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
655 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT036 | 0PT036(1/2) | 2-POSTS-231-0PT036 | 1 | 39.4 | 39.4 |  |  | Steel Structure | [11 empty] | 0 | 39.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
656 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT036 | 0PT036(2/2) | 2-POSTS-231-0PT036 | 1 | 39.4 | 39.4 |  |  | Steel Structure | [11 empty] | 0 | 39.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
657 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT037 | 0PT037(1/2) | 2-POSTS-231-0PT037 | 1 | 43.3 | 43.3 |  |  | Steel Structure | [11 empty] | 0 | 43.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
658 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT037 | 0PT037(2/2) | 2-POSTS-231-0PT037 | 1 | 43.3 | 43.3 |  |  | Steel Structure | [11 empty] | 0 | 43.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
659 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT038 | 0PT038 | ONE-POST-231-0PT038 | 1 | 50 | 50 |  |  | Steel Structure | [11 empty] | 0 | 50 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
660 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT039 | 0PT039 | ONE-POST-231-0PT039 | 1 | 50 | 50 |  |  | Steel Structure | [11 empty] | 0 | 50 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
661 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT056 | 0PT056 | ONE-POST-231-0PT056 | 1 | 19.4 | 19.4 |  |  | Steel Structure | [11 empty] | 0 | 19.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
662 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT057 | 0PT057 | ONE-POST-231-0PT057 | 1 | 85.3 | 85.3 |  |  | Steel Structure | [11 empty] | 0 | 85.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
663 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT058 | 0PT058 | ONE-POST-231-0PT058 | 1 | 84.8 | 84.8 |  |  | Steel Structure | [11 empty] | 0 | 84.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
664 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT059 | 0PT059 | ONE-POST-231-0PT059 | 1 | 97.9 | 97.9 |  |  | Steel Structure | [11 empty] | 0 | 97.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
665 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT060 | 0PT060 | ONE-POST-231-0PT060 | 1 | 97.9 | 97.9 |  |  | Steel Structure | [11 empty] | 0 | 97.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
666 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0PT062 | 0PT062 | ONE-POST-231-0PT062 | 1 | 105.3 | 105.3 |  |  | Steel Structure | [11 empty] | 0 | 105.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
667 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB001 | 0VB001(1/2) | 2-VBRACES-231-0VB001 | 1 | 118.5 | 118.5 |  |  | Steel Structure | [11 empty] | 0 | 118.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
668 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB001 | 0VB001(2/2) | 2-VBRACES-231-0VB001 | 1 | 118.5 | 118.5 |  |  | Steel Structure | [11 empty] | 0 | 118.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
669 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB002 | 0VB002(1/5) | 5-VBRACES-231-0VB002 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
670 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB002 | 0VB002(2/5) | 5-VBRACES-231-0VB002 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
671 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB002 | 0VB002(3/5) | 5-VBRACES-231-0VB002 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
672 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB002 | 0VB002(4/5) | 5-VBRACES-231-0VB002 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
673 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB002 | 0VB002(5/5) | 5-VBRACES-231-0VB002 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
674 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB003 | 0VB003(1/4) | 4-VBRACES-231-0VB003 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
675 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB003 | 0VB003(2/4) | 4-VBRACES-231-0VB003 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
676 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB003 | 0VB003(3/4) | 4-VBRACES-231-0VB003 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
677 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB003 | 0VB003(4/4) | 4-VBRACES-231-0VB003 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
678 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB004 | 0VB004 | ONE-VBRACE-231-0VB004 | 1 | 110.9 | 110.9 |  |  | Steel Structure | [11 empty] | 0 | 110.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
679 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB005 | 0VB005 | ONE-BEAM-231-0VB005 | 1 | 110.9 | 110.9 |  |  | Steel Structure | [11 empty] | 0 | 110.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
680 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB006 | 0VB006 | ONE-VBRACE-231-0VB006 | 1 | 110.9 | 110.9 |  |  | Steel Structure | [11 empty] | 0 | 110.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
681 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB007 | 0VB007 | ONE-VBRACE-231-0VB007 | 1 | 89.2 | 89.2 |  |  | Steel Structure | [11 empty] | 0 | 89.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
682 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB008 | 0VB008 | ONE-VBRACE-231-0VB008 | 1 | 115.8 | 115.8 |  |  | Steel Structure | [11 empty] | 0 | 115.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
683 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB009 | 0VB009 | ONE-VBRACE-231-0VB009 | 1 | 115.8 | 115.8 |  |  | Steel Structure | [11 empty] | 0 | 115.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
684 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB010 | 0VB010 | ONE-VBRACE-231-0VB010 | 1 | 76.3 | 76.3 |  |  | Steel Structure | [11 empty] | 0 | 76.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
685 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB011 | 0VB011 | ONE-BEAM-231-0VB011 | 1 | 117.4 | 117.4 |  |  | Steel Structure | [11 empty] | 0 | 117.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
686 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB012 | 0VB012 | ONE-VBRACE-231-0VB012 | 1 | 154.2 | 154.2 |  |  | Steel Structure | [11 empty] | 0 | 154.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
687 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB013 | 0VB013 | ONE-VBRACE-231-0VB013 | 1 | 154.2 | 154.2 |  |  | Steel Structure | [11 empty] | 0 | 154.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
688 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB014 | 0VB014 | ONE-VBRACE-231-0VB014 | 1 | 152 | 152 |  |  | Steel Structure | [11 empty] | 0 | 152 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
689 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB015 | 0VB015(1/2) | 2-VBRACES-231-0VB015 | 1 | 97.9 | 97.9 |  |  | Steel Structure | [11 empty] | 0 | 97.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
690 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB015 | 0VB015(2/2) | 2-VBRACES-231-0VB015 | 1 | 97.9 | 97.9 |  |  | Steel Structure | [11 empty] | 0 | 97.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
691 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB016 | 0VB016 | ONE-VBRACE-231-0VB016 | 1 | 79.2 | 79.2 |  |  | Steel Structure | [11 empty] | 0 | 79.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
692 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB017 | 0VB017 | ONE-VBRACE-231-0VB017 | 1 | 109.4 | 109.4 |  |  | Steel Structure | [11 empty] | 0 | 109.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
693 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB018 | 0VB018 | ONE-VBRACE-231-0VB018 | 1 | 69.9 | 69.9 |  |  | Steel Structure | [11 empty] | 0 | 69.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
694 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB019 | 0VB019(1/4) | 4-VBRACES-231-0VB019 | 1 | 119.6 | 119.6 |  |  | Steel Structure | [11 empty] | 0 | 119.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
695 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB019 | 0VB019(2/4) | 4-VBRACES-231-0VB019 | 1 | 119.6 | 119.6 |  |  | Steel Structure | [11 empty] | 0 | 119.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
696 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB019 | 0VB019(3/4) | 4-VBRACES-231-0VB019 | 1 | 119.6 | 119.6 |  |  | Steel Structure | [11 empty] | 0 | 119.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
697 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB019 | 0VB019(4/4) | 4-VBRACES-231-0VB019 | 1 | 119.6 | 119.6 |  |  | Steel Structure | [11 empty] | 0 | 119.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
698 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB020 | 0VB020 | ONE-VBRACE-231-0VB020 | 1 | 115.2 | 115.2 |  |  | Steel Structure | [11 empty] | 0 | 115.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
699 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB021 | 0VB021(1/3) | 3-VBRACES-231-0VB021 | 1 | 113.1 | 113.1 |  |  | Steel Structure | [11 empty] | 0 | 113.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
700 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB021 | 0VB021(2/3) | 3-VBRACES-231-0VB021 | 1 | 113.1 | 113.1 |  |  | Steel Structure | [11 empty] | 0 | 113.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
701 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB021 | 0VB021(3/3) | 3-VBRACES-231-0VB021 | 1 | 113.1 | 113.1 |  |  | Steel Structure | [11 empty] | 0 | 113.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
702 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB022 | 0VB022(1/2) | 2-VBRACES-231-0VB022 | 1 | 113.1 | 113.1 |  |  | Steel Structure | [11 empty] | 0 | 113.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
703 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB022 | 0VB022(2/2) | 2-VBRACES-231-0VB022 | 1 | 113.1 | 113.1 |  |  | Steel Structure | [11 empty] | 0 | 113.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
704 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB023 | 0VB023 | ONE-VBRACE-231-0VB023 | 1 | 109.3 | 109.3 |  |  | Steel Structure | [11 empty] | 0 | 109.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
705 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB024 | 0VB024 | ONE-VBRACE-231-0VB024 | 1 | 37.6 | 37.6 |  |  | Steel Structure | [11 empty] | 0 | 37.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
706 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB025 | 0VB025(1/2) | 2-VBRACES-231-0VB025 | 1 | 100.1 | 100.1 |  |  | Steel Structure | [11 empty] | 0 | 100.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
707 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB025 | 0VB025(2/2) | 2-VBRACES-231-0VB025 | 1 | 100.1 | 100.1 |  |  | Steel Structure | [11 empty] | 0 | 100.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
708 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB026 | 0VB026(1/2) | 2-VBRACES-231-0VB026 | 1 | 296.6 | 296.6 |  |  | Steel Structure | [11 empty] | 0 | 296.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
709 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB026 | 0VB026(2/2) | 2-VBRACES-231-0VB026 | 1 | 296.6 | 296.6 |  |  | Steel Structure | [11 empty] | 0 | 296.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
710 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB027 | 0VB027(1/2) | 2-VBRACES-231-0VB027 | 1 | 156.4 | 156.4 |  |  | Steel Structure | [11 empty] | 0 | 156.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
711 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB027 | 0VB027(2/2) | 2-VBRACES-231-0VB027 | 1 | 156.4 | 156.4 |  |  | Steel Structure | [11 empty] | 0 | 156.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
712 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB028 | 0VB028 | ONE-VBRACE-231-0VB028 | 1 | 139.1 | 139.1 |  |  | Steel Structure | [11 empty] | 0 | 139.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
713 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB029 | 0VB029 | ONE-VBRACE-231-0VB029 | 1 | 139.1 | 139.1 |  |  | Steel Structure | [11 empty] | 0 | 139.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
714 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB030 | 0VB030 | ONE-VBRACE-231-0VB030 | 1 | 95.8 | 95.8 |  |  | Steel Structure | [11 empty] | 0 | 95.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
715 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB031 | 0VB031 | ONE-VBRACE-231-0VB031 | 1 | 108.4 | 108.4 |  |  | Steel Structure | [11 empty] | 0 | 108.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
716 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB032 | 0VB032 | ONE-VBRACE-231-0VB032 | 1 | 157.8 | 157.8 |  |  | Steel Structure | [11 empty] | 0 | 157.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
717 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB033 | 0VB033 | ONE-VBRACE-231-0VB033 | 1 | 151.4 | 151.4 |  |  | Steel Structure | [11 empty] | 0 | 151.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
718 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB034 | 0VB034 | ONE-VBRACE-231-0VB034 | 1 | 95.7 | 95.7 |  |  | Steel Structure | [11 empty] | 0 | 95.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
719 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB035 | 0VB035 | ONE-VBRACE-231-0VB035 | 1 | 95.7 | 95.7 |  |  | Steel Structure | [11 empty] | 0 | 95.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
720 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB036 | 0VB036(1/2) | 2-VBRACES-231-0VB036 | 1 | 123 | 123 |  |  | Steel Structure | [11 empty] | 0 | 123 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
721 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB036 | 0VB036(2/2) | 2-VBRACES-231-0VB036 | 1 | 123 | 123 |  |  | Steel Structure | [11 empty] | 0 | 123 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
722 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB037 | 0VB037 | ONE-VBRACE-231-0VB037 | 1 | 163.3 | 163.3 |  |  | Steel Structure | [11 empty] | 0 | 163.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
723 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB038 | 0VB038 | ONE-VBRACE-231-0VB038 | 1 | 110.3 | 110.3 |  |  | Steel Structure | [11 empty] | 0 | 110.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
724 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB039 | 0VB039 | ONE-VBRACE-231-0VB039 | 1 | 109.8 | 109.8 |  |  | Steel Structure | [11 empty] | 0 | 109.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
725 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB040 | 0VB040 | ONE-VBRACE-231-0VB040 | 1 | 109.3 | 109.3 |  |  | Steel Structure | [11 empty] | 0 | 109.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
726 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB041 | 0VB041 | ONE-VBRACE-231-0VB041 | 1 | 108.7 | 108.7 |  |  | Steel Structure | [11 empty] | 0 | 108.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
727 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB042 | 0VB042 | ONE-VBRACE-231-0VB042 | 1 | 76.8 | 76.8 |  |  | Steel Structure | [11 empty] | 0 | 76.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
728 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB043 | 0VB043(1/2) | 2-VBRACES-231-0VB043 | 1 | 128.2 | 128.2 |  |  | Steel Structure | [11 empty] | 0 | 128.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
729 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB043 | 0VB043(2/2) | 2-VBRACES-231-0VB043 | 1 | 128.2 | 128.2 |  |  | Steel Structure | [11 empty] | 0 | 128.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
730 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB044 | 0VB044 | ONE-VBRACE-231-0VB044 | 1 | 19.8 | 19.8 |  |  | Steel Structure | [11 empty] | 0 | 19.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
731 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB045 | 0VB045 | ONE-VBRACE-231-0VB045 | 1 | 54.9 | 54.9 |  |  | Steel Structure | [11 empty] | 0 | 54.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
732 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB046 | 0VB046 | ONE-VBRACE-231-0VB046 | 1 | 20.4 | 20.4 |  |  | Steel Structure | [11 empty] | 0 | 20.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
733 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB047 | 0VB047(1/2) | 2-VBRACES-231-0VB047 | 1 | 27.9 | 27.9 |  |  | Steel Structure | [11 empty] | 0 | 27.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
734 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB047 | 0VB047(2/2) | 2-VBRACES-231-0VB047 | 1 | 27.9 | 27.9 |  |  | Steel Structure | [11 empty] | 0 | 27.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
735 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB048 | 0VB048 | ONE-VBRACE-231-0VB048 | 1 | 65.7 | 65.7 |  |  | Steel Structure | [11 empty] | 0 | 65.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
736 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB049 | 0VB049(1/2) | 2-VBRACES-231-0VB049 | 1 | 60.3 | 60.3 |  |  | Steel Structure | [11 empty] | 0 | 60.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
737 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB049 | 0VB049(2/2) | 2-VBRACES-231-0VB049 | 1 | 60.3 | 60.3 |  |  | Steel Structure | [11 empty] | 0 | 60.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
738 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB051 | 0VB051 | ONE-VBRACE-231-0VB051 | 1 | 131.5 | 131.5 |  |  | Steel Structure | [11 empty] | 0 | 131.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
739 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB052 | 0VB052 | ONE-VBRACE-231-0VB052 | 1 | 131.5 | 131.5 |  |  | Steel Structure | [11 empty] | 0 | 131.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
740 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB053 | 0VB053(1/2) | 2-VBRACES-231-0VB053 | 1 | 130.4 | 130.4 |  |  | Steel Structure | [11 empty] | 0 | 130.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
741 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB053 | 0VB053(2/2) | 2-VBRACES-231-0VB053 | 1 | 130.4 | 130.4 |  |  | Steel Structure | [11 empty] | 0 | 130.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
742 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB054 | 0VB054(1/2) | 2-VBRACES-231-0VB054 | 1 | 130.4 | 130.4 |  |  | Steel Structure | [11 empty] | 0 | 130.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
743 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB054 | 0VB054(2/2) | 2-VBRACES-231-0VB054 | 1 | 130.4 | 130.4 |  |  | Steel Structure | [11 empty] | 0 | 130.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
744 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB055 | 0VB055 | ONE-VBRACE-231-0VB055 | 1 | 126.5 | 126.5 |  |  | Steel Structure | [11 empty] | 0 | 126.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
745 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB056 | 0VB056 | ONE-VBRACE-231-0VB056 | 1 | 123.9 | 123.9 |  |  | Steel Structure | [11 empty] | 0 | 123.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
746 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB057 | 0VB057 | ONE-VBRACE-231-0VB057 | 1 | 123.9 | 123.9 |  |  | Steel Structure | [11 empty] | 0 | 123.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
747 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB058 | 0VB058 | ONE-VBRACE-231-0VB058 | 1 | 111.1 | 111.1 |  |  | Steel Structure | [11 empty] | 0 | 111.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
748 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB059 | 0VB059(1/2) | 2-VBRACES-231-0VB059 | 1 | 86.4 | 86.4 |  |  | Steel Structure | [11 empty] | 0 | 86.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
749 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB059 | 0VB059(2/2) | 2-VBRACES-231-0VB059 | 1 | 86.4 | 86.4 |  |  | Steel Structure | [11 empty] | 0 | 86.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
750 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB060 | 0VB060 | ONE-VBRACE-231-0VB060 | 1 | 64.3 | 64.3 |  |  | Steel Structure | [11 empty] | 0 | 64.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
751 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB061 | 0VB061 | ONE-VBRACE-231-0VB061 | 1 | 63.3 | 63.3 |  |  | Steel Structure | [11 empty] | 0 | 63.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
752 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB062 | 0VB062(1/2) | 2-VBRACES-231-0VB062 | 1 | 59.1 | 59.1 |  |  | Steel Structure | [11 empty] | 0 | 59.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
753 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB062 | 0VB062(2/2) | 2-VBRACES-231-0VB062 | 1 | 59.1 | 59.1 |  |  | Steel Structure | [11 empty] | 0 | 59.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
754 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB063 | 0VB063(1/3) | 3-VBRACES-231-0VB063 | 1 | 57.9 | 57.9 |  |  | Steel Structure | [11 empty] | 0 | 57.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
755 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB063 | 0VB063(2/3) | 3-VBRACES-231-0VB063 | 1 | 57.9 | 57.9 |  |  | Steel Structure | [11 empty] | 0 | 57.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
756 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB063 | 0VB063(3/3) | 3-VBRACES-231-0VB063 | 1 | 57.9 | 57.9 |  |  | Steel Structure | [11 empty] | 0 | 57.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
757 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB064 | 0VB064(1/2) | 2-VBRACES-231-0VB064 | 1 | 61.1 | 61.1 |  |  | Steel Structure | [11 empty] | 0 | 61.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
758 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB064 | 0VB064(2/2) | 2-VBRACES-231-0VB064 | 1 | 61.1 | 61.1 |  |  | Steel Structure | [11 empty] | 0 | 61.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
759 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB066 | 0VB066(1/2) | 2-VBRACES-231-0VB066 | 1 | 21.9 | 21.9 |  |  | Steel Structure | [11 empty] | 0 | 21.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
760 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB066 | 0VB066(2/2) | 2-VBRACES-231-0VB066 | 1 | 21.9 | 21.9 |  |  | Steel Structure | [11 empty] | 0 | 21.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
761 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB067 | 0VB067 | ONE-VBRACE-231-0VB067 | 1 | 56.3 | 56.3 |  |  | Steel Structure | [11 empty] | 0 | 56.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
762 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB068 | 0VB068 | ONE-VBRACE-231-0VB068 | 1 | 27.7 | 27.7 |  |  | Steel Structure | [11 empty] | 0 | 27.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
763 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB069 | 0VB069 | ONE-VBRACE-231-0VB069 | 1 | 23.3 | 23.3 |  |  | Steel Structure | [11 empty] | 0 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
764 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB070 | 0VB070 | ONE-VBRACE-231-0VB070 | 1 | 22.3 | 22.3 |  |  | Steel Structure | [11 empty] | 0 | 22.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
765 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB071 | 0VB071(1/2) | 2-VBRACES-231-0VB071 | 1 | 44.9 | 44.9 |  |  | Steel Structure | [11 empty] | 0 | 44.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
766 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB071 | 0VB071(2/2) | 2-VBRACES-231-0VB071 | 1 | 44.9 | 44.9 |  |  | Steel Structure | [11 empty] | 0 | 44.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
767 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB072 | 0VB072 | ONE-VBRACE-231-0VB072 | 1 | 29.9 | 29.9 |  |  | Steel Structure | [11 empty] | 0 | 29.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
768 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB073 | 0VB073 | ONE-VBRACE-231-0VB073 | 1 | 117.9 | 117.9 |  |  | Steel Structure | [11 empty] | 0 | 117.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
769 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB074 | 0VB074 | ONE-VBRACE-231-0VB074 | 1 | 125.3 | 125.3 |  |  | Steel Structure | [11 empty] | 0 | 125.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
770 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB075 | 0VB075 | ONE-VBRACE-231-0VB075 | 1 | 33.7 | 33.7 |  |  | Steel Structure | [11 empty] | 0 | 33.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
771 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB076 | 0VB076 | ONE-VBRACE-231-0VB076 | 1 | 31.1 | 31.1 |  |  | Steel Structure | [11 empty] | 0 | 31.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
772 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB077 | 0VB077(1/2) | 2-VBRACES-231-0VB077 | 1 | 23.3 | 23.3 |  |  | Steel Structure | [11 empty] | 0 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
773 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB077 | 0VB077(2/2) | 2-VBRACES-231-0VB077 | 1 | 23.3 | 23.3 |  |  | Steel Structure | [11 empty] | 0 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
774 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB078 | 0VB078(1/3) | 3-VBRACES-231-0VB078 | 1 | 40.7 | 40.7 |  |  | Steel Structure | [11 empty] | 0 | 40.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
775 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB078 | 0VB078(2/3) | 3-VBRACES-231-0VB078 | 1 | 40.7 | 40.7 |  |  | Steel Structure | [11 empty] | 0 | 40.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
776 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB078 | 0VB078(3/3) | 3-VBRACES-231-0VB078 | 1 | 40.7 | 40.7 |  |  | Steel Structure | [11 empty] | 0 | 40.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
777 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB079 | 0VB079(1/2) | 2-VBRACES-231-0VB079 | 1 | 41.1 | 41.1 |  |  | Steel Structure | [11 empty] | 0 | 41.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
778 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB079 | 0VB079(2/2) | 2-VBRACES-231-0VB079 | 1 | 41.1 | 41.1 |  |  | Steel Structure | [11 empty] | 0 | 41.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
779 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB080 | 0VB080(1/3) | 3-VBRACES-231-0VB080 | 1 | 42.7 | 42.7 |  |  | Steel Structure | [11 empty] | 0 | 42.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
780 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB080 | 0VB080(2/3) | 3-VBRACES-231-0VB080 | 1 | 42.7 | 42.7 |  |  | Steel Structure | [11 empty] | 0 | 42.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
781 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB080 | 0VB080(3/3) | 3-VBRACES-231-0VB080 | 1 | 42.7 | 42.7 |  |  | Steel Structure | [11 empty] | 0 | 42.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
782 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB081 | 0VB081(1/2) | 2-VBRACES-231-0VB081 | 1 | 43.1 | 43.1 |  |  | Steel Structure | [11 empty] | 0 | 43.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
783 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB081 | 0VB081(2/2) | 2-VBRACES-231-0VB081 | 1 | 43.1 | 43.1 |  |  | Steel Structure | [11 empty] | 0 | 43.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
784 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB082 | 0VB082(1/3) | 3-VBRACES-231-0VB082 | 1 | 43.7 | 43.7 |  |  | Steel Structure | [11 empty] | 0 | 43.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
785 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB082 | 0VB082(2/3) | 3-VBRACES-231-0VB082 | 1 | 43.7 | 43.7 |  |  | Steel Structure | [11 empty] | 0 | 43.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
786 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB082 | 0VB082(3/3) | 3-VBRACES-231-0VB082 | 1 | 43.7 | 43.7 |  |  | Steel Structure | [11 empty] | 0 | 43.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
787 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB083 | 0VB083(1/2) | 2-VBRACES-231-0VB083 | 1 | 44.1 | 44.1 |  |  | Steel Structure | [11 empty] | 0 | 44.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
788 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB083 | 0VB083(2/2) | 2-VBRACES-231-0VB083 | 1 | 44.1 | 44.1 |  |  | Steel Structure | [11 empty] | 0 | 44.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
789 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB084 | 0VB084 | ONE-VBRACE-231-0VB084 | 1 | 29.5 | 29.5 |  |  | Steel Structure | [11 empty] | 0 | 29.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
790 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB085 | 0VB085(1/3) | 3-VBRACES-231-0VB085 | 1 | 45.5 | 45.5 |  |  | Steel Structure | [11 empty] | 0 | 45.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
791 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB085 | 0VB085(2/3) | 3-VBRACES-231-0VB085 | 1 | 45.5 | 45.5 |  |  | Steel Structure | [11 empty] | 0 | 45.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
792 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB085 | 0VB085(3/3) | 3-VBRACES-231-0VB085 | 1 | 45.5 | 45.5 |  |  | Steel Structure | [11 empty] | 0 | 45.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
793 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB086 | 0VB086(1/2) | 2-VBRACES-231-0VB086 | 1 | 45.9 | 45.9 |  |  | Steel Structure | [11 empty] | 0 | 45.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
794 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB086 | 0VB086(2/2) | 2-VBRACES-231-0VB086 | 1 | 45.9 | 45.9 |  |  | Steel Structure | [11 empty] | 0 | 45.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
795 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB087 | 0VB087(1/3) | 3-VBRACES-231-0VB087 | 1 | 53.9 | 53.9 |  |  | Steel Structure | [11 empty] | 0 | 53.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
796 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB087 | 0VB087(2/3) | 3-VBRACES-231-0VB087 | 1 | 53.9 | 53.9 |  |  | Steel Structure | [11 empty] | 0 | 53.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
797 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB087 | 0VB087(3/3) | 3-VBRACES-231-0VB087 | 1 | 53.9 | 53.9 |  |  | Steel Structure | [11 empty] | 0 | 53.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
798 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB088 | 0VB088(1/2) | 2-VBRACES-231-0VB088 | 1 | 54.3 | 54.3 |  |  | Steel Structure | [11 empty] | 0 | 54.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
799 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB088 | 0VB088(2/2) | 2-VBRACES-231-0VB088 | 1 | 54.3 | 54.3 |  |  | Steel Structure | [11 empty] | 0 | 54.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
800 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB089 | 0VB089 | ONE-VBRACE-231-0VB089 | 1 | 33.3 | 33.3 |  |  | Steel Structure | [11 empty] | 0 | 33.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
801 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB090 | 0VB090(1/3) | 3-VBRACES-231-0VB090 | 1 | 56.1 | 56.1 |  |  | Steel Structure | [11 empty] | 0 | 56.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
802 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB090 | 0VB090(2/3) | 3-VBRACES-231-0VB090 | 1 | 56.1 | 56.1 |  |  | Steel Structure | [11 empty] | 0 | 56.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
803 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB090 | 0VB090(3/3) | 3-VBRACES-231-0VB090 | 1 | 56.1 | 56.1 |  |  | Steel Structure | [11 empty] | 0 | 56.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
804 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB091 | 0VB091(1/2) | 2-VBRACES-231-0VB091 | 1 | 56.5 | 56.5 |  |  | Steel Structure | [11 empty] | 0 | 56.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
805 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB091 | 0VB091(2/2) | 2-VBRACES-231-0VB091 | 1 | 56.5 | 56.5 |  |  | Steel Structure | [11 empty] | 0 | 56.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
806 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB092 | 0VB092(1/2) | 2-VBRACES-231-0VB092 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
807 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB092 | 0VB092(2/2) | 2-VBRACES-231-0VB092 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
808 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB093 | 0VB093(1/3) | 3-VBRACES-231-0VB093 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
809 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB093 | 0VB093(2/3) | 3-VBRACES-231-0VB093 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
810 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB093 | 0VB093(3/3) | 3-VBRACES-231-0VB093 | 1 | 46.7 | 46.7 |  |  | Steel Structure | [11 empty] | 0 | 46.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
811 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB094 | 0VB094(1/3) | 3-VBRACES-231-0VB094 | 1 | 48.3 | 48.3 |  |  | Steel Structure | [11 empty] | 0 | 48.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
812 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB094 | 0VB094(2/3) | 3-VBRACES-231-0VB094 | 1 | 48.3 | 48.3 |  |  | Steel Structure | [11 empty] | 0 | 48.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
813 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB094 | 0VB094(3/3) | 3-VBRACES-231-0VB094 | 1 | 48.3 | 48.3 |  |  | Steel Structure | [11 empty] | 0 | 48.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
814 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB095 | 0VB095(1/2) | 2-VBRACES-231-0VB095 | 1 | 48.3 | 48.3 |  |  | Steel Structure | [11 empty] | 0 | 48.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
815 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB095 | 0VB095(2/2) | 2-VBRACES-231-0VB095 | 1 | 48.3 | 48.3 |  |  | Steel Structure | [11 empty] | 0 | 48.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
816 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB096 | 0VB096 | ONE-VBRACE-231-0VB096 | 1 | 75.7 | 75.7 |  |  | Steel Structure | [11 empty] | 0 | 75.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
817 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB097 | 0VB097 | ONE-VBRACE-231-0VB097 | 1 | 73.7 | 73.7 |  |  | Steel Structure | [11 empty] | 0 | 73.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
818 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB098 | 0VB098 | ONE-VBRACE-231-0VB098 | 1 | 75.9 | 75.9 |  |  | Steel Structure | [11 empty] | 0 | 75.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
819 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB099 | 0VB099 | ONE-VBRACE-231-0VB099 | 1 | 70.9 | 70.9 |  |  | Steel Structure | [11 empty] | 0 | 70.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
820 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB100 | 0VB100 | ONE-VBRACE-231-0VB100 | 1 | 78.3 | 78.3 |  |  | Steel Structure | [11 empty] | 0 | 78.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
821 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB101 | 0VB101 | ONE-VBRACE-231-0VB101 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
822 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB102 | 0VB102 | ONE-VBRACE-231-0VB102 | 1 | 82.7 | 82.7 |  |  | Steel Structure | [11 empty] | 0 | 82.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
823 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB103 | 0VB103 | ONE-VBRACE-231-0VB103 | 1 | 81.1 | 81.1 |  |  | Steel Structure | [11 empty] | 0 | 81.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
824 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB104 | 0VB104 | ONE-VBRACE-231-0VB104 | 1 | 66.7 | 66.7 |  |  | Steel Structure | [11 empty] | 0 | 66.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
825 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB105 | 0VB105 | ONE-VBRACE-231-0VB105 | 1 | 67.5 | 67.5 |  |  | Steel Structure | [11 empty] | 0 | 67.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
826 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-231-0VB106 | 0VB106 | ONE-VBRACE-231-0VB106 | 1 | 109.3 | 109.3 |  |  | Steel Structure | [11 empty] | 0 | 109.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
827 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI001 | 0GI001(1/2) | 2-GIRTHS-385-0GI001 | 1 | 94.7 | 94.7 |  |  | Steel Structure | [11 empty] | 0 | 94.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
828 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI001 | 0GI001(2/2) | 2-GIRTHS-385-0GI001 | 1 | 94.7 | 94.7 |  |  | Steel Structure | [11 empty] | 0 | 94.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
829 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI002 | 0GI002 | ONE-GIRTH-385-0GI002 | 1 | 78 | 78 |  |  | Steel Structure | [11 empty] | 0 | 78 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
830 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI003 | 0GI003 | ONE-GIRTH-385-0GI003 | 1 | 81.5 | 81.5 |  |  | Steel Structure | [11 empty] | 0 | 81.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
831 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI004 | 0GI004(1/2) | 2-GIRTHS-385-0GI004 | 1 | 74.1 | 74.1 |  |  | Steel Structure | [11 empty] | 0 | 74.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
832 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI004 | 0GI004(2/2) | 2-GIRTHS-385-0GI004 | 1 | 74.1 | 74.1 |  |  | Steel Structure | [11 empty] | 0 | 74.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
833 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI005 | 0GI005(1/2) | 2-GIRTHS-385-0GI005 | 1 | 90.7 | 90.7 |  |  | Steel Structure | [11 empty] | 0 | 90.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
834 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI005 | 0GI005(2/2) | 2-GIRTHS-385-0GI005 | 1 | 90.7 | 90.7 |  |  | Steel Structure | [11 empty] | 0 | 90.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
835 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI006 | 0GI006(1/2) | 2-GIRTHS-385-0GI006 | 1 | 90.7 | 90.7 |  |  | Steel Structure | [11 empty] | 0 | 90.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
836 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI006 | 0GI006(2/2) | 2-GIRTHS-385-0GI006 | 1 | 90.7 | 90.7 |  |  | Steel Structure | [11 empty] | 0 | 90.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
837 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI007 | 0GI007 | ONE-GIRTH-385-0GI007 | 1 | 38.9 | 38.9 |  |  | Steel Structure | [11 empty] | 0 | 38.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
838 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI008 | 0GI008 | ONE-GIRTH-385-0GI008 | 1 | 78 | 78 |  |  | Steel Structure | [11 empty] | 0 | 78 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
839 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI009 | 0GI009 | ONE-GIRTH-385-0GI009 | 1 | 42.4 | 42.4 |  |  | Steel Structure | [11 empty] | 0 | 42.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
840 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI010 | 0GI010 | ONE-GIRTH-385-0GI010 | 1 | 94.6 | 94.6 |  |  | Steel Structure | [11 empty] | 0 | 94.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
841 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI011 | 0GI011 | ONE-GIRTH-385-0GI011 | 1 | 94.6 | 94.6 |  |  | Steel Structure | [11 empty] | 0 | 94.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
842 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI012 | 0GI012 | ONE-GIRTH-385-0GI012 | 1 | 86.8 | 86.8 |  |  | Steel Structure | [11 empty] | 0 | 86.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
843 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI013 | 0GI013 | ONE-GIRTH-385-0GI013 | 1 | 86.8 | 86.8 |  |  | Steel Structure | [11 empty] | 0 | 86.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
844 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI014 | 0GI014 | ONE-GIRTH-385-0GI014 | 1 | 81.9 | 81.9 |  |  | Steel Structure | [11 empty] | 0 | 81.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
845 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI015 | 0GI015 | ONE-GIRTH-385-0GI015 | 1 | 81.9 | 81.9 |  |  | Steel Structure | [11 empty] | 0 | 81.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
846 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI016 | 0GI016 | ONE-GIRTH-385-0GI016 | 1 | 98.7 | 98.7 |  |  | Steel Structure | [11 empty] | 0 | 98.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
847 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI017 | 0GI017 | ONE-GIRTH-385-0GI017 | 1 | 98.7 | 98.7 |  |  | Steel Structure | [11 empty] | 0 | 98.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
848 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI018 | 0GI018 | ONE-GIRTH-385-0GI018 | 1 | 79.4 | 79.4 |  |  | Steel Structure | [11 empty] | 0 | 79.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
849 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI019 | 0GI019 | ONE-GIRTH-385-0GI019 | 1 | 79.4 | 79.4 |  |  | Steel Structure | [11 empty] | 0 | 79.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
850 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI020 | 0GI020 | ONE-GIRTH-385-0GI020 | 1 | 94.6 | 94.6 |  |  | Steel Structure | [11 empty] | 0 | 94.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
851 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0GI021 | 0GI021 | ONE-GIRTH-385-0GI021 | 1 | 94.6 | 94.6 |  |  | Steel Structure | [11 empty] | 0 | 94.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
852 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU001 | 0PU001 | ONE-PURLIN-385-0PU001 | 1 | 39.9 | 39.9 |  |  | Steel Structure | [11 empty] | 0 | 39.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
853 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU002 | 0PU002 | ONE-PURLIN-385-0PU002 | 1 | 38.5 | 38.5 |  |  | Steel Structure | [11 empty] | 0 | 38.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
854 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU003 | 0PU003 | ONE-PURLIN-385-0PU003 | 1 | 82.7 | 82.7 |  |  | Steel Structure | [11 empty] | 0 | 82.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
855 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU004 | 0PU004 | ONE-PURLIN-385-0PU004 | 1 | 14.2 | 14.2 |  |  | Steel Structure | [11 empty] | 0 | 14.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
856 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU005 | 0PU005 | ONE-PURLIN-385-0PU005 | 1 | 14.8 | 14.8 |  |  | Steel Structure | [11 empty] | 0 | 14.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
857 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU006 | 0PU006 | ONE-PURLIN-385-0PU006 | 1 | 16.6 | 16.6 |  |  | Steel Structure | [11 empty] | 0 | 16.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
858 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU007 | 0PU007 | ONE-PURLIN-385-0PU007 | 1 | 17.1 | 17.1 |  |  | Steel Structure | [11 empty] | 0 | 17.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
859 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU008 | 0PU008 | ONE-PURLIN-385-0PU008 | 1 | 39.3 | 39.3 |  |  | Steel Structure | [11 empty] | 0 | 39.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
860 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU009 | 0PU009 | ONE-PURLIN-385-0PU009 | 1 | 39.3 | 39.3 |  |  | Steel Structure | [11 empty] | 0 | 39.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
861 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU010 | 0PU010 | ONE-PURLIN-385-0PU010 | 1 | 36.1 | 36.1 |  |  | Steel Structure | [11 empty] | 0 | 36.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
862 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU011 | 0PU011 | ONE-PURLIN-385-0PU011 | 1 | 36.1 | 36.1 |  |  | Steel Structure | [11 empty] | 0 | 36.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
863 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU012 | 0PU012 | ONE-PURLIN-385-0PU012 | 1 | 88.2 | 88.2 |  |  | Steel Structure | [11 empty] | 0 | 88.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
864 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU013 | 0PU013 | ONE-PURLIN-385-0PU013 | 1 | 14.9 | 14.9 |  |  | Steel Structure | [11 empty] | 0 | 14.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
865 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU014 | 0PU014 | ONE-PURLIN-385-0PU014 | 1 | 14.3 | 14.3 |  |  | Steel Structure | [11 empty] | 0 | 14.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
866 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU015 | 0PU015 | ONE-PURLIN-385-0PU015 | 1 | 12.6 | 12.6 |  |  | Steel Structure | [11 empty] | 0 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
867 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU016 | 0PU016 | ONE-PURLIN-385-0PU016 | 1 | 12 | 12 |  |  | Steel Structure | [11 empty] | 0 | 12 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
868 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU017 | 0PU017 | ONE-PURLIN-385-0PU017 | 1 | 44.5 | 44.5 |  |  | Steel Structure | [11 empty] | 0 | 44.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
869 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU018 | 0PU018 | ONE-PURLIN-385-0PU018 | 1 | 40.2 | 40.2 |  |  | Steel Structure | [11 empty] | 0 | 40.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
870 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU019 | 0PU019 | ONE-PURLIN-385-0PU019 | 1 | 82.7 | 82.7 |  |  | Steel Structure | [11 empty] | 0 | 82.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
871 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU020 | 0PU020 | ONE-PURLIN-385-0PU020 | 1 | 8.7 | 8.7 |  |  | Steel Structure | [11 empty] | 0 | 8.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
872 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU021 | 0PU021 | ONE-PURLIN-385-0PU021 | 1 | 9.2 | 9.2 |  |  | Steel Structure | [11 empty] | 0 | 9.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
873 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU022 | 0PU022 | ONE-PURLIN-385-0PU022 | 1 | 41.6 | 41.6 |  |  | Steel Structure | [11 empty] | 0 | 41.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
874 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU023 | 0PU023 | ONE-PURLIN-385-0PU023 | 1 | 37.6 | 37.6 |  |  | Steel Structure | [11 empty] | 0 | 37.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
875 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU024 | 0PU024 | ONE-PURLIN-385-0PU024 | 1 | 57.9 | 57.9 |  |  | Steel Structure | [11 empty] | 0 | 57.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
876 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU025 | 0PU025(1/6) | 6-PURLINS-385-0PU025 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
877 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU025 | 0PU025(2/6) | 6-PURLINS-385-0PU025 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
878 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU025 | 0PU025(3/6) | 6-PURLINS-385-0PU025 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
879 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU025 | 0PU025(4/6) | 6-PURLINS-385-0PU025 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
880 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU025 | 0PU025(5/6) | 6-PURLINS-385-0PU025 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
881 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU025 | 0PU025(6/6) | 6-PURLINS-385-0PU025 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
882 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU026 | 0PU026 | ONE-PURLIN-385-0PU026 | 1 | 8.7 | 8.7 |  |  | Steel Structure | [11 empty] | 0 | 8.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
883 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU027 | 0PU027 | ONE-PURLIN-385-0PU027 | 1 | 8.2 | 8.2 |  |  | Steel Structure | [11 empty] | 0 | 8.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
884 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU028 | 0PU028 | ONE-PURLIN-385-0PU028 | 1 | 25.1 | 25.1 |  |  | Steel Structure | [11 empty] | 0 | 25.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
885 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU029 | 0PU029 | ONE-PURLIN-385-0PU029 | 1 | 41.3 | 41.3 |  |  | Steel Structure | [11 empty] | 0 | 41.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
886 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU030 | 0PU030 | ONE-PURLIN-385-0PU030 | 1 | 40 | 40 |  |  | Steel Structure | [11 empty] | 0 | 40 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
887 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU031 | 0PU031(1/2) | 2-PURLINS-385-0PU031 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
888 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU031 | 0PU031(2/2) | 2-PURLINS-385-0PU031 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
889 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU032 | 0PU032 | ONE-PURLIN-385-0PU032 | 1 | 11.7 | 11.7 |  |  | Steel Structure | [11 empty] | 0 | 11.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
890 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU033 | 0PU033 | ONE-PURLIN-385-0PU033 | 1 | 12.3 | 12.3 |  |  | Steel Structure | [11 empty] | 0 | 12.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
891 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU034 | 0PU034 | ONE-PURLIN-385-0PU034 | 1 | 31.1 | 31.1 |  |  | Steel Structure | [11 empty] | 0 | 31.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
892 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU035 | 0PU035 | ONE-PURLIN-385-0PU035 | 1 | 40.7 | 40.7 |  |  | Steel Structure | [11 empty] | 0 | 40.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
893 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU036 | 0PU036 | ONE-PURLIN-385-0PU036 | 1 | 16.8 | 16.8 |  |  | Steel Structure | [11 empty] | 0 | 16.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
894 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU037 | 0PU037 | ONE-PURLIN-385-0PU037 | 1 | 17.2 | 17.2 |  |  | Steel Structure | [11 empty] | 0 | 17.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
895 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU038 | 0PU038 | ONE-PURLIN-385-0PU038 | 1 | 16.7 | 16.7 |  |  | Steel Structure | [11 empty] | 0 | 16.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
896 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU039 | 0PU039 | ONE-PURLIN-385-0PU039 | 1 | 93.1 | 93.1 |  |  | Steel Structure | [11 empty] | 0 | 93.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
897 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU040 | 0PU040(1/5) | 5-PURLINS-385-0PU040 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
898 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU040 | 0PU040(2/5) | 5-PURLINS-385-0PU040 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
899 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU040 | 0PU040(3/5) | 5-PURLINS-385-0PU040 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
900 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU040 | 0PU040(4/5) | 5-PURLINS-385-0PU040 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
901 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU040 | 0PU040(5/5) | 5-PURLINS-385-0PU040 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
902 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU041 | 0PU041 | ONE-PURLIN-385-0PU041 | 1 | 85.7 | 85.7 |  |  | Steel Structure | [11 empty] | 0 | 85.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
903 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU042 | 0PU042 | ONE-PURLIN-385-0PU042 | 1 | 47 | 47 |  |  | Steel Structure | [11 empty] | 0 | 47 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
904 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU043 | 0PU043 | ONE-PURLIN-385-0PU043 | 1 | 20.6 | 20.6 |  |  | Steel Structure | [11 empty] | 0 | 20.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
905 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU044 | 0PU044 | ONE-PURLIN-385-0PU044 | 1 | 23.7 | 23.7 |  |  | Steel Structure | [11 empty] | 0 | 23.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
906 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU045 | 0PU045(1/2) | 2-PURLINS-385-0PU045 | 1 | 41.1 | 41.1 |  |  | Steel Structure | [11 empty] | 0 | 41.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
907 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU045 | 0PU045(2/2) | 2-PURLINS-385-0PU045 | 1 | 41.1 | 41.1 |  |  | Steel Structure | [11 empty] | 0 | 41.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
908 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU046 | 0PU046 | ONE-PURLIN-385-0PU046 | 1 | 50.5 | 50.5 |  |  | Steel Structure | [11 empty] | 0 | 50.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
909 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU047 | 0PU047 | ONE-PURLIN-385-0PU047 | 1 | 42.3 | 42.3 |  |  | Steel Structure | [11 empty] | 0 | 42.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
910 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU048 | 0PU048 | ONE-PURLIN-385-0PU048 | 1 | 18.5 | 18.5 |  |  | Steel Structure | [11 empty] | 0 | 18.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
911 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU049 | 0PU049 | ONE-PURLIN-385-0PU049 | 1 | 15.4 | 15.4 |  |  | Steel Structure | [11 empty] | 0 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
912 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU050 | 0PU050 | ONE-PURLIN-385-0PU050 | 1 | 73.6 | 73.6 |  |  | Steel Structure | [11 empty] | 0 | 73.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
913 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU051 | 0PU051 | ONE-PURLIN-385-0PU051 | 1 | 79.2 | 79.2 |  |  | Steel Structure | [11 empty] | 0 | 79.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
914 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU052 | 0PU052 | ONE-PURLIN-385-0PU052 | 1 | 59.5 | 59.5 |  |  | Steel Structure | [11 empty] | 0 | 59.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
915 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU053 | 0PU053 | ONE-PURLIN-385-0PU053 | 1 | 22 | 22 |  |  | Steel Structure | [11 empty] | 0 | 22 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
916 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU054 | 0PU054 | ONE-PURLIN-385-0PU054 | 1 | 23.9 | 23.9 |  |  | Steel Structure | [11 empty] | 0 | 23.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
917 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU055 | 0PU055 | ONE-PURLIN-385-0PU055 | 1 | 85.6 | 85.6 |  |  | Steel Structure | [11 empty] | 0 | 85.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
918 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU056 | 0PU056(1/3) | 3-PURLINS-385-0PU056 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
919 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU056 | 0PU056(2/3) | 3-PURLINS-385-0PU056 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
920 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU056 | 0PU056(3/3) | 3-PURLINS-385-0PU056 | 1 | 23.4 | 23.4 |  |  | Steel Structure | [11 empty] | 0 | 23.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
921 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU057 | 0PU057 | ONE-PURLIN-385-0PU057 | 1 | 14.4 | 14.4 |  |  | Steel Structure | [11 empty] | 0 | 14.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
922 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU058 | 0PU058 | ONE-PURLIN-385-0PU058 | 1 | 15.2 | 15.2 |  |  | Steel Structure | [11 empty] | 0 | 15.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
923 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU059 | 0PU059 | ONE-PURLIN-385-0PU059 | 1 | 77 | 77 |  |  | Steel Structure | [11 empty] | 0 | 77 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
924 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU060 | 0PU060 | ONE-PURLIN-385-0PU060 | 1 | 69.2 | 69.2 |  |  | Steel Structure | [11 empty] | 0 | 69.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
925 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU061 | 0PU061(1/2) | 2-PURLINS-385-0PU061 | 1 | 34.6 | 34.6 |  |  | Steel Structure | [11 empty] | 0 | 34.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
926 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU061 | 0PU061(2/2) | 2-PURLINS-385-0PU061 | 1 | 34.6 | 34.6 |  |  | Steel Structure | [11 empty] | 0 | 34.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
927 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU062 | 0PU062 | ONE-PURLIN-385-0PU062 | 1 | 70.8 | 70.8 |  |  | Steel Structure | [11 empty] | 0 | 70.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
928 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU063 | 0PU063 | ONE-PURLIN-385-0PU063 | 1 | 51.4 | 51.4 |  |  | Steel Structure | [11 empty] | 0 | 51.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
929 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU064 | 0PU064 | ONE-PURLIN-385-0PU064 | 1 | 16.6 | 16.6 |  |  | Steel Structure | [11 empty] | 0 | 16.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
930 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU065 | 0PU065 | ONE-PURLIN-385-0PU065 | 1 | 16.5 | 16.5 |  |  | Steel Structure | [11 empty] | 0 | 16.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
931 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU066 | 0PU066 | ONE-PURLIN-385-0PU066 | 1 | 15.8 | 15.8 |  |  | Steel Structure | [11 empty] | 0 | 15.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
932 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU067 | 0PU067 | ONE-PURLIN-385-0PU067 | 1 | 24.9 | 24.9 |  |  | Steel Structure | [11 empty] | 0 | 24.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
933 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU068 | 0PU068 | ONE-PURLIN-385-0PU068 | 1 | 52.5 | 52.5 |  |  | Steel Structure | [11 empty] | 0 | 52.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
934 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU069 | 0PU069 | ONE-PURLIN-385-0PU069 | 1 | 23.6 | 23.6 |  |  | Steel Structure | [11 empty] | 0 | 23.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
935 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU070 | 0PU070 | ONE-PURLIN-385-0PU070 | 1 | 34.5 | 34.5 |  |  | Steel Structure | [11 empty] | 0 | 34.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
936 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU071 | 0PU071 | ONE-PURLIN-385-0PU071 | 1 | 32.6 | 32.6 |  |  | Steel Structure | [11 empty] | 0 | 32.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
937 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU072 | 0PU072 | ONE-PURLIN-385-0PU072 | 1 | 38.4 | 38.4 |  |  | Steel Structure | [11 empty] | 0 | 38.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
938 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU073 | 0PU073 | ONE-PURLIN-385-0PU073 | 1 | 31.9 | 31.9 |  |  | Steel Structure | [11 empty] | 0 | 31.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
939 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU074 | 0PU074 | ONE-PURLIN-385-0PU074 | 1 | 38.2 | 38.2 |  |  | Steel Structure | [11 empty] | 0 | 38.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
940 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU075 | 0PU075 | ONE-PURLIN-385-0PU075 | 1 | 38.7 | 38.7 |  |  | Steel Structure | [11 empty] | 0 | 38.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
941 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-385-0PU076 | 0PU076 | ONE-PURLIN-385-0PU076 | 1 | 16.9 | 16.9 |  |  | Steel Structure | [11 empty] | 0 | 16.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
942 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT001 | 0PT001 | ONE-POST-418-0PT001 | 1 | 210.9 | 210.9 |  |  | Steel Structure | [11 empty] | 0 | 210.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
943 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT002 | 0PT002 | ONE-POST-418-0PT002 | 1 | 193.8 | 193.8 |  |  | Steel Structure | [11 empty] | 0 | 193.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
944 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT003 | 0PT003 | ONE-POST-418-0PT003 | 1 | 188.9 | 188.9 |  |  | Steel Structure | [11 empty] | 0 | 188.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
945 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT004 | 0PT004 | ONE-POST-418-0PT004 | 1 | 213.8 | 213.8 |  |  | Steel Structure | [11 empty] | 0 | 213.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
946 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT005 | 0PT005 | ONE-POST-418-0PT005 | 1 | 196.5 | 196.5 |  |  | Steel Structure | [11 empty] | 0 | 196.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
947 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT006 | 0PT006 | ONE-POST-418-0PT006 | 1 | 205.8 | 205.8 |  |  | Steel Structure | [11 empty] | 0 | 205.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
948 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT007 | 0PT007 | ONE-POST-418-0PT007 | 1 | 173.1 | 173.1 |  |  | Steel Structure | [11 empty] | 0 | 173.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
949 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT008 | 0PT008 | ONE-POST-418-0PT008 | 1 | 173 | 173 |  |  | Steel Structure | [11 empty] | 0 | 173 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
950 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT009 | 0PT009 | ONE-POST-418-0PT009 | 1 | 188 | 188 |  |  | Steel Structure | [11 empty] | 0 | 188 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
951 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT010 | 0PT010 | ONE-POST-418-0PT010 | 1 | 170.4 | 170.4 |  |  | Steel Structure | [11 empty] | 0 | 170.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
952 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT011 | 0PT011 | ONE-POST-418-0PT011 | 1 | 170.4 | 170.4 |  |  | Steel Structure | [11 empty] | 0 | 170.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
953 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT012 | 0PT012 | ONE-POST-418-0PT012 | 1 | 176.6 | 176.6 |  |  | Steel Structure | [11 empty] | 0 | 176.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
954 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT013 | 0PT013 | ONE-POST-418-0PT013 | 1 | 171.7 | 171.7 |  |  | Steel Structure | [11 empty] | 0 | 171.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
955 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT014 | 0PT014 | ONE-POST-418-0PT014 | 1 | 201.3 | 201.3 |  |  | Steel Structure | [11 empty] | 0 | 201.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
956 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT015 | 0PT015 | ONE-POST-418-0PT015 | 1 | 184 | 184 |  |  | Steel Structure | [11 empty] | 0 | 184 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
957 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT016 | 0PT016 | ONE-POST-418-0PT016 | 1 | 181.6 | 181.6 |  |  | Steel Structure | [11 empty] | 0 | 181.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
958 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT017 | 0PT017 | ONE-POST-418-0PT017 | 1 | 181.5 | 181.5 |  |  | Steel Structure | [11 empty] | 0 | 181.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
959 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-418-0PT018 | 0PT018 | ONE-POST-418-0PT018 | 1 | 170.1 | 170.1 |  |  | Steel Structure | [11 empty] | 0 | 170.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
960 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-001 | 0MR001 | ONE-MONORAIL-229-0MR001 | 1 | 494 | 494 |  |  | Steel Structure | [11 empty] | 0 | 494 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
961 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-002 | 0MR002 | ONE-MONORAIL-229-0MR002 | 1 | 250.5 | 250.5 |  |  | Steel Structure | [11 empty] | 0 | 250.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
962 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-002 | 0MR003 | ONE-MONORAIL-229-0MR003 | 1 | 257 | 257 |  |  | Steel Structure | [11 empty] | 0 | 257 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
963 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-003 | 0MR004 | ONE-MONORAIL-229-0MR004 | 1 | 289.3 | 289.3 |  |  | Steel Structure | [11 empty] | 0 | 289.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
964 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-003 | 0MR005 | ONE-MONORAIL-229-0MR005 | 1 | 345.9 | 345.9 |  |  | Steel Structure | [11 empty] | 0 | 345.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
965 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-004 | 0MR006 | ONE-MONORAIL-229-0MR006 | 1 | 245.2 | 245.2 |  |  | Steel Structure | [11 empty] | 0 | 245.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
966 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-005 | 0MR007 | ONE-MONORAIL-229-0MR007 | 1 | 157.1 | 157.1 |  |  | Steel Structure | [11 empty] | 0 | 157.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
967 | M304 | Shipment 7 Steel Structure U5 | Shipment 7 | Steel Structure U5 | Steel Structure | 2026-06-04 | HRSG | HSG16 | S4 | 25HG001-351-DD0-229-0MR-005 | 0MR008 | ONE-MONORAIL-229-0MR008 | 1 | 290 | 290 |  |  | Steel Structure | [11 empty] | 0 | 290 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | Truong An
[30 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
[30 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
[30 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
[30 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
[30 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0
[30 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0