## Cover
TÌNH TRẠNG DỰ ÁN
TT | Dự án/Project | Hạng mục/Item | Khối lượng/TW | Tiếp nhận/ Reveived | Còn thiếu/ Remain | Đồng bộ | % | Đã triển khai | KL còn lại có thể triển khai
X | U284 | Vogt | 274787.12 | 267662.84 | 7124.28 | 267662.84 | 97.41% | 244453.8 | 23209.04
1 | U284 | SCR Duct | 145074.6 | 144617.42 | 457.18 | 144617.42 | 99.68% | 126331 | 18286.42
2 | U284 | Oulet Stack | 129712.52 | 123045.42 | 6667.1 | 123045.42 | 94.86% | 118122.8 | 4922.62
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
0

## BTP-U284SCR
U284SCR
| Chủng loại | Thiết kế |  | Đã nhận |  | Còn thiếu |  |  |  | Đã nhận |  | Đồng bộ |  | Đã triển khai
|  | T.Q'ty | T.Weight | T.Q'ty | T.Weight | T.Q'ty | T.Weight |  |  | Số chi tiết | Khối lượng | Số chi tiết lớn | Khối lượng | Số chi tiết lớn | Khối lượng
| Shape | 1190 | 109028.5 | 1157 | 109017.7 | 33 | 10.8 |  | Total | 4142 | 144617.42 |  | 15326.8 |  | 0
| Plate | 3015 | 35626.02 | 2985 | 35599.72 | 30 | 26.3
| Purchasing | 11084 | 420.08 | 0 | 0 | 11084 | 420.08
| Total | 15289 | 145074.6 | 4142 | 144617.42 | 11147 | 457.18
Chủng loại thép hình
| Shape | 2" SCH.40 | 3/4" SCH.80 | RB14
| Chiều dài theo thiết kế (mm) | 5964 | 344 | 5316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL TK | 48 | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Đã nhận (mm) | 4932 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL Nhận | 36 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Còn thiếu (mm) | 1032 | 258 | 5316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL thiếu | 12 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu (kg) | 6 | 0.6 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chiều dày tôn
| Plate | 10 | 2.6 | 2
| Diện tích m2 theo thiết kế | 62.2408 | 0.34297 | 90.465 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| SL TK | 945 | 30 | 276 | 0 | 0 | 0 | 0
| Diện tích còn thiếu( m2) | 0.16051 | 0.097991 | 0.74522 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Sl còn thiếu | 6 | 20 | 4 | 0 | 0 | 0 | 0
| KL còn thiếu(kg) | 12.6 | 2 | 11.7 | 0 | 0 | 0 | 0
[11 empty] | 8197.8 | 98.4 | 2040.4 | 906.4 | 344.8 | 7.9 | 44000.4 | 943.4 | 1032.6 | 3630.4447 | 1139.3446 | 1738.1 | 733.2 | 135.6 | 4273.3 | 32918.7058 | 274.2 | 15625.2 | 151 | 19.2 | 375.2 | 19.3 | 991.8 | 125.8 | 250.8 | 461.8 | 52.0388 | 1271.7 | 1283.7 | 8277 | 483.8 | 15575.2 | 29.4 | 1648.2 | 466.0388 | 366 | 13.8 | 1.7 | 8302.8 | 817.4 | 8503.8 | 139.2 | 453.9 | 93.1 | 307.2 | 0 | 18.2 | 327.3 | 3270.1 | 5 | 156.5 | 14 | 8.4 | 87.72 | 29702.372 | #VALUE!
[11 empty] | 286 | 12 | 25 | 8 | 12 | 9 | 128 | 6 | 40 | 20.8241 | 14.1857 | 24 | 12 | 3 | 77 | 2.483 | 56 | 4 | 8 | 64 | 162 | 39 | 8 | 74 | 48 | 242 | 0.7767 | 957 | 216 | 310 | 58 | 7 | 14 | 473 | 73.7767 | 24 | 6 | 17 | 60 | 426 | 14 | 16 | 217 | 19 | 96 | 94 | 14 | 158 | 9 | 10 | 1 | 1 | 6 | 112 | 3.24 | #VALUE!
Chủng loại | Part No.1 | Size | Description | Length | Material | T.Q'ty | U.Weight | T.Weight | Đã nhận | Còn thiếu | 2026-05-03 | 2026-05-12 | 2026-05-13 | 2026-05-15 | 2026-05-23 | 2026-05-22 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-06-01 | 2026-06-04 | 2026-06-10 | 2026-06-13 | 2026-06-22 | 2026-06-29 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-27 | 2026-07-28 | 2026-08-03 | 2026-08-05 | 2026-08-07 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-10-16 | KO BB | Lấy data | Ktra nối | Tôn | Cảnh báo thừa | DVG | MPR No | Qty MPR | Cutting No. | Qty Cutting | Date Issue
| SR111R-3-PX-20 | PL1.5*556 | AIG BAFFLE 111R | 89 | SS400 | 1 | 0.6 | 0.6 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14
| SR111L-3-PX-17 | PL1.5*556 | AIG BAFFLE 111L | 89 | SS400 | 1 | 0.6 | 0.6 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14
| SR110R-1-PX-21 | PL1.5*520.7 | AIG BAFFLE 110R | 89 | SS400 | 48 | 0.5 | 24 | 0 | 48 | [55 empty] | #VALUE! |  |  |  | PMC | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 48 | 2026-07-14
| SR110L-1-PX-18 | PL1.5*520.7 | AIG BAFFLE 110L | 89 | SS400 | 48 | 0.5 | 24 | 0 | 48 | [55 empty] | #VALUE! |  |  |  | PMC | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 48 | 2026-07-14
| SR109R-2-PX-22 | PL1.5*585 | AIG BAFFLE 109R | 89 | SS400 | 1 | 0.6 | 0.6 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14
| SR109L-2-PX-19 | PL1.5*585 | AIG BAFFLE 109L | 89 | SS400 | 1 | 0.6 | 0.6 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14
| SR-10303-G-32 | PL1.5*127 | BATWING SHEET 103 | 1901 | A-240 TP304H | 96 | 2.8 | 268.8 | 0 | 96 | [55 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-4 DCC26-U284-0113-VTC-1 |  | U284-07-CP038 | 96 | 2026-07-14
Plate | SR-10203-GX-1 | PL1.5*127 | BATWING SHEET 102 | 2133 | A-240 TP304H | 96 | 3.2 | 307.2 | 96 | 0 | [44 empty] | 96 | [10 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0085-VTC-4 DCC26-U284-0113-VTC-1 |  | U284-07-CP038 | 96 | 2026-07-14
| SR-10103-G-29 | PL1.5*127 | BATWING SHEET 101 | 1372 | A-240 TP304H | 384 | 2.1 | 806.4 | 216 | 168 | [42 empty] | 216 | [12 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-4 DCC26-U284-0113-VTC-1 |  | U284-07-CP038 | 384 | 2026-07-14
Purchasing | M-3-M-30 | NUT_M12 | NUT M12 | 10 | A-479 TP304 | 768 | 0 | 0 | 0 | 768 | [55 empty] | #VALUE! |  |  |  | KHO | DCC26-U284-0086-VTP-02
Purchasing | M-3-M-29 | D12 | U-BOLT 2 1/2"x1/2"DIA | 357 | A-105 | 192 | 0.3 | 57.6 | 0 | 192 | [55 empty] | #VALUE! |  |  |  | KHO | DCC26-U284-0086-VTP-01
Purchasing | M-2-M-32 | D26 | WASHER 1/2" DIA | 2 | TP304 | 2304 | 0 | 0 | 0 | 2304 | [55 empty] | #VALUE! |  |  |  | KHO | DCC26-U284-0086-VTP-03
Purchasing | M-2-M-31 | PL1.5*32 | U-BOLT STRAP | 127 | A-240 TP304H | 1152 | 0 | 0 | 0 | 1152 | [55 empty] | #VALUE! |  |  |  | KHO | DCC26-U284-0086-VTP-04
Purchasing | M-2-M-30 | NUT_M12 | NUT M12 | 10 | A-479 TP304 | 4608 | 0 | 0 | 0 | 4608 | [55 empty] | #VALUE! |  |  |  | KHO | DCC26-U284-0086-VTP-02
Purchasing | M-2-M-29 | D12 | U-BOLT 2 1/2"x1/2"DIA | 357 | A-105 | 1152 | 0.3 | 345.6 | 0 | 1152 | [55 empty] | #VALUE! |  |  |  | KHO | DCC26-U284-0086-VTP-01
Purchasing | DR070R-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING | SCREWS |  | STAINLESS STEEL | 120 | 0.01 | 1.2 | 0 | 120 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-07
Purchasing | DR070R-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE | ADHESIVE |  | SILICONE | 3 | 0.1 | 0.3 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-10
Purchasing | DR070R-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. | TADPOLE GASKET 1000°F |  | SILICA W/INCONEL CORE | 3 | 0.12 | 0.36 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-09
Purchasing | DR070R-DR071-30 | M10 | HEX NUT |  | SS400 | 48 | 0.01 | 0.48 | 0 | 48 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-21
Plate | DR070R-DR071-29 | PL1.5 x OD76 x ID11 | WASHER |  | SS400 | 48 | 0.07 | 3.36 | 48 | 0 | [53 empty] | 48 |  | #VALUE! |  | PL1.5 |  | MCC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26
Shape | DR070R-DR071-28 | Ø10(M10) | STUD BOLT | 108 | SS400 | 24 | 0.15 | 3.6 | 24 | 0 | [47 empty] | 24 | [7 empty] | #VALUE! |  |  |  | PMC
Plate | DR070R-DR071-27 | PL1.5x683 | LINER PLATE | 1293 | SS400 | 3 | 10.4 | 31.2 | 3 | 0 | [47 empty] | 3 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26
Plate | DR070R-DR071-26B | PL1.5x140 | LINER PLATE | 1308 | SS400 | 6 | 2 | 12 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070R-DR071-26A | PL1.5x140 | LINER PLATE | 699 | SS400 | 6 | 1.2 | 7.2 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070R-DR071-22 | PL10x75 | FLATBAR | 236 | SS400 | 12 | 1.4 | 16.8 | 12 | 0 | [33 empty] | 12 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26
Plate | DR070R-DR071-21 | PL10x75 | FLATBAR | 737 | SS400 | 9 | 4.4 | 39.6 | 9 | 0 | [33 empty] | 9 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26
Plate | DR070R-DR071-20 | PL10x800 | PLATE | 1410 | SS400 | 3 | 88.5 | 265.5 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Purchasing | DR070R-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) | EYE BOLT/2NUTS/1PW |  | - | 3 | 0.3 | 0.9 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-01
Shape | DR070R-DR071-113 | RB14 | DOOR HANGER | 350 | SS400 | 3 | 0.4 | 1.2 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | PMC | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26
Plate | DR070R-DR071-112 | PL10x65 | GUSSET PLATE | 83 | SS400 | 60 | 0.4 | 24 | 60 | 0 | [33 empty] | 60 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26
Shape | DR070R-DR071-111 | RB14 | DOOR HANDLE | 268 | SS400 | 6 | 0.15 | 0.9 | 0 | 6 | [55 empty] | #VALUE! |  |  |  | PMC | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26
Shape | DR070R-DR071-02B | L100x75x10 | ANGLE | 1490 | SS400 | 6 | 19.2 | 115.2 | 6 | 0 | [35 empty] | 6 | [19 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26
Shape | DR070R-DR071-02A | L100x75x10 | ANGLE | 880 | SS400 | 6 | 11.3 | 67.8 | 6 | 0 | [35 empty] | 6 | [19 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26
Purchasing | DR070R-DR070-W02 | ZINC PLATED, 5/8" DIA. | FLAT WASHER |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-06
Purchasing | DR070R-DR070-W01 | ZINC PLATED, 1/2" DIA. | FLAT WASHER |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-02
Shape | DR070R-DR070-RB01 | RB45 | DAVIT | 1190 | SS400 | 3 | 12.7 | 38.1 | 3 | 0 | [39 empty] | 3 | [15 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26
Purchasing | DR070R-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL | CLEVIS PIN WITH REUSABLE COTTER PIN |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-05
Plate | DR070R-DR070-P04 | PL10x270 | PLATE | 467 | SS400 | 3 | 1.7 | 5.1 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | DR070R-DR070-P03 | PL10xID.46xOD.70 | DAVIT WASHER |  | SS400 | 3 | 0.3 | 0.9 | 3 | 0 | [33 empty] | 2 |  |  | 1 | [18 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | DR070R-DR070-P02 | PL10x38 | PLATE | 41 | SS400 | 60 | 0.01 | 0.6 | 60 | 0 | [33 empty] | 60 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26
Plate | DR070R-DR070-P01 | PL10x51 | PLATE | 54 | SS400 | 30 | 0.02 | 0.6 | 30 | 0 | [33 empty] | 30 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26
Purchasing | DR070R-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL | EASY GRIP HANDLE |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-04
Purchasing | DR070R-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL | SQUARE SHOUDERED SOLID ROD END BLACK OXID |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-03
Purchasing | DR070R-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE | ADHESIVE |  | SILICONE | 3 | 0.3 | 0.9 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-10
Purchasing | DR070R-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. | TADPOLE GASKET 2300°F |  | SILICA W/INCONEL CORE | 3 | 0.4 | 1.2 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-08
Purchasing | DR070R-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING | SCREWS |  | STAINLESS STEEL | 120 | 0.01 | 1.2 | 0 | 120 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-07
Plate | DR070R-DR070-126 | PL10x89 | DAVIT BRACKET | 344 | SS400 | 3 | 2.1 | 6.3 | 0 | 3 | [55 empty] | #VALUE! |  | PL10 |  | PMC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Shape | DR070R-DR070-110 | RB19 | GRAB BAR | 535 | SS400 | 3 | 1.2 | 3.6 | 3 | 0 | [38 empty] | 3 | [16 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26
Plate | DR070R-DR070-09 | PL10x152 | PLATE | 229 | SS400 | 3 | 2.7 | 8.1 | 3 | 0 | [33 empty] | 1 |  |  | 2 | [18 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | DR070R-DR070-04B | PL1.5x227 | LINER PLATE | 819 | SS400 | 6 | 2.2 | 13.2 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070R-DR070-04A | PL1.5x227 | LINER PLATE | 1429 | SS400 | 6 | 3.8 | 22.8 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070R-DR070-01 | PL10x940 | PLATE | 1549 | SS400 | 3 | 40.4 | 121.2 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Purchasing | DR070L-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING | SCREWS |  | STAINLESS STEEL | 120 | 0.01 | 1.2 | 0 | 120 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-07
Purchasing | DR070L-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE | ADHESIVE |  | SILICONE | 3 | 0.1 | 0.3 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-10
Purchasing | DR070L-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. | TADPOLE GASKET 1000°F |  | SILICA W/INCONEL CORE | 3 | 0.12 | 0.36 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-09
Purchasing | DR070L-DR071-30 | M10 | HEX NUT |  | SS400 | 48 | 0.01 | 0.48 | 0 | 48 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-21
Plate | DR070L-DR071-29 | PL1.5 x OD76 x ID11 | WASHER |  | SS400 | 48 | 0.07 | 3.36 | 48 | 0 | [53 empty] | 48 |  | #VALUE! |  | PL1.5 |  | MCC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26
Shape | DR070L-DR071-28 | Ø10(M10) | STUD BOLT | 108 | SS400 | 24 | 0.15 | 3.6 | 24 | 0 | [47 empty] | 24 | [7 empty] | #VALUE! |  |  |  | PMC
Plate | DR070L-DR071-27 | PL1.5x683 | LINER PLATE | 1293 | SS400 | 3 | 10.4 | 31.2 | 3 | 0 | [47 empty] | 3 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26
Plate | DR070L-DR071-26B | PL1.5x140 | LINER PLATE | 1308 | SS400 | 6 | 2 | 12 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070L-DR071-26A | PL1.5x140 | LINER PLATE | 699 | SS400 | 6 | 1.2 | 7.2 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070L-DR071-22 | PL10x75 | FLATBAR | 236 | SS400 | 12 | 1.4 | 16.8 | 12 | 0 | [33 empty] | 12 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26
Plate | DR070L-DR071-21 | PL10x75 | FLATBAR | 737 | SS400 | 9 | 4.4 | 39.6 | 9 | 0 | [33 empty] | 9 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26
Plate | DR070L-DR071-20 | PL10x800 | PLATE | 1410 | SS400 | 3 | 88.5 | 265.5 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Purchasing | DR070L-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) | EYE BOLT/2NUTS/1PW |  | - | 3 | 0.3 | 0.9 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-01
Shape | DR070L-DR071-113 | RB14 | DOOR HANGER | 350 | SS400 | 3 | 0.4 | 1.2 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | PMC | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26
Plate | DR070L-DR071-112 | PL10x65 | GUSSET PLATE | 83 | SS400 | 60 | 0.4 | 24 | 60 | 0 | [33 empty] | 60 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26
Shape | DR070L-DR071-111 | RB14 | DOOR HANDLE | 268 | SS400 | 6 | 0.15 | 0.9 | 0 | 6 | [55 empty] | #VALUE! |  |  |  | PMC | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26
Shape | DR070L-DR071-02B | L100x75x10 | ANGLE | 1490 | SS400 | 6 | 19.2 | 115.2 | 6 | 0 | [35 empty] | 6 | [19 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26
Shape | DR070L-DR071-02A | L100x75x10 | ANGLE | 880 | SS400 | 6 | 11.3 | 67.8 | 6 | 0 | [35 empty] | 6 | [19 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26
Purchasing | DR070L-DR070-W02 | ZINC PLATED, 5/8" DIA. | FLAT WASHER |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-06
Purchasing | DR070L-DR070-W01 | ZINC PLATED, 1/2" DIA. | FLAT WASHER |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-02
Shape | DR070L-DR070-RB01 | RB45 | DAVIT | 1190 | SS400 | 3 | 12.7 | 38.1 | 3 | 0 | [39 empty] | 3 | [15 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26
Purchasing | DR070L-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL | CLEVIS PIN WITH REUSABLE COTTER PIN |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-05
Plate | DR070L-DR070-P04 | PL10x270 | PLATE | 467 | SS400 | 3 | 1.7 | 5.1 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | DR070L-DR070-P03 | PL10xID.46xOD.70 | DAVIT WASHER |  | SS400 | 3 | 0.3 | 0.9 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | DR070L-DR070-P02 | PL10x38 | PLATE | 41 | SS400 | 60 | 0.01 | 0.6 | 60 | 0 | [33 empty] | 60 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26
Plate | DR070L-DR070-P01 | PL10x51 | PLATE | 54 | SS400 | 30 | 0.02 | 0.6 | 30 | 0 | [33 empty] | 30 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26
Purchasing | DR070L-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL | EASY GRIP HANDLE |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-04
Purchasing | DR070L-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL | SQUARE SHOUDERED SOLID ROD END BLACK OXID |  | - | 30 | 0.01 | 0.3 | 0 | 30 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-03
Purchasing | DR070L-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE | ADHESIVE |  | SILICONE | 3 | 0.3 | 0.9 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-10
Purchasing | DR070L-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. | TADPOLE GASKET 2300°F |  | SILICA W/INCONEL CORE | 3 | 0.4 | 1.2 | 0 | 3 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-08
Purchasing | DR070L-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING | SCREWS |  | STAINLESS STEEL | 120 | 0.01 | 1.2 | 0 | 120 | [55 empty] | #VALUE! |  |  |  | KHO | DCC25-U284-0017-VTP-07
Plate | DR070L-DR070-126 | PL10x89 | DAVIT BRACKET | 344 | SS400 | 3 | 2.1 | 6.3 | 0 | 3 | [55 empty] | #VALUE! |  | PL10 |  | PMC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Shape | DR070L-DR070-110 | RB19 | GRAB BAR | 535 | SS400 | 3 | 1.2 | 3.6 | 3 | 0 | [38 empty] | 3 | [16 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26
Plate | DR070L-DR070-09 | PL10x152 | PLATE | 229 | SS400 | 3 | 2.7 | 8.1 | 3 | 0 | [36 empty] | 3 | [18 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | DR070L-DR070-04B | PL1.5x227 | LINER PLATE | 819 | SS400 | 6 | 2.2 | 13.2 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070L-DR070-04A | PL1.5x227 | LINER PLATE | 1429 | SS400 | 6 | 3.8 | 22.8 | 6 | 0 | [47 empty] | 6 | [7 empty] | #VALUE! |  | PL1.5 |  | PMC | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26
Plate | DR070L-DR070-01 | PL10x940 | PLATE | 1549 | SS400 | 3 | 40.4 | 121.2 | 3 | 0 | [33 empty] | 3 | [21 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26
Plate | COT-6-SH-11 | PL6*1249 | CASING PLATE | 9785 | SS400 | 1 | 573.8 | 573.8 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COT-6-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
| COT-6-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-6-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-6-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COT-6-D-2 | 3" SCH.40 | PIPE | 315 | A-312 TP.304 | 6 | 3.5 | 21 | 6 | 0 | [25 empty] | 6 | [29 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0016-VTC-30 |  | U284-07-CP504 | 6 | 2026-04-21
Shape | COT-6-CY-43 | [200*80*7.5*11 | CHANNEL | 558 | SS400 | 2 | 12.1 | 24.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COT-6-CY-42 | [200*80*7.5*11 | CHANNEL | 553 | SS400 | 2 | 12.6 | 25.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COT-6-CY-41 | [200*80*7.5*11 | CHANNEL | 558 | SS400 | 5 | 12.1 | 60.5 | 5 | 0 | 5 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 5 | 2026-04-22
Shape | COT-6-CY-40 | [200*80*7.5*11 | CHANNEL | 553 | SS400 | 5 | 12.6 | 63 | 5 | 0 | 5 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 5 | 2026-04-22
Shape | COT-6-C-2 | [200*80*7.5*11 | CHANNEL | 9785 | SS400 | 1 | 237.7 | 237.7 | 1 | 0 | 1 | [21 empty] | 1 | [32 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27
Shape | COT-6-A-3 | L75*75*6 | ANGLE | 9785 | SS400 | 1 | 67 | 67 | 1 | 0 | [8 empty] | 1 | [17 empty] | 0.38835 | [28 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COT-5-SH-12 | PL6*2006 | CASING PLATE | 3085 | SS400 | 1 | 291.5 | 291.5 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
| COT-5-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-5-M-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-5-G-8002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-5-G-8001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COT-5-G-4 | PL6*124 | PLATE | 2006 | SS400 | 1 | 11.7 | 11.7 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COT-5-G-3 | PL12*200 | PLATE | 1448 | SS400 | 2 | 27.2 | 54.4 | 2 | 0 | [24 empty] | 2 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16
Shape | COT-5-CY-50 | [200*80*7.5*11 | CHANNEL | 1448 | SS400 | 3 | 34.9 | 104.7 | 3 | 0 | 3 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 3 | 2026-04-22
Shape | COT-5-CY-47 | [200*80*7.5*11 | CHANNEL | 3079 | SS400 | 1 | 73.6 | 73.6 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COT-5-CY-35 | [200*80*7.5*11 | CHANNEL | 3079 | SS400 | 1 | 73.6 | 73.6 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Plate | COT-4-SH-13 | PL6*2006 | CASING PLATE | 3350 | SS400 | 1 | 316.6 | 316.6 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
| COT-4-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-4-M-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-4-G-8003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Purchasing | COT-4-G-5 | PL3*124 | GASKET | 2006 | NON-METALLIC | 2 | 0.4 | 0.8 | 0 | 2 | [55 empty] | #VALUE! |  |  |  | KHO
Plate | COT-4-G-4 | PL6*124 | PLATE | 2006 | SS400 | 2 | 11.7 | 23.4 | 2 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16
Plate | COT-4-G-3 | PL12*200 | PLATE | 1448 | SS400 | 2 | 27.2 | 54.4 | 2 | 0 | [24 empty] | 2 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16
Shape | COT-4-CY-50 | [200*80*7.5*11 | CHANNEL | 1448 | SS400 | 3 | 34.9 | 104.7 | 3 | 0 | 2 | [13 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 3 | 2026-04-22
Shape | COT-4-CY-49 | [200*80*7.5*11 | CHANNEL | 3338 | SS400 | 1 | 79.5 | 79.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COT-4-CY-48 | [200*80*7.5*11 | CHANNEL | 3338 | SS400 | 1 | 79.9 | 79.9 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Plate | COT-3-SH-12 | PL6*2006 | CASING PLATE | 3085 | SS400 | 1 | 291.5 | 291.5 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
| COT-3-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-3-M-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-3-G-8002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-3-G-8001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COT-3-G-4 | PL6*124 | PLATE | 2006 | SS400 | 1 | 11.7 | 11.7 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COT-3-G-3 | PL12*200 | PLATE | 1448 | SS400 | 2 | 27.2 | 54.4 | 2 | 0 | [24 empty] | 2 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16
Shape | COT-3-CY-50 | [200*80*7.5*11 | CHANNEL | 1448 | SS400 | 3 | 34.9 | 104.7 | 3 | 0 | [14 empty] | 3 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 3 | 2026-04-22
Shape | COT-3-CY-47 | [200*80*7.5*11 | CHANNEL | 3079 | SS400 | 2 | 73.6 | 147.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Plate | COT-2-SH-10 | PL6*3422 | CASING PLATE | 9785 | SS400 | 1 | 759.1 | 759.1 | 1 | 0 | [6 empty] | 4 | [48 empty] | #VALUE! | A B1 B2 C | PL6 | Thừa 3 | MCC |  |  | chi tiết chia nối | 1
Plate | COT-2-PY-3 | PL28*206 | PLATE | 357 | SM490 | 8 | 8.7 | 69.6 | 8 | 0 | [41 empty] | 8 | [13 empty] | #VALUE! |  | PL28 |  | MCC | U284-14-CP010-1 |  | U284-07-CP017 | 8 | 2026-04-16
Plate | COT-2-P-8004 | PL10*188 | PLATE | 824 | SM490 | 8 | 12.1 | 96.8 | 8 | 0 | [30 empty] | 8 | [24 empty] | #VALUE! |  | PL10 |  | MCC | U284-10-CP005-2 |  | U284-07-CP037 | 8 | 2026-07-09
| COT-2-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-2-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-2-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COT-2-HY-1 | H400*200*8*13 | H-BEAM | 9823 | SS400 | 1 | 642.9 | 642.9 | 1 | 0 | [10 empty] | 1 | [44 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0043-3 |  | U284-07-CP517 | 1 | 2026-04-21
Plate | COT-2-GYZ-1 | PL38*239 | LIFTING LUG "A" | 229 | SM490 | 4 | 14 | 56 | 4 | 0 | [11 empty] | 3 | 1 | [42 empty] | #VALUE! |  | PL38 |  | MCC | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16
Plate | COT-2-G-1 | PL38*400 | PLATE | 1312 | SM490 | 4 | 156.5 | 626 | 4 | 0 | [11 empty] | 1 | [18 empty] | 2 | [19 empty] | 1 |  |  |  |  | #VALUE! |  | PL38 |  | MCC | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16
Shape | COT-2-D-2 | 3" SCH.40 | PIPE | 315 | A-312 TP.304 | 6 | 3.5 | 21 | 6 | 0 | [25 empty] | 6 | [29 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0016-VTC-30 |  | U284-07-CP504 | 6 | 2026-04-21
Shape | COT-2-CY-46 | [200*80*7.5*11 | CHANNEL | 474 | SS400 | 7 | 9.6 | 67.2 | 7 | 0 | 2 | [13 empty] | 5 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COT-2-CY-45 | [200*80*7.5*11 | CHANNEL | 282 | SS400 | 7 | 4.9 | 34.3 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COT-2-CY-44 | [200*80*7.5*11 | CHANNEL | 806 | SS400 | 7 | 17.7 | 123.9 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COT-2-C-4 | [200*80*7.5*11 | CHANNEL | 378 | SS400 | 14 | 9.2 | 128.8 | 14 | 0 | 9 | [13 empty] | 5 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 14 | 2026-04-22
Shape | COT-2-BY-7 | BH900*400*25*38 | BUILT-UP H-BEAM | 9747 | SM490 | 2 | 3891.3 | 7782.6 | 2 | 0 | [31 empty] | 2 | [23 empty] | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | COT-2-AY-4 | L150*150*12 | ANGLE | 9347 | SS400 | 2 | 255.1 | 510.2 | 2 | 0 | [12 empty] | 2 | [42 empty] | #VALUE! |  |  |  | MCC | U284-02A-CP504-2 DCC25-U284-0016-VTC-9 |  | U284-07-CP520 | 2 | 2026-04-21
Shape | COT-2-AY-3 | L150*150*12 | ANGLE | 2032 | SS400 | 2 | 55.5 | 111 | 2 | 0 | [12 empty] | 2 | [42 empty] | #VALUE! |  |  |  | MCC | U284-02A-CP504-2 DCC25-U284-0016-VTC-9 |  | U284-07-CP520 | 2 | 2026-04-21
Shape | COT-2-A-21 | L90*90*6 | ANGLE | 9785 | SS400 | 2 | 81 | 162 | 2 | 0 | [11 empty] | 2 | [15 empty] | 4 | [27 empty] | #VALUE! | AB |  | Thừa 4 | MCC |  |  | chi tiết chia nối | 2
Plate | COT-1-SH-9 | PL6*2773 | CASING PLATE | 9785 | SS400 | 1 | 1276.2 | 1276.2 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COT-1-P-8005 | PL10*152 | PLATE | 152 | SS400 | 2 | 1.8 | 3.6 | 2 | 0 | [53 empty] | 2 |  | #VALUE! |  | PL10 |  | MCC | U284-701-CP009-OS-1 |  | U284-09A-CP015 | 2 | 2026-06-16
Plate | COT-1-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
Plate | COT-1-P-29 | PL6*78 | PLATE | 78 | A387 GR.11 CL.2 | 2 | 0.2 | 0.4 | 2 | 0 | [22 empty] | 2 | [32 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP020 | 2 | 2026-04-16
| COT-1-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-1-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-1-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COT-1-D-7-1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [21 empty] | 2 | [33 empty] | #VALUE! |  |  | Thừa 2
Shape | COT-1-D-7 | 3" SCH.40 | PIPE | 62 | A355-P11 | 2 | 0.7 | 1.4 | 2 | 0 | [21 empty] | 2 | [33 empty] | #VALUE! |  |  |  | MCC | DCC26-U284-0052-VTC-4 |  | U284-07-CP506 | 2 | 2026-04-21
Shape | COT-1-D-2 | 3" SCH.40 | PIPE | 315 | A-312 TP.304 | 6 | 3.5 | 21 | 6 | 0 | [25 empty] | 6 | [29 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0016-VTC-30 |  | U284-07-CP504 | 6 | 2026-04-21
Shape | COT-1-CY-39 | [200*80*7.5*11 | CHANNEL | 299 | SS400 | 7 | 6.5 | 45.5 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COT-1-CY-38 | [200*80*7.5*11 | CHANNEL | 1747 | SS400 | 7 | 39.6 | 277.2 | 7 | 0 | 4 | [13 empty] | 3 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COT-1-CY-37 | [200*80*7.5*11 | CHANNEL | 581 | SS400 | 7 | 14 | 98 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COT-1-C-1 | [200*80*7.5*11 | CHANNEL | 9785 | SS400 | 2 | 237.7 | 475.4 | 2 | 0 | 2 | [21 empty] | 2 | [32 empty] | #VALUE! |  |  | Thừa 2 | MCC | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 2 | 2026-06-27
Shape | COT-1-A-3 | L75*75*6 | ANGLE | 9785 | SS400 | 1 | 67 | 67 | 1 | 0 | [8 empty] | 1 | [25 empty] | 0.38835 | [20 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | CO-SP-4-P-25 | PL12*200 | PLATE | 951 | A387 GR.11 CL.2 | 4 | 17.9 | 71.6 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16
Plate | CO-SP-4-P-24 | PL12*78 | PLATE 758 | 951 | A387 GR.11 CL.2 | 8 | 7 | 56 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16
Plate | CO-RC-3-SX-3 | PL2.6*51 | FIELD RETAINER CLIP | 103 | SS400 | 8 | 0.1 | 0.8 | 0 | 8 | [55 empty] | #VALUE! |  | PL2.6 |  | PMC | U284-03A-CP019-1 |  | U284-07-CP031 | 8 | 2026-05-07
Plate | CO-RC-2-SX-2 | PL2.6*51 | FIELD RETAINER CLIP | 103 | SS400 | 2 | 0.1 | 0.2 | 0 | 2 | [55 empty] | #VALUE! |  | PL2.6 |  | PMC | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 2 | 2026-04-16
Plate | CO-RC-1-SX-1 | PL2.6*51 | FIELD RETAINER CLIP | 103 | SS400 | 10 | 0.1 | 1 | 0 | 10 | [55 empty] | #VALUE! |  | PL2.6 |  | PMC | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 10 | 2026-04-16
Plate | COR-5-SH-4 | PL6*1136 | CASING PLATE | 12233 | SS400 | 1 | 652.3 | 652.3 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COR-5-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
| COR-5-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-5-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COR-5-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 1 | 0.1 | 0.1 | 1 | 0 | [53 empty] | 1 |  | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07
Plate | COR-5-G-17 | PL6*127 | PLATE | 127 | SS400 | 7 | 0.6 | 4.2 | 7 | 0 | [6 empty] | 7 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 7 | 2026-04-16
Shape | COR-5-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 1 | 0.5 | 0.5 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21
Shape | COR-5-D-6 | 2" SCH.40 | PIPE | 137 | A-106 Gr.B | 7 | 0.7 | 4.9 | 7 | 0 | [46 empty] | 7 | [8 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 7 | 2026-04-21
Shape | COR-5-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 4 | 4.9 | 19.6 | 4 | 0 | [43 empty] | 4 | [11 empty] | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21
Shape | COR-5-CY-3 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 8 | 6.2 | 49.6 | 8 | 0 | 8 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22
Shape | COR-5-CY-27 | [200*80*7.5*11 | CHANNEL | 57 | SS400 | 8 | 1.3 | 10.4 | 8 | 0 | 6 | [13 empty] | 2 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22
Shape | COR-5-CY-26 | [200*80*7.5*11 | CHANNEL | 722 | SS400 | 8 | 14.7 | 117.6 | 8 | 0 | 5 | [13 empty] | 3 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22
Shape | COR-5-CY-24 | [200*80*7.5*11 | CHANNEL | 12246 | SS400 | 1 | 296.8 | 296.8 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-5-CY-22 | [200*80*7.5*11 | CHANNEL | 12246 | SS400 | 1 | 296.8 | 296.8 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-5-AY-2 | L75*75*6 | ANGLE | 1089 | SS400 | 1 | 7.5 | 7.5 | 1 | 0 | [8 empty] | 1 | [46 empty] | #VALUE! |  |  |  | MCC | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22
Shape | COR-5-A-9 | L90*90*10 | ANGLE | 1262 | SS400 | 1 | 16.8 | 16.8 | 1 | 0 | [11 empty] | 1 | [26 empty] | 1 | [16 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22
Shape | COR-5-A-5 | L100*100*10 | ANGLE | 12246 | SS400 | 1 | 182.6 | 182.6 | 1 | 0 | [9 empty] | 0.85742 | 0.1438 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COR-4-SH-5 | PL6*1136 | CASING PLATE | 12360 | SS400 | 1 | 603 | 603 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COR-4-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
| COR-4-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-4-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COR-4-H-7 | H194*150*6*9 | H-BEAM | 2187 | SS400 | 1 | 65.4 | 65.4 | 1 | 0 | [10 empty] | 1 | [44 empty] | #VALUE! |  |  |  | MCC | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21
Plate | COR-4-G-9 | PL6*360 | PLATE | 360 | SS400 | 2 | 3 | 6 | 2 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16
Plate | COR-4-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 2 | 0.1 | 0.2 | 2 | 0 | [21 empty] | 2 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07
Plate | COR-4-G-17 | PL6*127 | PLATE | 127 | SS400 | 11 | 0.6 | 6.6 | 11 | 0 | [6 empty] | 11 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 11 | 2026-04-16
Shape | COR-4-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 2 | 0.5 | 1 | 0 | 2 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21
Shape | COR-4-D-6 | 2" SCH.40 | PIPE | 137 | A-106 Gr.B | 11 | 0.7 | 7.7 | 11 | 0 | [21 empty] | 11 | [33 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 11 | 2026-04-21
Shape | COR-4-D-5 | 8" SCH.40 | PIPE | 309 | A-106 Gr.B | 2 | 13.1 | 26.2 | 2 | 0 | [28 empty] | 2 | [26 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0034-VTC-10 |  | U284-07-CP511 | 2 | 2026-04-21
Shape | COR-4-D-4 | 4" SCH.40 | PIPE | 309 | A-312 TP.304 | 1 | 4.9 | 4.9 | 1 | 0 | [25 empty] | 2 | [29 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-14 |  | U284-07-CP509 | 2 | 2026-04-21
Shape | COR-4-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 3 | 4.9 | 14.7 | 3 | 0 | [43 empty] | 3 | [11 empty] | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 3 | 2026-04-21
Shape | COR-4-D-11 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 1 | 4.9 | 4.9 | 1 | 0 | [31 empty] | 1 | [23 empty] | #VALUE! |  |  |  | MCC | U284-01-CP503-1 |  | U284-07-CP525 | 1 | 2026-05-07
Shape | COR-4-CY-4 | [200*80*7.5*11 | CHANNEL | 1089 | SS400 | 1 | 25.6 | 25.6 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-4-CY-3 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 6 | 6.2 | 37.2 | 6 | 0 | 6 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22
Shape | COR-4-CY-27 | [200*80*7.5*11 | CHANNEL | 57 | SS400 | 6 | 1.3 | 7.8 | 6 | 0 | 6 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22
Shape | COR-4-CY-26 | [200*80*7.5*11 | CHANNEL | 722 | SS400 | 6 | 14.7 | 88.2 | 6 | 0 | 6 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22
Shape | COR-4-CY-25 | [200*80*7.5*11 | CHANNEL | 10127 | SS400 | 1 | 244.5 | 244.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-4-CY-23 | [200*80*7.5*11 | CHANNEL | 10127 | SS400 | 1 | 244.5 | 244.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-4-CY-2 | [200*80*7.5*11 | CHANNEL | 1089 | SS400 | 2 | 25.6 | 51.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COR-4-A-6 | L100*100*10 | ANGLE | 12373 | SS400 | 1 | 184.5 | 184.5 | 1 | 0 | [9 empty] | 0.84862 | 0.15259 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-4-A-18 | L90*90*10 | ANGLE | 1262 | SS400 | 1 | 16.8 | 16.8 | 1 | 0 | [11 empty] | 1 | [16 empty] | 1 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COR-4-A-12 | L100*100*7 | ANGLE | 152 | SS400 | 2 | 1.6 | 3.2 | 2 | 0 | [10 empty] | 2 | [44 empty] | #VALUE! |  |  |  | MCC | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21
Plate | COR-3-SH-3 | PL6*3422 | CASING PLATE | 24619 | SS400 | 1 | 3906.3 | 3906.3 | 1 | 0 | [6 empty] | 2 | [10 empty] | 2 | [37 empty] | #VALUE! | A1 B2 A2 B1 | PL6 | Thừa 3 | MCC |  |  | chi tiết chia nối | 1
Plate | COR-3-PY-2 | PL20*181 | PLATE | 812 | SM490 | 16 | 22.3 | 356.8 | 16 | 0 | [8 empty] | 16 | [46 empty] | #VALUE! |  | PL20 |  | MCC | U284-14-CP008 |  | U284-07-CP014 | 16 | 2026-04-16
Plate | COR-3-PY-1 | PL25*400 | PLATE | 900 | SM490 | 2 | 70.1 | 140.2 | 2 | 0 |  |  |  | 2 | [51 empty] | #VALUE! |  | PL25 |  | MCC | DCC25-U284-0002-VTC-4 U284-17A-CP009-3 DCC25-U284-0002-VTC-3 U284-09B-CP005-1 PHỤC VỤ CHUNG |  | U284-07-CP016 | 2 | 2026-04-16
Plate | COR-3-P-6 | PL10*184 | PLATE | 612 | SS400 | 16 | 8.8 | 140.8 | 16 | 0 | [16 empty] | 12 |  |  |  | 4 | [34 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 16 | 2026-04-16
Plate | COR-3-P-50 | PL19*57 | PLATE | 198 | A387 GR.11 CL.2 | 5 | 1.7 | 8.5 | 5 | 0 | [33 empty] | 5 | [21 empty] | #VALUE! |  | PL19 |  | MCC | U284-07-CP011-1 |  | U284-05A-CP015 | 5 | 2026-05-13
Plate | COR-3-P-49 | PL19*198 | PLATE | 270 | A387 GR.11 CL.2 | 5 | 7.9 | 39.5 | 5 | 0 | [33 empty] | 5 | [21 empty] | #VALUE! |  | PL19 |  | MCC | U284-07-CP011-1 |  | U284-05A-CP015 | 5 | 2026-05-13
Plate | COR-3-P-4 | PL8*156 | PLATE | 182 | SS400 | 37 | 1.7 | 62.9 | 37 | 0 | [23 empty] | 37 | [31 empty] | #VALUE! |  | PL8 |  | MCC | DCC25-U284-0034-VTC-3 |  | U284-07-CP022 | 37 | 2026-04-16
Plate | COR-3-P-33 | PL10*152 | PLATE | 229 | SS400 | 1 | 2.7 | 2.7 | 1 | 0 | [25 empty] | 1 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 1 | 2026-04-16
Plate | COR-3-P-32 | PL10*111 | PLATE | 152 | SS400 | 2 | 1.3 | 2.6 | 2 | 0 | [25 empty] | 2 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 2 | 2026-04-16
Plate | COR-3-P-3 | PL10*20 | BACKING BAR | 162 | SM490 | 32 | 0.3 | 9.6 | 32 | 0 | [19 empty] | 32 | [35 empty] | #VALUE! |  | PL10 |  | MCC | U284-10-CP005-1 |  | U284-07-CP006 | 32 | 2026-04-16
Plate | COR-3-P-2 | PL60*127 | PLATE | 220 | SM490 | 4 | 13.2 | 52.8 | 4 | 0 |  |  |  |  | 4 | [50 empty] | #VALUE! |  | PL60 |  | MCC | U284-14-CP014-1 |  | U284-07-CP021 | 4 | 2026-04-16
Plate | COR-3-P-1 | PL60*127 | PLATE | 1000 | SM490 | 2 | 59.8 | 119.6 | 2 | 0 |  |  |  |  | 2 | [50 empty] | #VALUE! |  | PL60 |  | MCC | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16
| COR-3-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-3-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-3-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COR-3-GZ-8000 | PL12*76 | PLATE | 102 | SS400 | 1 | 0.7 | 0.7 | 1 | 0 | [7 empty] | 1 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL12 | Thừa 1 | PMC | VẬT TƯ TẬN DỤNG |  | U284-07-CP026 | 1 | 2026-05-07
Plate | COR-3-GZ-1 | PL60*500 | BASE PLATE | 1000 | SM490 | 2 | 235.5 | 471 | 2 | 0 | [7 empty] | 2 | [47 empty] | #VALUE! |  | PL60 |  | MCC | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16
Plate | COR-3-GYZ-1 | PL38*239 | LIFTING LUG "A" | 229 | SM490 | 4 | 14 | 56 | 4 | 0 | [12 empty] | 4 | [42 empty] | #VALUE! |  | PL38 |  | MCC | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16
Shape | COR-3-CY-9 | [200*80*7.5*11 | CHANNEL | 3023 | SS400 | 9 | 69.2 | 622.8 | 9 | 0 | 9 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COR-3-CY-8 | [250*90*9*13 | CHANNEL | 3023 | SS400 | 8 | 97.9 | 783.2 | 8 | 0 |  |  | 8 | [52 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 8 | 2026-04-21
Shape | COR-3-CY-12 | [200*80*7.5*11 | CHANNEL | 1998 | SS400 | 1 | 47.5 | 47.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-3-BY-1-2 | BH900*400*25*38 | BUILT-UP H-BEAM | 33116 | SM490 | 1 | 13257.8 | 13257.8 | 1 | 0 | [15 empty] | 0.51694 | [38 empty] | 0.52 | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | COR-3-BY-1-1 | BH900*400*25*38 | BUILT-UP H-BEAM | 33116 | SM490 | 1 | 13257.8 | 13257.8 | 1 | 0 | [15 empty] | 0.96606 | [38 empty] | 0.2 | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | COR-3-A-8 | L90*90*10 | ANGLE | 3448 | SS400 | 1 | 46 | 46 | 1 | 0 | [11 empty] | 2 | [42 empty] | -1 | #VALUE! |  |  |  | MCC | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 2 | 2026-04-22
Shape | COR-3-A-22 | L90*90*10 | ANGLE | 3448 | SS400 | 1 | 46 | 46 | 1 | 0 | [28 empty] | 1 | [25 empty] | 1 | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COR-3-A-11 | L90*90*6 | ANGLE | 24619 | SS400 | 1 | 203.9 | 203.9 | 1 | 0 | [11 empty] | 1 | [43 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-3-A-10 | L90*90*6 | ANGLE | 24619 | SS400 | 1 | 203.9 | 203.9 | 1 | 0 | [11 empty] | 1 | [43 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COR-2-SH-1 | PL6*2560 | CASING PLATE | 12293 | SS400 | 1 | 1465.2 | 1465.2 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COR-2-P-7 | PL12*89 | PLATE | 141 | SS400 | 9 | 1.2 | 10.8 | 9 | 0 | [24 empty] | 9 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 9 | 2026-04-16
Plate | COR-2-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
Plate | COR-2-P-28 | PL12*64 | PLATE | 64 | A387 GR.11 CL.2 | 16 | 0.3 | 4.8 | 16 | 0 | [27 empty] | 16 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 16 | 2026-04-16
Plate | COR-2-P-27 | PL25*168 | PLATE | 305 | A387 GR.11 CL.2 | 4 | 10.1 | 40.4 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 4 | 2026-07-09
| COR-2-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-2-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COR-2-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 1 | 0.1 | 0.1 | 1 | 0 | [21 empty] | 1 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07
Plate | COR-2-G-14 | PL10*206 | PLATE | 229 | SS400 | 9 | 2.3 | 20.7 | 9 | 0 | [25 empty] | 9 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16
Plate | COR-2-G-13 | PL10*208 | PLATE | 229 | SS400 | 9 | 2.3 | 20.7 | 9 | 0 | [16 empty] | 2 | [8 empty] | 7 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16
| COR-2-G-11-8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COR-2-G-11 | PL10*228 | PLATE | 229 | SS400 | 29 | 2.7 | 78.3 | 29 | 0 | [20 empty] | 30 | [34 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 30 | 2026-04-16
Shape | COR-2-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 1 | 0.5 | 0.5 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21
Shape | COR-2-D-9 | 3" SCH.40 | PIPE | 436 | A-106 Gr.C | 48 | 4.8 | 230.4 | 48 | 0 | [28 empty] | 48 | [26 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21
Shape | COR-2-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 4 | 4.9 | 19.6 | 4 | 0 | [43 empty] | 4 | [11 empty] | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21
Shape | COR-2-CY-6 | [200*80*7.5*11 | CHANNEL | 455 | SS400 | 9 | 10 | 90 | 9 | 0 | 9 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COR-2-CY-21 | [200*80*7.5*11 | CHANNEL | 838 | SS400 | 1 | 20.3 | 20.3 | 1 | 0 | 1 | [21 empty] | 1 | [32 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27
Shape | COR-2-CY-20 | [200*80*7.5*11 | CHANNEL | 1301 | SS400 | 1 | 29.4 | 29.4 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-2-CY-18 | [200*80*7.5*11 | CHANNEL | 1864 | SS400 | 9 | 42.5 | 382.5 | 9 | 0 | 9 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COR-2-CY-16 | [200*80*7.5*11 | CHANNEL | 12306 | SS400 | 1 | 298.2 | 298.2 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-2-CY-15 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 9 | 6.2 | 55.8 | 9 | 0 | 9 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COR-2-CY-14 | [200*80*7.5*11 | CHANNEL | 12306 | SS400 | 1 | 298.2 | 298.2 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-2-CY-11 | [200*80*7.5*11 | CHANNEL | 1263 | SS400 | 2 | 29.2 | 58.4 | 2 | 0 | 1 | [13 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COR-2-B-1 | B354*100*9*13 | BUILT-UP CHANNEL | 12325 | SS400 | 1 | 537.2 | 537.2 | 1 | 0 | [48 empty] | 1 | [6 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-2-AY-1 | L75*75*6 | ANGLE | 2629 | SS400 | 1 | 18 | 18 | 1 | 0 | [8 empty] | 1 | [46 empty] | #VALUE! |  |  |  | MCC | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22
Shape | COR-2-A-17 | L90*90*10 | ANGLE | 2786 | SS400 | 1 | 37.2 | 37.2 | 1 | 0 | [11 empty] | 1 | [16 empty] | 1 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COR-2-A-1 | L100*100*10 | ANGLE | 12306 | SS400 | 1 | 183.5 | 183.5 | 1 | 0 | [9 empty] | 0.85324 | 0.14798 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COR-1-SH-2 | PL6*2560 | CASING PLATE | 12300 | SS400 | 1 | 1413.5 | 1413.5 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COR-1-P-7 | PL12*89 | PLATE | 141 | SS400 | 10 | 1.2 | 12 | 10 | 0 | [24 empty] | 10 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 10 | 2026-04-16
Plate | COR-1-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
Plate | COR-1-P-28 | PL12*64 | PLATE | 64 | A387 GR.11 CL.2 | 8 | 0.3 | 2.4 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16
Plate | COR-1-P-27 | PL25*168 | PLATE | 305 | A387 GR.11 CL.2 | 2 | 10.1 | 20.2 | 2 | 0 | [27 empty] | 2 | [27 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 2 | 2026-07-09
| COR-1-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COR-1-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COR-1-H-1 | H194*150*6*9 | H-BEAM | 2261 | SS400 | 1 | 67.6 | 67.6 | 1 | 0 | [10 empty] | 1 | [44 empty] | #VALUE! |  |  |  | MCC | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21
Plate | COR-1-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 2 | 0.1 | 0.2 | 2 | 0 | [21 empty] | 2 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07
Plate | COR-1-G-16 | PL10*208 | PLATE | 229 | SS400 | 9 | 2.3 | 20.7 | 9 | 0 | [25 empty] | 9 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16
Plate | COR-1-G-15 | PL10*207 | PLATE | 229 | SS400 | 10 | 2.3 | 23 | 10 | 0 | [25 empty] | 10 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 10 | 2026-04-16
Plate | COR-1-G-11-8001 | PL10*190 | PLATE | 229 | SS400 | 1 | 2.5 | 2.5 | 1 | 0 | [53 empty] | 1 |  | #VALUE! |  | PL10 |  | MCC | U284-01-CP003-4 |  | U284-07-CP024 | 1 | 2026-05-07
Plate | COR-1-G-11 | PL10*228 | PLATE | 229 | SS400 | 28 | 2.7 | 75.6 | 28 | 0 | [20 empty] | 29 | [34 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 29 | 2026-04-16
Shape | COR-1-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 2 | 0.5 | 1 | 0 | 2 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21
Shape | COR-1-D-9 | 3" SCH.40 | PIPE | 436 | A-106 Gr.C | 48 | 4.8 | 230.4 | 48 | 0 | [28 empty] | 48 | [26 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21
Shape | COR-1-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 4 | 4.9 | 19.6 | 4 | 0 | [43 empty] | 5 | [10 empty] | -1 | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 5 | 2026-04-21
Shape | COR-1-D-10 | 4" SCH.40 | PIPE | 309 | A-312 TP.304 | 1 | 4.9 | 4.9 | 1 | 0 | [46 empty] | 1 | [7 empty] | 1 | #VALUE! | chuyển 1 ct từ cor-1-d3 sang |  | Thừa 1 | MCC | U284-07-CP509-1 |  | U284-07-CP524 | 1 | 2026-05-07
Shape | COR-1-CY-7 | [200*80*7.5*11 | CHANNEL | 2629 | SS400 | 1 | 61.5 | 61.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-1-CY-6 | [200*80*7.5*11 | CHANNEL | 455 | SS400 | 7 | 10 | 70 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COR-1-CY-5 | [200*80*7.5*11 | CHANNEL | 1388 | SS400 | 1 | 31.4 | 31.4 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-1-CY-19 | [200*80*7.5*11 | CHANNEL | 12227 | SS400 | 1 | 295.7 | 295.7 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-1-CY-18 | [200*80*7.5*11 | CHANNEL | 1864 | SS400 | 7 | 42.5 | 297.5 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COR-1-CY-17 | [200*80*7.5*11 | CHANNEL | 10066 | SS400 | 1 | 243 | 243 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-1-CY-15 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 10 | 6.2 | 62 | 10 | 0 | 10 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 10 | 2026-04-22
Shape | COR-1-CY-13 | [200*80*7.5*11 | CHANNEL | 931 | SS400 | 2 | 21.1 | 42.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COR-1-CY-11 | [200*80*7.5*11 | CHANNEL | 1263 | SS400 | 2 | 29.2 | 58.4 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COR-1-CY-10 | [200*80*7.5*11 | CHANNEL | 3295 | SS400 | 1 | 78.5 | 78.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-1-CY-1 | [200*80*7.5*11 | CHANNEL | 2327 | SS400 | 1 | 54.2 | 54.2 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COR-1-B-2 | B354*100*9*13 | BUILT-UP CHANNEL | 12332 | SS400 | 1 | 537.5 | 537.5 | 1 | 0 | [48 empty] | 1 | [6 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-1-A-7 | L90*90*10 | ANGLE | 2786 | SS400 | 1 | 37.2 | 37.2 | 1 | 0 | [11 empty] | 1 | [26 empty] | 1 | [16 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22
Shape | COR-1-A-2 | L100*100*10 | ANGLE | 12313 | SS400 | 1 | 183.6 | 183.6 | 1 | 0 | [9 empty] | 0.85276 | 0.14846 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COR-1-A-12 | L100*100*7 | ANGLE | 152 | SS400 | 2 | 1.6 | 3.2 | 2 | 0 | [10 empty] | 2 | [44 empty] | #VALUE! |  |  |  | MCC | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21
Plate | CO-PL-9-S-5 | PL6*50 | FIELD PLATE | 51 | SS400 | 2 | 0.1 | 0.2 | 2 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16
Plate | CO-PL-8-S-9 | PL2*178 | FIELD COVER PLATE | 195 | SS400 | 2 | 0.5 | 1 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-PL-7-S-8 | PL2*178 | FIELD COVER PLATE | 214 | SS400 | 2 | 0.5 | 1 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-PL-6-S-7 | PL12*718 | FIELD PLATE | 330 | SS400 | 2 | 20.3 | 40.6 | 2 | 0 | [24 empty] | 2 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16
Plate | CO-PL-5-S-1 | PL10*64 | FIELD PLATE | 220 | SS400 | 74 | 1.1 | 81.4 | 74 | 0 | [20 empty] | 48 |  |  |  |  | 26 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 74 | 2026-04-16
Plate | CO-PL-4-S-2 | PL6*75 | FIELD PLATE | 210 | SS400 | 21 | 0.7 | 14.7 | 21 | 0 | [6 empty] | 21 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 21 | 2026-04-16
Plate | CO-PL-3-S-3 | PL10*152 | FIELD PLATE | 210 | SS400 | 14 | 2.5 | 35 | 14 | 0 | [25 empty] | 14 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 14 | 2026-04-16
Plate | CO-PL-2-S-4 | PL2.6*191 | FIELD COVER RING | 191 | SS400 | 4 | 0.5 | 2 | 4 | 0 | [49 empty] | 4 | [5 empty] | #VALUE! |  | PL2.6 |  | MCC | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 4 | 2026-04-16
Plate | CO-PL-1-S-6 | PL6*19 | FIELD PLATE | 51 | SS400 | 6 | 0 | 0 | 6 | 0 | [6 empty] | 6 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 6 | 2026-04-16
Plate | CO-PL-19-S-8000 | PL2*104 | FIELD COVER RING | 384 | SS400 | 2 | 0.5 | 1 | 0 | 2 | [55 empty] | #VALUE! |  | PL2 |  | MCC | U284-07-CP012-1 DCC25-U284-0047-2 |  | U284-07-CP029 | 2 | 2026-05-07
Plate | CO-PL-18-S-15 | PL1.5*160 | FIELD COVER RING | 161 | SS400 | 4 | 0.2 | 0.8 | 4 | 0 | [52 empty] | 3 | 1 |  | #VALUE! |  | PL1.5 |  | MCC | DCC25-U284-0006-VTC-3/1 |  | U284-07-CP002 | 4 | 2026-04-16
Plate | CO-PL-17-S-9 | PL2*178 | FIELD COVER PLATE | 195 | SS400 | 8 | 0.5 | 4 | 8 | 0 | [34 empty] | 8 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 8 | 2026-04-16
Plate | CO-PL-16-S-11 | PL2*157 | FIELD COVER PLATE | 527 | SS400 | 4 | 0.7 | 2.8 | 4 | 0 | [33 empty] | 4 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16
Plate | CO-PL-15-S-10 | PL2*157 | FIELD COVER PLATE | 527 | SS400 | 4 | 0.7 | 2.8 | 4 | 0 | [33 empty] | 4 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16
Plate | CO-PL-14-S-8 | PL2*178 | FIELD COVER PLATE | 214 | SS400 | 8 | 0.5 | 4 | 8 | 0 | [33 empty] | 8 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 8 | 2026-04-16
Plate | CO-PL-13-S-13 | PL2*132 | FIELD COVER PLATE | 276 | SS400 | 8 | 0.4 | 3.2 | 8 | 0 | [34 empty] | 8 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 8 | 2026-04-16
Plate | CO-PL-12-S-12 | PL2*157 | FIELD COVER PLATE | 350 | SS400 | 4 | 0.5 | 2 | 4 | 0 | [33 empty] | 4 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16
Plate | CO-PL-11-S-4 | PL2.6*191 | FIELD COVER RING | 191 | SS400 | 1 | 0.5 | 0.5 | 1 | 0 | [49 empty] | 1 | [5 empty] | #VALUE! |  | PL2.6 |  | MCC | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 1 | 2026-04-16
Plate | CO-PL-10-S-14 | PL2.6*191 | FIELD COVER RING | 191 | SS400 | 5 | 0.5 | 2.5 | 5 | 0 | [49 empty] | 5 | [5 empty] | #VALUE! |  | PL2.6 |  | MCC | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 5 | 2026-04-16
Plate | COL-8-SH-16 | PL6*1136 | CASING PLATE | 12233 | SS400 | 1 | 652.3 | 652.3 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COL-8-P-8 | PL6*127 | PLATE | 127 | SS400 | 7 | 0.6 | 4.2 | 7 | 0 | [6 empty] | 7 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 7 | 2026-04-16
Plate | COL-8-P-34 | PL6*52 | PLATE | 52 | SS400 | 7 | 0.1 | 0.7 | 7 | 0 | [6 empty] | 7 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 7 | 2026-04-16
Plate | COL-8-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
| COL-8-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-8-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COL-8-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 1 | 0.1 | 0.1 | 1 | 0 | [21 empty] | 1 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07
Shape | COL-8-DZ-2 | 3/4" SCH.80 | PIPE | 86 | A-106 Gr.B | 1 | 0.2 | 0.2 | 1 | 0 | [31 empty] | 1 | [23 empty] | #VALUE! |  |  |  | MCC | U284-07-CP507-1 |  | U284-07-CP523 | 1 | 2026-05-07
Shape | COL-8-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 1 | 0.5 | 0.5 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21
Shape | COL-8-D-6 | 2" SCH.40 | PIPE | 137 | A-106 Gr.B | 7 | 0.7 | 4.9 | 7 | 0 | [21 empty] | 7 | [33 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 7 | 2026-04-21
Shape | COL-8-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 4 | 4.9 | 19.6 | 4 | 0 | [28 empty] | 1 | [14 empty] | 3 | [11 empty] | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21
Shape | COL-8-CY-65 | [200*80*7.5*11 | CHANNEL | 57 | SS400 | 8 | 1.3 | 10.4 | 8 | 0 | 8 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22
Shape | COL-8-CY-26 | [200*80*7.5*11 | CHANNEL | 722 | SS400 | 8 | 14.7 | 117.6 | 8 | 0 | 5 | [13 empty] | 3 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22
Shape | COL-8-CY-24 | [200*80*7.5*11 | CHANNEL | 12246 | SS400 | 1 | 296.8 | 296.8 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-8-CY-22 | [200*80*7.5*11 | CHANNEL | 12246 | SS400 | 1 | 296.8 | 296.8 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-8-CY-15 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 8 | 6.2 | 49.6 | 8 | 0 | 6 | [13 empty] | 2 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22
Shape | COL-8-AY-6 | L75*75*6 | ANGLE | 1089 | SS400 | 1 | 7.5 | 7.5 | 1 | 0 | [8 empty] | 1 | [46 empty] | #VALUE! |  |  |  | MCC | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22
Shape | COL-8-A-9 | L90*90*10 | ANGLE | 1262 | SS400 | 1 | 16.8 | 16.8 | 1 | 0 | [11 empty] | 1 | [26 empty] | 1 | [16 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22
Shape | COL-8-A-15 | L100*100*10 | ANGLE | 12246 | SS400 | 1 | 182.6 | 182.6 | 1 | 0 | [9 empty] | 0.85742 | 0.1438 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COL-7-SH-5 | PL6*1136 | CASING PLATE | 12360 | SS400 | 1 | 603 | 603 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Plate | COL-7-P-8 | PL6*127 | PLATE | 127 | SS400 | 11 | 0.6 | 6.6 | 11 | 0 | [6 empty] | 11 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 11 | 2026-04-16
Plate | COL-7-P-34 | PL6*52 | PLATE | 52 | SS400 | 11 | 0.1 | 1.1 | 11 | 0 | [6 empty] | 11 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 11 | 2026-04-16
Plate | COL-7-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
| COL-7-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-21 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-7-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COL-7-H-7 | H194*150*6*9 | H-BEAM | 2187 | SS400 | 1 | 65.4 | 65.4 | 1 | 0 | [10 empty] | 1 | [44 empty] | #VALUE! |  |  |  | MCC | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21
Plate | COL-7-G-9 | PL6*360 | PLATE | 360 | SS400 | 2 | 3 | 6 | 2 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16
Plate | COL-7-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 2 | 0.1 | 0.2 | 2 | 0 | [21 empty] | 2 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07
Shape | COL-7-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 2 | 0.5 | 1 | 0 | 2 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21
Shape | COL-7-D-6 | 2" SCH.40 | PIPE | 137 | A-106 Gr.B | 11 | 0.7 | 7.7 | 11 | 0 | [21 empty] | 6 | [24 empty] | 5 | [8 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 11 | 2026-04-21
Shape | COL-7-D-5 | 8" SCH.40 | PIPE | 309 | A-106 Gr.B | 2 | 13.1 | 26.2 | 2 | 0 | [28 empty] | 2 | [26 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0034-VTC-10 |  | U284-07-CP511 | 2 | 2026-04-21
Shape | COL-7-D-4 | 4" SCH.40 | PIPE | 309 | A-312 TP.304 | 1 | 4.9 | 4.9 | 1 | 0 | [25 empty] | 2 | [29 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-14 |  | U284-07-CP509 | 2 | 2026-04-21
Shape | COL-7-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 3 | 4.9 | 14.7 | 3 | 0 | [28 empty] | 3 | [26 empty] | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 3 | 2026-04-21
Shape | COL-7-D-11 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 1 | 4.9 | 4.9 | 1 | 0 | [31 empty] | 1 | [23 empty] | #VALUE! |  |  |  | MCC | U284-01-CP503-1 |  | U284-07-CP525 | 1 | 2026-05-07
Shape | COL-7-CY-65 | [200*80*7.5*11 | CHANNEL | 57 | SS400 | 6 | 1.3 | 7.8 | 6 | 0 | 6 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22
Shape | COL-7-CY-64 | [200*80*7.5*11 | CHANNEL | 1089 | SS400 | 1 | 25.6 | 25.6 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-7-CY-63 | [200*80*7.5*11 | CHANNEL | 1089 | SS400 | 2 | 25.6 | 51.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COL-7-CY-26 | [200*80*7.5*11 | CHANNEL | 722 | SS400 | 6 | 14.7 | 88.2 | 6 | 0 | [14 empty] | 6 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22
Shape | COL-7-CY-25 | [200*80*7.5*11 | CHANNEL | 10127 | SS400 | 1 | 244.5 | 244.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-7-CY-23 | [200*80*7.5*11 | CHANNEL | 10127 | SS400 | 1 | 244.5 | 244.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-7-CY-15 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 6 | 6.2 | 37.2 | 6 | 0 | [14 empty] | 6 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22
Shape | COL-7-A-20 | L90*90*10 | ANGLE | 1262 | SS400 | 1 | 16.8 | 16.8 | 1 | 0 | [11 empty] | 1 | [16 empty] | 1 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COL-7-A-16 | L100*100*10 | ANGLE | 12373 | SS400 | 1 | 184.5 | 184.5 | 1 | 0 | [9 empty] | 0.84862 | 0.15259 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-7-A-12 | L100*100*7 | ANGLE | 152 | SS400 | 2 | 1.6 | 3.2 | 2 | 0 | [10 empty] | 2 | [44 empty] | #VALUE! |  |  |  | MCC | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21
Plate | COL-5-SH-14 | PL6*3422 | CASING PLATE | 24619 | SS400 | 1 | 3906.3 | 3906.3 | 1 | 0 | [6 empty] | 2 | [10 empty] | 2 | [37 empty] | #VALUE! | A1 B2 A2 B1 | PL6 | Thừa 3 | MCC |  |  | chi tiết chia nối | 1
Plate | COL-5-PY-2 | PL20*181 | PLATE | 812 | SM490 | 16 | 22.3 | 356.8 | 16 | 0 | [8 empty] | 16 | [46 empty] | #VALUE! |  | PL20 |  | MCC | U284-14-CP008 |  | U284-07-CP014 | 16 | 2026-04-16
Plate | COL-5-PY-1 | PL25*400 | PLATE | 900 | SM490 | 2 | 70.1 | 140.2 | 2 | 0 |  |  |  | 2 | [51 empty] | #VALUE! |  | PL25 |  | MCC | DCC25-U284-0002-VTC-4 U284-17A-CP009-3 DCC25-U284-0002-VTC-3 U284-09B-CP005-1 PHỤC VỤ CHUNG |  | U284-07-CP016 | 2 | 2026-04-16
Plate | COL-5-P-9 | PL19*181 | PLATE | 270 | A387 GR.11 CL.2 | 5 | 7.2 | 36 | 5 | 0 | [33 empty] | 5 | [21 empty] | #VALUE! |  | PL19 |  | MCC | DCC26-U284-0052-VTC-12 |  | U284-07-CP011 | 5 | 2026-04-16
Plate | COL-5-P-6 | PL10*184 | PLATE | 612 | SS400 | 16 | 8.8 | 140.8 | 16 | 0 | [16 empty] | 16 | [38 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 16 | 2026-04-16
Plate | COL-5-P-4 | PL8*156 | PLATE | 182 | SS400 | 37 | 1.7 | 62.9 | 37 | 0 | [23 empty] | 37 | [31 empty] | #VALUE! |  | PL8 |  | MCC | DCC25-U284-0034-VTC-3 |  | U284-07-CP022 | 37 | 2026-04-16
Plate | COL-5-P-33 | PL10*152 | PLATE | 229 | SS400 | 1 | 2.7 | 2.7 | 1 | 0 | [25 empty] | 1 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 1 | 2026-04-16
Plate | COL-5-P-32 | PL10*111 | PLATE | 152 | SS400 | 2 | 1.3 | 2.6 | 2 | 0 | [25 empty] | 2 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 2 | 2026-04-16
Plate | COL-5-P-3 | PL10*20 | BACKING BAR | 162 | SM490 | 32 | 0.3 | 9.6 | 32 | 0 | [19 empty] | 32 | [35 empty] | #VALUE! |  | PL10 |  | MCC | U284-10-CP005-1 |  | U284-07-CP006 | 32 | 2026-04-16
Plate | COL-5-P-2 | PL60*127 | PLATE | 220 | SM490 | 4 | 13.2 | 52.8 | 4 | 0 |  |  |  |  | 4 | [50 empty] | #VALUE! |  | PL60 |  | MCC | U284-14-CP014-1 |  | U284-07-CP021 | 4 | 2026-04-16
Plate | COL-5-P-10 | PL19*57 | PLATE | 181 | A387 GR.11 CL.2 | 5 | 1.5 | 7.5 | 5 | 0 | [33 empty] | 5 | [21 empty] | #VALUE! |  | PL19 |  | MCC | DCC26-U284-0052-VTC-12 |  | U284-07-CP011 | 5 | 2026-04-16
Plate | COL-5-P-1 | PL60*127 | PLATE | 1000 | SM490 | 2 | 59.8 | 119.6 | 2 | 0 |  |  |  |  | 2 | [50 empty] | #VALUE! |  | PL60 |  | MCC | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16
| COL-5-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-5-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-5-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-5-M-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-5-M-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COL-5-GZ-8000 | PL12*76 | PLATE | 102 | SS400 | 1 | 0.7 | 0.7 | 1 | 0 | [7 empty] | 1 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL12 | Thừa 1 | PMC | VẬT TƯ TẬN DỤNG |  | U284-07-CP026 | 1 | 2026-05-07
Plate | COL-5-GZ-1 | PL60*500 | BASE PLATE | 1000 | SM490 | 2 | 235.5 | 471 | 2 | 0 | [7 empty] | 2 | [47 empty] | #VALUE! |  | PL60 |  | MCC | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16
Plate | COL-5-GYZ-1 | PL38*239 | LIFTING LUG "A" | 229 | SM490 | 4 | 14 | 56 | 4 | 0 | [12 empty] | 3 | [38 empty] | 1 |  |  |  | #VALUE! |  | PL38 |  | MCC | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16
Plate | COL-5-G-8000 | PL16*152 | PLATE | 152 | SS400 | 2 | 2.9 | 5.8 | 2 | 0 | [5 empty] | 2 | [49 empty] | #VALUE! |  | PL16 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP028 | 2 | 2026-05-07
Shape | COL-5-DZ-2 | 3/4" SCH.80 | PIPE | 86 | A-106 Gr.B | 1 | 0.2 | 0.2 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC
Shape | COL-5-CY-9 | [200*80*7.5*11 | CHANNEL | 3023 | SS400 | 9 | 69.2 | 622.8 | 9 | 0 | 7 | [13 empty] | 2 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COL-5-CY-8 | [250*90*9*13 | CHANNEL | 3023 | SS400 | 8 | 97.9 | 783.2 | 8 | 0 |  |  | 8 | [52 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 8 | 2026-04-21
Shape | COL-5-CY-51 | [200*80*7.5*11 | CHANNEL | 1998 | SS400 | 1 | 47.5 | 47.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-5-BY-8-2 | BH900*400*25*38 | BUILT-UP H-BEAM | 33116 | SM490 | 1 | 13257.8 | 13257.8 | 1 | 0 | [15 empty] | 0.51694 | [38 empty] | 0.52 | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | COL-5-BY-8-1 | BH900*400*25*38 | BUILT-UP H-BEAM | 33116 | SM490 | 1 | 13257.8 | 13257.8 | 1 | 0 | [15 empty] | 0.48303 | [38 empty] | 1 | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | COL-5-A-23 | L90*90*10 | ANGLE | 3448 | SS400 | 1 | 46 | 46 | 1 | 0 | [11 empty] | 1 | [16 empty] | 1 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COL-5-A-22 | L90*90*10 | ANGLE | 3448 | SS400 | 1 | 46 | 46 | 1 | 0 | [11 empty] | 1 | [16 empty] | 1 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COL-5-A-14 | L90*90*6 | ANGLE | 24619 | SS400 | 1 | 203.9 | 203.9 | 1 | 0 | [11 empty] | 1 | [43 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-5-A-13 | L90*90*6 | ANGLE | 24619 | SS400 | 1 | 203.9 | 203.9 | 1 | 0 | [11 empty] | 1 | [43 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COL-2-SH-15 | PL6*2560 | CASING PLATE | 12293 | SS400 | 1 | 1465.3 | 1465.3 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COL-2-P-7 | PL12*89 | PLATE | 141 | SS400 | 9 | 1.2 | 10.8 | 9 | 0 | [24 empty] | 9 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 9 | 2026-04-16
Plate | COL-2-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
Plate | COL-2-P-28 | PL12*64 | PLATE | 64 | A387 GR.11 CL.2 | 16 | 0.3 | 4.8 | 16 | 0 | [27 empty] | 16 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 16 | 2026-04-16
Plate | COL-2-P-27 | PL25*168 | PLATE | 305 | A387 GR.11 CL.2 | 4 | 10.1 | 40.4 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 4 | 2026-07-09
| COL-2-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-2-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | COL-2-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 1 | 0.1 | 0.1 | 1 | 0 | [21 empty] | 1 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07
Plate | COL-2-G-14 | PL10*206 | PLATE | 229 | SS400 | 9 | 2.3 | 20.7 | 9 | 0 | [25 empty] | 9 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16
Plate | COL-2-G-13 | PL10*208 | PLATE | 229 | SS400 | 9 | 2.3 | 20.7 | 9 | 0 | [25 empty] | 9 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16
Plate | COL-2-G-11-8000 | PL10*190 | PLATE | 229 | SS400 | 1 | 2.5 | 2.5 | 1 | 0 | [53 empty] | 1 |  | #VALUE! |  | PL10 |  | MCC | U284-01-CP003-4 |  | U284-07-CP024 | 1 | 2026-05-07
Plate | COL-2-G-11 | PL10*228 | PLATE | 229 | SS400 | 29 | 2.7 | 78.3 | 29 | 0 | [20 empty] | 30 | [34 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 30 | 2026-04-16
Shape | COL-2-DZ-2 | 3/4" SCH.80 | PIPE | 86 | A-106 Gr.B | 2 | 0.2 | 0.4 | 0 | 2 | [55 empty] | #VALUE! |  |  |  | PMC
Shape | COL-2-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 1 | 0.5 | 0.5 | 0 | 1 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21
Shape | COL-2-D-9 | 3" SCH.40 | PIPE | 436 | A-106 Gr.C | 48 | 4.8 | 230.4 | 48 | 0 | [28 empty] | 48 | [26 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21
Shape | COL-2-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 4 | 4.9 | 19.6 | 4 | 0 | [28 empty] | 4 | [26 empty] | #VALUE! |  |  |  | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21
Shape | COL-2-CY-62 | [200*80*7.5*11 | CHANNEL | 838 | SS400 | 1 | 20.3 | 20.3 | 1 | 0 | 1 | [21 empty] | 1 | [32 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27
Shape | COL-2-CY-61 | [200*80*7.5*11 | CHANNEL | 1301 | SS400 | 1 | 29.4 | 29.4 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-2-CY-57 | [200*80*7.5*11 | CHANNEL | 1263 | SS400 | 2 | 29.2 | 58.4 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COL-2-CY-54 | [200*80*7.5*11 | CHANNEL | 455 | SS400 | 9 | 10 | 90 | 9 | 0 | 9 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COL-2-CY-3 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 9 | 6.2 | 55.8 | 9 | 0 | 2 | [13 empty] | 7 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COL-2-CY-18 | [200*80*7.5*11 | CHANNEL | 1864 | SS400 | 9 | 42.5 | 382.5 | 9 | 0 | 7 | [13 empty] | 2 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22
Shape | COL-2-CY-16 | [200*80*7.5*11 | CHANNEL | 12306 | SS400 | 1 | 298.2 | 298.2 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-2-CY-14 | [200*80*7.5*11 | CHANNEL | 12306 | SS400 | 1 | 298.2 | 298.2 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-2-B-3 | B354*100*9*13 | BUILT-UP CHANNEL | 12325 | SS400 | 1 | 537.2 | 537.2 | 1 | 0 | [48 empty] | 1 | [6 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-2-AY-5 | L75*75*6 | ANGLE | 2629 | SS400 | 1 | 18 | 18 | 1 | 0 | [8 empty] | 1 | [46 empty] | #VALUE! |  |  |  | MCC | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22
Shape | COL-2-A-19 | L90*90*10 | ANGLE | 2786 | SS400 | 1 | 37.2 | 37.2 | 1 | 0 | [11 empty] | 1 | [16 empty] | 1 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07
Shape | COL-2-A-1 | L100*100*10 | ANGLE | 12306 | SS400 | 1 | 183.5 | 183.5 | 1 | 0 | [9 empty] | 0.85324 | 0.14798 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COL-1-SH-2 | PL6*2560 | CASING PLATE | 12300 | SS400 | 1 | 1413.5 | 1413.5 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COL-1-P-7 | PL12*89 | PLATE | 141 | SS400 | 10 | 1.2 | 12 | 10 | 0 | [24 empty] | 10 | [30 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 10 | 2026-04-16
Plate | COL-1-P-31 | PL10*73 | PLATE | 184 | SS400 | 8 | 1 | 8 | 8 | 0 | [25 empty] | 8 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16
Plate | COL-1-P-28 | PL12*64 | PLATE | 64 | A387 GR.11 CL.2 | 8 | 0.3 | 2.4 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16
Plate | COL-1-P-27 | PL25*168 | PLATE | 305 | A387 GR.11 CL.2 | 2 | 10.1 | 20.2 | 2 | 0 | [27 empty] | 2 | [27 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 2 | 2026-07-09
| COL-1-M-9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COL-1-M-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COL-1-H-1 | H194*150*6*9 | H-BEAM | 2261 | SS400 | 1 | 67.6 | 67.6 | 1 | 0 | [10 empty] | 1 | [44 empty] | #VALUE! |  |  |  | MCC | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21
Plate | COL-1-G-28 | PL6*60 | PLATE | 60 | A-240 TP304 | 2 | 0.1 | 0.2 | 2 | 0 | [21 empty] | 2 | [33 empty] | #VALUE! |  | PL6 |  | MCC | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07
Plate | COL-1-G-16 | PL10*208 | PLATE | 229 | SS400 | 9 | 2.3 | 20.7 | 9 | 0 | [25 empty] | 9 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16
Plate | COL-1-G-15 | PL10*207 | PLATE | 229 | SS400 | 10 | 2.3 | 23 | 10 | 0 | [25 empty] | 10 | [29 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 10 | 2026-04-16
Plate | COL-1-G-11-8001 | PL10*190 | PLATE | 229 | SS400 | 1 | 2.5 | 2.5 | 1 | 0 | [53 empty] | 1 |  | #VALUE! |  | PL10 |  | MCC | U284-01-CP003-4 |  | U284-07-CP024 | 1 | 2026-05-07
Plate | COL-1-G-11 | PL10*228 | PLATE | 229 | SS400 | 28 | 2.7 | 75.6 | 28 | 0 | [20 empty] | 7 |  |  |  |  | 22 | [29 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 29 | 2026-04-16
Shape | COL-1-DZ-1 | 2" SCH.40 | PIPE | 86 | A-312 TP.304 | 2 | 0.5 | 1 | 0 | 2 | [55 empty] | #VALUE! |  |  |  | PMC | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21
Shape | COL-1-D-9 | 3" SCH.40 | PIPE | 436 | A-106 Gr.C | 48 | 4.8 | 230.4 | 48 | 0 | [28 empty] | 48 | [26 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21
Shape | COL-1-D-3 | 4" SCH.40 | PIPE | 309 | A-106 Gr.B | 4 | 4.9 | 19.6 | 4 | 0 | [28 empty] | 5 | [26 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 5 | 2026-04-21
Shape | COL-1-D-10 | 4" SCH.40 | PIPE | 309 | A-312 TP.304 | 1 | 4.9 | 4.9 | 1 | 0 | [46 empty] | 1 | [7 empty] | 1 | #VALUE! |  |  | Thừa 1 | MCC | U284-07-CP509-1 |  | U284-07-CP524 | 1 | 2026-05-07
Shape | COL-1-CY-60 | [200*80*7.5*11 | CHANNEL | 12227 | SS400 | 1 | 295.7 | 295.7 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-1-CY-59 | [200*80*7.5*11 | CHANNEL | 10066 | SS400 | 1 | 243 | 243 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-1-CY-58 | [200*80*7.5*11 | CHANNEL | 932 | SS400 | 2 | 21.1 | 42.2 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COL-1-CY-57 | [200*80*7.5*11 | CHANNEL | 1263 | SS400 | 2 | 29.2 | 58.4 | 2 | 0 | 2 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COL-1-CY-56 | [200*80*7.5*11 | CHANNEL | 3295 | SS400 | 1 | 78.5 | 78.5 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-1-CY-55 | [200*80*7.5*11 | CHANNEL | 2629 | SS400 | 1 | 61.5 | 61.5 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-1-CY-54 | [200*80*7.5*11 | CHANNEL | 455 | SS400 | 7 | 10 | 70 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COL-1-CY-53 | [200*80*7.5*11 | CHANNEL | 1388 | SS400 | 1 | 31.4 | 31.4 | 1 | 0 | 1 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-1-CY-52 | [200*80*7.5*11 | CHANNEL | 2327 | SS400 | 1 | 54.2 | 54.2 | 1 | 0 | [14 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22
Shape | COL-1-CY-3 | [200*80*7.5*11 | CHANNEL | 295 | SS400 | 10 | 6.2 | 62 | 10 | 0 | 4 | [13 empty] | 6 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 10 | 2026-04-22
Shape | COL-1-CY-18 | [200*80*7.5*11 | CHANNEL | 1864 | SS400 | 7 | 42.5 | 297.5 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COL-1-B-4 | B354*100*9*13 | BUILT-UP CHANNEL | 12332 | SS400 | 1 | 537.5 | 537.5 | 1 | 0 | [48 empty] | 1 | [6 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-1-A-7 | L90*90*10 | ANGLE | 2786 | SS400 | 1 | 37.2 | 37.2 | 1 | 0 | [11 empty] | 1 | [26 empty] | 1 | [16 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22
Shape | COL-1-A-2 | L100*100*10 | ANGLE | 12313 | SS400 | 1 | 183.6 | 183.6 | 1 | 0 | [9 empty] | 0.85276 | 0.14846 | [44 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | COL-1-A-12 | L100*100*7 | ANGLE | 152 | SS400 | 2 | 1.6 | 3.2 | 2 | 0 | [10 empty] | 2 | [44 empty] | #VALUE! |  |  |  | MCC | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21
Plate | CO-FL-9-L-89 | PL2*457 | FIELD LINER | 1219 | SS400 | 68 | 8.7 | 591.6 | 68 | 0 | [33 empty] | 61 | [19 empty] | 7 |  | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 68 | 2026-04-16
Plate | CO-FL-8-L-91 | PL2*457 | FIELD LINER | 622 | SS400 | 2 | 4.5 | 9 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-7-L-134 | PL2*457 | FIELD LINER | 1219 | SS400 | 1 | 8.7 | 8.7 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-6-L-119 | PL2*457 | FIELD LINER | 838 | SS400 | 1 | 6 | 6 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-5-L-133 | PL2*457 | FIELD LINER | 1219 | SS400 | 1 | 8.7 | 8.7 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-56-LX-17 | PL2*599.5 | FIELD LINER | 381 | SS400 | 1 | 3.6 | 3.6 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-55-LX-8 | PL2*599.5 | FIELD LINER | 381 | SS400 | 2 | 3.6 | 7.2 | 2 | 0 | [39 empty] | 2 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-54-LX-26 | PL2*599.5 | FIELD LINER | 381 | SS400 | 1 | 3.6 | 3.6 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-53-LX-16 | PL2*1219 | FIELD LINER | 381 | SS400 | 1 | 6.2 | 6.2 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-52-LX-7 | PL2*1219 | FIELD LINER | 381 | SS400 | 1 | 7.3 | 7.3 | 0 | 1 | [55 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-51-LX-25 | PL2*1219 | FIELD LINER | 381 | SS400 | 1 | 6.2 | 6.2 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-50-LX-32 | PL2*1219 | FIELD LINER | 381 | SS400 | 1 | 7.3 | 7.3 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-4-L-73 | PL2*457 | FIELD LINER | 1219 | SS400 | 20 | 8.7 | 174 | 20 | 0 | [34 empty] | 19 | [18 empty] | 1 |  | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 20 | 2026-04-16
Plate | CO-FL-49-LX-15 | PL2*457 | FIELD LINER | 381 | SS400 | 1 | 2.3 | 2.3 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-48-LX-24 | PL2*457 | FIELD LINER | 381 | SS400 | 1 | 2.3 | 2.3 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-47-LX-6 | PL2*1266.5 | FIELD LINER | 423 | SS400 | 1 | 8.4 | 8.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-46-LX-31 | PL2*1266.5 | FIELD LINER | 423 | SS400 | 1 | 8.4 | 8.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-45-LX-14 | PL2*1086.5 | FIELD LINER | 381 | SS400 | 1 | 5.4 | 5.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-44-LX-23 | PL2*1086.5 | FIELD LINER | 381 | SS400 | 1 | 5.4 | 5.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-43-LX-5 | PL2*663.5 | FIELD LINER | 423 | SS400 | 1 | 4.4 | 4.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-42-LX-30 | PL2*663.5 | FIELD LINER | 423 | SS400 | 1 | 4.4 | 4.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-41-LX-13 | PL2*970.5 | FIELD LINER | 381 | SS400 | 1 | 5.8 | 5.8 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-40-LX-22 | PL2*970.5 | FIELD LINER | 381 | SS400 | 1 | 5.8 | 5.8 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-3-L-135 | PL2*457 | FIELD LINER | 381 | SS400 | 4 | 2.7 | 10.8 | 4 | 0 | [34 empty] | 4 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16
Plate | CO-FL-39-LX-4 | PL2*836.5 | FIELD LINER | 381 | SS400 | 1 | 5 | 5 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-38-LX-29 | PL2*836.5 | FIELD LINER | 381 | SS400 | 1 | 5 | 5 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-37-LX-12 | PL2*1057 | FIELD LINER | 381 | SS400 | 1 | 6.4 | 6.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-36-LX-21 | PL2*1057 | FIELD LINER | 381 | SS400 | 1 | 6.4 | 6.4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-35-LX-3 | PL2*1238 | FIELD LINER | 381 | SS400 | 1 | 7.3 | 7.3 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-34-LX-28 | PL2*1238 | FIELD LINER | 381 | SS400 | 1 | 7.3 | 7.3 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-33-LX-11 | PL2*871 | FIELD LINER | 381 | SS400 | 1 | 5.1 | 5.1 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-32-LX-20 | PL2*871 | FIELD LINER | 381 | SS400 | 1 | 5.1 | 5.1 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-31-LX-2 | PL2*1138 | FIELD LINER | 381 | SS400 | 1 | 6.8 | 6.8 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-30-LX-27 | PL2*1138 | FIELD LINER | 381 | SS400 | 1 | 6.8 | 6.8 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-2-L-93 | PL2*457 | FIELD LINER | 1338 | SS400 | 2 | 9.2 | 18.4 | 2 | 0 | [33 empty] | 2 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-29-LX-10 | PL2*838 | FIELD LINER | 381 | SS400 | 1 | 5 | 5 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-28-LX-19 | PL2*838 | FIELD LINER | 381 | SS400 | 1 | 5 | 5 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-27-LX-9 | PL2*671.5 | FIELD LINER | 381 | SS400 | 1 | 4 | 4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-26-LX-1 | PL2*785.5 | FIELD LINER | 381 | SS400 | 2 | 4.7 | 9.4 | 2 | 0 | [39 empty] | 2 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-25-LX-18 | PL2*671.5 | FIELD LINER | 381 | SS400 | 1 | 4 | 4 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL2 |  | PMC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-24-L-206 | PL2*457 | FIELD LINER | 1143 | SS400 | 2 | 8.2 | 16.4 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-23-L-99 | PL2*457 | FIELD LINER | 981 | SS400 | 2 | 6.7 | 13.4 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-22-L-94 | PL2*457 | FIELD LINER | 1219 | SS400 | 4 | 8.5 | 34 | 4 | 0 | [34 empty] | 4 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16
Plate | CO-FL-21-L-95 | PL2*457 | FIELD LINER | 1219 | SS400 | 2 | 8.5 | 17 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-20-L-96 | PL2*457 | FIELD LINER | 1219 | SS400 | 2 | 8.5 | 17 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-1-L-92 | PL2*457 | FIELD LINER | 1167 | SS400 | 2 | 8.4 | 16.8 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-19-L-97 | PL2*457 | FIELD LINER | 1219 | SS400 | 2 | 8.5 | 17 | 2 | 0 | [34 empty] | 2 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-18-L-98 | PL2*457 | FIELD LINER | 1765 | SS400 | 2 | 12 | 24 | 2 | 0 | [33 empty] | 2 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16
Plate | CO-FL-17-L-142 | PL2*457 | FIELD LINER | 1524 | SS400 | 1 | 10.5 | 10.5 | 1 | 0 | [33 empty] | 1 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-16-L-140 | PL2*457 | FIELD LINER | 838 | SS400 | 1 | 5.4 | 5.4 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-15-L-141 | PL2*457 | FIELD LINER | 1219 | SS400 | 1 | 8.7 | 8.7 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-14-L-139 | PL2*457 | FIELD LINER | 1219 | SS400 | 1 | 8.6 | 8.6 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-13-L-138 | PL2*457 | FIELD LINER | 1219 | SS400 | 1 | 8.1 | 8.1 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-12-L-137 | PL2*457 | FIELD LINER | 1219 | SS400 | 1 | 8.7 | 8.7 | 1 | 0 | [34 empty] | 1 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-11-L-136 | PL2*457 | FIELD LINER | 1524 | SS400 | 1 | 10.5 | 10.5 | 1 | 0 | [33 empty] | 1 | [21 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16
Plate | CO-FL-10-L-90 | PL2*457 | FIELD LINER | 876 | SS400 | 4 | 6.3 | 25.2 | 4 | 0 | [34 empty] | 4 | [20 empty] | #VALUE! |  | PL2 |  | MCC | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16
Plate | CO-BF-9-PX-13 | PL2*1156 | BENT PLATE 110A | 141 | A-1011 CS | 20 | 2.5 | 50 | 20 | 0 | [47 empty] | 21 | [7 empty] | #VALUE! |  | PL2 | Thừa 1 | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 21 | 2026-05-07
Plate | CO-BF-8-PX-12 | PL2*300 | BENT PLATE 110A | 141 | A-1011 CS | 1 | 0.5 | 0.5 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07
Plate | CO-BF-7-PX-11 | PL2*344 | BENT PLATE 110B | 141 | A-1011 CS | 1 | 0.7 | 0.7 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07
Plate | CO-BF-6-PX-10 | PL2*1156 | BENT PLATE 110B | 141 | A-1011 CS | 20 | 2.5 | 50 | 20 | 0 | [47 empty] | 21 | [7 empty] | #VALUE! |  | PL2 | Thừa 1 | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 21 | 2026-05-07
Plate | CO-BF-5-PX-9 | PL2*300 | BENT PLATE 110B | 141 | A-1011 CS | 1 | 0.5 | 0.5 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07
Plate | CO-BF-4-P-47 | PL3*38 | BAFFLE | 2862 | A-1011 CS | 1 | 2.6 | 2.6 | 1 | 0 | [52 empty] | 1 |  |  | #VALUE! |  | PL3 |  | MCC | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07
Plate | CO-BF-3-P-46 | PL3*38 | BAFFLE | 2914 | A-1011 CS | 1 | 2.6 | 2.6 | 1 | 0 | [52 empty] | 1 |  |  | #VALUE! |  | PL3 |  | MCC | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07
Plate | CO-BF-30-PX-16 | PL2*1024 | BENT PLATE 110A | 141 | A-1011 CS | 1 | 2.2 | 2.2 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | MCC | U284-07-CP030-3 |  | U284-05A-CP017 | 1 | 2026-05-13
Plate | CO-BF-2-P-45 | PL3*38 | BAFFLE | 2881 | A-1011 CS | 1 | 2.6 | 2.6 | 1 | 0 | [52 empty] | 1 |  |  | #VALUE! |  | PL3 |  | MCC | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07
Plate | CO-BF-29-PX-15 | PL2*1024 | BENT PLATE 110B | 141 | A-1011 CS | 1 | 2.2 | 2.2 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | MCC | U284-07-CP030-3 |  | U284-05A-CP017 | 1 | 2026-05-13
Plate | CO-BF-28-PX-2 | PL10*9574 | BENT PLATE | 224 | A387 GR.11 CL.2 | 16 | 167.2 | 2675.2 | 16 | 0 | [38 empty] | 48 | [16 empty] | #VALUE! | 16A16B16C | PL10 | Thừa 32 | PMC |  |  | chi tiết chia nối | 16
Plate | CO-BF-28-P-41 | PL6*77 | PLATE | 137 | A387 GR.11 CL.2 | 208 | 0.5 | 104 | 208 | 0 | [27 empty] | 208 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 208 | 2026-07-09
Plate | CO-BF-27-PX-7 | PL2*835 | BENT PLATE | 255 | A-1011 CS | 1 | 3.3 | 3.3 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07
Plate | CO-BF-27-P-48 | PL2*49 | PLATE | 189 | A-1011 CS | 1 | 0.1 | 0.1 | 1 | 0 | [37 empty] | 1 | [17 empty] | #VALUE! |  | PL2 |  | MCC | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07
Plate | CO-BF-26-PX-6 | PL2*1156 | BENT PLATE | 255 | A-1011 CS | 7 | 4.6 | 32.2 | 7 | 0 | [47 empty] | 7 | [7 empty] | #VALUE! |  | PL2 |  | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 7 | 2026-05-07
Plate | CO-BF-26-P-48 | PL2*49 | PLATE | 189 | A-1011 CS | 14 | 0.1 | 1.4 | 14 | 0 | [37 empty] | 14 | [17 empty] | #VALUE! |  | PL2 |  | MCC | DCC25-U284-0046-1 |  | U284-07-CP030 | 14 | 2026-05-07
Plate | CO-BF-25-PX-8 | PL2*854 | BENT PLATE | 255 | A-1011 CS | 1 | 3.4 | 3.4 | 0 | 1 | [55 empty] | #VALUE! |  | PL2 |  | PMC | U284-07-CP030-3 |  | U284-05A-CP017 | 1 | 2026-05-13
Plate | CO-BF-25-P-48 | PL2*49 | PLATE | 189 | A-1011 CS | 2 | 0.1 | 0.2 | 2 | 0 | [37 empty] | 2 | [17 empty] | #VALUE! |  | PL2 |  | MCC | DCC25-U284-0046-1 |  | U284-07-CP030 | 2 | 2026-05-07
Plate | CO-BF-24-P-39 | PL6*96 | PLATE | 276 | A387 GR.11 CL.2 | 48 | 1.2 | 57.6 | 48 | 0 | [27 empty] | 48 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 48 | 2026-07-09
Shape | CO-BF-24-B-6 | BH300*200*8*12 | BUILT-UP H-BEAM | 9574 | A387 GR.11 CL.2 | 6 | 526.7 | 3160.2 | 6 | 0 | [40 empty] | 6 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 6
Shape | CO-BF-23-PI-1 | D4 | INSULATION PIN | 195 | TP304 | 27 | 0 | 0 | 27 | 0 | [45 empty] | 27 | [9 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 27 | 2026-05-07
Plate | CO-BF-23-P-43 | PL6*51 | PLATE | 167 | A387 GR.11 CL.2 | 28 | 0.4 | 11.2 | 28 | 0 | [27 empty] | 28 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 28 | 2026-07-09
Plate | CO-BF-23-P-40 | PL12*149 | PLATE | 276 | A387 GR.11 CL.2 | 1 | 3.4 | 3.4 | 1 | 0 | [27 empty] | 1 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 1 | 2026-05-07
Plate | CO-BF-23-P-38 | PL10*96 | PLATE | 276 | A387 GR.11 CL.2 | 4 | 2.1 | 8.4 | 4 | 0 | [27 empty] | 4 |  |  | 4 | [24 empty] | #VALUE! |  | PL10 | Thừa 4 | MCC | U284-07-CP025-2 |  | U284-05A-CP012 | 4 | 2026-05-13
Plate | CO-BF-23-P-20 | PL12*67 | PLATE | 150 | A387 GR.11 CL.2 | 2 | 0.9 | 1.8 | 2 | 0 | [27 empty] | 2 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 2 | 2026-05-07
Shape | CO-BF-23-BY-3 | BH300*200*8*12 | BUILT-UP H-BEAM | 13328 | A387 GR.11 CL.2 | 1 | 733.1 | 733.1 | 1 | 0 | [40 empty] | 1 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | CO-BF-22-PI-1 | D4 | INSULATION PIN | 195 | TP304 | 20 | 0 | 0 | 20 | 0 | [45 empty] | 20 | [9 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 20 | 2026-05-07
Plate | CO-BF-22-P-43 | PL6*51 | PLATE | 167 | A387 GR.11 CL.2 | 24 | 0.4 | 9.6 | 24 | 0 | [27 empty] | 24 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 24 | 2026-07-09
Plate | CO-BF-22-P-38 | PL10*96 | PLATE | 276 | A387 GR.11 CL.2 | 2 | 2.1 | 4.2 | 2 | 0 | [27 empty] | 2 | [27 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 2 | 2026-05-07
Shape | CO-BF-22-BY-6 | BH300*200*8*12 | BUILT-UP H-BEAM | 11000 | A387 GR.11 CL.2 | 1 | 602.8 | 602.8 | 1 | 0 | [40 empty] | 1 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | CO-BF-21-PX-3 | PL6*3241 | BENT PLATE | 490 | A387 GR.11 CL.2 | 1 | 74.1 | 74.1 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL6 |  | PMC | DCC25-U284-0046-3 |  | U284-07-CP035 | 1 | 2026-07-09
Shape | CO-BF-20-BY-5 | BC300*100*12*12 | BUILT-UP CHANNEL | 2906 | A387 GR.11 CL.2 | 1 | 130.3 | 130.3 | 1 | 0 | [48 empty] | 1 | [6 empty] | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 1
Shape | CO-BF-1-B-5 | BC250*90*12*12 | BUILT-UP CHANNEL | 9574 | A387 GR.11 CL.2 | 2 | 366.2 | 732.4 | 2 | 0 | [48 empty] | 2 | [6 empty] | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Plate | CO-BF-19-PX-5 | PL6*3241 | BENT PLATE | 490 | A387 GR.11 CL.2 | 1 | 74.1 | 74.1 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL6 |  | PMC | DCC25-U284-0046-3 |  | U284-07-CP035 | 1 | 2026-07-09
Plate | CO-BF-18-PX-4 | PL6*3144 | BENT PLATE | 490 | A387 GR.11 CL.2 | 1 | 72.1 | 72.1 | 1 | 0 | [39 empty] | 1 | [15 empty] | #VALUE! |  | PL6 |  | PMC | DCC25-U284-0046-3 |  | U284-07-CP035 | 1 | 2026-07-09
Plate | CO-BF-17-P-42 | PL6*51 | PLATE | 196 | A387 GR.11 CL.2 | 112 | 0.5 | 56 | 112 | 0 | [27 empty] | 112 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 112 | 2026-07-09
Plate | CO-BF-17-P-40 | PL12*149 | PLATE | 276 | A387 GR.11 CL.2 | 4 | 3.4 | 13.6 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 4 | 2026-05-07
Plate | CO-BF-17-P-38 | PL10*96 | PLATE | 276 | A387 GR.11 CL.2 | 16 | 2.1 | 33.6 | 16 | 0 | [27 empty] | 16 |  |  | 16 | [24 empty] | #VALUE! |  | PL10 | Thừa 16 | MCC | U284-07-CP025-2 |  | U284-05A-CP012 | 16 | 2026-05-13
Plate | CO-BF-17-P-20 | PL12*67 | PLATE | 150 | A387 GR.11 CL.2 | 8 | 0.9 | 7.2 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 8 | 2026-05-07
Shape | CO-BF-17-BY-3 | BH300*200*8*12 | BUILT-UP H-BEAM | 13328 | A387 GR.11 CL.2 | 2 | 733.1 | 1466.2 | 2 | 0 | [40 empty] | 2 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 2
Plate | CO-BF-16-P-42 | PL6*51 | PLATE | 196 | A387 GR.11 CL.2 | 96 | 0.5 | 48 | 96 | 0 | [27 empty] | 96 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 96 | 2026-07-09
Plate | CO-BF-16-P-38 | PL10*96 | PLATE | 276 | A387 GR.11 CL.2 | 8 | 2.1 | 16.8 | 8 | 0 | [27 empty] | 8 |  |  |  |  | 8 | [22 empty] | #VALUE! |  | PL10 | Thừa 8 | MCC | U284-07-CP025-2 |  | U284-05A-CP012 | 8 | 2026-05-13
Shape | CO-BF-16-BY-6 | BH300*200*8*12 | BUILT-UP H-BEAM | 11000 | A387 GR.11 CL.2 | 2 | 602.8 | 1205.6 | 2 | 0 | [40 empty] | 2 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 2
Shape | CO-BF-15-BY-4 | BC300*100*12*12 | BUILT-UP CHANNEL | 2877 | A387 GR.11 CL.2 | 2 | 129 | 258 | 2 | 0 | [48 empty] | 2 | [6 empty] | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | CO-BF-14-PI-1 | D4 | INSULATION PIN | 195 | TP304 | 27 | 0 | 0 | 27 | 0 | [45 empty] | 27 | [9 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 27 | 2026-05-07
Plate | CO-BF-14-P-43 | PL6*51 | PLATE | 167 | A387 GR.11 CL.2 | 28 | 0.4 | 11.2 | 28 | 0 | [27 empty] | 28 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 28 | 2026-07-09
Plate | CO-BF-14-P-40 | PL12*149 | PLATE | 276 | A387 GR.11 CL.2 | 1 | 3.4 | 3.4 | 1 | 0 | [27 empty] | 1 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 1 | 2026-05-07
Plate | CO-BF-14-P-38 | PL10*96 | PLATE | 276 | A387 GR.11 CL.2 | 4 | 2.1 | 8.4 | 4 | 0 | [27 empty] | 4 |  |  |  |  | 4 | [22 empty] | #VALUE! |  | PL10 | Thừa 4 | MCC | U284-07-CP025-2 |  | U284-05A-CP012 | 4 | 2026-05-13
Plate | CO-BF-14-P-20 | PL12*67 | PLATE | 150 | A387 GR.11 CL.2 | 2 | 0.9 | 1.8 | 2 | 0 | [27 empty] | 2 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0046-6 |  | U284-07-CP027 | 2 | 2026-05-07
Shape | CO-BF-14-BY-3 | BH300*200*8*12 | BUILT-UP H-BEAM | 13328 | A387 GR.11 CL.2 | 1 | 733.1 | 733.1 | 1 | 0 | [40 empty] | 1 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Shape | CO-BF-13-PI-1 | D4 | INSULATION PIN | 178 | TP304 | 20 | 0 | 0 | 20 | 0 | [45 empty] | 20 | [9 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 20 | 2026-05-07
Plate | CO-BF-13-P-43 | PL6*51 | PLATE | 167 | A387 GR.11 CL.2 | 24 | 0.4 | 9.6 | 24 | 0 | [27 empty] | 24 | [27 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0046-3 |  | U284-07-CP035 | 24 | 2026-07-09
Plate | CO-BF-13-P-38 | PL10*96 | PLATE | 276 | A387 GR.11 CL.2 | 2 | 2.1 | 4.2 | 2 | 0 | [27 empty] | 2 |  |  |  |  | 2 | [22 empty] | #VALUE! |  | PL10 | Thừa 2 | MCC | U284-07-CP025-2 |  | U284-05A-CP012 | 2 | 2026-05-13
Shape | CO-BF-13-BY-6 | BH300*200*8*12 | BUILT-UP H-BEAM | 11000 | A387 GR.11 CL.2 | 1 | 602.8 | 602.8 | 1 | 0 | [40 empty] | 1 | [14 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | CO-BF-12-P-44 | PL3*12 | BAFFLE | 35 | A-1011 CS | 1 | 0 | 0 | 1 | 0 | [53 empty] | 1 |  | #VALUE! |  | PL3 |  | MCC | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07
| CO-BF-11-M-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| CO-BF-11-M-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| CO-BF-11-M-26 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| CO-BF-11-M-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Plate | CO-BF-10-PX-14 | PL2*344 | BENT PLATE 110A | 141 | A-1011 CS | 1 | 0.7 | 0.7 | 1 | 0 | [47 empty] | 1 | [7 empty] | #VALUE! |  | PL2 |  | PMC | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07
Plate | COB-3-SH-6 | PL6*2773 | CASING PLATE | 9785 | SS400 | 1 | 1278.1 | 1278.1 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COB-3-P-30 | PL25*254 | PLATE | 254 | A387 GR.11 CL.2 | 7 | 12.7 | 88.9 | 7 | 0 | [27 empty] | 7 | [27 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 7 | 2026-07-09
| COB-3-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COB-3-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COB-3-HYZ-1 | H150*150*7*10 | H-BEAM | 265 | SS400 | 4 | 8.2 | 32.8 | 4 | 0 |  | 4 | [53 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0034-VTC-20 |  | U284-07-CP514 | 4 | 2026-04-21
Shape | COB-3-HY-3 | H294*200*8*12 | H-BEAM | 2642 | SS400 | 6 | 147.4 | 884.4 | 6 | 0 | [9 empty] | 6 | [45 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 6 | 2026-04-21
Shape | COB-3-HY-2 | H294*200*8*12 | H-BEAM | 2642 | SS400 | 1 | 147.4 | 147.4 | 1 | 0 | [9 empty] | 1 | [45 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 1 | 2026-04-21
Plate | COB-3-GZ-2 | PL16*90 | PLATE | 90 | SS400 | 8 | 0.8 | 6.4 | 8 | 0 | [16 empty] | 8 | [38 empty] | #VALUE! |  | PL16 |  | MCC | U284-14-CP006-1 |  | U284-07-CP010 | 8 | 2026-04-16
Shape | COB-3-D-8 | 6" XXS | PIPE | 123 | A53 | 7 | 9.7 | 67.9 | 7 | 0 | [18 empty] | 7 | [36 empty] | #VALUE! |  |  |  | MCC | DCC26-U284-0052-VTC-2 |  | U284-07-CP510 | 7 | 2026-04-16
Shape | COB-3-CY-31 | [250*90*9*13 | CHANNEL | 1564 | SS400 | 4 | 51.1 | 204.4 | 4 | 0 |  |  | 4 | [52 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 4 | 2026-04-21
Shape | COB-3-CY-30 | [250*90*9*13 | CHANNEL | 1389 | SS400 | 4 | 45.2 | 180.8 | 4 | 0 |  |  | 1 | [10 empty] | 3 | [41 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 4 | 2026-04-21
Shape | COB-3-CY-29 | [200*80*7.5*11 | CHANNEL | 1710 | SS400 | 2 | 39.8 | 79.6 | 2 | 0 | [14 empty] | 2 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COB-3-CY-28 | [250*90*9*13 | CHANNEL | 1710 | SS400 | 4 | 56.1 | 224.4 | 4 | 0 |  |  | 4 | [52 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 4 | 2026-04-21
Shape | COB-3-A-3 | L75*75*6 | ANGLE | 9785 | SS400 | 1 | 67 | 67 | 1 | 0 | [8 empty] | 1 | [25 empty] | 0.38835 | [20 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COB-2-SH-8 | PL6*1249 | CASING PLATE | 9785 | SS400 | 1 | 567.9 | 567.9 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
Shape | COB-2-P-5 | PL1.2*456 | 1/2" NO.16 EXPANDED | 456 | EXPANDED METAL | 1 | 0.3 | 0.3 | 1 | 0 | [42 empty] | 1 | [12 empty] | #VALUE! |  |  |  | MCC | DCC26-U284-0052-VTC-16 |  | U284-07-CP001 | 1 | 2026-04-16
Plate | COB-2-P-37 | PL6*102 | PLATE | 432 | SS400 | 2 | 2.1 | 4.2 | 2 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16
Plate | COB-2-P-36 | PL6*702 | PLATE | 676 | SS400 | 1 | 8 | 8 | 1 | 0 | [6 empty] | 1 | [48 empty] | #VALUE! |  | PL6 |  | MCC | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16
| COB-2-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COB-2-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COB-2-HYZ-1 | H150*150*7*10 | H-BEAM | 265 | SS400 | 4 | 8.2 | 32.8 | 4 | 0 |  | 4 | [53 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0034-VTC-20 |  | U284-07-CP514 | 4 | 2026-04-21
Plate | COB-2-GZ-2 | PL16*90 | PLATE | 90 | SS400 | 8 | 0.8 | 6.4 | 8 | 0 | [16 empty] | 8 | [38 empty] | #VALUE! |  | PL16 |  | MCC | U284-14-CP006-1 |  | U284-07-CP010 | 8 | 2026-04-16
Shape | COB-2-D-1 | 18" SCH. STD | PIPE | 796 | SA-106 GR.B | 1 | 83.1 | 83.1 | 1 | 0 | [18 empty] | 1 | [36 empty] | #VALUE! |  |  |  | MCC | DCC26-U284-0052-VTC-1 |  | U284-07-CP501 | 1 | 2026-04-16
Shape | COB-2-CY-36 | [200*80*7.5*11 | CHANNEL | 304 | SS400 | 7 | 6 | 42 | 7 | 0 | 6 | [13 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COB-2-CY-34 | [200*80*7.5*11 | CHANNEL | 807 | SS400 | 7 | 18.8 | 131.6 | 7 | 0 | 7 | [54 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22
Shape | COB-2-C-3 | [200*80*7.5*11 | CHANNEL | 9785 | SS400 | 1 | 237.7 | 237.7 | 1 | 0 | 1 | [21 empty] | 1 | [32 empty] | #VALUE! |  |  | Thừa 1 | MCC | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27
Shape | COB-2-A-3 | L75*75*6 | ANGLE | 9785 | SS400 | 1 | 67 | 67 | 1 | 0 | [8 empty] | 1 | [17 empty] | 0.38835 | [28 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 1
Plate | COB-1-SH-7 | PL6*3422 | CASING PLATE | 9785 | SS400 | 1 | 1577.2 | 1577.2 | 1 | 0 | [6 empty] | 2 | [48 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | COB-1-PY-3 | PL28*206 | PLATE | 357 | SM490 | 8 | 8.7 | 69.6 | 8 | 0 | [41 empty] | 8 | [13 empty] | #VALUE! |  | PL28 |  | MCC | U284-14-CP010-1 |  | U284-07-CP017 | 8 | 2026-04-16
Plate | COB-1-P-8000 | PL4*102 | PLATE | 102 | SS400 | 7 | 0.3 | 2.1 | 7 | 0 | [5 empty] | 7 | [49 empty] | #VALUE! |  | PL4 |  | MCC | U284-18-CP014-1 |  | U284-07-CP033 | 7 | 2026-05-07
Plate | COB-1-P-26 | PL10*96 | PLATE | 270 | SS400 | 16 | 2 | 32 | 16 | 0 | [16 empty] | 2 |  |  |  | 14 | [34 empty] | #VALUE! |  | PL10 |  | MCC | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 16 | 2026-04-16
Plate | COB-1-P-23 | PL8*75 | PLATE 755 | 145 | A387 GR.11 CL.2 | 8 | 0.7 | 5.6 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL8 |  | MCC | U284-07-CP036-1 |  | U284-07-CP023 | 8 | 2026-07-09
Plate | COB-1-P-22 | PL12*150 | PLATE | 200 | A387 GR.11 CL.2 | 8 | 2.8 | 22.4 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16
Plate | COB-1-P-21 | PL8*67 | PLATE 756 | 151 | A387 GR.11 CL.2 | 8 | 0.6 | 4.8 | 8 | 0 | [27 empty] | 8 | [27 empty] | #VALUE! |  | PL8 |  | MCC | U284-07-CP036-1 |  | U284-07-CP023 | 8 | 2026-07-09
Plate | COB-1-P-20 | PL12*67 | PLATE 758 | 150 | A387 GR.11 CL.2 | 16 | 0.9 | 14.4 | 16 | 0 | [27 empty] | 16 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 16 | 2026-04-16
Plate | COB-1-P-18 | PL10*75 | PLATE 753A | 220 | A387 GR.11 CL.2 | 4 | 1.3 | 5.2 | 4 | 0 | [30 empty] | 4 | [24 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0028-VTC-6 |  | U284-07-CP005 | 4 | 2026-04-16
Plate | COB-1-P-17 | PL10*67 | PLATE 754A | 230 | A387 GR.11 CL.2 | 4 | 1.2 | 4.8 | 4 | 0 | [30 empty] | 4 | [24 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0028-VTC-6 |  | U284-07-CP005 | 4 | 2026-04-16
Plate | COB-1-P-16 | PL12*200 | PLATE | 276 | A387 GR.11 CL.2 | 4 | 5.2 | 20.8 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16
Plate | COB-1-P-15 | PL12*75 | PLATE 753B | 220 | A387 GR.11 CL.2 | 4 | 1.5 | 6 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16
Plate | COB-1-P-14 | PL12*200 | PLATE | 451 | A387 GR.11 CL.2 | 4 | 8.5 | 34 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16
Plate | COB-1-P-13 | PL10*67 | PLATE | 200 | A387 GR.11 CL.2 | 20 | 1.1 | 22 | 20 | 0 | [30 empty] | 20 | [24 empty] | #VALUE! |  | PL10 |  | MCC | DCC25-U284-0028-VTC-6 |  | U284-07-CP005 | 20 | 2026-04-16
Plate | COB-1-P-12 | PL12*67 | PLATE 754C | 165 | A387 GR.11 CL.2 | 4 | 1 | 4 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16
Plate | COB-1-P-11 | PL12*67 | PLATE 754B | 230 | A387 GR.11 CL.2 | 4 | 1.4 | 5.6 | 4 | 0 | [27 empty] | 4 | [27 empty] | #VALUE! |  | PL12 |  | MCC | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16
| COB-1-M-5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
| COB-1-M-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [55 empty] | #VALUE!
Shape | COB-1-HYZ-1 | H150*150*7*10 | H-BEAM | 265 | SS400 | 4 | 8.2 | 32.8 | 4 | 0 |  | 4 | [53 empty] | #VALUE! |  |  |  | PMC | DCC25-U284-0034-VTC-20 |  | U284-07-CP514 | 4 | 2026-04-21
Shape | COB-1-HY-6 | H294*200*8*12 | H-BEAM | 3448 | SS400 | 1 | 192.3 | 192.3 | 1 | 0 | [9 empty] | 1 | [45 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 1 | 2026-04-21
Shape | COB-1-HY-5 | H294*200*8*12 | H-BEAM | 3448 | SS400 | 4 | 192.3 | 769.2 | 4 | 0 | [9 empty] | 4 | [45 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 4 | 2026-04-21
Shape | COB-1-HY-4 | H294*200*8*12 | H-BEAM | 3448 | SS400 | 2 | 192.3 | 384.6 | 2 | 0 | [9 empty] | 2 | [45 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 2 | 2026-04-21
Plate | COB-1-GZ-2 | PL16*90 | PLATE | 90 | SS400 | 8 | 0.8 | 6.4 | 8 | 0 | [16 empty] | 8 | [38 empty] | #VALUE! |  | PL16 |  | MCC | U284-14-CP006-1 |  | U284-07-CP010 | 8 | 2026-04-16
Plate | COB-1-G-1 | PL38*400 | PLATE | 1312 | SM490 | 4 | 156.5 | 626 | 4 | 0 |  |  |  | 4 | [51 empty] | #VALUE! |  | PL38 |  | MCC | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16
Shape | COB-1-CY-33 | [200*80*7.5*11 | CHANNEL | 1564 | SS400 | 2 | 36.2 | 72.4 | 2 | 0 | 1 | [13 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COB-1-CY-32 | [200*80*7.5*11 | CHANNEL | 1389 | SS400 | 2 | 32 | 64 | 2 | 0 | [14 empty] | 2 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COB-1-CY-29 | [200*80*7.5*11 | CHANNEL | 1710 | SS400 | 2 | 39.8 | 79.6 | 2 | 0 | 1 | [13 empty] | 1 | [40 empty] | #VALUE! |  |  |  | MCC | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22
Shape | COB-1-BY-2 | BH900*400*25*38 | BUILT-UP H-BEAM | 9747 | SM490 | 2 | 3891.3 | 7782.6 | 2 | 0 | [31 empty] | 2 | [23 empty] | #VALUE! |  |  |  | WTC |  |  | chi tiết chia nối | 2
Shape | COB-1-A-4 | L90*90*6 | ANGLE | 9785 | SS400 | 2 | 81 | 162 | 2 | 0 | [11 empty] | 2 | [26 empty] | 2 | [16 empty] | #VALUE! | B |  | Thừa 2 | MCC |  |  | chi tiết chia nối | 2
Plate | AIG-9-G-36 | PL8*51 | PLATE | 75 | A387 GR.11 CL.2 | 32 | 0.2 | 6.4 | 32 | 0 | [27 empty] | 64 | [27 empty] | #VALUE! |  | PL8 | Thừa 32 | MCC | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 64 | 2026-07-14
Plate | AIG-8-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-8-G-30 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-8-D-18 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 24 | [25 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 | 24 | 2026-07-14
Plate | AIG-7-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-7-G-30 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-7-D-16 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 24 | [25 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 | 24 | 2026-07-14
Plate | AIG-6-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-6-G-30 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-6-D-14 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 24 | [25 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 | 24 | 2026-07-14
Plate | AIG-5-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-5-G-30 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-5-D-12 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 46 | [25 empty] | #VALUE! | AB |  | Thừa 22 | MCC | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 22 chi tiết chia nối | 2 | 2026-07-14
Plate | AIG-4-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-4-G-31 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-4-D-15 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 48 | [25 empty] | #VALUE! | AB |  | Thừa 24 | MCC |  |  | chi tiết chia nối | 24
Plate | AIG-3-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 12 | 0.3 | 3.6 | 12 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  | Thừa 12 | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14
Plate | AIG-3-G-31 | PL12*124 | PLATE | 202 | A-240 TP304H | 12 | 1.5 | 18 | 12 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  | Thừa 12 | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14
Shape | AIG-3-D-13 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 12 | 26.7 | 320.4 | 12 | 0 | [29 empty] | 48 | [25 empty] | #VALUE! | AB |  | Thừa 36 | MCC |  |  | chi tiết chia nối | 12
Plate | AIG-2-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-2-G-31 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-2-D-19 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 48 | [25 empty] | #VALUE! | AB |  | Thừa 24 | MCC |  |  | chi tiết chia nối | 24
Plate | AIG-1-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 24 | 0.3 | 7.2 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Plate | AIG-1-G-31 | PL12*124 | PLATE | 202 | A-240 TP304H | 24 | 1.5 | 36 | 24 | 0 | [39 empty] | 24 | [15 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14
Shape | AIG-1-D-17 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 24 | 26.7 | 640.8 | 24 | 0 | [29 empty] | 48 | [25 empty] | #VALUE! | AB |  | Thừa 24 | MCC |  |  | chi tiết chia nối | 24
| AIG-14-G-33 | PL12*67 | PLATE | 67 | A-240 TP304H | 12 | 0.3 | 3.6 | 0 | 12 | [55 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14
| AIG-14-G-31 | PL12*124 | PLATE | 202 | A-240 TP304H | 12 | 1.5 | 18 | 0 | 12 | [55 empty] | #VALUE! |  |  |  | MCC | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14
| AIG-14-D-13 | 2 1/2" SCH.10S | PIPE | 5135 | A-312 TP.304 | 12 | 26.7 | 320.4 | 0 | 12 | [55 empty] | #VALUE! |  |  |  | MCC |  |  | chi tiết chia nối | 12
| AIG-13-G-34 | PL8*89 | PLATE | 89 | A387 GR.11 CL.2 | 32 | 0.5 | 16 | 32 | 0 | [27 empty] | 32 | [27 empty] | #VALUE! |  |  |  | MCC | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 32 | 2026-07-14
| AIG-13-A-25 | L75*75*6 | ANGLE | 633 | A387 GR.11 CL.2 | 32 | 4.3 | 137.6 | 0 | 32 | [55 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 32 | 2026-07-14
| AIG-13-A-24 | L75*75*6 | ANGLE | 1448 | A387 GR.11 CL.2 | 16 | 9.9 | 158.4 | 0 | 16 | [55 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 16 | 2026-07-14
| AIG-12-G-34 | PL8*89 | PLATE | 89 | A387 GR.11 CL.2 | 32 | 0.5 | 16 | 32 | 0 | [27 empty] | 32 | [27 empty] | #VALUE! |  |  |  | MCC | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 32 | 2026-07-14
| AIG-12-A-25 | L75*75*6 | ANGLE | 633 | A387 GR.11 CL.2 | 32 | 4.3 | 137.6 | 0 | 32 | [55 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 32 | 2026-07-14
| AIG-12-A-24 | L75*75*6 | ANGLE | 1448 | A387 GR.11 CL.2 | 16 | 9.9 | 158.4 | 0 | 16 | [55 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 16 | 2026-07-14
| AIG-11-A-26 | L75*75*6 | ANGLE | 51 | A387 GR.11 CL.2 | 32 | 0.3 | 9.6 | 0 | 32 | [55 empty] | #VALUE! |  |  |  | MCC | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 64 | 2026-07-14
| AIG-10-G-35 | PL8*51 | PLATE | 89 | A387 GR.11 CL.2 | 32 | 0.3 | 9.6 | 32 | 0 | [27 empty] | 64 | [27 empty] | #VALUE! |  |  | Thừa 32 | MCC | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 64 | 2026-07-14

## U284SCR
ASSEMBLY PART LIST | [54 empty] | Số Unit cần đảm bảo
Project name / Tên Dự án : ILS POWER GENERATION | [54 empty] | 1
Item Name / Tên Hạng mục : CO SCR Duct
Contract No. / Số Hợp đồng : U284 |  | U284SCR | [49 empty] | chi tiết chia nối |  |  | Số Unit
Prepared By / Chuẩn bị : Design Consultant Center | [54 empty] | 1
Document No. / Số Tài liệu : U284-07-APL-001 | [7 empty] | Rev./ Số Sửa đổi: 9 | [13 empty] | 15326.8 | #DIV/0! | [5 empty] | Date: 21-Jul-2026 |  |  |  | Content Rev. | [8 empty] | Type Fabrication | [6 empty] | Type | Document Cutting
DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC-F | DCC-X | DCC-Y | DCC-Z | DCC-J | DCC-BH | DCC | DCC |  | DCC | DCC | DCC | DCC
No. | Drawing Number | Assembly No. | Description | Part No. |  | Size | Length | Material | Q'ty | Set | T.Q'ty | U.Weight | T.Weight | Scope of Steel Work | Chung loai | Dang | Phan giao to | Ngay giao | Da nhan | Con thieu | Lam tron | Dong bo | Ti le dong bo | Fitup | Inspection | Clear | Loose Part | Total Area (m2) | Remark | AS Symbol | Delivery item | Scope of Painting Work Unit-1 | Rev.1 (17/04/2026) | Rev.2 (03/05/2026) | Rev.3 (09/05/2026) | Rev.4 (08/06/2026) | Rev.5 (12/06/2026) | Rev.6 (04/07/2026) | Rev.7 (10/07/2026) | Rev.8 (16/07/2026) | Rev.9 (21/07/2026) | Khoan Lỗ | Lốc tròn (Uốn cong) | Sấn | Vát mép & Cắt miệng | Gia công cơ khí (Không thay đổi chiều dày) | Gia công cơ khí (Có thay đổi chiều dày) | Tổ hợp | Fabrication or Purchasing | MPR No. | Q'Ty in MPR Bolt & Fitting | Cutting No. Unit 1 | Q'TY Unit 1 | Date Issue | Remain (T'Qty-Q'Ty) Unit 1
1 | 2A | 3 | 4 | 5A (Marking as Dwg.) | 5B (Marking as Cutting) | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [5 empty] | 20 | 21 | 22 | 23 | 24 |  |  |  | 14 | 17 | 18 | 19 | 20 | 29A | 30A | 30B | 30C | 30D | 30E | 30F | 30G | 30H | 30I | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
1 | V17566-DWXD-7532 | CO-FL-1 | FIELD LINER |  |  | (457x2x1167) |  |  |  | 2 |  | 8.4 | 16.7 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7532 | CO-FL-1 | FIELD LINER | L-92 | CO-FL-1-L-92 | PL2*457 | 1167 | SS400 | 1 |  | 2 | 8.4 | 16.7 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [10 empty] | PAC | [9 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
2 | V17566-DWXD-7533 | CO-FL-2 | FIELD LINER |  |  | (457x2x1338) |  |  |  | 2 |  | 9.2 | 18.3 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7533 | CO-FL-2 | FIELD LINER | L-93 | CO-FL-2-L-93 | PL2*457 | 1338 | SS400 | 1 |  | 2 | 9.2 | 18.3 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
3 | V17566-DWXD-7534 | CO-FL-3 | FIELD LINER |  |  | (457x2x381) |  |  |  | 4 |  | 2.7 | 10.9 | AMC2 | [7 empty] | 4 | 1 | [6 empty] | x | o
| V17566-DWXD-7534 | CO-FL-3 | FIELD LINER | L-135 | CO-FL-3-L-135 | PL2*457 | 381 | SS400 | 1 |  | 4 | 2.7 | 10.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16 | 0
4 | V17566-DWXD-7535 | CO-FL-4 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 20 |  | 8.7 | 174.9 | AMC2 | [7 empty] | 20 | 1 | [6 empty] | x | o
| V17566-DWXD-7535 | CO-FL-4 | FIELD LINER | L-73 | CO-FL-4-L-73 | PL2*457 | 1219 | SS400 | 1 |  | 20 | 8.7 | 174.9 | AMC2 | Plate | MCC |  |  | 20 | 0 | 20 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 20 | 2026-04-16 | 0
5 | V17566-DWXD-7536 | CO-FL-5 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 1 |  | 8.7 | 8.7 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7536 | CO-FL-5 | FIELD LINER | L-133 | CO-FL-5-L-133 | PL2*457 | 1219 | SS400 | 1 |  | 1 | 8.7 | 8.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
6 | V17566-DWXD-7537 | CO-FL-6 | FIELD LINER |  |  | (457x2x838) |  |  |  | 1 |  | 6 | 6 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7537 | CO-FL-6 | FIELD LINER | L-119 | CO-FL-6-L-119 | PL2*457 | 838 | SS400 | 1 |  | 1 | 6 | 6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
7 | V17566-DWXD-7538 | CO-FL-7 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 1 |  | 8.7 | 8.7 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7538 | CO-FL-7 | FIELD LINER | L-134 | CO-FL-7-L-134 | PL2*457 | 1219 | SS400 | 1 |  | 1 | 8.7 | 8.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
8 | V17566-DWXD-7539 | CO-FL-8 | FIELD LINER |  |  | (457x2x622) |  |  |  | 2 |  | 4.5 | 8.9 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7539 | CO-FL-8 | FIELD LINER | L-91 | CO-FL-8-L-91 | PL2*457 | 622 | SS400 | 1 |  | 2 | 4.5 | 8.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
9 | V17566-DWXD-7540 | CO-FL-9 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 68 |  | 8.7 | 594.7 | AMC2 | [7 empty] | 68 | 1 | [6 empty] | x | o
| V17566-DWXD-7540 | CO-FL-9 | FIELD LINER | L-89 | CO-FL-9-L-89 | PL2*457 | 1219 | SS400 | 1 |  | 68 | 8.7 | 594.7 | AMC2 | Plate | MCC |  |  | 68 | 0 | 68 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 68 | 2026-04-16 | 0
10 | V17566-DWXD-7541 | CO-FL-10 | FIELD LINER |  |  | (457x2x876) |  |  |  | 4 |  | 6.3 | 25.1 | AMC2 | [7 empty] | 4 | 1 | [6 empty] | x | o
| V17566-DWXD-7541 | CO-FL-10 | FIELD LINER | L-90 | CO-FL-10-L-90 | PL2*457 | 876 | SS400 | 1 |  | 4 | 6.3 | 25.1 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16 | 0
11 | V17566-DWXD-7542 | CO-FL-11 | FIELD LINER |  |  | (457x2x1524) |  |  |  | 1 |  | 10.5 | 10.5 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7542 | CO-FL-11 | FIELD LINER | L-136 | CO-FL-11-L-136 | PL2*457 | 1524 | SS400 | 1 |  | 1 | 10.5 | 10.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
12 | V17566-DWXD-7543 | CO-FL-12 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 1 |  | 8.7 | 8.7 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7543 | CO-FL-12 | FIELD LINER | L-137 | CO-FL-12-L-137 | PL2*457 | 1219 | SS400 | 1 |  | 1 | 8.7 | 8.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
13 | V17566-DWXD-7544 | CO-FL-13 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 1 |  | 8.1 | 8.1 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7544 | CO-FL-13 | FIELD LINER | L-138 | CO-FL-13-L-138 | PL2*457 | 1219 | SS400 | 1 |  | 1 | 8.1 | 8.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
14 | V17566-DWXD-7545 | CO-FL-14 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 1 |  | 8.6 | 8.6 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7545 | CO-FL-14 | FIELD LINER | L-139 | CO-FL-14-L-139 | PL2*457 | 1219 | SS400 | 1 |  | 1 | 8.6 | 8.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
15 | V17566-DWXD-7546 | CO-FL-15 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 1 |  | 8.7 | 8.7 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7546 | CO-FL-15 | FIELD LINER | L-141 | CO-FL-15-L-141 | PL2*457 | 1219 | SS400 | 1 |  | 1 | 8.7 | 8.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
16 | V17566-DWXD-7547 | CO-FL-16 | FIELD LINER |  |  | (457x2x838) |  |  |  | 1 |  | 5.4 | 5.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7547 | CO-FL-16 | FIELD LINER | L-140 | CO-FL-16-L-140 | PL2*457 | 838 | SS400 | 1 |  | 1 | 5.4 | 5.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
17 | V17566-DWXD-7548 | CO-FL-17 | FIELD LINER |  |  | (457x2x1524) |  |  |  | 1 |  | 10.5 | 10.5 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7548 | CO-FL-17 | FIELD LINER | L-142 | CO-FL-17-L-142 | PL2*457 | 1524 | SS400 | 1 |  | 1 | 10.5 | 10.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
18 | V17566-DWXD-7549 | CO-FL-18 | FIELD LINER |  |  | (457x2x1765) |  |  |  | 2 |  | 12 | 23.9 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7549 | CO-FL-18 | FIELD LINER | L-98 | CO-FL-18-L-98 | PL2*457 | 1765 | SS400 | 1 |  | 2 | 12 | 23.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
19 | V17566-DWXD-7550 | CO-FL-19 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 2 |  | 8.5 | 16.9 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7550 | CO-FL-19 | FIELD LINER | L-97 | CO-FL-19-L-97 | PL2*457 | 1219 | SS400 | 1 |  | 2 | 8.5 | 16.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
20 | V17566-DWXD-7551 | CO-FL-20 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 2 |  | 8.5 | 16.9 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7551 | CO-FL-20 | FIELD LINER | L-96 | CO-FL-20-L-96 | PL2*457 | 1219 | SS400 | 1 |  | 2 | 8.5 | 16.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
21 | V17566-DWXD-7552 | CO-FL-21 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 2 |  | 8.5 | 16.9 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7552 | CO-FL-21 | FIELD LINER | L-95 | CO-FL-21-L-95 | PL2*457 | 1219 | SS400 | 1 |  | 2 | 8.5 | 16.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
22 | V17566-DWXD-7553 | CO-FL-22 | FIELD LINER |  |  | (457x2x1219) |  |  |  | 4 |  | 8.5 | 33.9 | AMC2 | [7 empty] | 4 | 1 | [6 empty] | x | o
| V17566-DWXD-7553 | CO-FL-22 | FIELD LINER | L-94 | CO-FL-22-L-94 | PL2*457 | 1219 | SS400 | 1 |  | 4 | 8.5 | 33.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16 | 0
23 | V17566-DWXD-7554 | CO-FL-23 | FIELD LINER |  |  | (457x2x981) |  |  |  | 2 |  | 6.7 | 13.5 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7554 | CO-FL-23 | FIELD LINER | L-99 | CO-FL-23-L-99 | PL2*457 | 981 | SS400 | 1 |  | 2 | 6.7 | 13.5 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
24 | V17566-DWXD-7555 | CO-FL-24 | FIELD LINER |  |  | (457x2x1143) |  |  |  | 2 |  | 8.2 | 16.4 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7555 | CO-FL-24 | FIELD LINER | L-206 | CO-FL-24-L-206 | PL2*457 | 1143 | SS400 | 1 |  | 2 | 8.2 | 16.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
25 | V17566-DWXD-7556 | CO-FL-25 | FIELD LINER |  |  | (672x192x192) |  |  |  | 1 |  | 4 | 4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7556 | CO-FL-25 | FIELD LINER | LX-18 | CO-FL-25-LX-18 | PL2*671.5 | 381 | SS400 | 1 |  | 1 | 4 | 4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
26 | V17566-DWXD-7557 | CO-FL-26 | FIELD LINER |  |  | (786x192x192) |  |  |  | 2 |  | 4.7 | 9.4 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7557 | CO-FL-26 | FIELD LINER | LX-1 | CO-FL-26-LX-1 | PL2*785.5 | 381 | SS400 | 1 |  | 2 | 4.7 | 9.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
27 | V17566-DWXD-7558 | CO-FL-27 | FIELD LINER |  |  | (672x192x192) |  |  |  | 1 |  | 4 | 4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7558 | CO-FL-27 | FIELD LINER | LX-9 | CO-FL-27-LX-9 | PL2*671.5 | 381 | SS400 | 1 |  | 1 | 4 | 4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
28 | V17566-DWXD-7559 | CO-FL-28 | FIELD LINER |  |  | (838x192x192) |  |  |  | 1 |  | 5 | 5 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7559 | CO-FL-28 | FIELD LINER | LX-19 | CO-FL-28-LX-19 | PL2*838 | 381 | SS400 | 1 |  | 1 | 5 | 5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
29 | V17566-DWXD-7560 | CO-FL-29 | FIELD LINER |  |  | (838x192x192) |  |  |  | 1 |  | 5 | 5 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7560 | CO-FL-29 | FIELD LINER | LX-10 | CO-FL-29-LX-10 | PL2*838 | 381 | SS400 | 1 |  | 1 | 5 | 5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
30 | V17566-DWXD-7561 | CO-FL-30 | FIELD LINER |  |  | (1138x192x192) |  |  |  | 1 |  | 6.8 | 6.8 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7561 | CO-FL-30 | FIELD LINER | LX-27 | CO-FL-30-LX-27 | PL2*1138 | 381 | SS400 | 1 |  | 1 | 6.8 | 6.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
31 | V17566-DWXD-7562 | CO-FL-31 | FIELD LINER |  |  | (1138x192x192) |  |  |  | 1 |  | 6.8 | 6.8 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7562 | CO-FL-31 | FIELD LINER | LX-2 | CO-FL-31-LX-2 | PL2*1138 | 381 | SS400 | 1 |  | 1 | 6.8 | 6.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
32 | V17566-DWXD-7563 | CO-FL-32 | FIELD LINER |  |  | (871x193x192) |  |  |  | 1 |  | 5.1 | 5.1 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7563 | CO-FL-32 | FIELD LINER | LX-20 | CO-FL-32-LX-20 | PL2*871 | 381 | SS400 | 1 |  | 1 | 5.1 | 5.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
33 | V17566-DWXD-7564 | CO-FL-33 | FIELD LINER |  |  | (871x193x192) |  |  |  | 1 |  | 5.1 | 5.1 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7564 | CO-FL-33 | FIELD LINER | LX-11 | CO-FL-33-LX-11 | PL2*871 | 381 | SS400 | 1 |  | 1 | 5.1 | 5.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
34 | V17566-DWXD-7565 | CO-FL-34 | FIELD LINER |  |  | (1238x193x192) |  |  |  | 1 |  | 7.3 | 7.3 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7565 | CO-FL-34 | FIELD LINER | LX-28 | CO-FL-34-LX-28 | PL2*1238 | 381 | SS400 | 1 |  | 1 | 7.3 | 7.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
35 | V17566-DWXD-7566 | CO-FL-35 | FIELD LINER |  |  | (1238x193x192) |  |  |  | 1 |  | 7.3 | 7.3 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7566 | CO-FL-35 | FIELD LINER | LX-3 | CO-FL-35-LX-3 | PL2*1238 | 381 | SS400 | 1 |  | 1 | 7.3 | 7.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
36 | V17566-DWXD-7567 | CO-FL-36 | FIELD LINER |  |  | (1057x192x192) |  |  |  | 1 |  | 6.4 | 6.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7567 | CO-FL-36 | FIELD LINER | LX-21 | CO-FL-36-LX-21 | PL2*1057 | 381 | SS400 | 1 |  | 1 | 6.4 | 6.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
37 | V17566-DWXD-7568 | CO-FL-37 | FIELD LINER |  |  | (1057x192x192) |  |  |  | 1 |  | 6.4 | 6.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7568 | CO-FL-37 | FIELD LINER | LX-12 | CO-FL-37-LX-12 | PL2*1057 | 381 | SS400 | 1 |  | 1 | 6.4 | 6.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
38 | V17566-DWXD-7569 | CO-FL-38 | FIELD LINER |  |  | (837x192x192) |  |  |  | 1 |  | 5 | 5 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7569 | CO-FL-38 | FIELD LINER | LX-29 | CO-FL-38-LX-29 | PL2*836.5 | 381 | SS400 | 1 |  | 1 | 5 | 5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
39 | V17566-DWXD-7570 | CO-FL-39 | FIELD LINER |  |  | (837x192x192) |  |  |  | 1 |  | 5 | 5 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7570 | CO-FL-39 | FIELD LINER | LX-4 | CO-FL-39-LX-4 | PL2*836.5 | 381 | SS400 | 1 |  | 1 | 5 | 5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
40 | V17566-DWXD-7571 | CO-FL-40 | FIELD LINER |  |  | (971x192x192) |  |  |  | 1 |  | 5.8 | 5.8 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7571 | CO-FL-40 | FIELD LINER | LX-22 | CO-FL-40-LX-22 | PL2*970.5 | 381 | SS400 | 1 |  | 1 | 5.8 | 5.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
41 | V17566-DWXD-7572 | CO-FL-41 | FIELD LINER |  |  | (971x192x192) |  |  |  | 1 |  | 5.8 | 5.8 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7572 | CO-FL-41 | FIELD LINER | LX-13 | CO-FL-41-LX-13 | PL2*970.5 | 381 | SS400 | 1 |  | 1 | 5.8 | 5.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
42 | V17566-DWXD-7573 | CO-FL-42 | FIELD LINER |  |  | (664x167x257) |  |  |  | 1 |  | 4.4 | 4.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7573 | CO-FL-42 | FIELD LINER | LX-30 | CO-FL-42-LX-30 | PL2*663.5 | 423 | SS400 | 1 |  | 1 | 4.4 | 4.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
43 | V17566-DWXD-7574 | CO-FL-43 | FIELD LINER |  |  | (664x167x257) |  |  |  | 1 |  | 4.4 | 4.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7574 | CO-FL-43 | FIELD LINER | LX-5 | CO-FL-43-LX-5 | PL2*663.5 | 423 | SS400 | 1 |  | 1 | 4.4 | 4.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
44 | V17566-DWXD-7575 | CO-FL-44 | FIELD LINER |  |  | (1087x192x192) |  |  |  | 1 |  | 5.4 | 5.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7575 | CO-FL-44 | FIELD LINER | LX-23 | CO-FL-44-LX-23 | PL2*1086.5 | 381 | SS400 | 1 |  | 1 | 5.4 | 5.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
45 | V17566-DWXD-7576 | CO-FL-45 | FIELD LINER |  |  | (1087x192x192) |  |  |  | 1 |  | 5.4 | 5.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7576 | CO-FL-45 | FIELD LINER | LX-14 | CO-FL-45-LX-14 | PL2*1086.5 | 381 | SS400 | 1 |  | 1 | 5.4 | 5.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
46 | V17566-DWXD-7577 | CO-FL-46 | FIELD LINER |  |  | (1267x167x257) |  |  |  | 1 |  | 8.4 | 8.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7577 | CO-FL-46 | FIELD LINER | LX-31 | CO-FL-46-LX-31 | PL2*1266.5 | 423 | SS400 | 1 |  | 1 | 8.4 | 8.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
47 | V17566-DWXD-7578 | CO-FL-47 | FIELD LINER |  |  | (1267x167x257) |  |  |  | 1 |  | 8.4 | 8.4 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7578 | CO-FL-47 | FIELD LINER | LX-6 | CO-FL-47-LX-6 | PL2*1266.5 | 423 | SS400 | 1 |  | 1 | 8.4 | 8.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
48 | V17566-DWXD-7579 | CO-FL-48 | FIELD LINER |  |  | (457x192x192) |  |  |  | 1 |  | 2.3 | 2.3 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7579 | CO-FL-48 | FIELD LINER | LX-24 | CO-FL-48-LX-24 | PL2*457 | 381 | SS400 | 1 |  | 1 | 2.3 | 2.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
49 | V17566-DWXD-7580 | CO-FL-49 | FIELD LINER |  |  | (457x192x192) |  |  |  | 1 |  | 2.3 | 2.3 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7580 | CO-FL-49 | FIELD LINER | LX-15 | CO-FL-49-LX-15 | PL2*457 | 381 | SS400 | 1 |  | 1 | 2.3 | 2.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
50 | V17566-DWXD-7581 | CO-FL-50 | FIELD LINER |  |  | (1219x192x192) |  |  |  | 1 |  | 7.3 | 7.3 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7581 | CO-FL-50 | FIELD LINER | LX-32 | CO-FL-50-LX-32 | PL2*1219 | 381 | SS400 | 1 |  | 1 | 7.3 | 7.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
51 | V17566-DWXD-7582 | CO-FL-51 | FIELD LINER |  |  | (1219x192x192) |  |  |  | 1 |  | 6.2 | 6.2 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7582 | CO-FL-51 | FIELD LINER | LX-25 | CO-FL-51-LX-25 | PL2*1219 | 381 | SS400 | 1 |  | 1 | 6.2 | 6.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
52 | V17566-DWXD-7583 | CO-FL-52 | FIELD LINER |  |  | (1219x192x192) |  |  |  | 1 |  | 7.3 | 7.3 | AMC2 | [7 empty] | 0 | 0 | [6 empty] | x | o
| V17566-DWXD-7583 | CO-FL-52 | FIELD LINER | LX-7 | CO-FL-52-LX-7 | PL2*1219 | 381 | SS400 | 1 |  | 1 | 7.3 | 7.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
53 | V17566-DWXD-7584 | CO-FL-53 | FIELD LINER |  |  | (1219x192x192) |  |  |  | 1 |  | 6.2 | 6.2 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7584 | CO-FL-53 | FIELD LINER | LX-16 | CO-FL-53-LX-16 | PL2*1219 | 381 | SS400 | 1 |  | 1 | 6.2 | 6.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
54 | V17566-DWXD-7585 | CO-FL-54 | FIELD LINER |  |  | (600x192x192) |  |  |  | 1 |  | 3.6 | 3.6 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7585 | CO-FL-54 | FIELD LINER | LX-26 | CO-FL-54-LX-26 | PL2*599.5 | 381 | SS400 | 1 |  | 1 | 3.6 | 3.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
55 | V17566-DWXD-7586 | CO-FL-55 | FIELD LINER |  |  | (600x192x192) |  |  |  | 2 |  | 3.6 | 7.2 | AMC2 | [7 empty] | 2 | 1 | [6 empty] | x | o
| V17566-DWXD-7586 | CO-FL-55 | FIELD LINER | LX-8 | CO-FL-55-LX-8 | PL2*599.5 | 381 | SS400 | 1 |  | 2 | 3.6 | 7.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
56 | V17566-DWXD-7587 | CO-FL-56 | FIELD LINER |  |  | (600x192x192) |  |  |  | 1 |  | 3.6 | 3.6 | AMC2 | [7 empty] | 1 | 1 | [6 empty] | x | o
| V17566-DWXD-7587 | CO-FL-56 | FIELD LINER | LX-17 | CO-FL-56-LX-17 | PL2*599.5 | 381 | SS400 | 1 |  | 1 | 3.6 | 3.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [20 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 1 | 2026-04-16 | 0
57 | V17566-DWXD-7481 | CO-PL-1 | FIELD PLATE |  |  | (51x6x19) |  |  |  | 6 |  | 0 | 0.3 | AMC2 | [7 empty] | 6 | 1 |  |  |  |  | 0 |  | x | o
| V17566-DWXD-7481 | CO-PL-1 | FIELD PLATE | S-6 | CO-PL-1-S-6 | PL6*19 | 51 | SS400 | 1 |  | 6 | 0 | 0.3 | AMC2 | Plate | MCC |  |  | 6 | 0 | 6 | [6 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 6 | 2026-04-16 | 0
58 | V17566-DWXD-7482 | CO-PL-2 | FIELD COVER RING |  |  | (191x3x191) |  |  |  | 4 |  | 0.5 | 1.8 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 0.2 |  | x | o
| V17566-DWXD-7482 | CO-PL-2 | FIELD COVER RING | S-4 | CO-PL-2-S-4 | PL2.6*191 | 191 | SS400 | 1 |  | 4 | 0.5 | 1.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 4 | 2026-04-16 | 0
59 | V17566-DWXD-7483 | CO-PL-3 | FIELD PLATE |  |  | (152x10x210) |  |  |  | 14 |  | 2.5 | 35.1 | AMC2 | [7 empty] | 14 | 1 |  |  |  |  | 1 |  | x | o
| V17566-DWXD-7483 | CO-PL-3 | FIELD PLATE | S-3 | CO-PL-3-S-3 | PL10*152 | 210 | SS400 | 1 |  | 14 | 2.5 | 35.1 | AMC2 | Plate | MCC |  |  | 14 | 0 | 14 | [6 empty] | 1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 14 | 2026-04-16 | 0
60 | V17566-DWXD-7484 | CO-PL-4 | FIELD PLATE |  |  | (75x6x210) |  |  |  | 21 |  | 0.7 | 15.6 | AMC2 | [7 empty] | 21 | 1 |  |  |  |  | 0.7 |  | x | o
| V17566-DWXD-7484 | CO-PL-4 | FIELD PLATE | S-2 | CO-PL-4-S-2 | PL6*75 | 210 | SS400 | 1 |  | 21 | 0.7 | 15.6 | AMC2 | Plate | MCC |  |  | 21 | 0 | 21 | [6 empty] | 0.7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 21 | 2026-04-16 | 0
61 | V17566-DWXD-7485 | CO-PL-5 | FIELD PLATE |  |  | (64x10x220) |  |  |  | 74 |  | 1.1 | 81.8 | AMC2 | [7 empty] | 74 | 1 |  |  |  |  | 2.5 |  | x | o
| V17566-DWXD-7485 | CO-PL-5 | FIELD PLATE | S-1 | CO-PL-5-S-1 | PL10*64 | 220 | SS400 | 1 |  | 74 | 1.1 | 81.8 | AMC2 | Plate | MCC |  |  | 74 | 0 | 74 | [6 empty] | 2.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 74 | 2026-04-16 | 0
62 | V17566-DWXD-7486 | CO-PL-6 | FIELD PLATE |  |  | (718x12x330) |  |  |  | 2 |  | 20.3 | 40.6 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.9 |  | x | o
| V17566-DWXD-7486 | CO-PL-6 | FIELD PLATE | S-7 | CO-PL-6-S-7 | PL12*718 | 330 | SS400 | 1 |  | 2 | 20.3 | 40.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.9 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16 | 0
63 | V17566-DWXD-7487 | CO-PL-7 | FIELD COVER PLATE |  |  | (214x2x178) |  |  |  | 2 |  | 0.5 | 1 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.1 |  | x | o
| V17566-DWXD-7487 | CO-PL-7 | FIELD COVER PLATE | S-8 | CO-PL-7-S-8 | PL2*178 | 214 | SS400 | 1 |  | 2 | 0.5 | 1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
64 | V17566-DWXD-7488 | CO-PL-8 | FIELD COVER PLATE |  |  | (178x2x195) |  |  |  | 2 |  | 0.5 | 1 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.1 |  | x | o
| V17566-DWXD-7488 | CO-PL-8 | FIELD COVER PLATE | S-9 | CO-PL-8-S-9 | PL2*178 | 195 | SS400 | 1 |  | 2 | 0.5 | 1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 2 | 2026-04-16 | 0
65 | V17566-DWXD-7489 | CO-PL-9 | FIELD PLATE |  |  | (51x6x50) |  |  |  | 2 |  | 0.1 | 0.2 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0 |  | x | o
| V17566-DWXD-7489 | CO-PL-9 | FIELD PLATE | S-5 | CO-PL-9-S-5 | PL6*50 | 51 | SS400 | 1 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16 | 0
66 | V17566-DWXD-7490 | CO-PL-10 | FIELD COVER RING |  |  | (191x3x191) |  |  |  | 5 |  | 0.5 | 2.3 | AMC2 | [7 empty] | 5 | 1 |  |  |  |  | 0.2 |  | x | o
| V17566-DWXD-7490 | CO-PL-10 | FIELD COVER RING | S-14 | CO-PL-10-S-14 | PL2.6*191 | 191 | SS400 | 1 |  | 5 | 0.5 | 2.3 | AMC2 | Plate | MCC |  |  | 5 | 0 | 5 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 5 | 2026-04-16 | 0
67 | V17566-DWXD-7491 | CO-PL-11 | FIELD COVER RING |  |  | (191x3x191) |  |  |  | 1 |  | 0.5 | 0.5 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0 |  | x | o
| V17566-DWXD-7491 | CO-PL-11 | FIELD COVER RING | S-4 | CO-PL-11-S-4 | PL2.6*191 | 191 | SS400 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 1 | 2026-04-16 | 0
68 | V17566-DWXD-7492 | CO-PL-12 | FIELD COVER PLATE |  |  | (157x2x350) |  |  |  | 4 |  | 0.5 | 2.1 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 0.3 |  | x | o
| V17566-DWXD-7492 | CO-PL-12 | FIELD COVER PLATE | S-12 | CO-PL-12-S-12 | PL2*157 | 350 | SS400 | 1 |  | 4 | 0.5 | 2.1 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16 | 0
69 | V17566-DWXD-7493 | CO-PL-13 | FIELD COVER PLATE |  |  | (132x2x276) |  |  |  | 8 |  | 0.4 | 3.2 | AMC2 | [7 empty] | 8 | 1 |  |  |  |  | 0.4 |  | x | o
| V17566-DWXD-7493 | CO-PL-13 | FIELD COVER PLATE | S-13 | CO-PL-13-S-13 | PL2*132 | 276 | SS400 | 1 |  | 8 | 0.4 | 3.2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 8 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 8 | 2026-04-16 | 0
70 | V17566-DWXD-7494 | CO-PL-14 | FIELD COVER PLATE |  |  | (214x2x178) |  |  |  | 8 |  | 0.5 | 4.1 | AMC2 | [7 empty] | 8 | 1 |  |  |  |  | 0.5 |  | x | o
| V17566-DWXD-7494 | CO-PL-14 | FIELD COVER PLATE | S-8 | CO-PL-14-S-8 | PL2*178 | 214 | SS400 | 1 |  | 8 | 0.5 | 4.1 | AMC2 | Plate | MCC |  |  | 8 | 0 | 8 | [6 empty] | 0.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 8 | 2026-04-16 | 0
71 | V17566-DWXD-7495 | CO-PL-15 | FIELD COVER PLATE |  |  | (527x2x157) |  |  |  | 4 |  | 0.7 | 2.9 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 0.4 |  | x | o
| V17566-DWXD-7495 | CO-PL-15 | FIELD COVER PLATE | S-10 | CO-PL-15-S-10 | PL2*157 | 527 | SS400 | 1 |  | 4 | 0.7 | 2.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16 | 0
72 | V17566-DWXD-0323 | CO-PL-16 | FIELD COVER PLATE |  |  | (157x2x527) |  |  |  | 4 |  | 0.7 | 2.9 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 0.4 |  | x | o
| V17566-DWXD-0323 | CO-PL-16 | FIELD COVER PLATE | S-11 | CO-PL-16-S-11 | PL2*157 | 527 | SS400 | 1 |  | 4 | 0.7 | 2.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 4 | 2026-04-16 | 0
73 | V17566-DWXD-7497 | CO-PL-17 | FIELD COVER PLATE |  |  | (178x2x195) |  |  |  | 8 |  | 0.5 | 3.9 | AMC2 | [7 empty] | 8 | 1 |  |  |  |  | 0.5 |  | x | o
| V17566-DWXD-7497 | CO-PL-17 | FIELD COVER PLATE | S-9 | CO-PL-17-S-9 | PL2*178 | 195 | SS400 | 1 |  | 8 | 0.5 | 3.9 | AMC2 | Plate | MCC |  |  | 8 | 0 | 8 | [6 empty] | 0.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-13 |  | U284-07-CP012 | 8 | 2026-04-16 | 0
74 | V17566-DWXD-7498 | CO-PL-18 | FIELD COVER RING |  |  | (161x2x161) |  |  |  | 4 |  | 0.2 | 0.9 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 0.2 |  | x | o
| V17566-DWXD-7498 | CO-PL-18 | FIELD COVER RING | S-15 | CO-PL-18-S-15 | PL1.5*160 | 161 | SS400 | 1 |  | 4 | 0.2 | 0.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 0.2 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/1 |  | U284-07-CP002 | 4 | 2026-04-16 | 0
75 | V17566-DWXD-7591 | CO-PL-19 | FIELD COVER PLATE |  |  | (384x2x104) |  |  |  | 2 |  | 0.5 | 1 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 0.2 | ADDED, thêm mới | x | o |  |  | ADDED, thêm mới
| V17566-DWXD-7591 | CO-PL-19 | FIELD COVER RING | S-8000 | CO-PL-19-S-8000 | PL2*104 | 384 | SS400 | 1 |  | 2 | 0.5 | 1 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.2 | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP012-1 DCC25-U284-0047-2 |  | U284-07-CP029 | 2 | 2026-05-07 | 0
76 | V17566-DWXD-7499 | CO-RC-1 | FIELD RETAINER CLIP |  |  | (51x5x102) |  |  |  | 10 |  | 0.1 | 1.1 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 0.1 |  | x | o
| V17566-DWXD-7499 | CO-RC-1 | FIELD RETAINER CLIP | SX-1 | CO-RC-1-SX-1 | PL2.6*51 | 103 | SS400 | 1 |  | 10 | 0.1 | 1.1 | AMC2 | Plate | PMC |  |  | 0 | 10 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 10 | 2026-04-16 | 0
77 | V17566-DWXD-7500 | CO-RC-2 | FIELD RETAINER CLIP |  |  | (51x5x102) |  |  |  | 2 |  | 0.1 | 0.2 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 0 |  | x | o
| V17566-DWXD-7500 | CO-RC-2 | FIELD RETAINER CLIP | SX-2 | CO-RC-2-SX-2 | PL2.6*51 | 103 | SS400 | 1 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-14 |  | U284-07-CP013 | 2 | 2026-04-16 | 0
78 | V17566-DWXD- | CO-RC-3 | FIELD RETAINER CLIP |  |  | (51x5x102) |  |  |  | 8 |  | 0.1 | 0.9 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 0.1 | ADDED | x |  |  | ADDED
| V17566-DWXD- | CO-RC-3 | FIELD RETAINER CLIP | SX-3 | CO-RC-3-SX-3 | PL2.6*51 | 103 | SS400 | 1 |  | 8 | 0.1 | 0.9 | AMC2 | Plate | PMC |  |  | 0 | 8 | 0 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-03A-CP019-1 |  | U284-07-CP031 | 8 | 2026-05-07 | 0
79 | V17566-DWXD-7501 | CO-SP-4 | SUPPORT CHANNEL |  |  | (951x90x200) |  |  |  | 4 |  | 31.9 | 127.5 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 3 |  | x | o
| V17566-DWXD-7501 | CO-SP-4 | PLATE 758 | P-24 | CO-SP-4-P-24 | PL12*78 | 951 | A387 GR.11 CL.2 | 2 |  | 8 | 7 | 55.9 | AMC2 | Plate | MCC |  |  | 8 | 0 | 4 | [6 empty] | 1.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16 | 0
| V17566-DWXD-7501 | CO-SP-4 | PLATE | P-25 | CO-SP-4-P-25 | PL12*200 | 951 | A387 GR.11 CL.2 | 1 |  | 4 | 17.9 | 71.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 1.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16 | 0
80 | V17566-DWXD-7401 | COB-1 | BOTTOM PANEL |  |  | (1671x3448x9823) |  |  |  | 1 |  | 12843 | 12843 | AMC2 | [7 empty] | 0 | 0.15888 |  |  |  |  | 191.4 | REVISED | x | o |  |  | REVISED
| V17566-DWXD-7401 | COB-1 | ANGLE | A-4 | COB-1-A-4 | L90*90*6 | 9785 | SS400 | 2 |  | 2 | 81 | 162.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 6.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài: 9677->9785 |  |  |  |  | MODIFY, tăng chiều dài: 9677->9785 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
| V17566-DWXD-7401 | COB-1 | BUILT-UP H-BEAM | BY-2 | COB-1-BY-2 | BH900*400*25*38 | 9747 | SM490 | 2 |  | 2 | 3891.3 | 7782.6 | AMC2 | Shape | WTC |  |  | 2 | 0 | 1 | [6 empty] | 65.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
| V17566-DWXD-7401 | COB-1 | CHANNEL | CY-29 | COB-1-CY-29 | [200*80*7.5*11 | 1710 | SS400 | 2 |  | 2 | 39.8 | 79.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7401 | COB-1 | CHANNEL | CY-32 | COB-1-CY-32 | [200*80*7.5*11 | 1389 | SS400 | 2 |  | 2 | 32 | 64 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7401 | COB-1 | CHANNEL | CY-33 | COB-1-CY-33 | [200*80*7.5*11 | 1564 | SS400 | 2 |  | 2 | 36.2 | 72.5 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | G-1 | COB-1-G-1 | PL38*400 | 1312 | SM490 | 4 |  | 4 | 156.5 | 626.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 4.7 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | GZ-2 | COB-1-GZ-2 | PL16*90 | 90 | SS400 | 8 |  | 8 | 0.8 | 6.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.1 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-14-CP006-1 |  | U284-07-CP010 | 8 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | H-BEAM | HY-4 | COB-1-HY-4 | H294*200*8*12 | 3448 | SS400 | 2 |  | 2 | 192.3 | 384.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 9.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 2 | 2026-04-21 | 0
| V17566-DWXD-7401 | COB-1 | H-BEAM | HY-5 | COB-1-HY-5 | H294*200*8*12 | 3448 | SS400 | 4 |  | 4 | 192.3 | 769.2 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 18.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 4 | 2026-04-21 | 0
| V17566-DWXD-7401 | COB-1 | H-BEAM | HY-6 | COB-1-HY-6 | H294*200*8*12 | 3448 | SS400 | 1 |  | 1 | 192.3 | 192.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 1 | 2026-04-21 | 0
| V17566-DWXD-7401 | COB-1 | H-BEAM | HYZ-1 | COB-1-HYZ-1 | H150*150*7*10 | 265 | SS400 | 4 |  | 4 | 8.2 | 33 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 0.9 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-20 |  | U284-07-CP514 | 4 | 2026-04-21 | 0
| V17566-DWXD-7401 | COB-1 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 540 |  | 540 | 0 | 6.6 | AMC2 | Purchasing | KHO |  |  | 0 | 540 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 540 |  | 0
| V17566-DWXD-7401 | COB-1 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 270 |  | 270 | 0 | 13.3 | AMC2 | Purchasing | KHO |  |  | 0 | 270 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 270 |  | 0
| V17566-DWXD-7401 | COB-1 | PLATE 754B | P-11 | COB-1-P-11 | PL12*67 | 230 | A387 GR.11 CL.2 | 4 |  | 4 | 1.4 | 5.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 754C | P-12 | COB-1-P-12 | PL12*67 | 165 | A387 GR.11 CL.2 | 4 |  | 4 | 1 | 4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | P-13 | COB-1-P-13 | PL10*67 | 200 | A387 GR.11 CL.2 | 20 |  | 20 | 1.1 | 21 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-6 |  | U284-07-CP005 | 20 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | P-14 | COB-1-P-14 | PL12*200 | 451 | A387 GR.11 CL.2 | 4 |  | 4 | 8.5 | 34 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 753B | P-15 | COB-1-P-15 | PL12*75 | 220 | A387 GR.11 CL.2 | 4 |  | 4 | 1.5 | 6.1 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | P-16 | COB-1-P-16 | PL12*200 | 276 | A387 GR.11 CL.2 | 4 |  | 4 | 5.2 | 20.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 754A | P-17 | COB-1-P-17 | PL10*67 | 230 | A387 GR.11 CL.2 | 4 |  | 4 | 1.2 | 4.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-6 |  | U284-07-CP005 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 753A | P-18 | COB-1-P-18 | PL10*75 | 220 | A387 GR.11 CL.2 | 4 |  | 4 | 1.3 | 5.1 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-6 |  | U284-07-CP005 | 4 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 758 | P-20 | COB-1-P-20 | PL12*67 | 150 | A387 GR.11 CL.2 | 16 |  | 16 | 0.9 | 15.1 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 16 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 756 | P-21 | COB-1-P-21 | PL8*67 | 151 | A387 GR.11 CL.2 | 8 |  | 8 | 0.6 | 4.9 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP036-1 |  | U284-07-CP023 | 8 | 2026-07-09 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | P-22 | COB-1-P-22 | PL12*150 | 200 | A387 GR.11 CL.2 | 8 |  | 8 | 2.8 | 22.6 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE 755 | P-23 | COB-1-P-23 | PL8*75 | 145 | A387 GR.11 CL.2 | 8 |  | 8 | 0.7 | 5.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP036-1 |  | U284-07-CP023 | 8 | 2026-07-09 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | P-26 | COB-1-P-26 | PL10*96 | 270 | SS400 | 16 |  | 16 | 2 | 31.8 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 0.9 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 16 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | P-8000 | COB-1-P-8000 | PL4*102 | 102 | SS400 | 7 |  | 7 | 0.3 | 2.3 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP014-1 |  | U284-07-CP033 | 7 | 2026-05-07 | 0
| V17566-DWXD-7401 | COB-1 | PLATE | PY-3 | COB-1-PY-3 | PL28*206 | 357 | SM490 | 8 |  | 8 | 8.7 | 69.7 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-14-CP010-1 |  | U284-07-CP017 | 8 | 2026-04-16 | 0
| V17566-DWXD-7401 | COB-1 | CASING PLATE | SH-7 | COB-1-SH-7 | PL6*3422 | 9785 | SS400 | 1 |  | 1 | 1577.2 | 1577.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 67.1 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
81 | V17566-DWXD-7423 | COB-2 | BOTTOM PANEL |  |  | (796x1262x9785) |  |  |  | 1 |  | 1436.1 | 1436.1 | AMC2 | [7 empty] | 0 | 0.090426 |  |  |  |  | 80.5 | REVISED | x | o |  |  | REVISED
| V17566-DWXD-7423 | COB-2 | PLATE | P-36 | COB-2-P-36 | PL6*702 | 676 | SS400 | 1 |  | 1 | 8 | 8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
| V17566-DWXD-7423 | COB-2 | PLATE | P-37 | COB-2-P-37 | PL6*102 | 432 | SS400 | 2 |  | 2 | 2.1 | 4.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 6.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16 | 0
| V17566-DWXD-7423 | COB-2 | ANGLE | A-3 | COB-2-A-3 | L75*75*6 | 9785 | SS400 | 1 |  | 1 | 67 | 67 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài: 9677->9785 |  |  |  |  | MODIFY, tăng chiều dài: 9677->9785 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7423 | COB-2 | CHANNEL | C-3 | COB-2-C-3 | [200*80*7.5*11 | 9785 | SS400 | 1 |  | 1 | 237.7 | 237.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài: 9520->9785 |  |  |  |  | MODIFY, tăng chiều dài: 9520->9785 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27 | 0
| V17566-DWXD-7423 | COB-2 | CHANNEL | CY-34 | COB-2-CY-34 | [200*80*7.5*11 | 807 | SS400 | 7 |  | 7 | 18.8 | 131.6 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 1.2 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7423 | COB-2 | CHANNEL | CY-36 | COB-2-CY-36 | [200*80*7.5*11 | 304 | SS400 | 7 |  | 7 | 6 | 41.8 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7423 | COB-2 | PIPE | D-1 | COB-2-D-1 | 18" SCH. STD | 796 | SA-106 GR.B | 1 |  | 1 | 83.1 | 83.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.6 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-1 |  | U284-07-CP501 | 1 | 2026-04-16 | 0
| V17566-DWXD-7423 | COB-2 | PLATE | GZ-2 | COB-2-GZ-2 | PL16*90 | 90 | SS400 | 8 |  | 8 | 0.8 | 6.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 20.4 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-14-CP006-1 |  | U284-07-CP010 | 8 | 2026-04-16 | 0
| V17566-DWXD-7423 | COB-2 | H-BEAM | HYZ-1 | COB-2-HYZ-1 | H150*150*7*10 | 265 | SS400 | 4 |  | 4 | 8.2 | 33 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 17.7 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-20 |  | U284-07-CP514 | 4 | 2026-04-21 | 0
| V17566-DWXD-7423 | COB-2 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 228 |  | 228 | 0 | 2.8 | AMC2 | Purchasing | KHO |  |  | 0 | 228 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 228 |  | 0
| V17566-DWXD-7423 | COB-2 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 114 |  | 114 | 0 | 5.6 | AMC2 | Purchasing | KHO |  |  | 0 | 114 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 114 |  | 0
| V17566-DWXD-7423 | COB-2 | 1/2" NO.16 EXPANDED | P-5 | COB-2-P-5 | PL1.2*456 | 456 | EXPANDED METAL | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-16 |  | U284-07-CP001 | 1 | 2026-04-16 | 0
| V17566-DWXD-7423 | COB-2 | CASING PLATE | SH-8 | COB-2-SH-8 | PL6*1249 | 9785 | SS400 | 1 |  | 1 | 567.9 | 567.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 24.3 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
82 | V17566-DWXD-7427 | COB-3 | BOTTOM PANEL |  |  | (565x2786x9785) |  |  |  | 1 |  | 3925.2 | 3925.2 | AMC2 | [7 empty] | 0 | 0.06274 |  |  |  |  | 103.8 | REVISED | x | o |  | REVISED | REVISED
| V17566-DWXD-7427 | COB-3 | ANGLE | A-3 | COB-3-A-3 | L75*75*6 | 9785 | SS400 | 1 |  | 1 | 67 | 67 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài: 9677->9785 |  |  |  |  | MODIFY, tăng chiều dài: 9677->9785 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7427 | COB-3 | CHANNEL | CY-28 | COB-3-CY-28 | [250*90*9*13 | 1710 | SS400 | 4 |  | 4 | 56.1 | 224.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 5.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 4 | 2026-04-21 | 0
| V17566-DWXD-7427 | COB-3 | CHANNEL | CY-29 | COB-3-CY-29 | [200*80*7.5*11 | 1710 | SS400 | 2 |  | 2 | 39.8 | 79.5 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7427 | COB-3 | CHANNEL | CY-30 | COB-3-CY-30 | [250*90*9*13 | 1389 | SS400 | 4 |  | 4 | 45.2 | 180.6 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 4.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 4 | 2026-04-21 | 0
| V17566-DWXD-7427 | COB-3 | CHANNEL | CY-31 | COB-3-CY-31 | [250*90*9*13 | 1564 | SS400 | 4 |  | 4 | 51.1 | 204.6 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 4 | 2026-04-21 | 0
| V17566-DWXD-7427 | COB-3 | PIPE | D-8 | COB-3-D-8 | 6" XXS | 123 | A53 | 7 |  | 7 | 9.7 | 67.6 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-2 |  | U284-07-CP510 | 7 | 2026-04-16 | 0
| V17566-DWXD-7427 | COB-3 | PLATE | GZ-2 | COB-3-GZ-2 | PL16*90 | 90 | SS400 | 8 |  | 8 | 0.8 | 6.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.1 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-14-CP006-1 |  | U284-07-CP010 | 8 | 2026-04-16 | 0
| V17566-DWXD-7427 | COB-3 | H-BEAM | HY-2 | COB-3-HY-2 | H294*200*8*12 | 2642 | SS400 | 1 |  | 1 | 147.4 | 147.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 1 | 2026-04-21 | 0
| V17566-DWXD-7427 | COB-3 | H-BEAM | HY-3 | COB-3-HY-3 | H294*200*8*12 | 2642 | SS400 | 6 |  | 6 | 147.4 | 884.1 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 21.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0052-VTC-6 |  | U284-07-CP516 | 6 | 2026-04-21 | 0
| V17566-DWXD-7427 | COB-3 | H-BEAM | HYZ-1 | COB-3-HYZ-1 | H150*150*7*10 | 265 | SS400 | 4 |  | 4 | 8.2 | 33 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 0.9 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-20 |  | U284-07-CP514 | 4 | 2026-04-21 | 0
| V17566-DWXD-7427 | COB-3 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 488 |  | 488 | 0 | 6 | AMC2 | Purchasing | KHO |  |  | 0 | 488 | 0 | [7 empty] | MODIFY, Tăng Q.ty: 440->488 |  |  |  | MODIFY, Tăng Q.ty: 440->488 | [8 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 488 |  | 0
| V17566-DWXD-7427 | COB-3 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 244 |  | 244 | 0 | 12.1 | AMC2 | Purchasing | KHO |  |  | 0 | 244 | 0 | [7 empty] | MODIFY, Tăng Q.ty: 220->244 |  |  |  | MODIFY, Tăng Q.ty: 220->244 | [8 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 244 |  | 0
| V17566-DWXD-7427 | COB-3 | PLATE | P-30 | COB-3-P-30 | PL25*254 | 254 | A387 GR.11 CL.2 | 7 |  | 7 | 12.7 | 88.6 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | 1.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 7 | 2026-07-09 | 0
| V17566-DWXD-7427 | COB-3 | CASING PLATE | SH-6 | COB-3-SH-6 | PL6*2773 | 9785 | SS400 | 1 |  | 1 | 1278.1 | 1278.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 54.4 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
83 | V17566-DWXD-7431 | COL-1 | LEFT PANEL |  |  | (568x2786x12332) |  |  |  | 1 |  | 5046 | 5343.9 | AMC2 | [7 empty] | 0 | 0.16523 |  |  |  |  | 138 | Bổ sung thêm khối lượng Access Door | x | o |  | REVISED | REVISED
| V17566-DWXD-7431 | COL-1 | ANGLE | A-2 | COL-1-A-2 | L100*100*10 | 12313 | SS400 | 1 |  | 1 | 183.6 | 183.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7431 | COL-1 | ANGLE | A-7 | COL-1-A-7 | L90*90*10 | 2786 | SS400 | 1 |  | 1 | 37.2 | 37.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 |  |  |  |  | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | ANGLE | A-12 | COL-1-A-12 | L100*100*7 | 152 | SS400 | 2 |  | 2 | 1.6 | 3.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21 | 0
| V17566-DWXD-7431 | COL-1 | BUILT-UP CHANNEL | B-4 | COL-1-B-4 | B354*100*9*13 | 12332 | SS400 | 1 |  | 1 | 537.5 | 537.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 13.4 | Cắt dương lên 50mm theo yêu cầu KOM, Flange không khoan lỗ MODIFY, Tăng chiều dài: 12319->12332 |  |  |  | MODIFY, Tăng chiều dài: 12319->12332 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-3 | COL-1-CY-3 | [200*80*7.5*11 | 295 | SS400 | 10 |  | 10 | 6.2 | 61.6 | AMC2 | Shape | MCC |  |  | 10 | 0 | 1 | [6 empty] | 1.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 10 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-18 | COL-1-CY-18 | [200*80*7.5*11 | 1864 | SS400 | 7 |  | 7 | 42.5 | 297.3 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 8.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-52 | COL-1-CY-52 | [200*80*7.5*11 | 2327 | SS400 | 1 |  | 1 | 54.2 | 54.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-53 | COL-1-CY-53 | [200*80*7.5*11 | 1388 | SS400 | 1 |  | 1 | 31.4 | 31.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-54 | COL-1-CY-54 | [200*80*7.5*11 | 455 | SS400 | 7 |  | 7 | 10 | 69.9 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-55 | COL-1-CY-55 | [200*80*7.5*11 | 2629 | SS400 | 1 |  | 1 | 61.5 | 61.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.8 | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt |  |  |  |  | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-56 | COL-1-CY-56 | [200*80*7.5*11 | 3295 | SS400 | 1 |  | 1 | 78.5 | 78.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-57 | COL-1-CY-57 | [200*80*7.5*11 | 1263 | SS400 | 2 |  | 2 | 29.2 | 58.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-58 | COL-1-CY-58 | [200*80*7.5*11 | 932 | SS400 | 2 |  | 2 | 21.1 | 42.2 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.2 | MODIFY, Giảm chiều dài: 932->931 |  |  |  | MODIFY, Giảm chiều dài: 932->931 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-59 | COL-1-CY-59 | [200*80*7.5*11 | 10066 | SS400 | 1 |  | 1 | 243 | 243 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 6.9 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7431 | COL-1 | CHANNEL | CY-60 | COL-1-CY-60 | [200*80*7.5*11 | 12227 | SS400 | 1 |  | 1 | 295.7 | 295.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7431 | COL-1 | PIPE | D-3 | COL-1-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 4 |  | 4 | 4.9 | 19.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.6 | Cắt dương lên 5mm MODIFY, giảm Q.ty: 5->4 |  |  |  |  | MODIFY, giảm Q.ty: 5->4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 5 | 2026-04-21 | -1
| V17566-DWXD-7431 | COL-1 | PIPE | DZ-1 | COL-1-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 2 |  | 2 | 0.5 | 0.9 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | 5.9 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21 | 0
| V17566-DWXD-7431 | COL-1 | PIPE | D-9 | COL-1-D-9 | 3" SCH.40 | 436 | A-106 Gr.C | 48 |  | 48 | 4.8 | 230.7 | AMC2 | Shape | MCC |  |  | 48 | 0 | 1 | [6 empty] | 0.7 | Cắt dương lên 5mm MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí |  |  |  | MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21 | 0
| V17566-DWXD-7431 | COL-1 | PIPE | D-10 | COL-1-D-10 | 4" SCH.40 | 309 | A-312 TP.304 | 1 |  | 1 | 4.9 | 4.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP509-1 |  | U284-07-CP524 | 1 | 2026-05-07 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | G-11 | COL-1-G-11 | PL10*228 | 229 | SS400 | 28 |  | 28 | 2.7 | 75.9 | AMC2 | Plate | MCC |  |  | 28 | 0 | 1 | [6 empty] | 2.3 | MODIFY, giảm Q.ty: 29->28 |  |  |  |  | MODIFY, giảm Q.ty: 29->28 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 29 | 2026-04-16 | -1
| V17566-DWXD-7431 | COL-1 | PLATE | G-11-8001 | COL-1-G-11-8001 | PL10*190 | 229 | SS400 | 1 |  | 1 | 2.5 | 2.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-01-CP003-4 |  | U284-07-CP024 | 1 | 2026-05-07 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | G-15 | COL-1-G-15 | PL10*207 | 229 | SS400 | 10 |  | 10 | 2.3 | 23.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | 0.7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 10 | 2026-04-16 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | G-16 | COL-1-G-16 | PL10*208 | 229 | SS400 | 9 |  | 9 | 2.3 | 21 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | G-28 | COL-1-G-28 | PL6*60 | 60 | A-240 TP304 | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07 | 0
| V17566-DWXD-7431 | COL-1 | H-BEAM | H-1 | COL-1-H-1 | H194*150*6*9 | 2261 | SS400 | 1 |  | 1 | 67.6 | 67.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.2 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21 | 0
| V17566-DWXD-7431 | COL-1 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 5 |  | 5 | 0.2 | 0.9 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 5 |  | 0
| V17566-DWXD-7431 | COL-1 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 530 |  | 530 | 0 | 6.5 | AMC2 | Purchasing | KHO |  |  | 0 | 530 | 0 | [7 empty] | MODIFY, Giảm Q.ty: 536-> 530 |  |  |  | MODIFY, Giảm Q.ty: 536-> 530 | [8 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 530 |  | 0
| V17566-DWXD-7431 | COL-1 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 5 |  | 5 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 5 |  | 0
| V17566-DWXD-7431 | COL-1 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 2 |  | 2 | 1.4 | 2.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 2 |  | 0
| V17566-DWXD-7431 | COL-1 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 2 |  | 2 | 0.6 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 2 |  | 0
| V17566-DWXD-7431 | COL-1 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 5 |  | 5 | 0.1 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 5
| V17566-DWXD-7431 | COL-1 | FLANGE 4" 150# SO-RF | M-18 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 5.9 | 29.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 5 |  | 0
| V17566-DWXD-7431 | COL-1 | 4" 150# RF BLIND FLG. | M-19 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 7.6 | 38.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 5 |  | 0
| V17566-DWXD-7431 | COL-1 | FLANGE 3" 150# SO-RF | M-20 |  | PL22*191 | 191 | A-105 | 48 |  | 48 | 4.1 | 196.2 | AMC2 | Purchasing | KHO |  |  | 0 | 48 | 0 | [6 empty] | 3.3 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-18 |  |  | 48 |  | 0
| V17566-DWXD-7431 | COL-1 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 260 |  | 260 | 0 | 12.8 | AMC2 | Purchasing | KHO |  |  | 0 | 260 | 0 | [7 empty] | MODIFY, Giảm Q.ty: 263->260 |  |  |  | MODIFY, Giảm Q.ty: 263->260 | [8 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 260 |  | 0
| V17566-DWXD-7431 | COL-1 | PLATE | P-7 | COL-1-P-7 | PL12*89 | 141 | SS400 | 10 |  | 10 | 1.2 | 11.7 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 10 | 2026-04-16 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | P-27 | COL-1-P-27 | PL25*168 | 305 | A387 GR.11 CL.2 | 2 |  | 2 | 10.1 | 20.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 2 | 2026-07-09 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | P-28 | COL-1-P-28 | PL12*64 | 64 | A387 GR.11 CL.2 | 8 |  | 8 | 0.3 | 2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16 | 0
| V17566-DWXD-7431 | COL-1 | PLATE | P-31 | COL-1-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7431 | COL-1 | CASING PLATE | SH-2 | COL-1-SH-2 | PL6*2560 | 12300 | SS400 | 1 |  | 1 | 1413.5 | 1413.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 60.3 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
83 | V17566-DRXD-7055 | DR070L |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 87.9 | 87.9 | AMC2 | [14 empty] | ADDED Gắn vào panel COL-1 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7055 | DR070L | PLATE | DR070-01 | DR070L-DR070-01 | PL10x940 | 1549 | SS400 | 1 |  | 1 | 40.4 | 40.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | LINER PLATE | DR070-04A | DR070L-DR070-04A | PL1.5x227 | 1429 | SS400 | 2 |  | 2 | 3.8 | 7.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | LINER PLATE | DR070-04B | DR070L-DR070-04B | PL1.5x227 | 819 | SS400 | 2 |  | 2 | 2.2 | 4.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-09 | DR070L-DR070-09 | PL10x152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | SCREWS | DR070-16 | DR070L-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7055 | DR070L | TADPOLE GASKET 2300°F | DR070-17 | DR070L-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-08
| V17566-DRXD-7055 | DR070L | ADHESIVE | DR070-18 | DR070L-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7055 | DR070L | GRAB BAR | DR070-110 | DR070L-DR070-110 | RB19 | 535 | SS400 | 1 |  | 1 | 1.2 | 1.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | DAVIT BRACKET | DR070-126 | DR070L-DR070-126 | PL10x89 | 344 | SS400 | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P01 | DR070L-DR070-P01 | PL10x51 | 54 | SS400 | 10 |  | 10 | 0.02 | 0.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P02 | DR070L-DR070-P02 | PL10x38 | 41 | SS400 | 20 |  | 20 | 0.01 | 0.2 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | FLAT WASHER | DR070-W01 | DR070L-DR070-W01 | ZINC PLATED, 1/2" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-02
| V17566-DRXD-7055 | DR070L | SQUARE SHOUDERED SOLID ROD END BLACK OXID | DR070-B01 | DR070L-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-03
| V17566-DRXD-7055 | DR070L | EASY GRIP HANDLE | DR070-GR01 | DR070L-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-04
| V17566-DRXD-7055 | DR070L | CLEVIS PIN WITH REUSABLE COTTER PIN | DR070-PN01 | DR070L-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-05
| V17566-DRXD-7055 | DR070L | FLAT WASHER | DR070-W02 | DR070L-DR070-W02 | ZINC PLATED, 5/8" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-06
| V17566-DRXD-7055 | DR070L | DAVIT | DR070-RB01 | DR070L-DR070-RB01 | RB45 | 1190 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | DAVIT WASHER | DR070-P03 | DR070L-DR070-P03 | PL10xID.46xOD.70 |  | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P04 | DR070L-DR070-P04 | PL10x270 | 467 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
83 | V17566-DRXD-7056 | DR070L |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 210 | 210 | AMC2 | [14 empty] | ADDED Gắn vào panel COL-1 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7056 | DR070L | ANGLE | DR071-02A | DR070L-DR071-02A | L100x75x10 | 880 | SS400 | 2 |  | 2 | 11.3 | 22.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | ANGLE | DR071-02B | DR070L-DR071-02B | L100x75x10 | 1490 | SS400 | 2 |  | 2 | 19.2 | 38.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | PLATE | DR071-20 | DR070L-DR071-20 | PL10x800 | 1410 | SS400 | 1 |  | 1 | 88.5 | 88.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | FLATBAR | DR071-21 | DR070L-DR071-21 | PL10x75 | 737 | SS400 | 3 |  | 3 | 4.4 | 13.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | FLATBAR | DR071-22 | DR070L-DR071-22 | PL10x75 | 236 | SS400 | 4 |  | 4 | 1.4 | 5.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-26A | DR070L-DR071-26A | PL1.5x140 | 699 | SS400 | 2 |  | 2 | 1.2 | 2.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-26B | DR070L-DR071-26B | PL1.5x140 | 1308 | SS400 | 2 |  | 2 | 2 | 4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-27 | DR070L-DR071-27 | PL1.5x683 | 1293 | SS400 | 1 |  | 1 | 10.4 | 10.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | STUD BOLT | DR071-28 | DR070L-DR071-28 | Ø10(M10) | 108 | SS400 | 8 |  | 8 | 0.15 | 1.2 | AMC2 | Shape | PMC |  |  | 8 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 8
| V17566-DRXD-7056 | DR070L | WASHER | DR071-29 | DR070L-DR071-29 | PL1.5 x OD76 x ID11 |  | SS400 | 16 |  | 16 | 0.07 | 1.12 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | HEX NUT | DR071-30 | DR070L-DR071-30 | M10 |  | SS400 | 16 |  | 16 | 0.01 | 0.16 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-21
| V17566-DRXD-7056 | DR070L | TADPOLE GASKET 1000°F | DR071-31 | DR070L-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.12 | 0.12 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-09
| V17566-DRXD-7056 | DR070L | ADHESIVE | DR071-32 | DR070L-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7056 | DR070L | SCREWS | DR071-33 | DR070L-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7056 | DR070L | DOOR HANDLE | DR071-111 | DR070L-DR071-111 | RB14 | 268 | SS400 | 2 |  | 2 | 0.15 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | GUSSET PLATE | DR071-112 | DR070L-DR071-112 | PL10x65 | 83 | SS400 | 20 |  | 20 | 0.4 | 8 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | DOOR HANGER | DR071-113 | DR070L-DR071-113 | RB14 | 350 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | EYE BOLT/2NUTS/1PW | DR071-114 | DR070L-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) |  | - | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-01
84 | V17566-DWXD-7436 | COL-2 | LEFT PANEL |  |  | (530x2786x12325) |  |  |  | 1 |  | 5000.6 | 5000.6 | AMC2 | [7 empty] | 0 | 0.16698 |  |  |  |  | 136.1 | REVISED | x | o |  | REVISED | REVISED
| V17566-DWXD-7436 | COL-2 | ANGLE | A-1 | COL-2-A-1 | L100*100*10 | 12306 | SS400 | 1 |  | 1 | 183.5 | 183.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7436 | COL-2 | ANGLE | A-19 | COL-2-A-19 | L90*90*10 | 2786 | SS400 | 1 |  | 1 | 37.2 | 37.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7436 | COL-2 | ANGLE | AY-5 | COL-2-AY-5 | L75*75*6 | 2629 | SS400 | 1 |  | 1 | 18 | 18 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt |  |  |  |  | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22 | 0
| V17566-DWXD-7436 | COL-2 | BUILT-UP CHANNEL | B-3 | COL-2-B-3 | B354*100*9*13 | 12325 | SS400 | 1 |  | 1 | 537.2 | 537.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 13.4 | Cắt dương lên 50mm theo yêu cầu KOM, Flange không khoan lỗ | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-3 | COL-2-CY-3 | [200*80*7.5*11 | 295 | SS400 | 9 |  | 9 | 6.2 | 55.5 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 1.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-14 | COL-2-CY-14 | [200*80*7.5*11 | 12306 | SS400 | 1 |  | 1 | 298.2 | 298.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12176->12306 |  |  |  |  | MODIFY, tăng chiều dài 12176->12306 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-16 | COL-2-CY-16 | [200*80*7.5*11 | 12306 | SS400 | 1 |  | 1 | 298.2 | 298.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12176->12306 |  |  |  |  | MODIFY, tăng chiều dài 12176->12306 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-18 | COL-2-CY-18 | [200*80*7.5*11 | 1864 | SS400 | 9 |  | 9 | 42.5 | 382.3 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 11 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-54 | COL-2-CY-54 | [200*80*7.5*11 | 455 | SS400 | 9 |  | 9 | 10 | 89.9 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 2.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-57 | COL-2-CY-57 | [200*80*7.5*11 | 1263 | SS400 | 2 |  | 2 | 29.2 | 58.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-61 | COL-2-CY-61 | [200*80*7.5*11 | 1301 | SS400 | 1 |  | 1 | 29.4 | 29.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7436 | COL-2 | CHANNEL | CY-62 | COL-2-CY-62 | [200*80*7.5*11 | 838 | SS400 | 1 |  | 1 | 20.3 | 20.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 | MODIFY, tăng chiều dài 708->838 |  |  |  |  | MODIFY, tăng chiều dài 708->838 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27 | 0
| V17566-DWXD-7436 | COL-2 | PIPE | D-3 | COL-2-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 4 |  | 4 | 4.9 | 19.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21 | 0
| V17566-DWXD-7436 | COL-2 | PIPE | DZ-1 | COL-2-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | 5.9 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21 | 0
| V17566-DWXD-7436 | COL-2 | PIPE | DZ-2 | COL-2-DZ-2 | 3/4" SCH.80 | 86 | A-106 Gr.B | 2 |  | 2 | 0.2 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, chuyển từ Assembly COR-2 sang |  |  |  |  | ADDED, chuyển từ Assembly COR-2 sang | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 2
| V17566-DWXD-7436 | COL-2 | PIPE | D-9 | COL-2-D-9 | 3" SCH.40 | 436 | A-106 Gr.C | 48 |  | 48 | 4.8 | 230.7 | AMC2 | Shape | MCC |  |  | 48 | 0 | 1 | [6 empty] | 0.7 | Cắt dương lên 5mm MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí |  |  |  | MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | G-11 | COL-2-G-11 | PL10*228 | 229 | SS400 | 29 |  | 29 | 2.7 | 78.6 | AMC2 | Plate | MCC |  |  | 29 | 0 | 1 | [6 empty] | 2.4 | MODIFY, giảm Q.ty: 30->29 |  |  |  |  | MODIFY, giảm Q.ty: 30->29 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 30 | 2026-04-16 | -1
| V17566-DWXD-7436 | COL-2 | PLATE | G-11-8000 | COL-2-G-11-8000 | PL10*190 | 229 | SS400 | 1 |  | 1 | 2.5 | 2.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-01-CP003-4 |  | U284-07-CP024 | 1 | 2026-05-07 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | G-13 | COL-2-G-13 | PL10*208 | 229 | SS400 | 9 |  | 9 | 2.3 | 21.1 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | G-14 | COL-2-G-14 | PL10*206 | 229 | SS400 | 9 |  | 9 | 2.3 | 20.8 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | G-28 | COL-2-G-28 | PL6*60 | 60 | A-240 TP304 | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07 | 0
| V17566-DWXD-7436 | COL-2 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 4 |  | 4 | 0.2 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 4 |  | 0
| V17566-DWXD-7436 | COL-2 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 536 |  | 536 | 0 | 6.6 | AMC2 | Purchasing | KHO |  |  | 0 | 536 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 536 |  | 0
| V17566-DWXD-7436 | COL-2 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 4 |  | 4 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 4 |  | 0
| V17566-DWXD-7436 | COL-2 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 1 |  | 1 | 1.4 | 1.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 1 |  | 0
| V17566-DWXD-7436 | COL-2 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 1 |  | 0
| V17566-DWXD-7436 | COL-2 | COUPING FULL THREAD | M-11 |  | 3/4" 3000# COUPING FULL THREAD | 51 | A-105 | 2 |  | 2 | 0.2 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-24 |  |  | 2 |  | 0
| V17566-DWXD-7436 | COL-2 | SQUARE HEAD PLUG | M-12 |  | 3/4" 3000# SQUARE HEAD PLUG | 24 | A-105 | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-25 |  |  |  |  | 2
| V17566-DWXD-7436 | COL-2 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 5 |  | 5 | 0.1 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 5
| V17566-DWXD-7436 | COL-2 | FLANGE 4" 150# SO-RF | M-18 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 5.9 | 23.6 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 4 |  | 0
| V17566-DWXD-7436 | COL-2 | 4" 150# RF BLIND FLG. | M-19 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 7.6 | 30.5 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 4 |  | 0
| V17566-DWXD-7436 | COL-2 | FLANGE 3" 150# SO-RF | M-20 |  | PL22*191 | 191 | A-105 | 48 |  | 48 | 4.1 | 196.2 | AMC2 | Purchasing | KHO |  |  | 0 | 48 | 0 | [6 empty] | 3.3 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-18 |  |  | 48 |  | 0
| V17566-DWXD-7436 | COL-2 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 264 |  | 264 | 0 | 13 | AMC2 | Purchasing | KHO |  |  | 0 | 264 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 264 |  | 0
| V17566-DWXD-7436 | COL-2 | PLATE | P-7 | COL-2-P-7 | PL12*89 | 141 | SS400 | 9 |  | 9 | 1.2 | 10.5 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 9 | 2026-04-16 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | P-27 | COL-2-P-27 | PL25*168 | 305 | A387 GR.11 CL.2 | 4 |  | 4 | 10.1 | 40.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 4 | 2026-07-09 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | P-28 | COL-2-P-28 | PL12*64 | 64 | A387 GR.11 CL.2 | 16 |  | 16 | 0.3 | 4.1 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 16 | 2026-04-16 | 0
| V17566-DWXD-7436 | COL-2 | PLATE | P-31 | COL-2-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7436 | COL-2 | CASING PLATE | SH-15 | COL-2-SH-15 | PL6*2560 | 12293 | SS400 | 1 |  | 1 | 1465.3 | 1465.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 62.5 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, bổ sung lỗ khoét |  |  |  |  | MODIFY, bổ sung lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
85 | V17566-DWXD-7405 | COL-5 | LEFT PANEL |  |  | (1189x3548x33567) |  |  |  | 1 |  | 35974.9 | 36272.8 | AMC2 | [7 empty] | 0 | 0.072491 |  |  |  |  | 467.2 | Bổ sung thêm khối lượng Access Door | x | o |  |  | REVISED | REVISED
| V17566-DWXD-7405 | COL-5 | ANGLE | A-22 | COL-5-A-22 | L90*90*10 | 3448 | SS400 | 1 |  | 1 | 46 | 46 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7405 | COL-5 | ANGLE | A-23 | COL-5-A-23 | L90*90*10 | 3448 | SS400 | 1 |  | 1 | 46 | 46 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7405 | COL-5 | ANGLE | A-13 | COL-5-A-13 | L90*90*6 | 24619 | SS400 | 1 |  | 1 | 203.9 | 203.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7405 | COL-5 | ANGLE | A-14 | COL-5-A-14 | L90*90*6 | 24619 | SS400 | 1 |  | 1 | 203.9 | 203.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7405 | COL-5 | BUILT-UP H-BEAM | BY-8-1 | COL-5-BY-8-1 | BH900*400*25*38 | 33116 | SM490 | 1 |  | 1 | 13257.8 | 13257.8 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 111 | MODIFY, đổi tên BY-8 thành BY-8-1. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi |  |  |  |  | MODIFY, đổi mark BY-1 thành BY-8. Bổ sung lỗ hole theo basic sửa đổi | MODIFY, đổi tên BY-8 thành BY-8-1. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | -1
| V17566-DWXD-7405 | COL-5 | BUILT-UP H-BEAM | BY-8-2 | COL-5-BY-8-2 | BH900*400*25*38 | 33116 | SM490 | 1 |  | 1 | 13257.8 | 13257.8 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 111 | MODIFY, đổi tên BY-8 thành BY-8-2. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi |  |  |  |  | MODIFY, đổi mark BY-1 thành BY-8. Bổ sung lỗ hole theo basic sửa đổi | MODIFY, đổi tên BY-8 thành BY-8-2. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | -1
| V17566-DWXD-7405 | COL-5 | CHANNEL | CY-8 | COL-5-CY-8 | [250*90*9*13 | 3023 | SS400 | 8 |  | 8 | 97.9 | 783.6 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 19.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 8 | 2026-04-21 | 0
| V17566-DWXD-7405 | COL-5 | CHANNEL | CY-9 | COL-5-CY-9 | [200*80*7.5*11 | 3023 | SS400 | 9 |  | 9 | 69.2 | 622.7 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 17.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7405 | COL-5 | CHANNEL | CY-51 | COL-5-CY-51 | [200*80*7.5*11 | 1998 | SS400 | 1 |  | 1 | 47.5 | 47.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7405 | COL-5 | PIPE | DZ-2 | COL-5-DZ-2 | 3/4" SCH.80 | 86 | A-106 Gr.B | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Shape | MCC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, chuyển từ Assembly COR-3 sang |  |  |  |  | ADDED, chuyển từ Assembly COR-3 sang | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [5 empty] | 1
| V17566-DWXD-7405 | COL-5 | PLATE | G-8000 | COL-5-G-8000 | PL16*152 | 152 | SS400 | 2 |  | 2 | 2.9 | 5.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP028 | 2 | 2026-05-07 | 0
| V17566-DWXD-7405 | COL-5 | LIFTING LUG "A" | GYZ-1 | COL-5-GYZ-1 | PL38*239 | 229 | SM490 | 4 |  | 4 | 14 | 55.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Không khoan lỗ, chỉ để dấu chữ thập, đơn vị sẽ khoan sau khi UT. | [12 empty] | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Fabrication | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | BASE PLATE | GZ-1 | COL-5-GZ-1 | PL60*500 | 1000 | SM490 | 2 |  | 2 | 235.5 | 471 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.4 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | GZ-8000 | COL-5-GZ-8000 | PL12*76 | 102 | SS400 | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP026 | 1 | 2026-05-07 | 0
| V17566-DWXD-7405 | COL-5 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 1322 |  | 1322 | 0 | 16.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1322 | 0 | [7 empty] | MODIFY, tăng Q.ty: 1320->1322 | [5 empty] | MODIFY, tăng Q.ty: 1320->1322 | [6 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 1320 |  | 2
| V17566-DWXD-7405 | COL-5 | COUPING FULL THREAD | M-11 |  | 3/4" 3000# COUPING FULL THREAD | 51 | A-105 | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-24 |  |  | 1 |  | 0
| V17566-DWXD-7405 | COL-5 | SQUARE HEAD PLUG | M-12 |  | 3/4" 3000# SQUARE HEAD PLUG | 24 | A-105 | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-25 |  |  |  |  | 1
| V17566-DWXD-7405 | COL-5 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 10 |  | 10 | 0.1 | 1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 10
| V17566-DWXD-7405 | COL-5 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 661 |  | 661 | 0 | 32.7 | AMC2 | Purchasing | KHO |  |  | 0 | 661 | 0 | [7 empty] | MODIFY, tăng Q.ty: 660->661 | [5 empty] | MODIFY, tăng Q.ty: 660->661 | [6 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 660 |  | 1
| V17566-DWXD-7405 | COL-5 | PLATE | P-1 | COL-5-P-1 | PL60*127 | 1000 | SM490 | 2 |  | 2 | 59.8 | 119.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-2 | COL-5-P-2 | PL60*127 | 220 | SM490 | 4 |  | 4 | 13.2 | 52.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-14-CP014-1 |  | U284-07-CP021 | 4 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | BACKING BAR | P-3 | COL-5-P-3 | PL10*20 | 162 | SM490 | 32 |  | 32 | 0.3 | 8.1 | AMC2 | Plate | MCC |  |  | 32 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP005-1 |  | U284-07-CP006 | 32 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-4 | COL-5-P-4 | PL8*156 | 182 | SS400 | 37 |  | 37 | 1.7 | 64.3 | AMC2 | Plate | MCC |  |  | 37 | 0 | 1 | [6 empty] | 2.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-3 |  | U284-07-CP022 | 37 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-6 | COL-5-P-6 | PL10*184 | 612 | SS400 | 16 |  | 16 | 8.8 | 140.9 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 3.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 16 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-9 | COL-5-P-9 | PL19*181 | 270 | A387 GR.11 CL.2 | 5 |  | 5 | 7.2 | 36.2 | AMC2 | Plate | MCC |  |  | 5 | 0 | 1 | [6 empty] | 0.6 | MODIFY, giảm kích thước 193->181 | [5 empty] | MODIFY, giảm kích thước 193->181 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-12 |  | U284-07-CP011 | 5 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-10 | COL-5-P-10 | PL19*57 | 181 | A387 GR.11 CL.2 | 5 |  | 5 | 1.5 | 7.7 | AMC2 | Plate | MCC |  |  | 5 | 0 | 1 | [6 empty] | 0.2 | MODIFY, giảm kích thước 193->181 | [5 empty] | MODIFY, giảm kích thước 193->181 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-12 |  | U284-07-CP011 | 5 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-32 | COL-5-P-32 | PL10*111 | 152 | SS400 | 2 |  | 2 | 1.3 | 2.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 2 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | P-33 | COL-5-P-33 | PL10*152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 1 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | PY-1 | COL-5-PY-1 | PL25*400 | 900 | SM490 | 2 |  | 2 | 70.1 | 140.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0002-VTC-4 U284-17A-CP009-3 DCC25-U284-0002-VTC-3 U284-09B-CP005-1 PHỤC VỤ CHUNG |  | U284-07-CP016 | 2 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | PLATE | PY-2 | COL-5-PY-2 | PL20*181 | 812 | SM490 | 16 |  | 16 | 22.3 | 356.5 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 5.2 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-14-CP008 |  | U284-07-CP014 | 16 | 2026-04-16 | 0
| V17566-DWXD-7405 | COL-5 | CASING PLATE | SH-14 | COL-5-SH-14 | PL6*3422 | 24619 | SS400 | 1 |  | 1 | 3906.3 | 3906.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 166.7 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, bổ sung lỗ khoét theo basic sửa đổi. |  |  |  |  | MODIFY, bổ sung lỗ khoét | MODIFY, bổ sung lỗ khoét theo basic sửa đổi. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
85 | V17566-DRXD-7055 | DR070L |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 87.9 | 87.9 | AMC2 | [14 empty] | ADDED Gắn vào panel COL-5 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7055 | DR070L | PLATE | DR070-01 | DR070L-DR070-01 | PL10x940 | 1549 | SS400 | 1 |  | 1 | 40.4 | 40.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | LINER PLATE | DR070-04A | DR070L-DR070-04A | PL1.5x227 | 1429 | SS400 | 2 |  | 2 | 3.8 | 7.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | LINER PLATE | DR070-04B | DR070L-DR070-04B | PL1.5x227 | 819 | SS400 | 2 |  | 2 | 2.2 | 4.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-09 | DR070L-DR070-09 | PL10x152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | SCREWS | DR070-16 | DR070L-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7055 | DR070L | TADPOLE GASKET 2300°F | DR070-17 | DR070L-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-08
| V17566-DRXD-7055 | DR070L | ADHESIVE | DR070-18 | DR070L-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7055 | DR070L | GRAB BAR | DR070-110 | DR070L-DR070-110 | RB19 | 535 | SS400 | 1 |  | 1 | 1.2 | 1.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | DAVIT BRACKET | DR070-126 | DR070L-DR070-126 | PL10x89 | 344 | SS400 | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P01 | DR070L-DR070-P01 | PL10x51 | 54 | SS400 | 10 |  | 10 | 0.02 | 0.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P02 | DR070L-DR070-P02 | PL10x38 | 41 | SS400 | 20 |  | 20 | 0.01 | 0.2 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | FLAT WASHER | DR070-W01 | DR070L-DR070-W01 | ZINC PLATED, 1/2" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-02
| V17566-DRXD-7055 | DR070L | SQUARE SHOUDERED SOLID ROD END BLACK OXID | DR070-B01 | DR070L-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-03
| V17566-DRXD-7055 | DR070L | EASY GRIP HANDLE | DR070-GR01 | DR070L-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-04
| V17566-DRXD-7055 | DR070L | CLEVIS PIN WITH REUSABLE COTTER PIN | DR070-PN01 | DR070L-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-05
| V17566-DRXD-7055 | DR070L | FLAT WASHER | DR070-W02 | DR070L-DR070-W02 | ZINC PLATED, 5/8" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-06
| V17566-DRXD-7055 | DR070L | DAVIT | DR070-RB01 | DR070L-DR070-RB01 | RB45 | 1190 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | DAVIT WASHER | DR070-P03 | DR070L-DR070-P03 | PL10xID.46xOD.70 |  | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P04 | DR070L-DR070-P04 | PL10x270 | 467 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
85 | V17566-DRXD-7056 | DR070L |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 210 | 210 | AMC2 | [14 empty] | ADDED Gắn vào panel COL-5 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7056 | DR070L | ANGLE | DR071-02A | DR070L-DR071-02A | L100x75x10 | 880 | SS400 | 2 |  | 2 | 11.3 | 22.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | ANGLE | DR071-02B | DR070L-DR071-02B | L100x75x10 | 1490 | SS400 | 2 |  | 2 | 19.2 | 38.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | PLATE | DR071-20 | DR070L-DR071-20 | PL10x800 | 1410 | SS400 | 1 |  | 1 | 88.5 | 88.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | FLATBAR | DR071-21 | DR070L-DR071-21 | PL10x75 | 737 | SS400 | 3 |  | 3 | 4.4 | 13.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | FLATBAR | DR071-22 | DR070L-DR071-22 | PL10x75 | 236 | SS400 | 4 |  | 4 | 1.4 | 5.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-26A | DR070L-DR071-26A | PL1.5x140 | 699 | SS400 | 2 |  | 2 | 1.2 | 2.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-26B | DR070L-DR071-26B | PL1.5x140 | 1308 | SS400 | 2 |  | 2 | 2 | 4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-27 | DR070L-DR071-27 | PL1.5x683 | 1293 | SS400 | 1 |  | 1 | 10.4 | 10.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | STUD BOLT | DR071-28 | DR070L-DR071-28 | Ø10(M10) | 108 | SS400 | 8 |  | 8 | 0.15 | 1.2 | AMC2 | Shape | PMC |  |  | 8 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 8
| V17566-DRXD-7056 | DR070L | WASHER | DR071-29 | DR070L-DR071-29 | PL1.5 x OD76 x ID11 |  | SS400 | 16 |  | 16 | 0.07 | 1.12 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | HEX NUT | DR071-30 | DR070L-DR071-30 | M10 |  | SS400 | 16 |  | 16 | 0.01 | 0.16 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-21
| V17566-DRXD-7056 | DR070L | TADPOLE GASKET 1000°F | DR071-31 | DR070L-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.12 | 0.12 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-09
| V17566-DRXD-7056 | DR070L | ADHESIVE | DR071-32 | DR070L-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7056 | DR070L | SCREWS | DR071-33 | DR070L-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7056 | DR070L | DOOR HANDLE | DR071-111 | DR070L-DR071-111 | RB14 | 268 | SS400 | 2 |  | 2 | 0.15 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | GUSSET PLATE | DR071-112 | DR070L-DR071-112 | PL10x65 | 83 | SS400 | 20 |  | 20 | 0.4 | 8 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | DOOR HANGER | DR071-113 | DR070L-DR071-113 | RB14 | 350 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | EYE BOLT/2NUTS/1PW | DR071-114 | DR070L-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) |  | - | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-01
86 | V17566-DWXD-7441 | COL-7 | LEFT PANEL |  |  | (1262x549x12386) |  |  |  | 1 |  | 2103.7 | 2401.6 | AMC2 | [7 empty] | 0 | 0.162 |  |  |  |  | 58.9 | Bổ sung thêm khối lượng Access Door | x | o |  | REVISED | REVISED
| V17566-DWXD-7441 | COL-7 | ANGLE | A-20 | COL-7-A-20 | L90*90*10 | 1262 | SS400 | 1 |  | 1 | 16.8 | 16.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7441 | COL-7 | ANGLE | A-12 | COL-7-A-12 | L100*100*7 | 152 | SS400 | 2 |  | 2 | 1.6 | 3.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21 | 0
| V17566-DWXD-7441 | COL-7 | ANGLE | A-16 | COL-7-A-16 | L100*100*10 | 12373 | SS400 | 1 |  | 1 | 184.5 | 184.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-15 | COL-7-CY-15 | [200*80*7.5*11 | 295 | SS400 | 6 |  | 6 | 6.2 | 37 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 1.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-23 | COL-7-CY-23 | [200*80*7.5*11 | 10127 | SS400 | 1 |  | 1 | 244.5 | 244.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-25 | COL-7-CY-25 | [200*80*7.5*11 | 10127 | SS400 | 1 |  | 1 | 244.5 | 244.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-26 | COL-7-CY-26 | [200*80*7.5*11 | 722 | SS400 | 6 |  | 6 | 14.7 | 88.3 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 2.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-63 | COL-7-CY-63 | [200*80*7.5*11 | 1089 | SS400 | 2 |  | 2 | 25.6 | 51.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-64 | COL-7-CY-64 | [200*80*7.5*11 | 1089 | SS400 | 1 |  | 1 | 25.6 | 25.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | [13 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | CHANNEL | CY-65 | COL-7-CY-65 | [200*80*7.5*11 | 57 | SS400 | 6 |  | 6 | 1.3 | 7.6 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22 | 0
| V17566-DWXD-7441 | COL-7 | PIPE | D-3 | COL-7-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 3 |  | 3 | 4.9 | 14.6 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 3 | 2026-04-21 | 0
| V17566-DWXD-7441 | COL-7 | PIPE | D-4 | COL-7-D-4 | 4" SCH.40 | 309 | A-312 TP.304 | 1 |  | 1 | 4.9 | 4.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | Cắt dương lên 5mm MODIFY, giảm Q.ty: 2->1 |  |  |  |  | MODIFY, giảm Q.ty: 2->1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-14 |  | U284-07-CP509 | 2 | 2026-04-21 | -1
| V17566-DWXD-7441 | COL-7 | PIPE | D-5 | COL-7-D-5 | 8" SCH.40 | 309 | A-106 Gr.B | 2 |  | 2 | 13.1 | 26.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.4 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-10 |  | U284-07-CP511 | 2 | 2026-04-21 | 0
| V17566-DWXD-7441 | COL-7 | PIPE | D-6 | COL-7-D-6 | 2" SCH.40 | 137 | A-106 Gr.B | 11 |  | 11 | 0.7 | 8 | AMC2 | Shape | MCC |  |  | 11 | 0 | 1 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 11 | 2026-04-21 | 0
| V17566-DWXD-7441 | COL-7 | PIPE | D-11 | COL-7-D-11 | 4" SCH.40 | 309 | A-106 Gr.B | 1 |  | 1 | 4.9 | 4.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-01-CP503-1 |  | U284-07-CP525 | 1 | 2026-05-07 | 0
| V17566-DWXD-7441 | COL-7 | PIPE | DZ-1 | COL-7-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 2 |  | 2 | 0.5 | 0.9 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21 | 0
| V17566-DWXD-7441 | COL-7 | PLATE | G-9 | COL-7-G-9 | PL6*360 | 360 | SS400 | 2 |  | 2 | 3 | 6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16 | 0
| V17566-DWXD-7441 | COL-7 | PLATE | G-28 | COL-7-G-28 | PL6*60 | 60 | A-240 TP304 | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07 | 0
| V17566-DWXD-7441 | COL-7 | H-BEAM | H-7 | COL-7-H-7 | H194*150*6*9 | 2187 | SS400 | 1 |  | 1 | 65.4 | 65.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21 | 0
| V17566-DWXD-7441 | COL-7 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 7 |  | 7 | 0.2 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 7 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 7 |  | 0
| V17566-DWXD-7441 | COL-7 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 258 |  | 258 | 0 | 3.2 | AMC2 | Purchasing | KHO |  |  | 0 | 258 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 258 |  | 0
| V17566-DWXD-7441 | COL-7 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 5 |  | 5 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 5 |  | 0
| V17566-DWXD-7441 | COL-7 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 2 |  | 2 | 1.4 | 2.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 2 |  | 0
| V17566-DWXD-7441 | COL-7 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 2 |  | 2 | 0.6 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 2 |  | 0
| V17566-DWXD-7441 | COL-7 | GASKET 8" 150# | M-14 |  | PL3*268 | 269 | NON-METALLIC | 2 |  | 2 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-12 |  |  | 2 |  | 0
| V17566-DWXD-7441 | COL-7 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 4 |  | 4 | 0.1 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [7 empty] | MODIFY, giảm Q.ty: 5->4 |  |  |  |  | MODIFY, giảm Q.ty: 5->4 | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 4
| V17566-DWXD-7441 | COL-7 | FLANGE 4" 150# SO-RF | M-18 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 5.9 | 29.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 5 |  | 0
| V17566-DWXD-7441 | COL-7 | 4" 150# RF BLIND FLG. | M-19 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 7.6 | 38.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 5 |  | 0
| V17566-DWXD-7441 | COL-7 | FLANGE 8" 150# SO-RF | M-21 |  | PL27*342 | 343 | A-105 | 2 |  | 2 | 12.9 | 25.8 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-10 |  |  | 2 |  | 0
| V17566-DWXD-7441 | COL-7 | 8" 150# RF BLIND FLG. | M-22 |  | PL27*342 | 342 | A-105 | 2 |  | 2 | 20.4 | 40.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-11 |  |  | 2 |  | 0
| V17566-DWXD-7441 | COL-7 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 123 |  | 123 | 0 | 6.1 | AMC2 | Purchasing | KHO |  |  | 0 | 123 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 123 |  | 0
| V17566-DWXD-7441 | COL-7 | PLATE | P-8 | COL-7-P-8 | PL6*127 | 127 | SS400 | 11 |  | 11 | 0.6 | 6.5 | AMC2 | Plate | MCC |  |  | 11 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 11 | 2026-04-16 | 0
| V17566-DWXD-7441 | COL-7 | PLATE | P-31 | COL-7-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7441 | COL-7 | PLATE | P-34 | COL-7-P-34 | PL6*52 | 52 | SS400 | 11 |  | 11 | 0.1 | 1.1 | AMC2 | Plate | MCC |  |  | 11 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 11 | 2026-04-16 | 0
| V17566-DWXD-7441 | COL-7 | CASING PLATE | SH-5 | COL-7-SH-5 | PL6*1136 | 12360 | SS400 | 1 |  | 1 | 603 | 603 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 25.8 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
86 | V17566-DRXD-7055 | DR070L |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 87.9 | 87.9 | AMC2 | [14 empty] | ADDED Gắn vào panel COL-7 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7055 | DR070L | PLATE | DR070-01 | DR070L-DR070-01 | PL10x940 | 1549 | SS400 | 1 |  | 1 | 40.4 | 40.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | LINER PLATE | DR070-04A | DR070L-DR070-04A | PL1.5x227 | 1429 | SS400 | 2 |  | 2 | 3.8 | 7.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | LINER PLATE | DR070-04B | DR070L-DR070-04B | PL1.5x227 | 819 | SS400 | 2 |  | 2 | 2.2 | 4.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-09 | DR070L-DR070-09 | PL10x152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | SCREWS | DR070-16 | DR070L-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7055 | DR070L | TADPOLE GASKET 2300°F | DR070-17 | DR070L-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-08
| V17566-DRXD-7055 | DR070L | ADHESIVE | DR070-18 | DR070L-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7055 | DR070L | GRAB BAR | DR070-110 | DR070L-DR070-110 | RB19 | 535 | SS400 | 1 |  | 1 | 1.2 | 1.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | DAVIT BRACKET | DR070-126 | DR070L-DR070-126 | PL10x89 | 344 | SS400 | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P01 | DR070L-DR070-P01 | PL10x51 | 54 | SS400 | 10 |  | 10 | 0.02 | 0.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P02 | DR070L-DR070-P02 | PL10x38 | 41 | SS400 | 20 |  | 20 | 0.01 | 0.2 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | FLAT WASHER | DR070-W01 | DR070L-DR070-W01 | ZINC PLATED, 1/2" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-02
| V17566-DRXD-7055 | DR070L | SQUARE SHOUDERED SOLID ROD END BLACK OXID | DR070-B01 | DR070L-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-03
| V17566-DRXD-7055 | DR070L | EASY GRIP HANDLE | DR070-GR01 | DR070L-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-04
| V17566-DRXD-7055 | DR070L | CLEVIS PIN WITH REUSABLE COTTER PIN | DR070-PN01 | DR070L-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-05
| V17566-DRXD-7055 | DR070L | FLAT WASHER | DR070-W02 | DR070L-DR070-W02 | ZINC PLATED, 5/8" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-06
| V17566-DRXD-7055 | DR070L | DAVIT | DR070-RB01 | DR070L-DR070-RB01 | RB45 | 1190 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | DAVIT WASHER | DR070-P03 | DR070L-DR070-P03 | PL10xID.46xOD.70 |  | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070L | PLATE | DR070-P04 | DR070L-DR070-P04 | PL10x270 | 467 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
86 | V17566-DRXD-7056 | DR070L |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 210 | 210 | AMC2 | [14 empty] | ADDED Gắn vào panel COL-7 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7056 | DR070L | ANGLE | DR071-02A | DR070L-DR071-02A | L100x75x10 | 880 | SS400 | 2 |  | 2 | 11.3 | 22.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | ANGLE | DR071-02B | DR070L-DR071-02B | L100x75x10 | 1490 | SS400 | 2 |  | 2 | 19.2 | 38.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | PLATE | DR071-20 | DR070L-DR071-20 | PL10x800 | 1410 | SS400 | 1 |  | 1 | 88.5 | 88.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | FLATBAR | DR071-21 | DR070L-DR071-21 | PL10x75 | 737 | SS400 | 3 |  | 3 | 4.4 | 13.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | FLATBAR | DR071-22 | DR070L-DR071-22 | PL10x75 | 236 | SS400 | 4 |  | 4 | 1.4 | 5.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-26A | DR070L-DR071-26A | PL1.5x140 | 699 | SS400 | 2 |  | 2 | 1.2 | 2.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-26B | DR070L-DR071-26B | PL1.5x140 | 1308 | SS400 | 2 |  | 2 | 2 | 4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | LINER PLATE | DR071-27 | DR070L-DR071-27 | PL1.5x683 | 1293 | SS400 | 1 |  | 1 | 10.4 | 10.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | STUD BOLT | DR071-28 | DR070L-DR071-28 | Ø10(M10) | 108 | SS400 | 8 |  | 8 | 0.15 | 1.2 | AMC2 | Shape | PMC |  |  | 8 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 8
| V17566-DRXD-7056 | DR070L | WASHER | DR071-29 | DR070L-DR071-29 | PL1.5 x OD76 x ID11 |  | SS400 | 16 |  | 16 | 0.07 | 1.12 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | HEX NUT | DR071-30 | DR070L-DR071-30 | M10 |  | SS400 | 16 |  | 16 | 0.01 | 0.16 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-21
| V17566-DRXD-7056 | DR070L | TADPOLE GASKET 1000°F | DR071-31 | DR070L-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.12 | 0.12 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-09
| V17566-DRXD-7056 | DR070L | ADHESIVE | DR071-32 | DR070L-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7056 | DR070L | SCREWS | DR071-33 | DR070L-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7056 | DR070L | DOOR HANDLE | DR071-111 | DR070L-DR071-111 | RB14 | 268 | SS400 | 2 |  | 2 | 0.15 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | GUSSET PLATE | DR071-112 | DR070L-DR071-112 | PL10x65 | 83 | SS400 | 20 |  | 20 | 0.4 | 8 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | DOOR HANGER | DR071-113 | DR070L-DR071-113 | RB14 | 350 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070L | EYE BOLT/2NUTS/1PW | DR071-114 | DR070L-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) |  | - | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-01
87 | V17566-DWXD-7445 | COL-8 | LEFT PANEL |  |  | (1262x412x12259) |  |  |  | 1 |  | 2058.5 | 2058.5 | AMC2 | [7 empty] | 0 | 0.13158 |  |  |  |  | 58.3 | REVISED | x | o |  | REVISED | REVISED
| V17566-DWXD-7445 | COL-8 | ANGLE | A-9 | COL-8-A-9 | L90*90*10 | 1262 | SS400 | 1 |  | 1 | 16.8 | 16.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 |  |  |  |  | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22 | 0
| V17566-DWXD-7445 | COL-8 | ANGLE | A-15 | COL-8-A-15 | L100*100*10 | 12246 | SS400 | 1 |  | 1 | 182.6 | 182.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7445 | COL-8 | ANGLE | AY-6 | COL-8-AY-6 | L75*75*6 | 1089 | SS400 | 1 |  | 1 | 7.5 | 7.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22 | 0
| V17566-DWXD-7445 | COL-8 | CHANNEL | CY-15 | COL-8-CY-15 | [200*80*7.5*11 | 295 | SS400 | 8 |  | 8 | 6.2 | 49.3 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 1.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22 | 0
| V17566-DWXD-7445 | COL-8 | CHANNEL | CY-22 | COL-8-CY-22 | [200*80*7.5*11 | 12246 | SS400 | 1 |  | 1 | 296.8 | 296.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12116->12246 |  |  |  |  | MODIFY, tăng chiều dài 12116->12246 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7445 | COL-8 | CHANNEL | CY-24 | COL-8-CY-24 | [200*80*7.5*11 | 12246 | SS400 | 1 |  | 1 | 296.8 | 296.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12116->12246 |  |  |  |  | MODIFY, tăng chiều dài 12116->12246 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7445 | COL-8 | CHANNEL | CY-26 | COL-8-CY-26 | [200*80*7.5*11 | 722 | SS400 | 8 |  | 8 | 14.7 | 117.8 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 3.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22 | 0
| V17566-DWXD-7445 | COL-8 | CHANNEL | CY-65 | COL-8-CY-65 | [200*80*7.5*11 | 57 | SS400 | 8 |  | 8 | 1.3 | 10.2 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22 | 0
| V17566-DWXD-7445 | COL-8 | PIPE | D-3 | COL-8-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 4 |  | 4 | 4.9 | 19.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21 | 0
| V17566-DWXD-7445 | COL-8 | PIPE | D-6 | COL-8-D-6 | 2" SCH.40 | 137 | A-106 Gr.B | 7 |  | 7 | 0.7 | 5.1 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0.2 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 7 | 2026-04-21 | 0
| V17566-DWXD-7445 | COL-8 | PIPE | DZ-1 | COL-8-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21 | 0
| V17566-DWXD-7445 | COL-8 | PIPE | DZ-2 | COL-8-DZ-2 | 3/4" SCH.80 | 86 | A-106 Gr.B | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP507-1 |  | U284-07-CP523 | 1 | 2026-05-07 | 0
| V17566-DWXD-7445 | COL-8 | PLATE | G-28 | COL-8-G-28 | PL6*60 | 60 | A-240 TP304 | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07 | 0
| V17566-DWXD-7445 | COL-8 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 4 |  | 4 | 0.2 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 4 |  | 0
| V17566-DWXD-7445 | COL-8 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 272 |  | 272 | 0 | 3.3 | AMC2 | Purchasing | KHO |  |  | 0 | 272 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 272 |  | 0
| V17566-DWXD-7445 | COL-8 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 4 |  | 4 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 4 |  | 0
| V17566-DWXD-7445 | COL-8 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 1 |  | 1 | 1.4 | 1.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 1 |  | 0
| V17566-DWXD-7445 | COL-8 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 1 |  | 0
| V17566-DWXD-7445 | COL-8 | COUPING FULL THREAD | M-11 |  | 3/4" 3000# COUPING FULL THREAD | 51 | A-105 | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-24 |  |  | 1 |  | 0
| V17566-DWXD-7445 | COL-8 | SQUARE HEAD PLUG | M-12 |  | 3/4" 3000# SQUARE HEAD PLUG | 24 | A-105 | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-25 |  |  |  |  | 1
| V17566-DWXD-7445 | COL-8 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 4 |  | 4 | 0.1 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [7 empty] | MODIFY, giảm Q.ty: 5->4 |  |  |  |  | MODIFY, giảm Q.ty: 5->4 | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 4
| V17566-DWXD-7445 | COL-8 | FLANGE 4" 150# SO-RF | M-18 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 5.9 | 23.6 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 4 |  | 0
| V17566-DWXD-7445 | COL-8 | 4" 150# RF BLIND FLG. | M-19 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 7.6 | 30.5 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 4 |  | 0
| V17566-DWXD-7445 | COL-8 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 132 |  | 132 | 0 | 6.5 | AMC2 | Purchasing | KHO |  |  | 0 | 132 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 132 |  | 0
| V17566-DWXD-7445 | COL-8 | PLATE | P-8 | COL-8-P-8 | PL6*127 | 127 | SS400 | 7 |  | 7 | 0.6 | 4.2 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 7 | 2026-04-16 | 0
| V17566-DWXD-7445 | COL-8 | PLATE | P-31 | COL-8-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7445 | COL-8 | PLATE | P-34 | COL-8-P-34 | PL6*52 | 52 | SS400 | 7 |  | 7 | 0.1 | 0.7 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 7 | 2026-04-16 | 0
| V17566-DWXD-7445 | COL-8 | CASING PLATE | SH-16 | COL-8-SH-16 | PL6*1136 | 12233 | SS400 | 1 |  | 1 | 652.3 | 652.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 27.9 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, bổ sung lỗ khoét |  |  |  |  | MODIFY, bổ sung lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
88 | V17566-DWXD-7449 | COR-1 | RIGHT PANEL |  |  | (568x2786x12332) |  |  |  | 1 |  | 5046 | 5343.9 | AMC2 | [7 empty] | 0 | 0.16523 |  |  |  |  | 138 | Bổ sung thêm khối lượng Access Door | x | o |  | REVISED | REVISED
| V17566-DWXD-7449 | COR-1 | ANGLE | A-2 | COR-1-A-2 | L100*100*10 | 12313 | SS400 | 1 |  | 1 | 183.6 | 183.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7449 | COR-1 | ANGLE | A-7 | COR-1-A-7 | L90*90*10 | 2786 | SS400 | 1 |  | 1 | 37.2 | 37.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 |  |  |  |  | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | ANGLE | A-12 | COR-1-A-12 | L100*100*7 | 152 | SS400 | 2 |  | 2 | 1.6 | 3.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21 | 0
| V17566-DWXD-7449 | COR-1 | BUILT-UP CHANNEL | B-2 | COR-1-B-2 | B354*100*9*13 | 12332 | SS400 | 1 |  | 1 | 537.5 | 537.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 13.4 | Cắt dương lên 50mm theo yêu cầu KOM, Flange không khoan lỗ MODIFY, Tăng chiều dài: 12319->12332 |  |  |  | MODIFY, Tăng chiều dài: 12319->12332 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-1 | COR-1-CY-1 | [200*80*7.5*11 | 2327 | SS400 | 1 |  | 1 | 54.2 | 54.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-5 | COR-1-CY-5 | [200*80*7.5*11 | 1388 | SS400 | 1 |  | 1 | 31.4 | 31.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-6 | COR-1-CY-6 | [200*80*7.5*11 | 455 | SS400 | 7 |  | 7 | 10 | 69.9 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-7 | COR-1-CY-7 | [200*80*7.5*11 | 2629 | SS400 | 1 |  | 1 | 61.5 | 61.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.8 | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt |  |  |  |  | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-10 | COR-1-CY-10 | [200*80*7.5*11 | 3295 | SS400 | 1 |  | 1 | 78.5 | 78.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-11 | COR-1-CY-11 | [200*80*7.5*11 | 1263 | SS400 | 2 |  | 2 | 29.2 | 58.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-13 | COR-1-CY-13 | [200*80*7.5*11 | 931 | SS400 | 2 |  | 2 | 21.1 | 42.2 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.2 | MODIFY, Giảm chiều dài: 932-> 931 |  |  |  | MODIFY, Giảm chiều dài: 932-> 931 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-15 | COR-1-CY-15 | [200*80*7.5*11 | 295 | SS400 | 10 |  | 10 | 6.2 | 61.6 | AMC2 | Shape | MCC |  |  | 10 | 0 | 1 | [6 empty] | 1.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 10 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-17 | COR-1-CY-17 | [200*80*7.5*11 | 10066 | SS400 | 1 |  | 1 | 243 | 243 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 6.9 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-18 | COR-1-CY-18 | [200*80*7.5*11 | 1864 | SS400 | 7 |  | 7 | 42.5 | 297.3 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 8.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7449 | COR-1 | CHANNEL | CY-19 | COR-1-CY-19 | [200*80*7.5*11 | 12227 | SS400 | 1 |  | 1 | 295.7 | 295.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7449 | COR-1 | PIPE | D-3 | COR-1-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 4 |  | 4 | 4.9 | 19.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.6 | Cắt dương lên 5mm MODIFY, giảm Q.ty: 5->4 |  |  |  |  | MODIFY, giảm Q.ty: 5->4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 5 | 2026-04-21 | -1
| V17566-DWXD-7449 | COR-1 | PIPE | DZ-1 | COR-1-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 2 |  | 2 | 0.5 | 0.9 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | 5.9 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21 | 0
| V17566-DWXD-7449 | COR-1 | PIPE | D-9 | COR-1-D-9 | 3" SCH.40 | 436 | A-106 Gr.C | 48 |  | 48 | 4.8 | 230.7 | AMC2 | Shape | MCC |  |  | 48 | 0 | 1 | [6 empty] | 0.7 | Cắt dương lên 5mm MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí |  |  |  | MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21 | 0
| V17566-DWXD-7449 | COR-1 | PIPE | D-10 | COR-1-D-10 | 4" SCH.40 | 309 | A-312 TP.304 | 1 |  | 1 | 4.9 | 4.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP509-1 |  | U284-07-CP524 | 1 | 2026-05-07 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | G-11 | COR-1-G-11 | PL10*228 | 229 | SS400 | 28 |  | 28 | 2.7 | 75.9 | AMC2 | Plate | MCC |  |  | 28 | 0 | 1 | [6 empty] | 2.3 | MODIFY, Giảm Q.ty: 29->28 |  |  |  |  | MODIFY, Giảm Q.ty: 29->28 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 29 | 2026-04-16 | -1
| V17566-DWXD-7449 | COR-1 | PLATE | G-11-8001 | COR-1-G-11-8001 | PL10*190 | 229 | SS400 | 1 |  | 1 | 2.5 | 2.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-01-CP003-4 |  | U284-07-CP024 | 1 | 2026-05-07 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | G-15 | COR-1-G-15 | PL10*207 | 229 | SS400 | 10 |  | 10 | 2.3 | 23.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | 0.7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 10 | 2026-04-16 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | G-16 | COR-1-G-16 | PL10*208 | 229 | SS400 | 9 |  | 9 | 2.3 | 21 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | G-28 | COR-1-G-28 | PL6*60 | 60 | A-240 TP304 | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07 | 0
| V17566-DWXD-7449 | COR-1 | H-BEAM | H-1 | COR-1-H-1 | H194*150*6*9 | 2261 | SS400 | 1 |  | 1 | 67.6 | 67.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.2 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21 | 0
| V17566-DWXD-7449 | COR-1 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 5 |  | 5 | 0.2 | 0.9 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 5 |  | 0
| V17566-DWXD-7449 | COR-1 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 530 |  | 530 | 0 | 6.5 | AMC2 | Purchasing | KHO |  |  | 0 | 530 | 0 | [7 empty] | MODIFY, Giảm Q.ty: 536->530 |  |  |  | MODIFY, Giảm Q.ty: 536->530 | [8 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 530 |  | 0
| V17566-DWXD-7449 | COR-1 | FLANGE 4" 150# SO-RF | M-6 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 5.9 | 29.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 5 |  | 0
| V17566-DWXD-7449 | COR-1 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 5 |  | 5 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 5 |  | 0
| V17566-DWXD-7449 | COR-1 | 4" 150# RF BLIND FLG. | M-8 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 7.6 | 38.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 5 |  | 0
| V17566-DWXD-7449 | COR-1 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 2 |  | 2 | 1.4 | 2.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 2 |  | 0
| V17566-DWXD-7449 | COR-1 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 2 |  | 2 | 0.6 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 2 |  | 0
| V17566-DWXD-7449 | COR-1 | FLANGE 3" 150# SO-RF | M-16 |  | PL22*191 | 191 | A-105 | 48 |  | 48 | 4.1 | 196.2 | AMC2 | Purchasing | KHO |  |  | 0 | 48 | 0 | [6 empty] | 3.3 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-18 |  |  | 48 |  | 0
| V17566-DWXD-7449 | COR-1 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 5 |  | 5 | 0.1 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 5
| V17566-DWXD-7449 | COR-1 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 260 |  | 260 | 0 | 12.8 | AMC2 | Purchasing | KHO |  |  | 0 | 260 | 0 | [7 empty] | MODIFY, Giảm Q.ty: 263->260 |  |  |  | MODIFY, Giảm Q.ty: 263->260 | [8 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 260 |  | 0
| V17566-DWXD-7449 | COR-1 | PLATE | P-7 | COR-1-P-7 | PL12*89 | 141 | SS400 | 10 |  | 10 | 1.2 | 11.7 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 10 | 2026-04-16 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | P-27 | COR-1-P-27 | PL25*168 | 305 | A387 GR.11 CL.2 | 2 |  | 2 | 10.1 | 20.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 2 | 2026-07-09 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | P-28 | COR-1-P-28 | PL12*64 | 64 | A387 GR.11 CL.2 | 8 |  | 8 | 0.3 | 2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 8 | 2026-04-16 | 0
| V17566-DWXD-7449 | COR-1 | PLATE | P-31 | COR-1-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7449 | COR-1 | CASING PLATE | SH-2 | COR-1-SH-2 | PL6*2560 | 12300 | SS400 | 1 |  | 1 | 1413.5 | 1413.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 60.3 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
88 | V17566-DRXD-7055 | DR070R |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 87.9 | 87.9 | AMC2 | [14 empty] | ADDED Gắn vào panel COR-1 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7055 | DR070R | PLATE | DR070-01 | DR070R-DR070-01 | PL10x940 | 1549 | SS400 | 1 |  | 1 | 40.4 | 40.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | LINER PLATE | DR070-04A | DR070R-DR070-04A | PL1.5x227 | 1429 | SS400 | 2 |  | 2 | 3.8 | 7.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | LINER PLATE | DR070-04B | DR070R-DR070-04B | PL1.5x227 | 819 | SS400 | 2 |  | 2 | 2.2 | 4.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-09 | DR070R-DR070-09 | PL10x152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | SCREWS | DR070-16 | DR070R-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7055 | DR070R | TADPOLE GASKET 2300°F | DR070-17 | DR070R-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-08
| V17566-DRXD-7055 | DR070R | ADHESIVE | DR070-18 | DR070R-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7055 | DR070R | GRAB BAR | DR070-110 | DR070R-DR070-110 | RB19 | 535 | SS400 | 1 |  | 1 | 1.2 | 1.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | DAVIT BRACKET | DR070-126 | DR070R-DR070-126 | PL10x89 | 344 | SS400 | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P01 | DR070R-DR070-P01 | PL10x51 | 54 | SS400 | 10 |  | 10 | 0.02 | 0.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P02 | DR070R-DR070-P02 | PL10x38 | 41 | SS400 | 20 |  | 20 | 0.01 | 0.2 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | FLAT WASHER | DR070-W01 | DR070R-DR070-W01 | ZINC PLATED, 1/2" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-02
| V17566-DRXD-7055 | DR070R | SQUARE SHOUDERED SOLID ROD END BLACK OXID | DR070-B01 | DR070R-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-03
| V17566-DRXD-7055 | DR070R | EASY GRIP HANDLE | DR070-GR01 | DR070R-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-04
| V17566-DRXD-7055 | DR070R | CLEVIS PIN WITH REUSABLE COTTER PIN | DR070-PN01 | DR070R-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-05
| V17566-DRXD-7055 | DR070R | FLAT WASHER | DR070-W02 | DR070R-DR070-W02 | ZINC PLATED, 5/8" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-06
| V17566-DRXD-7055 | DR070R | DAVIT | DR070-RB01 | DR070R-DR070-RB01 | RB45 | 1190 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | DAVIT WASHER | DR070-P03 | DR070R-DR070-P03 | PL10xID.46xOD.70 |  | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P04 | DR070R-DR070-P04 | PL10x270 | 467 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
88 | V17566-DRXD-7056 | DR070R |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 210 | 210 | AMC2 | [14 empty] | ADDED Gắn vào panel COR-1 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7056 | DR070R | ANGLE | DR071-02A | DR070R-DR071-02A | L100x75x10 | 880 | SS400 | 2 |  | 2 | 11.3 | 22.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | ANGLE | DR071-02B | DR070R-DR071-02B | L100x75x10 | 1490 | SS400 | 2 |  | 2 | 19.2 | 38.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | PLATE | DR071-20 | DR070R-DR071-20 | PL10x800 | 1410 | SS400 | 1 |  | 1 | 88.5 | 88.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | FLATBAR | DR071-21 | DR070R-DR071-21 | PL10x75 | 737 | SS400 | 3 |  | 3 | 4.4 | 13.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | FLATBAR | DR071-22 | DR070R-DR071-22 | PL10x75 | 236 | SS400 | 4 |  | 4 | 1.4 | 5.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-26A | DR070R-DR071-26A | PL1.5x140 | 699 | SS400 | 2 |  | 2 | 1.2 | 2.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-26B | DR070R-DR071-26B | PL1.5x140 | 1308 | SS400 | 2 |  | 2 | 2 | 4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-27 | DR070R-DR071-27 | PL1.5x683 | 1293 | SS400 | 1 |  | 1 | 10.4 | 10.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | STUD BOLT | DR071-28 | DR070R-DR071-28 | Ø10(M10) | 108 | SS400 | 8 |  | 8 | 0.15 | 1.2 | AMC2 | Shape | PMC |  |  | 8 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 8
| V17566-DRXD-7056 | DR070R | WASHER | DR071-29 | DR070R-DR071-29 | PL1.5 x OD76 x ID11 |  | SS400 | 16 |  | 16 | 0.07 | 1.12 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | HEX NUT | DR071-30 | DR070R-DR071-30 | M10 |  | SS400 | 16 |  | 16 | 0.01 | 0.16 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-21
| V17566-DRXD-7056 | DR070R | TADPOLE GASKET 1000°F | DR071-31 | DR070R-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.12 | 0.12 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-09
| V17566-DRXD-7056 | DR070R | ADHESIVE | DR071-32 | DR070R-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7056 | DR070R | SCREWS | DR071-33 | DR070R-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7056 | DR070R | DOOR HANDLE | DR071-111 | DR070R-DR071-111 | RB14 | 268 | SS400 | 2 |  | 2 | 0.15 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | GUSSET PLATE | DR071-112 | DR070R-DR071-112 | PL10x65 | 83 | SS400 | 20 |  | 20 | 0.4 | 8 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | DOOR HANGER | DR071-113 | DR070R-DR071-113 | RB14 | 350 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | EYE BOLT/2NUTS/1PW | DR071-114 | DR070R-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) |  | - | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-01
89 | V17566-DWXD-7454 | COR-2 | RIGHT PANEL |  |  | (530x2786x12325) |  |  |  | 1 |  | 4999.6 | 4999.6 | AMC2 | [7 empty] | 0 | 0.16698 |  |  |  |  | 136.2 | REVISED | x | o |  | REVISED | REVISED
| V17566-DWXD-7454 | COR-2 | ANGLE | A-1 | COR-2-A-1 | L100*100*10 | 12306 | SS400 | 1 |  | 1 | 183.5 | 183.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7454 | COR-2 | ANGLE | A-17 | COR-2-A-17 | L90*90*10 | 2786 | SS400 | 1 |  | 1 | 37.2 | 37.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7454 | COR-2 | ANGLE | AY-1 | COR-2-AY-1 | L75*75*6 | 2629 | SS400 | 1 |  | 1 | 18 | 18 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt |  |  |  |  | MODIFY, bổ sung vết cắt theo basic sửa đổi Thay đổi lỗ bolt | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22 | 0
| V17566-DWXD-7454 | COR-2 | BUILT-UP CHANNEL | B-1 | COR-2-B-1 | B354*100*9*13 | 12325 | SS400 | 1 |  | 1 | 537.2 | 537.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 13.4 | Cắt dương lên 50mm theo yêu cầu KOM, Flange không khoan lỗ | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-6 | COR-2-CY-6 | [200*80*7.5*11 | 455 | SS400 | 9 |  | 9 | 10 | 89.9 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 2.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-11 | COR-2-CY-11 | [200*80*7.5*11 | 1263 | SS400 | 2 |  | 2 | 29.2 | 58.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-14 | COR-2-CY-14 | [200*80*7.5*11 | 12306 | SS400 | 1 |  | 1 | 298.2 | 298.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12176->12306 |  |  |  |  | MODIFY, tăng chiều dài 12176->12306 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-15 | COR-2-CY-15 | [200*80*7.5*11 | 295 | SS400 | 9 |  | 9 | 6.2 | 55.5 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 1.7 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-16 | COR-2-CY-16 | [200*80*7.5*11 | 12306 | SS400 | 1 |  | 1 | 298.2 | 298.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12176->12306 |  |  |  |  | MODIFY, tăng chiều dài 12176->12306 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-18 | COR-2-CY-18 | [200*80*7.5*11 | 1864 | SS400 | 9 |  | 9 | 42.5 | 382.3 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 11 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-20 | COR-2-CY-20 | [200*80*7.5*11 | 1301 | SS400 | 1 |  | 1 | 29.4 | 29.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7454 | COR-2 | CHANNEL | CY-21 | COR-2-CY-21 | [200*80*7.5*11 | 838 | SS400 | 1 |  | 1 | 20.3 | 20.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 | MODIFY, tăng chiều dài 708->838 |  |  |  |  | MODIFY, tăng chiều dài 708->838 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27 | 0
| V17566-DWXD-7454 | COR-2 | PIPE | D-3 | COR-2-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 4 |  | 4 | 4.9 | 19.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21 | 0
| V17566-DWXD-7454 | COR-2 | PIPE | DZ-1 | COR-2-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21 | 0
| V17566-DWXD-7454 | COR-2 | PIPE | D-9 | COR-2-D-9 | 3" SCH.40 | 436 | A-106 Gr.C | 48 |  | 48 | 4.8 | 230.7 | AMC2 | Shape | MCC |  |  | 48 | 0 | 1 | [6 empty] | 0.7 | Cắt dương lên 5mm MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí |  |  |  | MODIFY, đổi mark DZ-3 thành D-9, Không cần nguyên công gia công cơ khí | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-11 |  | U284-07-CP505 | 48 | 2026-04-21 | 0
| V17566-DWXD-7454 | COR-2 | PLATE | G-11 | COR-2-G-11 | PL10*228 | 229 | SS400 | 29 |  | 29 | 2.7 | 78.6 | AMC2 | Plate | MCC |  |  | 29 | 0 | 1 | [6 empty] | 2.4 | MODIFY, giảm Q.ty: 30->29 |  |  |  |  | MODIFY, giảm Q.ty: 30->29 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 30 | 2026-04-16 | -1
| V17566-DWXD-7454 | COR-2 | PLATE | G-11-8000 |  | PL10*190 | 229 | SS400 | 1 |  | 1 | 2.5 | 2.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.1 | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung
| V17566-DWXD-7454 | COR-2 | PLATE | G-13 | COR-2-G-13 | PL10*208 | 229 | SS400 | 9 |  | 9 | 2.3 | 21.1 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16 | 0
| V17566-DWXD-7454 | COR-2 | PLATE | G-14 | COR-2-G-14 | PL10*206 | 229 | SS400 | 9 |  | 9 | 2.3 | 20.8 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 9 | 2026-04-16 | 0
| V17566-DWXD-7454 | COR-2 | PLATE | G-28 | COR-2-G-28 | PL6*60 | 60 | A-240 TP304 | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07 | 0
| V17566-DWXD-7454 | COR-2 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 4 |  | 4 | 0.2 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 4 |  | 0
| V17566-DWXD-7454 | COR-2 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 536 |  | 536 | 0 | 6.6 | AMC2 | Purchasing | KHO |  |  | 0 | 536 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 536 |  | 0
| V17566-DWXD-7454 | COR-2 | FLANGE 4" 150# SO-RF | M-6 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 5.9 | 23.6 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 4 |  | 0
| V17566-DWXD-7454 | COR-2 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 4 |  | 4 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 4 |  | 0
| V17566-DWXD-7454 | COR-2 | 4" 150# RF BLIND FLG. | M-8 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 7.6 | 30.5 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 4 |  | 0
| V17566-DWXD-7454 | COR-2 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 1 |  | 1 | 1.4 | 1.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 1 |  | 0
| V17566-DWXD-7454 | COR-2 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 1 |  | 0
| V17566-DWXD-7454 | COR-2 | FLANGE 3" 150# SO-RF | M-16 |  | PL22*191 | 191 | A-105 | 48 |  | 48 | 4.1 | 196.2 | AMC2 | Purchasing | KHO |  |  | 0 | 48 | 0 | [6 empty] | 3.3 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-18 |  |  | 48 |  | 0
| V17566-DWXD-7454 | COR-2 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 5 |  | 5 | 0.1 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 5
| V17566-DWXD-7454 | COR-2 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 264 |  | 264 | 0 | 13 | AMC2 | Purchasing | KHO |  |  | 0 | 264 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 264 |  | 0
| V17566-DWXD-7454 | COR-2 | PLATE | P-7 | COR-2-P-7 | PL12*89 | 141 | SS400 | 9 |  | 9 | 1.2 | 10.5 | AMC2 | Plate | MCC |  |  | 9 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 9 | 2026-04-16 | 0
| V17566-DWXD-7454 | COR-2 | PLATE | P-27 | COR-2-P-27 | PL25*168 | 305 | A387 GR.11 CL.2 | 4 |  | 4 | 10.1 | 40.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0061-VTC-15 |  | U284-07-CP015 | 4 | 2026-07-09 | 0
| V17566-DWXD-7454 | COR-2 | PLATE | P-28 | COR-2-P-28 | PL12*64 | 64 | A387 GR.11 CL.2 | 16 |  | 16 | 0.3 | 4.1 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0028-VTC-7 |  | U284-07-CP008 | 16 | 2026-04-16 | 0
| V17566-DWXD-7454 | COR-2 | PLATE | P-31 | COR-2-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7454 | COR-2 | CASING PLATE | SH-1 | COR-2-SH-1 | PL6*2560 | 12293 | SS400 | 1 |  | 1 | 1465.2 | 1465.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 62.5 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, xoá bỏ 1 số vị trí lỗ khoét theo basic sửa đổi |  |  |  |  | MODIFY, xoá bỏ 1 số vị trí lỗ khoét theo basic sửa đổi | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
90 | V17566-DWXD-7408 | COR-3 | RIGHT PANEL |  |  | (1189x3548x33567) |  |  |  | 1 |  | 35972.7 | 36270.6 | AMC2 | [7 empty] | 0 | 0.071728 |  |  |  |  | 467.2 | Bổ sung thêm khối lượng Access Door | x | o |  |  | REVISED | REVISED
| V17566-DWXD-7408 | COR-3 | ANGLE | A-8 | COR-3-A-8 | L90*90*10 | 3448 | SS400 | 1 |  | 1 | 46 | 46 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 Giảm Q.Ty: 2->1 |  |  |  |  | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 Giảm Q.Ty: 2->1 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 2 | 2026-04-22 | -1
| V17566-DWXD-7408 | COR-3 | ANGLE | A-22 | COR-3-A-22 | L90*90*10 | 3448 | SS400 | 1 |  | 1 | 46 | 46 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7408 | COR-3 | ANGLE | A-10 | COR-3-A-10 | L90*90*6 | 24619 | SS400 | 1 |  | 1 | 203.9 | 203.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7408 | COR-3 | ANGLE | A-11 | COR-3-A-11 | L90*90*6 | 24619 | SS400 | 1 |  | 1 | 203.9 | 203.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7408 | COR-3 | BUILT-UP H-BEAM | BY-1-1 | COR-3-BY-1-1 | BH900*400*25*38 | 33116 | SM490 | 1 |  | 1 | 13257.8 | 13257.8 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 111 | MODIFY, đổi tên BY-1 thành BY-1-1. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi | [5 empty] | MODIFY, đổi tên BY-1 thành BY-1-1. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | -1
| V17566-DWXD-7408 | COR-3 | BUILT-UP H-BEAM | BY-1-2 | COR-3-BY-1-2 | BH900*400*25*38 | 33116 | SM490 | 1 |  | 1 | 13257.8 | 13257.8 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 111 | MODIFY, đổi tên BY-1 thành BY-1-2. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi | [5 empty] | MODIFY, đổi tên BY-1 thành BY-1-2. Giảm Q.ty: 2->1. Bổ sung thêm lỗ trên cột theo basic sửa đổi | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | -1
| V17566-DWXD-7408 | COR-3 | CHANNEL | CY-8 | COR-3-CY-8 | [250*90*9*13 | 3023 | SS400 | 8 |  | 8 | 97.9 | 783.6 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 19.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0015-VTC-3 DCC25-U284-0016-VTC-13 U284-18-CP512-1 DCC26-U184-0052-VTC-7 |  | U284-07-CP513 | 8 | 2026-04-21 | 0
| V17566-DWXD-7408 | COR-3 | CHANNEL | CY-9 | COR-3-CY-9 | [200*80*7.5*11 | 3023 | SS400 | 9 |  | 9 | 69.2 | 622.7 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 17.9 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 9 | 2026-04-22 | 0
| V17566-DWXD-7408 | COR-3 | CHANNEL | CY-12 | COR-3-CY-12 | [200*80*7.5*11 | 1998 | SS400 | 1 |  | 1 | 47.5 | 47.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7408 | COR-3 | LIFTING LUG "A" | GYZ-1 | COR-3-GYZ-1 | PL38*239 | 229 | SM490 | 4 |  | 4 | 14 | 55.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Không khoan lỗ, chỉ để dấu chữ thập, đơn vị sẽ khoan sau khi UT. | [12 empty] | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Fabrication | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | BASE PLATE | GZ-1 | COR-3-GZ-1 | PL60*500 | 1000 | SM490 | 2 |  | 2 | 235.5 | 471 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.4 | Cắt đường kính lỗ nhỏ hơn 10mm | [12 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | GZ-8000 | COR-3-GZ-8000 | PL12*76 | 102 | SS400 | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP026 | 1 | 2026-05-07 | 0
| V17566-DWXD-7408 | COR-3 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 1322 |  | 1322 | 0 | 16.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1322 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 1322 |  | 0
| V17566-DWXD-7408 | COR-3 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 10 |  | 10 | 0.1 | 1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 10
| V17566-DWXD-7408 | COR-3 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 661 |  | 661 | 0 | 32.7 | AMC2 | Purchasing | KHO |  |  | 0 | 661 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 661 |  | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-1 | COR-3-P-1 | PL60*127 | 1000 | SM490 | 2 |  | 2 | 59.8 | 119.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-14-CP014-1 |  | U284-07-CP021 | 2 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-2 | COR-3-P-2 | PL60*127 | 220 | SM490 | 4 |  | 4 | 13.2 | 52.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-14-CP014-1 |  | U284-07-CP021 | 4 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | BACKING BAR | P-3 | COR-3-P-3 | PL10*20 | 162 | SM490 | 32 |  | 32 | 0.3 | 8.1 | AMC2 | Plate | MCC |  |  | 32 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP005-1 |  | U284-07-CP006 | 32 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-4 | COR-3-P-4 | PL8*156 | 182 | SS400 | 37 |  | 37 | 1.7 | 64.3 | AMC2 | Plate | MCC |  |  | 37 | 0 | 1 | [6 empty] | 2.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-3 |  | U284-07-CP022 | 37 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-6 | COR-3-P-6 | PL10*184 | 612 | SS400 | 16 |  | 16 | 8.8 | 140.9 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 3.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 16 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-32 | COR-3-P-32 | PL10*111 | 152 | SS400 | 2 |  | 2 | 1.3 | 2.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 2 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-33 | COR-3-P-33 | PL10*152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 1 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-49 | COR-3-P-49 | PL19*198 | 270 | A387 GR.11 CL.2 | 5 |  | 5 | 7.9 | 39.6 | AMC2 | Plate | MCC |  |  | 5 | 0 | 1 | [6 empty] | 0.6 | ADDED, cắt mới bổ sung | [5 empty] | ADDED, cắt mới bổ sung | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP011-1 |  | U284-05A-CP015 | 5 | 2026-05-13 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | P-50 | COR-3-P-50 | PL19*57 | 198 | A387 GR.11 CL.2 | 5 |  | 5 | 1.7 | 8.4 | AMC2 | Plate | MCC |  |  | 5 | 0 | 1 | [6 empty] | 0.2 | ADDED, cắt mới bổ sung | [5 empty] | ADDED, cắt mới bổ sung | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP011-1 |  | U284-05A-CP015 | 5 | 2026-05-13 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | PY-1 | COR-3-PY-1 | PL25*400 | 900 | SM490 | 2 |  | 2 | 70.1 | 140.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0002-VTC-4 U284-17A-CP009-3 DCC25-U284-0002-VTC-3 U284-09B-CP005-1 PHỤC VỤ CHUNG |  | U284-07-CP016 | 2 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | PLATE | PY-2 | COR-3-PY-2 | PL20*181 | 812 | SM490 | 16 |  | 16 | 22.3 | 356.5 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 5.2 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-14-CP008 |  | U284-07-CP014 | 16 | 2026-04-16 | 0
| V17566-DWXD-7408 | COR-3 | CASING PLATE | SH-3 | COR-3-SH-3 | PL6*3422 | 24619 | SS400 | 1 |  | 1 | 3906.3 | 3906.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 166.7 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, xoá bỏ 1 số vị trí lỗ khoét theo basic sửa đổi |  |  |  |  | MODIFY, xoá bỏ 1 số vị trí lỗ khoét theo basic sửa đổi | MODIFY, bổ sung lỗ khoét theo basic sửa đổi. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
90 | V17566-DRXD-7055 | DR070R |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 87.9 | 87.9 | AMC2 | [14 empty] | ADDED Gắn vào panel COR-3 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7055 | DR070R | PLATE | DR070-01 | DR070R-DR070-01 | PL10x940 | 1549 | SS400 | 1 |  | 1 | 40.4 | 40.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | LINER PLATE | DR070-04A | DR070R-DR070-04A | PL1.5x227 | 1429 | SS400 | 2 |  | 2 | 3.8 | 7.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | LINER PLATE | DR070-04B | DR070R-DR070-04B | PL1.5x227 | 819 | SS400 | 2 |  | 2 | 2.2 | 4.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-09 | DR070R-DR070-09 | PL10x152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | SCREWS | DR070-16 | DR070R-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7055 | DR070R | TADPOLE GASKET 2300°F | DR070-17 | DR070R-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-08
| V17566-DRXD-7055 | DR070R | ADHESIVE | DR070-18 | DR070R-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7055 | DR070R | GRAB BAR | DR070-110 | DR070R-DR070-110 | RB19 | 535 | SS400 | 1 |  | 1 | 1.2 | 1.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | DAVIT BRACKET | DR070-126 | DR070R-DR070-126 | PL10x89 | 344 | SS400 | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P01 | DR070R-DR070-P01 | PL10x51 | 54 | SS400 | 10 |  | 10 | 0.02 | 0.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P02 | DR070R-DR070-P02 | PL10x38 | 41 | SS400 | 20 |  | 20 | 0.01 | 0.2 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | FLAT WASHER | DR070-W01 | DR070R-DR070-W01 | ZINC PLATED, 1/2" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-02
| V17566-DRXD-7055 | DR070R | SQUARE SHOUDERED SOLID ROD END BLACK OXID | DR070-B01 | DR070R-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-03
| V17566-DRXD-7055 | DR070R | EASY GRIP HANDLE | DR070-GR01 | DR070R-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-04
| V17566-DRXD-7055 | DR070R | CLEVIS PIN WITH REUSABLE COTTER PIN | DR070-PN01 | DR070R-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-05
| V17566-DRXD-7055 | DR070R | FLAT WASHER | DR070-W02 | DR070R-DR070-W02 | ZINC PLATED, 5/8" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-06
| V17566-DRXD-7055 | DR070R | DAVIT | DR070-RB01 | DR070R-DR070-RB01 | RB45 | 1190 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | DAVIT WASHER | DR070-P03 | DR070R-DR070-P03 | PL10xID.46xOD.70 |  | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P04 | DR070R-DR070-P04 | PL10x270 | 467 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
90 | V17566-DRXD-7056 | DR070R |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 210 | 210 | AMC2 | [14 empty] | ADDED Gắn vào panel COR-3 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7056 | DR070R | ANGLE | DR071-02A | DR070R-DR071-02A | L100x75x10 | 880 | SS400 | 2 |  | 2 | 11.3 | 22.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | ANGLE | DR071-02B | DR070R-DR071-02B | L100x75x10 | 1490 | SS400 | 2 |  | 2 | 19.2 | 38.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | PLATE | DR071-20 | DR070R-DR071-20 | PL10x800 | 1410 | SS400 | 1 |  | 1 | 88.5 | 88.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | FLATBAR | DR071-21 | DR070R-DR071-21 | PL10x75 | 737 | SS400 | 3 |  | 3 | 4.4 | 13.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | FLATBAR | DR071-22 | DR070R-DR071-22 | PL10x75 | 236 | SS400 | 4 |  | 4 | 1.4 | 5.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-26A | DR070R-DR071-26A | PL1.5x140 | 699 | SS400 | 2 |  | 2 | 1.2 | 2.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-26B | DR070R-DR071-26B | PL1.5x140 | 1308 | SS400 | 2 |  | 2 | 2 | 4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-27 | DR070R-DR071-27 | PL1.5x683 | 1293 | SS400 | 1 |  | 1 | 10.4 | 10.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | STUD BOLT | DR071-28 | DR070R-DR071-28 | Ø10(M10) | 108 | SS400 | 8 |  | 8 | 0.15 | 1.2 | AMC2 | Shape | PMC |  |  | 8 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 8
| V17566-DRXD-7056 | DR070R | WASHER | DR071-29 | DR070R-DR071-29 | PL1.5 x OD76 x ID11 |  | SS400 | 16 |  | 16 | 0.07 | 1.12 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | HEX NUT | DR071-30 | DR070R-DR071-30 | M10 |  | SS400 | 16 |  | 16 | 0.01 | 0.16 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-21
| V17566-DRXD-7056 | DR070R | TADPOLE GASKET 1000°F | DR071-31 | DR070R-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.12 | 0.12 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-09
| V17566-DRXD-7056 | DR070R | ADHESIVE | DR071-32 | DR070R-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7056 | DR070R | SCREWS | DR071-33 | DR070R-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7056 | DR070R | DOOR HANDLE | DR071-111 | DR070R-DR071-111 | RB14 | 268 | SS400 | 2 |  | 2 | 0.15 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | GUSSET PLATE | DR071-112 | DR070R-DR071-112 | PL10x65 | 83 | SS400 | 20 |  | 20 | 0.4 | 8 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | DOOR HANGER | DR071-113 | DR070R-DR071-113 | RB14 | 350 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | EYE BOLT/2NUTS/1PW | DR071-114 | DR070R-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) |  | - | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-01
91 | V17566-DWXD-7459 | COR-4 | RIGHT PANEL |  |  | (1262x543x12386) |  |  |  | 1 |  | 2102.6 | 2400.5 | AMC2 | [7 empty] | 0 | 0.14257 |  |  |  |  | 58.8 | Bổ sung thêm khối lượng Access Door | x | o |  | REVISED | REVISED
| V17566-DWXD-7459 | COR-4 | ANGLE | A-6 | COR-4-A-6 | L100*100*10 | 12373 | SS400 | 1 |  | 1 | 184.5 | 184.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7459 | COR-4 | ANGLE | A-12 | COR-4-A-12 | L100*100*7 | 152 | SS400 | 2 |  | 2 | 1.6 | 3.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-06A-CP509-1 |  | U284-07-CP519 | 2 | 2026-04-21 | 0
| V17566-DWXD-7459 | COR-4 | ANGLE | A-18 | COR-4-A-18 | L90*90*10 | 1262 | SS400 | 1 |  | 1 | 16.8 | 16.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-32 DCC25-U284-0070-VTC-2 U284-14-CP512-1 |  | U284-07-CP527 | 1 | 2026-05-07 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-2 | COR-4-CY-2 | [200*80*7.5*11 | 1089 | SS400 | 2 |  | 2 | 25.6 | 51.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-3 | COR-4-CY-3 | [200*80*7.5*11 | 295 | SS400 | 6 |  | 6 | 6.2 | 37 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 1.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-4 | COR-4-CY-4 | [200*80*7.5*11 | 1089 | SS400 | 1 |  | 1 | 25.6 | 25.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | [13 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-23 | COR-4-CY-23 | [200*80*7.5*11 | 10127 | SS400 | 1 |  | 1 | 244.5 | 244.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-25 | COR-4-CY-25 | [200*80*7.5*11 | 10127 | SS400 | 1 |  | 1 | 244.5 | 244.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 7 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-26 | COR-4-CY-26 | [200*80*7.5*11 | 722 | SS400 | 6 |  | 6 | 14.7 | 88.3 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 2.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | CHANNEL | CY-27 | COR-4-CY-27 | [200*80*7.5*11 | 57 | SS400 | 6 |  | 6 | 1.3 | 7.6 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 6 | 2026-04-22 | 0
| V17566-DWXD-7459 | COR-4 | PIPE | D-3 | COR-4-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 3 |  | 3 | 4.9 | 14.6 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 3 | 2026-04-21 | 0
| V17566-DWXD-7459 | COR-4 | PIPE | D-4 | COR-4-D-4 | 4" SCH.40 | 309 | A-312 TP.304 | 1 |  | 1 | 4.9 | 4.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | Cắt dương lên 5mm MODIFY, giảm Qty: 2->1 |  |  |  |  | MODIFY, giảm Qty: 2->1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-14 |  | U284-07-CP509 | 2 | 2026-04-21 | -1
| V17566-DWXD-7459 | COR-4 | PIPE | D-5 | COR-4-D-5 | 8" SCH.40 | 309 | A-106 Gr.B | 2 |  | 2 | 13.1 | 26.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.4 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-10 |  | U284-07-CP511 | 2 | 2026-04-21 | 0
| V17566-DWXD-7459 | COR-4 | PIPE | D-6 | COR-4-D-6 | 2" SCH.40 | 137 | A-106 Gr.B | 11 |  | 11 | 0.7 | 8 | AMC2 | Shape | MCC |  |  | 11 | 0 | 1 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 11 | 2026-04-21 | 0
| V17566-DWXD-7459 | COR-4 | PIPE | D-11 | COR-4-D-11 | 4" SCH.40 | 309 | A-106 Gr.B | 1 |  | 1 | 4.9 | 4.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | Cắt dương lên 5mm ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-01-CP503-1 |  | U284-07-CP525 | 1 | 2026-05-07 | 0
| V17566-DWXD-7459 | COR-4 | PIPE | DZ-1 | COR-4-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 2 |  | 2 | 0.5 | 0.9 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | 0.3 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 2 | 2026-04-21 | 0
| V17566-DWXD-7459 | COR-4 | PLATE | G-9 | COR-4-G-9 | PL6*360 | 360 | SS400 | 2 |  | 2 | 3 | 6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16 | 0
| V17566-DWXD-7459 | COR-4 | PLATE | G-17 | COR-4-G-17 | PL6*127 | 127 | SS400 | 11 |  | 11 | 0.6 | 6.5 | AMC2 | Plate | MCC |  |  | 11 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 11 | 2026-04-16 | 0
| V17566-DWXD-7459 | COR-4 | PLATE | G-28 | COR-4-G-28 | PL6*60 | 60 | A-240 TP304 | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 2 | 2026-05-07 | 0
| V17566-DWXD-7459 | COR-4 | H-BEAM | H-7 | COR-4-H-7 | H194*150*6*9 | 2187 | SS400 | 1 |  | 1 | 65.4 | 65.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP507-1 DCC25-U284-0034-VTC-22 |  | U284-07-CP515 | 1 | 2026-04-21 | 0
| V17566-DWXD-7459 | COR-4 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 7 |  | 7 | 0.2 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 7 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 7 |  | 0
| V17566-DWXD-7459 | COR-4 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 260 |  | 260 | 0 | 3.2 | AMC2 | Purchasing | KHO |  |  | 0 | 260 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 260 |  | 0
| V17566-DWXD-7459 | COR-4 | FLANGE 4" 150# SO-RF | M-6 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 5.9 | 29.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 5 |  | 0
| V17566-DWXD-7459 | COR-4 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 5 |  | 5 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 5 |  | 0
| V17566-DWXD-7459 | COR-4 | 4" 150# RF BLIND FLG. | M-8 |  | PL22.3*229 | 229 | A-105 | 5 |  | 5 | 7.6 | 38.1 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [6 empty] | 0.5 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 5 |  | 0
| V17566-DWXD-7459 | COR-4 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 2 |  | 2 | 1.4 | 2.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 2 |  | 0
| V17566-DWXD-7459 | COR-4 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 2 |  | 2 | 0.6 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 2 |  | 0
| V17566-DWXD-7459 | COR-4 | FLANGE 8" 150# SO-RF | M-13 |  | PL27*342 | 343 | A-105 | 2 |  | 2 | 12.9 | 25.8 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-10 |  |  | 2 |  | 0
| V17566-DWXD-7459 | COR-4 | GASKET 8" 150# | M-14 |  | PL3*268 | 269 | NON-METALLIC | 2 |  | 2 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-12 |  |  | 2 |  | 0
| V17566-DWXD-7459 | COR-4 | 8" 150# RF BLIND FLG. | M-15 |  | PL27*342 | 342 | A-105 | 2 |  | 2 | 20.4 | 40.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-11 |  |  | 2 |  | 0
| V17566-DWXD-7459 | COR-4 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 4 |  | 4 | 0.1 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [7 empty] | MODIFY, giảm Q.ty: 5->4 |  |  |  |  | MODIFY, giảm Q.ty: 5->4 | [7 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 4
| V17566-DWXD-7459 | COR-4 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 123 |  | 123 | 0 | 6.1 | AMC2 | Purchasing | KHO |  |  | 0 | 123 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 123 |  | 0
| V17566-DWXD-7459 | COR-4 | PLATE | P-31 | COR-4-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7459 | COR-4 | CASING PLATE | SH-5 | COR-4-SH-5 | PL6*1136 | 12360 | SS400 | 1 |  | 1 | 603 | 603 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 25.8 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
91 | V17566-DRXD-7055 | DR070R |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 87.9 | 87.9 | AMC2 | [14 empty] | ADDED Gắn vào panel COR-4 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7055 | DR070R | PLATE | DR070-01 | DR070R-DR070-01 | PL10x940 | 1549 | SS400 | 1 |  | 1 | 40.4 | 40.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | LINER PLATE | DR070-04A | DR070R-DR070-04A | PL1.5x227 | 1429 | SS400 | 2 |  | 2 | 3.8 | 7.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | LINER PLATE | DR070-04B | DR070R-DR070-04B | PL1.5x227 | 819 | SS400 | 2 |  | 2 | 2.2 | 4.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-09 | DR070R-DR070-09 | PL10x152 | 229 | SS400 | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | SCREWS | DR070-16 | DR070R-DR070-16 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7055 | DR070R | TADPOLE GASKET 2300°F | DR070-17 | DR070R-DR070-17 | 3/4" BULB DIA.x1 1/2" WIDE, 4500LG, MCMASTER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-08
| V17566-DRXD-7055 | DR070R | ADHESIVE | DR070-18 | DR070R-DR070-18 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7055 | DR070R | GRAB BAR | DR070-110 | DR070R-DR070-110 | RB19 | 535 | SS400 | 1 |  | 1 | 1.2 | 1.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-17 |  | U284-19A-CP510 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | DAVIT BRACKET | DR070-126 | DR070R-DR070-126 | PL10x89 | 344 | SS400 | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P01 | DR070R-DR070-P01 | PL10x51 | 54 | SS400 | 10 |  | 10 | 0.02 | 0.2 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 10 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P02 | DR070R-DR070-P02 | PL10x38 | 41 | SS400 | 20 |  | 20 | 0.01 | 0.2 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | FLAT WASHER | DR070-W01 | DR070R-DR070-W01 | ZINC PLATED, 1/2" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-02
| V17566-DRXD-7055 | DR070R | SQUARE SHOUDERED SOLID ROD END BLACK OXID | DR070-B01 | DR070R-DR070-B01 | 5/8"-11 THREADS MCMASTER-CARR PART 59895K21 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-03
| V17566-DRXD-7055 | DR070R | EASY GRIP HANDLE | DR070-GR01 | DR070R-DR070-GR01 | MALLEABLE IRON W/ZINC PLATE FINISH, 5/8"-11 THREADS MCMASTER-CARR PART 91044A035 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-04
| V17566-DRXD-7055 | DR070R | CLEVIS PIN WITH REUSABLE COTTER PIN | DR070-PN01 | DR070R-DR070-PN01 | ZINC PLATED, 1/2" IDA.x2LG (1 3/4" USABLE LENGTH) MCMASTER-CARR PART 97245A715 OR EQUAL |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-05
| V17566-DRXD-7055 | DR070R | FLAT WASHER | DR070-W02 | DR070R-DR070-W02 | ZINC PLATED, 5/8" DIA. |  | - | 10 |  | 10 | 0.01 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 10 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-06
| V17566-DRXD-7055 | DR070R | DAVIT | DR070-RB01 | DR070R-DR070-RB01 | RB45 | 1190 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-19 |  | U284-19A-CP512 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | DAVIT WASHER | DR070-P03 | DR070R-DR070-P03 | PL10xID.46xOD.70 |  | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7055 | DR070R | PLATE | DR070-P04 | DR070R-DR070-P04 | PL10x270 | 467 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
91 | V17566-DRXD-7056 | DR070R |  |  |  | (251x1197x1841) |  |  |  | 1 |  | 210 | 210 | AMC2 | [14 empty] | ADDED Gắn vào panel COR-4 khi giao hàng | i | [6 empty] | ADDED
| V17566-DRXD-7056 | DR070R | ANGLE | DR071-02A | DR070R-DR071-02A | L100x75x10 | 880 | SS400 | 2 |  | 2 | 11.3 | 22.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | ANGLE | DR071-02B | DR070R-DR071-02B | L100x75x10 | 1490 | SS400 | 2 |  | 2 | 19.2 | 38.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-20 |  | U284-19A-CP513 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | PLATE | DR071-20 | DR070R-DR071-20 | PL10x800 | 1410 | SS400 | 1 |  | 1 | 88.5 | 88.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | FLATBAR | DR071-21 | DR070R-DR071-21 | PL10x75 | 737 | SS400 | 3 |  | 3 | 4.4 | 13.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 3 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | FLATBAR | DR071-22 | DR070R-DR071-22 | PL10x75 | 236 | SS400 | 4 |  | 4 | 1.4 | 5.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 4 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-26A | DR070R-DR071-26A | PL1.5x140 | 699 | SS400 | 2 |  | 2 | 1.2 | 2.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-26B | DR070R-DR071-26B | PL1.5x140 | 1308 | SS400 | 2 |  | 2 | 2 | 4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | LINER PLATE | DR071-27 | DR070R-DR071-27 | PL1.5x683 | 1293 | SS400 | 1 |  | 1 | 10.4 | 10.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | STUD BOLT | DR071-28 | DR070R-DR071-28 | Ø10(M10) | 108 | SS400 | 8 |  | 8 | 0.15 | 1.2 | AMC2 | Shape | PMC |  |  | 8 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [5 empty] | 8
| V17566-DRXD-7056 | DR070R | WASHER | DR071-29 | DR070R-DR071-29 | PL1.5 x OD76 x ID11 |  | SS400 | 16 |  | 16 | 0.07 | 1.12 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-3/5 |  | U284-19A-CP019 | 16 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | HEX NUT | DR071-30 | DR070R-DR071-30 | M10 |  | SS400 | 16 |  | 16 | 0.01 | 0.16 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-21
| V17566-DRXD-7056 | DR070R | TADPOLE GASKET 1000°F | DR071-31 | DR070R-DR071-31 | 3/4" BULB DIA.x1 1/2" WIDE 4400LG, MCMATER-CARR PART 8853K26 OR EQUAL. |  | SILICA W/INCONEL CORE | 1 |  | 1 | 0.12 | 0.12 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-09
| V17566-DRXD-7056 | DR070R | ADHESIVE | DR071-32 | DR070R-DR071-32 | TUBE OF HIGH TEMPERATURE RED SILICONE |  | SILICONE | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-10
| V17566-DRXD-7056 | DR070R | SCREWS | DR071-33 | DR070R-DR071-33 | #10x10LG LOW PROFILE, SELF TRHREADING |  | STAINLESS STEEL | 40 |  | 40 | 0.01 | 0.4 | AMC2 | Purchasing | KHO |  |  | 0 | 40 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-07
| V17566-DRXD-7056 | DR070R | DOOR HANDLE | DR071-111 | DR070R-DR071-111 | RB14 | 268 | SS400 | 2 |  | 2 | 0.15 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 2 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | GUSSET PLATE | DR071-112 | DR070R-DR071-112 | PL10x65 | 83 | SS400 | 20 |  | 20 | 0.4 | 8 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0017-VTP-26 |  | U284-19A-CP022 | 20 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | DOOR HANGER | DR071-113 | DR070R-DR071-113 | RB14 | 350 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0103-VTC-2 |  | U284-19A-CP507 | 1 | 2026-06-26 | 0
| V17566-DRXD-7056 | DR070R | EYE BOLT/2NUTS/1PW | DR071-114 | DR070R-DR071-114 | FORGED EYE BOLT 1/2"-13x4" GALVANIZED STEEL (BOLT DEPOT P/N 13397 OR EQUAL) |  | - | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, Cắt mới bổ sung. | [7 empty] | ADDED, Cắt mới bổ sung. | [11 empty] | Purchasing | DCC25-U284-0017-VTP-01
92 | V17566-DWXD-7463 | COR-5 | RIGHT PANEL |  |  | (1262x406x12259) |  |  |  | 1 |  | 2057.2 | 2057.2 | AMC2 | [7 empty] | 0 | 0.11753 |  |  |  |  | 58.3 | REVISED | x | o |  | REVISED | REVISED
| V17566-DWXD-7463 | COR-5 | ANGLE | A-5 | COR-5-A-5 | L100*100*10 | 12246 | SS400 | 1 |  | 1 | 182.6 | 182.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7463 | COR-5 | ANGLE | A-9 | COR-5-A-9 | L90*90*10 | 1262 | SS400 | 1 |  | 1 | 16.8 | 16.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 |  |  |  |  | MODIFY, thay đổi profile L90x90x6 thành L90x90x10 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-03A-CP510-1 U284-06A-CP510-1 U284-020-CP505-1 U284-020-CP505-2 DCC25-U284-0029-VTC-9 DCC25-U284-0034-VTC-30 DCC26-U284-0052-VTC-17 |  | U284-07-CP522 | 1 | 2026-04-22 | 0
| V17566-DWXD-7463 | COR-5 | ANGLE | AY-2 | COR-5-AY-2 | L75*75*6 | 1089 | SS400 | 1 |  | 1 | 7.5 | 7.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-18-CP518-1 DCC25-U284-0050-VTC-4 |  | U284-07-CP521 | 1 | 2026-04-22 | 0
| V17566-DWXD-7463 | COR-5 | CHANNEL | CY-3 | COR-5-CY-3 | [200*80*7.5*11 | 295 | SS400 | 8 |  | 8 | 6.2 | 49.3 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 1.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22 | 0
| V17566-DWXD-7463 | COR-5 | CHANNEL | CY-22 | COR-5-CY-22 | [200*80*7.5*11 | 12246 | SS400 | 1 |  | 1 | 296.8 | 296.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12116->12246 |  |  |  |  | MODIFY, tăng chiều dài 12116->12246 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7463 | COR-5 | CHANNEL | CY-24 | COR-5-CY-24 | [200*80*7.5*11 | 12246 | SS400 | 1 |  | 1 | 296.8 | 296.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 8.4 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 12116->12246 |  |  |  |  | MODIFY, tăng chiều dài 12116->12246 | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7463 | COR-5 | CHANNEL | CY-26 | COR-5-CY-26 | [200*80*7.5*11 | 722 | SS400 | 8 |  | 8 | 14.7 | 117.8 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 3.5 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22 | 0
| V17566-DWXD-7463 | COR-5 | CHANNEL | CY-27 | COR-5-CY-27 | [200*80*7.5*11 | 57 | SS400 | 8 |  | 8 | 1.3 | 10.2 | AMC2 | Shape | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 8 | 2026-04-22 | 0
| V17566-DWXD-7463 | COR-5 | PIPE | D-3 | COR-5-D-3 | 4" SCH.40 | 309 | A-106 Gr.B | 4 |  | 4 | 4.9 | 19.5 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP504-1 U284-02A-CP502-1 DCC25-U284-0007-VTC-5B |  | U284-07-CP508 | 4 | 2026-04-21 | 0
| V17566-DWXD-7463 | COR-5 | PIPE | D-6 | COR-5-D-6 | 2" SCH.40 | 137 | A-106 Gr.B | 7 |  | 7 | 0.7 | 5.1 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0.2 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0029-VTC-1 U284-06A-CP501-1 |  | U284-07-CP502 | 7 | 2026-04-21 | 0
| V17566-DWXD-7463 | COR-5 | PIPE | DZ-1 | COR-5-DZ-1 | 2" SCH.40 | 86 | A-312 TP.304 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0 | Cắt dương lên 5mm | [12 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | U284-10-CP501-1 |  | U284-07-CP503 | 1 | 2026-04-21 | 0
| V17566-DWXD-7463 | COR-5 | PLATE | G-17 | COR-5-G-17 | PL6*127 | 127 | SS400 | 7 |  | 7 | 0.6 | 4.2 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 7 | 2026-04-16 | 0
| V17566-DWXD-7463 | COR-5 | PLATE | G-28 | COR-5-G-28 | PL6*60 | 60 | A-240 TP304 | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung |  |  |  | ADDED, cắt mới bổ sung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP034 | 1 | 2026-05-07 | 0
| V17566-DWXD-7463 | COR-5 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 4 |  | 4 | 0.2 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 4 |  | 0
| V17566-DWXD-7463 | COR-5 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 272 |  | 272 | 0 | 3.3 | AMC2 | Purchasing | KHO |  |  | 0 | 272 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 272 |  | 0
| V17566-DWXD-7463 | COR-5 | FLANGE 4" 150# SO-RF | M-6 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 5.9 | 23.6 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-14 |  |  | 4 |  | 0
| V17566-DWXD-7463 | COR-5 | GASKET 4" 150# | M-7 |  | PL3*156 | 157 | NON-METALLIC | 4 |  | 4 | 0 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.1 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-16 |  |  | 4 |  | 0
| V17566-DWXD-7463 | COR-5 | 4" 150# RF BLIND FLG. | M-8 |  | PL22.3*229 | 229 | A-105 | 4 |  | 4 | 7.6 | 30.5 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | 0.4 | [13 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-15 |  |  | 4 |  | 0
| V17566-DWXD-7463 | COR-5 | COUPING FULL THREAD | M-9 |  | 2" 3000# COUPING FULL THREAD | 86 | A-105 | 1 |  | 1 | 1.4 | 1.4 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-22 |  |  | 1 |  | 0
| V17566-DWXD-7463 | COR-5 | SQUARE HEAD PLUG | M-10 |  | 2" 3000# SQUARE HEAD PLUG | 40 | A-105 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 | [13 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-23 |  |  | 1 |  | 0
| V17566-DWXD-7463 | COR-5 | NUT M20 | M-17 | 3/4" | NUT_M20 | 16 | A563 | 5 |  | 5 | 0.1 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 5 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0056-VTP-03 |  |  |  |  | 5
| V17566-DWXD-7463 | COR-5 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 132 |  | 132 | 0 | 6.5 | AMC2 | Purchasing | KHO |  |  | 0 | 132 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 132 |  | 0
| V17566-DWXD-7463 | COR-5 | PLATE | P-31 | COR-5-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7463 | COR-5 | CASING PLATE | SH-4 | COR-5-SH-4 | PL6*1136 | 12233 | SS400 | 1 |  | 1 | 652.3 | 652.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 27.9 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, xoá bỏ 1 số vị trí lỗ khoét theo basic sửa đổi |  |  |  |  | MODIFY, xoá bỏ 1 số vị trí lỗ khoét theo basic sửa đổi | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
93 | V17566-DWXD-7467 | COT-1 | TOP PANEL |  |  | (582x2786x9785) |  |  |  | 1 |  | 2944.5 | 2944.5 | AMC2 | [7 empty] | 0 | 0.065502 |  |  |  |  | 84.8 | REVISED | x | o |  |  | REVISED
| V17566-DWXD-7467 | COT-1 | ANGLE | A-3 | COT-1-A-3 | L75*75*6 | 9785 | SS400 | 1 |  | 1 | 67 | 67 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 9677->9785 |  |  |  |  | MODIFY, tăng chiều dài 9677->9785 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7467 | COT-1 | CHANNEL | C-1 | COT-1-C-1 | [200*80*7.5*11 | 9785 | SS400 | 2 |  | 2 | 237.7 | 475.5 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 13.2 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 9506->9785 |  |  |  |  | MODIFY, tăng chiều dài 9506->9785 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 2 | 2026-06-27 | 0
| V17566-DWXD-7467 | COT-1 | CHANNEL | CY-37 | COT-1-CY-37 | [200*80*7.5*11 | 581 | SS400 | 7 |  | 7 | 14 | 98 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 2.8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7467 | COT-1 | CHANNEL | CY-38 | COT-1-CY-38 | [200*80*7.5*11 | 1747 | SS400 | 7 |  | 7 | 39.6 | 277.4 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7467 | COT-1 | CHANNEL | CY-39 | COT-1-CY-39 | [200*80*7.5*11 | 299 | SS400 | 7 |  | 7 | 6.5 | 45.2 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 1.4 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7467 | COT-1 | PIPE | D-2 | COT-1-D-2 | 3" SCH.40 | 315 | A-312 TP.304 | 6 |  | 6 | 3.5 | 21.1 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm MODIFY, tăng chiều dài 309->315 |  |  |  |  | MODIFY, tăng chiều dài 309->315 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | DCC25-U284-0016-VTC-30 |  | U284-07-CP504 | 6 | 2026-04-21 | 0
| V17566-DWXD-7467 | COT-1 | PIPE | D-7-1 | COT-1-D-7 | 3" SCH.40 | 62 | A355-P11 | 2 |  | 2 | 0.7 | 1.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 | MODIFY, giảm chiều dài 314->62 Cắt dương lên 5mm | [6 empty] | MODIFY, giảm chiều dài 314->62 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-U284-0052-VTC-4 |  | U284-07-CP506 | 2 | 2026-04-21 | 0
| V17566-DWXD-7467 | COT-1 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 6 |  | 6 | 0.2 | 1.1 | AMC2 | Purchasing | KHO |  |  | 0 | 6 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 6 |  | 0
| V17566-DWXD-7467 | COT-1 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 428 |  | 428 | 0 | 5.2 | AMC2 | Purchasing | KHO |  |  | 0 | 428 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 428 |  | 0
| V17566-DWXD-7467 | COT-1 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 208 |  | 208 | 0 | 10.3 | AMC2 | Purchasing | KHO |  |  | 0 | 208 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 208 |  | 0
| V17566-DWXD-7467 | COT-1 | PLATE | P-29 | COT-1-P-29 | PL6*78 | 78 | A387 GR.11 CL.2 | 2 |  | 2 | 0.2 | 0.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | VẬT TƯ TẬN DỤNG |  | U284-07-CP020 | 2 | 2026-04-16 | 0
| V17566-DWXD-7467 | COT-1 | PLATE | P-31 | COT-1-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7467 | COT-1 | PLATE | P-8005 | COT-1-P-8005 | PL10*152 | 152 | SS400 | 2 |  | 2 | 1.8 | 3.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [7 empty] | ADDED, cắt mới bổ sung | [6 empty] | ADDED, cắt mới bổ sung | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-701-CP009-OS-1 |  | U284-09A-CP015 | 2 | 2026-06-16 | 0
| V17566-DWXD-7467 | COT-1 | CASING PLATE | SH-9 | COT-1-SH-9 | PL6*2773 | 9785 | SS400 | 1 |  | 1 | 1276.2 | 1276.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 54.4 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, sửa đổi vị trí lỗ khoét theo basic sửa đổi |  |  |  |  | MODIFY, sửa đổi vị trí lỗ khoét theo basic sửa đổi | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
94 | V17566-DWXD-7411 | COT-2 | TOP PANEL |  |  | (1638x3448x9823) |  |  |  | 1 |  | 11595.1 | 11595.1 | AMC2 | [7 empty] | 0 | 0.10917 |  |  |  |  | 151.6 | REVISED | x | o |  |  | REVISED |  |  |  | REVISED | [16 empty] | 0
| V17566-DWXD-7411 | COT-2 | ANGLE | A-21 | COT-2-A-21 | L90*90*6 | 9785 | SS400 | 2 |  | 2 | 81 | 162.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 6.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn ADDED, cắt mới bổ sung |  |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
| V17566-DWXD-7411 | COT-2 | ANGLE | AY-3 | COT-2-AY-3 | L150*150*12 | 2032 | SS400 | 2 |  | 2 | 55.5 | 110.9 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.4 | MODIFY, thay đổi kích thước lỗ bolt |  |  |  |  | MODIFY, thay đổi kích thước lỗ bolt | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-02A-CP504-2 DCC25-U284-0016-VTC-9 |  | U284-07-CP520 | 2 | 2026-04-21 | 0
| V17566-DWXD-7411 | COT-2 | ANGLE | AY-4 | COT-2-AY-4 | L150*150*12 | 9347 | SS400 | 2 |  | 2 | 255.1 | 510.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 11 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, thay đổi kích thước lỗ bolt |  |  |  |  | MODIFY, thay đổi kích thước lỗ bolt | [7 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-02A-CP504-2 DCC25-U284-0016-VTC-9 |  | U284-07-CP520 | 2 | 2026-04-21 | 0
| V17566-DWXD-7411 | COT-2 | BUILT-UP H-BEAM | BY-7 | COT-2-BY-7 | BH900*400*25*38 | 9747 | SM490 | 2 |  | 2 | 3891.3 | 7782.6 | AMC2 | Shape | WTC |  |  | 2 | 0 | 1 | [6 empty] | 65.4 | MODIFY, đổi mark BY-2 thành BY-7. Bổ sung lỗ hole theo basic sửa đổi |  |  |  |  | MODIFY, đổi mark BY-2 thành BY-7. Bổ sung lỗ hole theo basic sửa đổi | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
| V17566-DWXD-7411 | COT-2 | CHANNEL | C-4 | COT-2-C-4 | [200*80*7.5*11 | 378 | SS400 | 14 |  | 14 | 9.2 | 128.6 | AMC2 | Shape | MCC |  |  | 14 | 0 | 1 | [6 empty] | 3.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 14 | 2026-04-22 | 0
| V17566-DWXD-7411 | COT-2 | CHANNEL | CY-44 | COT-2-CY-44 | [200*80*7.5*11 | 806 | SS400 | 7 |  | 7 | 17.7 | 123.8 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 3.6 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7411 | COT-2 | CHANNEL | CY-45 | COT-2-CY-45 | [200*80*7.5*11 | 282 | SS400 | 7 |  | 7 | 4.9 | 34.1 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 1.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7411 | COT-2 | CHANNEL | CY-46 | COT-2-CY-46 | [200*80*7.5*11 | 474 | SS400 | 7 |  | 7 | 9.6 | 67.4 | AMC2 | Shape | MCC |  |  | 7 | 0 | 1 | [6 empty] | 2 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 7 | 2026-04-22 | 0
| V17566-DWXD-7411 | COT-2 | PIPE | D-2 | COT-2-D-2 | 3" SCH.40 | 315 | A-312 TP.304 | 6 |  | 6 | 3.5 | 21.1 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm MODIFY, tăng chiều dài 309->315 |  |  |  |  | MODIFY, tăng chiều dài 309->315 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | DCC25-U284-0016-VTC-30 |  | U284-07-CP504 | 6 | 2026-04-21 | 0
| V17566-DWXD-7411 | COT-2 | PLATE | G-1 | COT-2-G-1 | PL38*400 | 1312 | SM490 | 4 |  | 4 | 156.5 | 626.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 4.7 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16 | 0
| V17566-DWXD-7411 | COT-2 | LIFTING LUG "A" | GYZ-1 | COT-2-GYZ-1 | PL38*239 | 229 | SM490 | 4 |  | 4 | 14 | 55.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.5 | Không khoan lỗ, chỉ để dấu chữ thập, đơn vị sẽ khoan sau khi UT. | [12 empty] | 1 | 0 | 0 | 1 | 1 | 0 | 0 | Fabrication | U284-06B-CP007-1 DCC25-U284-0002-VTC-12 DCC25-U284-0002-VTC-11 DCC25-U284-0002-VTC-10 |  | U284-07-CP018 | 4 | 2026-04-16 | 0
| V17566-DWXD-7411 | COT-2 | H-BEAM | HY-1 | COT-2-HY-1 | H400*200*8*13 | 9823 | SS400 | 1 |  | 1 | 642.9 | 642.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 15.3 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC25-U284-0043-3 |  | U284-07-CP517 | 1 | 2026-04-21 | 0
| V17566-DWXD-7411 | COT-2 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 6 |  | 6 | 0.2 | 1.1 | AMC2 | Purchasing | KHO |  |  | 0 | 6 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 6 |  | 0
| V17566-DWXD-7411 | COT-2 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 408 |  | 408 | 0 | 5 | AMC2 | Purchasing | KHO |  |  | 0 | 408 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 408 |  | 0
| V17566-DWXD-7411 | COT-2 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 198 |  | 198 | 0 | 9.8 | AMC2 | Purchasing | KHO |  |  | 0 | 198 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 198 |  | 0
| V17566-DWXD-7411 | COT-2 | PLATE | P-8004 | COT-2-P-8004 | PL10*188 | 824 | SM490 | 8 |  | 8 | 12.1 | 96.8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [7 empty] | MODIFY, thay đổi vật liệu SS400->SM490 | [6 empty] | ADDED, cắt mới bổ sung |  | MODIFY, thay đổi vật liệu SS400->SM490 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-10-CP005-2 |  | U284-07-CP037 | 8 | 2026-07-09 | 0
| V17566-DWXD-7411 | COT-2 | PLATE | PY-3 | COT-2-PY-3 | PL28*206 | 357 | SM490 | 8 |  | 8 | 8.7 | 69.7 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-14-CP010-1 |  | U284-07-CP017 | 8 | 2026-04-16 | 0
| V17566-DWXD-7411 | COT-2 | CASING PLATE | SH-10 | COT-2-SH-10 | PL6*3422 | 9785 | SS400 | 1 |  | 1 | 759.1 | 759.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 32.5 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
95 | V17566-DWXD-7471 | COT-3 | SCR DOOR |  |  | (451x2006x3085) |  |  |  | 1 |  | 916.2 | 916.2 | AMC2 | [7 empty] | 0 | 0.051724 |  |  |  |  | 21.6 | Gắn vào cùng Panel COT-2 trước khi giao hàng REVISED | x |  |  | REVISED | REVISED
| V17566-DWXD-7471 | COT-3 | CHANNEL | CY-47 | COT-3-CY-47 | [200*80*7.5*11 | 3079 | SS400 | 2 |  | 2 | 73.6 | 147.2 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 4.2 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7471 | COT-3 | CHANNEL | CY-50 | COT-3-CY-50 | [200*80*7.5*11 | 1448 | SS400 | 3 |  | 3 | 34.9 | 104.8 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 3.2 | MODIFY, thay đổi kích thước chamfer 19->25 |  |  |  | MODIFY, Giảm chiều dài: 1522->1448 | MODIFY, thay đổi kích thước chamfer 19->25 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 3 | 2026-04-22 | 0
| V17566-DWXD-7471 | COT-3 | PLATE | G-3 | COT-3-G-3 | PL12*200 | 1448 | SS400 | 2 |  | 2 | 27.2 | 54.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.3 | MODIFY, Giảm chiều dài: 1522->1448 |  |  |  | MODIFY, Giảm chiều dài: 1522->1448 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16 | 0
| V17566-DWXD-7471 | COT-3 | PLATE | G-4 | COT-3-G-4 | PL6*124 | 2006 | SS400 | 1 |  | 1 | 11.7 | 11.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
| V17566-DWXD-7471 | COT-3 | GASKET | G-8001 |  | PL3*50 | 2006 | NON-METALLIC | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 1 | [6 empty] | Purchasing | [5 empty] | 1
| V17566-DWXD-7471 | COT-3 | GASKET | G-8002 |  | PL3*50 | 3023 | NON-METALLIC | 2 |  | 2 | 0.2 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 1 | [6 empty] | Purchasing | [5 empty] | 2
| V17566-DWXD-7471 | COT-3 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 108 |  | 108 | 0 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 108 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 108 |  | 0
| V17566-DWXD-7471 | COT-3 | STUD 3/8" | M-24 |  | D10 | 245 | SS400 | 54 |  | 54 | 0.1 | 7.3 | AMC2 | Purchasing | KHO |  |  | 0 | 54 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-02 |  |  | 54 |  | 0
| V17566-DWXD-7471 | COT-3 | CASING PLATE | SH-12 | COT-3-SH-12 | PL6*2006 | 3085 | SS400 | 1 |  | 1 | 291.5 | 291.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 12.4 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, thay đổi kích thước lỗ bolt |  |  |  |  | MODIFY, thay đổi kích thước lỗ bolt | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
96 | V17566-DWXD-7473 | COT-4 | SCR DOOR |  |  | (451x2006x3356) |  |  |  | 1 |  | 1000.3 | 1000.3 | AMC2 | [7 empty] | 0 | 0.051546 |  |  |  |  | 24.6 | Gắn vào cùng Panel COT-2 trước khi giao hàng REVISED | x |  |  | REVISED | REVISED
| V17566-DWXD-7473 | COT-4 | CHANNEL | CY-48 | COT-4-CY-48 | [200*80*7.5*11 | 3338 | SS400 | 1 |  | 1 | 79.9 | 79.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7473 | COT-4 | CHANNEL | CY-49 | COT-4-CY-49 | [200*80*7.5*11 | 3338 | SS400 | 1 |  | 1 | 79.5 | 79.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.3 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7473 | COT-4 | CHANNEL | CY-50 | COT-4-CY-50 | [200*80*7.5*11 | 1448 | SS400 | 3 |  | 3 | 34.9 | 104.6 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 3.2 | MODIFY, thay đổi kích thước chamfer 19->25 |  |  |  | MODIFY, Giảm chiều dài: 1522->1448 | MODIFY, thay đổi kích thước chamfer 19->25 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 3 | 2026-04-22 | 0
| V17566-DWXD-7473 | COT-4 | PLATE | G-3 | COT-4-G-3 | PL12*200 | 1448 | SS400 | 2 |  | 2 | 27.2 | 54.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.3 | MODIFY, Giảm chiều dài: 1522->1448 |  |  |  | MODIFY, Giảm chiều dài: 1522->1448 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16 | 0
| V17566-DWXD-7473 | COT-4 | PLATE | G-4 | COT-4-G-4 | PL6*124 | 2006 | SS400 | 2 |  | 2 | 11.7 | 23.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 2 | 2026-04-16 | 0
| V17566-DWXD-7473 | COT-4 | GASKET | G-5 | COT-4-G-5 | PL3*124 | 2006 | NON-METALLIC | 2 |  | 2 | 0.4 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [5 empty] | 2
| V17566-DWXD-7473 | COT-4 | GASKET | G-8003 |  | PL3*50 | 3353 | NON-METALLIC | 2 |  | 2 | 0.3 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 1 | [6 empty] | Purchasing | [5 empty] | 2
| V17566-DWXD-7473 | COT-4 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 120 |  | 120 | 0 | 1.5 | AMC2 | Purchasing | KHO |  |  | 0 | 120 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 120 |  | 0
| V17566-DWXD-7473 | COT-4 | STUD 3/8" | M-24 |  | D10 | 245 | SS400 | 60 |  | 60 | 0.1 | 8.2 | AMC2 | Purchasing | KHO |  |  | 0 | 60 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-02 |  |  | 60 |  | 0
| V17566-DWXD-7473 | COT-4 | CASING PLATE | SH-13 | COT-4-SH-13 | PL6*2006 | 3350 | SS400 | 1 |  | 1 | 316.6 | 316.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 13.5 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, thay đổi kích thước lỗ bolt |  |  |  |  | MODIFY, thay đổi kích thước lỗ bolt | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
97 | V17566-DWXD-7475 | COT-5 | SCR DOOR |  |  | (451x2006x3085) |  |  |  | 1 |  | 916.5 | 916.5 | AMC2 | [7 empty] | 0 | 0.051724 |  |  |  |  | 21.6 | Gắn vào cùng Panel COT-2 trước khi giao hàng REVISED | x |  |  | REVISED | REVISED
| V17566-DWXD-7475 | COT-5 | CHANNEL | CY-35 | COT-5-CY-35 | [200*80*7.5*11 | 3079 | SS400 | 1 |  | 1 | 73.6 | 73.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7475 | COT-5 | CHANNEL | CY-47 | COT-5-CY-47 | [200*80*7.5*11 | 3079 | SS400 | 1 |  | 1 | 73.6 | 73.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.1 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 1 | 2026-04-22 | 0
| V17566-DWXD-7475 | COT-5 | CHANNEL | CY-50 | COT-5-CY-50 | [200*80*7.5*11 | 1448 | SS400 | 3 |  | 3 | 34.9 | 104.6 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 3.2 | MODIFY, thay đổi kích thước chamfer 19->25 |  |  |  | MODIFY, Giảm chiều dài: 1522->1448 | MODIFY, thay đổi kích thước chamfer 19->25 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 3 | 2026-04-22 | 0
| V17566-DWXD-7475 | COT-5 | PLATE | G-3 | COT-5-G-3 | PL12*200 | 1448 | SS400 | 2 |  | 2 | 27.2 | 54.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.3 | MODIFY, Giảm chiều dài: 1522->1448 |  |  |  | MODIFY, Giảm chiều dài: 1522->1448 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0034-VTC-5 |  | U284-07-CP007 | 2 | 2026-04-16 | 0
| V17566-DWXD-7475 | COT-5 | PLATE | G-4 | COT-5-G-4 | PL6*124 | 2006 | SS400 | 1 |  | 1 | 11.7 | 11.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
| V17566-DWXD-7475 | COT-5 | GASKET | G-8001 |  | PL3*50 | 2006 | NON-METALLIC | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 1 | [6 empty] | Purchasing | [5 empty] | 1
| V17566-DWXD-7475 | COT-5 | GASKET | G-8002 |  | PL3*50 | 3023 | NON-METALLIC | 2 |  | 2 | 0.2 | 0.5 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [7 empty] | ADDED, thêm mới |  |  |  |  | ADDED, thêm mới | [7 empty] | 1 | [6 empty] | Purchasing | [5 empty] | 2
| V17566-DWXD-7475 | COT-5 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 108 |  | 108 | 0 | 1.3 | AMC2 | Purchasing | KHO |  |  | 0 | 108 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 108 |  | 0
| V17566-DWXD-7475 | COT-5 | STUD 3/8" | M-24 |  | D10 | 245 | SS400 | 54 |  | 54 | 0.1 | 7.3 | AMC2 | Purchasing | KHO |  |  | 0 | 54 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-02 |  |  | 54 |  | 0
| V17566-DWXD-7475 | COT-5 | CASING PLATE | SH-12 | COT-5-SH-12 | PL6*2006 | 3085 | SS400 | 1 |  | 1 | 291.5 | 291.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 12.4 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau MODIFY, thay đổi kích thước lỗ bolt |  |  |  |  | MODIFY, thay đổi kích thước lỗ bolt | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
98 | V17566-DWXD-7477 | COT-6 | TOP PANEL |  |  | (364x1262x9785) |  |  |  | 1 |  | 1363 | 1363 | AMC2 | [7 empty] | 0 | 0.084469 |  |  |  |  | 40.8 | REVISED | x | o |  |  | REVISED
| V17566-DWXD-7477 | COT-6 | ANGLE | A-3 | COT-6-A-3 | L75*75*6 | 9785 | SS400 | 1 |  | 1 | 67 | 67 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 9677->9785 |  |  |  |  | MODIFY, tăng chiều dài 9677->9785 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7477 | COT-6 | CHANNEL | C-2 | COT-6-C-2 | [200*80*7.5*11 | 9785 | SS400 | 1 |  | 1 | 237.7 | 237.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 6.6 | Cắt dương lên 15mm theo yêu cầu KOM, khoan lỗ lấy 1 đầu làm chuẩn MODIFY, tăng chiều dài 9506->9785 |  |  |  |  | MODIFY, tăng chiều dài 9506->9785 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP521-1 DCC25-U284-0064-VTC-12 |  | U284-07-CP529 | 1 | 2026-06-27 | 0
| V17566-DWXD-7477 | COT-6 | CHANNEL | CY-40 | COT-6-CY-40 | [200*80*7.5*11 | 553 | SS400 | 5 |  | 5 | 12.6 | 63.1 | AMC2 | Shape | MCC |  |  | 5 | 0 | 1 | [6 empty] | 1.8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 5 | 2026-04-22 | 0
| V17566-DWXD-7477 | COT-6 | CHANNEL | CY-41 | COT-6-CY-41 | [200*80*7.5*11 | 558 | SS400 | 5 |  | 5 | 12.1 | 60.7 | AMC2 | Shape | MCC |  |  | 5 | 0 | 1 | [6 empty] | 1.8 | [13 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 5 | 2026-04-22 | 0
| V17566-DWXD-7477 | COT-6 | CHANNEL | CY-42 | COT-6-CY-42 | [200*80*7.5*11 | 553 | SS400 | 2 |  | 2 | 12.6 | 25.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.7 | [13 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7477 | COT-6 | CHANNEL | CY-43 | COT-6-CY-43 | [200*80*7.5*11 | 558 | SS400 | 2 |  | 2 | 12.1 | 24.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.7 | [13 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | U284-19B-CP503-2 U284-020-CP502-3 U284-020-CP502-4 U284-18-CP501-2 U284-18-CP511-1 DCC25-U284-0031-VTC-16 DCC25-U284-0034-VTC-17 DCC25-U284-0039-VTC-12 DCC25-U284-0015-VTC-2 |  | U284-07-CP512 | 2 | 2026-04-22 | 0
| V17566-DWXD-7477 | COT-6 | PIPE | D-2 | COT-6-D-2 | 3" SCH.40 | 315 | A-312 TP.304 | 6 |  | 6 | 3.5 | 21.1 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.5 | Cắt dương lên 5mm MODIFY, tăng chiều dài 309->315 |  |  |  |  | MODIFY, tăng chiều dài 309->315 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | DCC25-U284-0016-VTC-30 |  | U284-07-CP504 | 6 | 2026-04-21 | 0
| V17566-DWXD-7477 | COT-6 | STUD 3/8" | M-4 |  | D10 | 327 | SS400 | 6 |  | 6 | 0.2 | 1.1 | AMC2 | Purchasing | KHO |  |  | 0 | 6 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-03 |  |  | 6 |  | 0
| V17566-DWXD-7477 | COT-6 | NUT M10 | M-5 |  | NUT_M10 | 8 | SS400 | 224 |  | 224 | 0 | 2.7 | AMC2 | Purchasing | KHO |  |  | 0 | 224 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC25-U284-0010-VTP-03 |  |  | 224 |  | 0
| V17566-DWXD-7477 | COT-6 | STUD 3/8" | M-23 |  | D10 | 89 | SS400 | 106 |  | 106 | 0 | 5.2 | AMC2 | Purchasing | KHO |  |  | 0 | 106 | 0 | [20 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0057-VTP-01 |  |  | 106 |  | 0
| V17566-DWXD-7477 | COT-6 | PLATE | P-31 | COT-6-P-31 | PL10*73 | 184 | SS400 | 8 |  | 8 | 1 | 8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-18-CP016-1 DCC25-U284-0031-VTC-3/1 DCC25-U284-0016-VTC-21 |  | U284-07-CP004 | 8 | 2026-04-16 | 0
| V17566-DWXD-7477 | COT-6 | CASING PLATE | SH-11 | COT-6-SH-11 | PL6*1249 | 9785 | SS400 | 1 |  | 1 | 573.8 | 573.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 24.5 | Không cắt lỗ cho phần cửa + lỗ cho phần nozzle, đơn vị sẽ tự cắt sau | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0006-VTC-1/21 DCC25-U284-0006-VTC-1/22 DCC25-U284-0006-VTC-1/23. DCC25-U284-0006-VTC-1/24 |  | U284-07-CP019 | 1 | 2026-04-16 | 0
99 | V17566-DWXD-7503 | CO-BF-1 | BUILT-UP CHANNEL |  |  | (250x90x9574) |  |  |  | 2 |  | 366.2 | 732.3 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 16 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7503 | CO-BF-1 | BUILT-UP CHANNEL | B-5 | CO-BF-1-B-5 | BC250*90*12*12 | 9574 | A387 GR.11 CL.2 | 1 |  | 2 | 366.2 | 732.3 | AMC2 | Shape | WTC |  |  | 2 | 0 | 2 | [6 empty] | 16 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
100 | V17566-DWXD-7504 | CO-BF-2 | BAFFLE |  |  | (38x3x2881) |  |  |  | 1 |  | 2.6 | 2.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.2 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7504 | CO-BF-2 | BAFFLE | P-45 | CO-BF-2-P-45 | PL3*38 | 2881 | A-1011 CS | 1 |  | 1 | 2.6 | 2.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07 | 0
101 | V17566-DWXD-7505 | CO-BF-3 | BAFFLE |  |  | (38x3x2914) |  |  |  | 1 |  | 2.6 | 2.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.2 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7505 | CO-BF-3 | BAFFLE | P-46 | CO-BF-3-P-46 | PL3*38 | 2914 | A-1011 CS | 1 |  | 1 | 2.6 | 2.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07 | 0
102 | V17566-DWXD-7506 | CO-BF-4 | BAFFLE |  |  | (38x3x2862) |  |  |  | 1 |  | 2.6 | 2.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.2 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7506 | CO-BF-4 | BAFFLE | P-47 | CO-BF-4-P-47 | PL3*38 | 2862 | A-1011 CS | 1 |  | 1 | 2.6 | 2.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07 | 0
103 | V17566-DWXD-7507 | CO-BF-5 | BENT PLATE 110B |  |  | (300x51x90) |  |  |  | 1 |  | 0.5 | 0.5 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.1 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7507 | CO-BF-5 | BENT PLATE 110B | PX-9 | CO-BF-5-PX-9 | PL2*300 | 141 | A-1011 CS | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07 | 0
104 | V17566-DWXD-7508 | CO-BF-6 | BENT PLATE 110B |  |  | (1156x51x90) |  |  |  | 20 |  | 2.5 | 49.9 | AMC2 | [7 empty] | 20 | 1 |  |  |  |  | 6.8 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7508 | CO-BF-6 | BENT PLATE 110B | PX-10 | CO-BF-6-PX-10 | PL2*1156 | 141 | A-1011 CS | 1 |  | 20 | 2.5 | 49.9 | AMC2 | Plate | PMC |  |  | 20 | 0 | 20 | [6 empty] | 6.8 | MODIFY, giảm Q.ty: 21-> 20 |  |  |  | ADDED, thêm mới |  | MODIFY, giảm Q.ty: 21-> 20 | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 21 | 2026-05-07 | -1
105 | V17566-DWXD-7509 | CO-BF-7 | BENT PLATE 110B |  |  | (344x51x90) |  |  |  | 1 |  | 0.7 | 0.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.1 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7509 | CO-BF-7 | BENT PLATE 110B | PX-11 | CO-BF-7-PX-11 | PL2*344 | 141 | A-1011 CS | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07 | 0
106 | V17566-DWXD-7510 | CO-BF-8 | BENT PLATE 110A |  |  | (300x51x90) |  |  |  | 1 |  | 0.5 | 0.5 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.1 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7510 | CO-BF-8 | BENT PLATE 110A | PX-12 | CO-BF-8-PX-12 | PL2*300 | 141 | A-1011 CS | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07 | 0
107 | V17566-DWXD-7511 | CO-BF-9 | BENT PLATE 110A |  |  | (1156x51x90) |  |  |  | 20 |  | 2.5 | 49.9 | AMC2 | [7 empty] | 20 | 1 |  |  |  |  | 6.8 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7511 | CO-BF-9 | BENT PLATE 110A | PX-13 | CO-BF-9-PX-13 | PL2*1156 | 141 | A-1011 CS | 1 |  | 20 | 2.5 | 49.9 | AMC2 | Plate | PMC |  |  | 20 | 0 | 20 | [6 empty] | 6.8 | MODIFY, giảm Q.ty: 21-> 20 |  |  |  | ADDED, thêm mới |  | MODIFY, giảm Q.ty: 21-> 20 | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 21 | 2026-05-07 | -1
108 | V17566-DWXD-7512 | CO-BF-10 | BENT PLATE 110A |  |  | (344x51x90) |  |  |  | 1 |  | 0.7 | 0.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.1 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7512 | CO-BF-10 | BENT PLATE 110A | PX-14 | CO-BF-10-PX-14 | PL2*344 | 141 | A-1011 CS | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07 | 0
109 | V17566-DWXD-7588 | CO-BF-11 | STUD 5/8" |  |  | (102x40x184) |  |  |  | 156 |  | 1 | 157.3 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 5.5 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7588 | CO-BF-11 | STUD 5/8" | M-25 |  | D16 | 184 | A-193 Gr.B8 | 1 |  | 156 | 0.3 | 41.3 | AMC2 | Purchasing | KHO |  |  | 0 | 156 | 0 | [7 empty] | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0046-VTC-11 |  |  | 156 |  | 0
| V17566-DWXD-7588 | CO-BF-11 | NUT M16 | M-26 |  | NUT_M16 | 13 | A-194 Gr.8 | 2 |  | 312 | 0.1 | 16.1 | AMC2 | Purchasing | KHO |  |  | 0 | 312 | 0 | [7 empty] | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | [6 empty] | Purchasing | DCC26-U284-0046-VTC-11 |  |  | 312 |  | 0
| V17566-DWXD-7588 | CO-BF-11 | PLATE 206 | M-27 |  | PL10*40 | 102 | A387 GR.11 CL.2 | 1 |  | 156 | 0.3 | 50 | AMC2 | Plate | MCC |  |  | 0 | 156 | 0 | [7 empty] | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0046-VTC-11 |  |  | 156 |  | 0
| V17566-DWXD-7588 | CO-BF-11 | PLATE 205 | M-28 |  | PL10*40 | 102 | A387 GR.11 CL.2 | 1 |  | 156 | 0.3 | 50 | AMC2 | Plate | MCC |  |  | 0 | 156 | 0 | [7 empty] | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | [6 empty] | Purchasing | DCC26-U284-0046-VTC-11 |  |  | 156 |  | 0
110 | V17566-DWXD-7513 | CO-BF-12 | BAFFLE |  |  | (12x3x36) |  |  |  | 1 |  | 0 | 0 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7513 | CO-BF-12 | BAFFLE | P-44 | CO-BF-12-P-44 | PL3*12 | 35 | A-1011 CS | 1 |  | 1 | 0 | 0 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-2 |  | U284-07-CP032 | 1 | 2026-05-07 | 0
111 | V17566-DWXD-7514 | CO-BF-13 | BUILT-UP H-BEAM |  |  | (300x353x11000) |  |  |  | 1 |  | 616.3 | 616.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 15.8 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7514 | CO-BF-13 | BUILT-UP H-BEAM | BY-6 | CO-BF-13-BY-6 | BH300*200*8*12 | 11000 | A387 GR.11 CL.2 | 1 |  | 1 | 602.8 | 602.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 15.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7514 | CO-BF-13 | PLATE | P-38 | CO-BF-13-P-38 | PL10*96 | 276 | A387 GR.11 CL.2 | 2 |  | 2 | 2.1 | 4.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | MODIFY, thay đổi chiều dày PL12->PL10 |  |  |  | ADDED, thêm mới |  | MODIFY, thay đổi chiều dày PL12->PL10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP025-2 |  | U284-05A-CP012 | 2 | 2026-05-13 | 0
| V17566-DWXD-7514 | CO-BF-13 | PLATE | P-43 | CO-BF-13-P-43 | PL6*51 | 167 | A387 GR.11 CL.2 | 24 |  | 24 | 0.4 | 9.1 | AMC2 | Plate | MCC |  |  | 24 | 0 | 1 | [6 empty] | 0.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 24 | 2026-07-09 | 0
| V17566-DWXD-7514 | CO-BF-13 | INSULATION PIN | PI-1 | CO-BF-13-PI-1 | D4 | 178 | TP304 | 20 |  | 20 | 0 | 0.3 | AMC2 | Shape | MCC |  |  | 20 | 0 | 1 | [6 empty] | 0 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 20 | 2026-05-07 | 0
112 | V17566-DWXD-7515 | CO-BF-14 | BUILT-UP H-BEAM |  |  | (300x353x13328) |  |  |  | 1 |  | 757.7 | 757.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 19.4 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7515 | CO-BF-14 | BUILT-UP H-BEAM | BY-3 | CO-BF-14-BY-3 | BH300*200*8*12 | 13328 | A387 GR.11 CL.2 | 1 |  | 1 | 733.1 | 733.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 18.5 | MODIFY, giảm chiều dài 13334->13328 |  |  |  | ADDED, thêm mới |  | MODIFY, giảm chiều dài 13334->13328 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7515 | CO-BF-14 | PLATE | P-20 | CO-BF-14-P-20 | PL12*67 | 150 | A387 GR.11 CL.2 | 2 |  | 2 | 0.9 | 1.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 2 | 2026-05-07 | 0
| V17566-DWXD-7515 | CO-BF-14 | PLATE | P-38 | CO-BF-14-P-38 | PL10*96 | 276 | A387 GR.11 CL.2 | 4 |  | 4 | 2.1 | 8.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 | MODIFY, thay đổi chiều dày PL12->PL10 |  |  |  | ADDED, thêm mới |  | MODIFY, thay đổi chiều dày PL12->PL10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP025-2 |  | U284-05A-CP012 | 4 | 2026-05-13 | 0
| V17566-DWXD-7515 | CO-BF-14 | PLATE | P-40 | CO-BF-14-P-40 | PL12*149 | 276 | A387 GR.11 CL.2 | 1 |  | 1 | 3.4 | 3.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 1 | 2026-05-07 | 0
| V17566-DWXD-7515 | CO-BF-14 | PLATE | P-43 | CO-BF-14-P-43 | PL6*51 | 167 | A387 GR.11 CL.2 | 28 |  | 28 | 0.4 | 10.7 | AMC2 | Plate | MCC |  |  | 28 | 0 | 1 | [6 empty] | 0.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 28 | 2026-07-09 | 0
| V17566-DWXD-7515 | CO-BF-14 | INSULATION PIN | PI-1 | CO-BF-14-PI-1 | D4 | 195 | TP304 | 27 |  | 27 | 0 | 0.4 | AMC2 | Shape | MCC |  |  | 27 | 0 | 1 | [6 empty] | 0.1 | MODIFY, tăng chiều dài 178 -> 195 |  |  |  | ADDED, thêm mới |  | MODIFY, tăng chiều dài 178 -> 195 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 27 | 2026-05-07 | 0
113 | V17566-DWXD-7516 | CO-BF-15 | BUILT-UP CHANNEL |  |  | (300x100x2877) |  |  |  | 2 |  | 129 | 258 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 5.6 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7516 | CO-BF-15 | BUILT-UP CHANNEL | BY-4 | CO-BF-15-BY-4 | BC300*100*12*12 | 2877 | A387 GR.11 CL.2 | 1 |  | 2 | 129 | 258 | AMC2 | Shape | WTC |  |  | 2 | 0 | 2 | [6 empty] | 5.6 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
114 | V17566-DWXD-7517 | CO-BF-16 | BUILT-UP H-BEAM |  |  | (300x400x11000) |  |  |  | 2 |  | 632.6 | 1265.2 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 33.1 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7517 | CO-BF-16 | BUILT-UP H-BEAM | BY-6 | CO-BF-16-BY-6 | BH300*200*8*12 | 11000 | A387 GR.11 CL.2 | 1 |  | 2 | 602.8 | 1205.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 30.4 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
| V17566-DWXD-7517 | CO-BF-16 | PLATE | P-38 | CO-BF-16-P-38 | PL10*96 | 276 | A387 GR.11 CL.2 | 4 |  | 8 | 2.1 | 16.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 2 | [6 empty] | 0.5 | MODIFY, thay đổi chiều dày PL12->PL10 |  |  |  | ADDED, thêm mới |  | MODIFY, thay đổi chiều dày PL12->PL10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP025-2 |  | U284-05A-CP012 | 8 | 2026-05-13 | 0
| V17566-DWXD-7517 | CO-BF-16 | PLATE | P-42 | CO-BF-16-P-42 | PL6*51 | 196 | A387 GR.11 CL.2 | 48 |  | 96 | 0.5 | 43.2 | AMC2 | Plate | MCC |  |  | 96 | 0 | 2 | [6 empty] | 2.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 96 | 2026-07-09 | 0
115 | V17566-DWXD-7518 | CO-BF-17 | BUILT-UP H-BEAM |  |  | (300x400x13334) |  |  |  | 2 |  | 785.3 | 1570.6 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 41.1 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7518 | CO-BF-17 | BUILT-UP H-BEAM | BY-3 | CO-BF-17-BY-3 | BH300*200*8*12 | 13328 | A387 GR.11 CL.2 | 1 |  | 2 | 733.1 | 1466.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 36.9 | MODIFY, giảm chiều dài 13334->13328 |  |  |  | ADDED, thêm mới |  | MODIFY, giảm chiều dài 13334->13328 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 2 |  | 0
| V17566-DWXD-7518 | CO-BF-17 | PLATE | P-20 | CO-BF-17-P-20 | PL12*67 | 150 | A387 GR.11 CL.2 | 4 |  | 8 | 0.9 | 7.6 | AMC2 | Plate | MCC |  |  | 8 | 0 | 2 | [6 empty] | 0.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 8 | 2026-05-07 | 0
| V17566-DWXD-7518 | CO-BF-17 | PLATE | P-38 | CO-BF-17-P-38 | PL10*96 | 276 | A387 GR.11 CL.2 | 8 |  | 16 | 2.1 | 32.8 | AMC2 | Plate | MCC |  |  | 16 | 0 | 2 | [6 empty] | 1 | MODIFY, thay đổi chiều dày PL12->PL10 |  |  |  | ADDED, thêm mới |  | MODIFY, thay đổi chiều dày PL12->PL10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP025-2 |  | U284-05A-CP012 | 16 | 2026-05-13 | 0
| V17566-DWXD-7518 | CO-BF-17 | PLATE | P-40 | CO-BF-17-P-40 | PL12*149 | 276 | A387 GR.11 CL.2 | 2 |  | 4 | 3.4 | 13.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | 0.3 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 4 | 2026-05-07 | 0
| V17566-DWXD-7518 | CO-BF-17 | PLATE | P-42 | CO-BF-17-P-42 | PL6*51 | 196 | A387 GR.11 CL.2 | 56 |  | 112 | 0.5 | 50.4 | AMC2 | Plate | MCC |  |  | 112 | 0 | 2 | [6 empty] | 2.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 112 | 2026-07-09 | 0
116 | V17566-DWXD-7519 | CO-BF-18 | BENT PLATE |  |  | (3144x313x159) |  |  |  | 1 |  | 72.1 | 72.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 3.1 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7519 | CO-BF-18 | BENT PLATE | PX-4 | CO-BF-18-PX-4 | PL6*3144 | 490 | A387 GR.11 CL.2 | 1 |  | 1 | 72.1 | 72.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.1 | MODIFY, tăng chiều dài 489->490 |  |  |  | ADDED, thêm mới |  | MODIFY, tăng chiều dài 489->490 | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 1 | 2026-07-09 | 0
117 | V17566-DWXD-7520 | CO-BF-19 | BENT PLATE |  |  | (3241x313x159) |  |  |  | 1 |  | 74.1 | 74.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 3.2 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7520 | CO-BF-19 | BENT PLATE | PX-5 | CO-BF-19-PX-5 | PL6*3241 | 490 | A387 GR.11 CL.2 | 1 |  | 1 | 74.1 | 74.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.2 | MODIFY, tăng chiều dài 489->490 |  |  |  | ADDED, thêm mới |  | MODIFY, tăng chiều dài 489->490 | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 1 | 2026-07-09 | 0
118 | V17566-DWXD-7521 | CO-BF-20 | BUILT-UP CHANNEL |  |  | (300x100x2906) |  |  |  | 1 |  | 130.3 | 130.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 2.8 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7521 | CO-BF-20 | BUILT-UP CHANNEL | BY-5 | CO-BF-20-BY-5 | BC300*100*12*12 | 2906 | A387 GR.11 CL.2 | 1 |  | 1 | 130.3 | 130.3 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
119 | V17566-DWXD-7522 | CO-BF-21 | BENT PLATE |  |  | (3241x313x159) |  |  |  | 1 |  | 74.1 | 74.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 3.2 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7522 | CO-BF-21 | BENT PLATE | PX-3 | CO-BF-21-PX-3 | PL6*3241 | 490 | A387 GR.11 CL.2 | 1 |  | 1 | 74.1 | 74.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.2 | MODIFY, tăng chiều dài 489->490 |  |  |  | ADDED, thêm mới |  | MODIFY, tăng chiều dài 489->490 | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 1 | 2026-07-09 | 0
120 | V17566-DWXD-7523 | CO-BF-22 | BUILT-UP H-BEAM |  |  | (300x353x11000) |  |  |  | 1 |  | 616.3 | 616.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 15.8 | REVISED | x | o |  | ADDED, thêm mới
| V17566-DWXD-7523 | CO-BF-22 | BUILT-UP H-BEAM | BY-6 | CO-BF-22-BY-6 | BH300*200*8*12 | 11000 | A387 GR.11 CL.2 | 1 |  | 1 | 602.8 | 602.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 15.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7523 | CO-BF-22 | PLATE | P-38 | CO-BF-22-P-38 | PL10*96 | 276 | A387 GR.11 CL.2 | 2 |  | 2 | 2.1 | 4.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | MODIFY, thay đổi chiều dày PL12->PL10 |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 2 | 2026-05-07 | 0
| V17566-DWXD-7523 | CO-BF-22 | PLATE | P-43 | CO-BF-22-P-43 | PL6*51 | 167 | A387 GR.11 CL.2 | 24 |  | 24 | 0.4 | 9.1 | AMC2 | Plate | MCC |  |  | 24 | 0 | 1 | [6 empty] | 0.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 24 | 2026-07-09 | 0
| V17566-DWXD-7523 | CO-BF-22 | INSULATION PIN | PI-1 | CO-BF-22-PI-1 | D4 | 195 | TP304 | 20 |  | 20 | 0 | 0.3 | AMC2 | Shape | MCC |  |  | 20 | 0 | 1 | [6 empty] | 0 | MODIFY, tăng chiều dài 178 -> 195 |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 20 | 2026-05-07 | 0
121 | V17566-DWXD-7524 | CO-BF-23 | BUILT-UP H-BEAM |  |  | (300x282x13334) |  |  |  | 1 |  | 757.7 | 757.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 19.4 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7524 | CO-BF-23 | BUILT-UP H-BEAM | BY-3 | CO-BF-23-BY-3 | BH300*200*8*12 | 13328 | A387 GR.11 CL.2 | 1 |  | 1 | 733.1 | 733.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 18.5 | MODIFY, giảm chiều dài 13334->13328 |  |  |  | ADDED, thêm mới |  | MODIFY, giảm chiều dài 13334->13328 | [6 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 1 |  | 0
| V17566-DWXD-7524 | CO-BF-23 | PLATE | P-20 | CO-BF-23-P-20 | PL12*67 | 150 | A387 GR.11 CL.2 | 2 |  | 2 | 0.9 | 1.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 2 | 2026-05-07 | 0
| V17566-DWXD-7524 | CO-BF-23 | PLATE | P-38 | CO-BF-23-P-38 | PL10*96 | 276 | A387 GR.11 CL.2 | 4 |  | 4 | 2.1 | 8.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 | MODIFY, thay đổi chiều dày PL12->PL10 |  |  |  | ADDED, thêm mới |  | MODIFY, thay đổi chiều dày PL12->PL10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP025-2 |  | U284-05A-CP012 | 4 | 2026-05-13 | 0
| V17566-DWXD-7524 | CO-BF-23 | PLATE | P-40 | CO-BF-23-P-40 | PL12*149 | 276 | A387 GR.11 CL.2 | 1 |  | 1 | 3.4 | 3.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-6 |  | U284-07-CP027 | 1 | 2026-05-07 | 0
| V17566-DWXD-7524 | CO-BF-23 | PLATE | P-43 | CO-BF-23-P-43 | PL6*51 | 167 | A387 GR.11 CL.2 | 28 |  | 28 | 0.4 | 10.7 | AMC2 | Plate | MCC |  |  | 28 | 0 | 1 | [6 empty] | 0.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 28 | 2026-07-09 | 0
| V17566-DWXD-7524 | CO-BF-23 | INSULATION PIN | PI-1 | CO-BF-23-PI-1 | D4 | 195 | TP304 | 27 |  | 27 | 0 | 0.4 | AMC2 | Shape | MCC |  |  | 27 | 0 | 1 | [6 empty] | 0.1 | MODIFY, tăng chiều dài 178 -> 195 |  |  |  | ADDED, thêm mới |  | MODIFY, tăng chiều dài 178 -> 195 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-7 DCC25-U284-0070-VTC-1 |  | U284-07-CP526 | 27 | 2026-05-07 | 0
122 | V17566-DWXD-7525 | CO-BF-24 | BUILT-UP H-BEAM |  |  | (300x200x9574) |  |  |  | 6 |  | 536.5 | 3219.2 | AMC2 | [7 empty] | 6 | 1 |  |  |  |  | 82.3 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7525 | CO-BF-24 | BUILT-UP H-BEAM | B-6 | CO-BF-24-B-6 | BH300*200*8*12 | 9574 | A387 GR.11 CL.2 | 1 |  | 6 | 526.7 | 3160.2 | AMC2 | Shape | MCC |  |  | 6 | 0 | 6 | [6 empty] | 79.6 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication |  |  | chi tiết chia nối | 6 |  | 0
| V17566-DWXD-7525 | CO-BF-24 | PLATE | P-39 | CO-BF-24-P-39 | PL6*96 | 276 | A387 GR.11 CL.2 | 8 |  | 48 | 1.2 | 59.1 | AMC2 | Plate | MCC |  |  | 48 | 0 | 6 | [6 empty] | 2.7 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 48 | 2026-07-09 | 0
123 | V17566-DWXD-7526 | CO-BF-25 | BENT PLATE |  |  | (854x204x51) |  |  |  | 1 |  | 3.6 | 3.6 | AMC2 | [7 empty] | 0 | 0.66667 |  |  |  |  | 0.5 | REVISED | x | o |  | ADDED, thêm mới |  | REVISED
| V17566-DWXD-7526 | CO-BF-25 | PLATE | P-48 | CO-BF-25-P-48 | PL2*49 | 189 | A-1011 CS | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 2 | 2026-05-07 | 0
| V17566-DWXD-7526 | CO-BF-25 | BENT PLATE | PX-8 | CO-BF-25-PX-8 | PL2*854 | 255 | A-1011 CS | 1 |  | 1 | 3.4 | 3.4 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0.5 | MODIFY, giảm chiều dài 902-> 854 |  |  |  | ADDED, thêm mới |  | MODIFY, giảm chiều dài 902-> 854 | [6 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP030-3 |  | U284-05A-CP017 | 1 | 2026-05-13 | 0
124 | V17566-DWXD-7527 | CO-BF-26 | BENT PLATE |  |  | (1156x204x51) |  |  |  | 7 |  | 4.7 | 33.1 | AMC2 | [7 empty] | 7 | 1 |  |  |  |  | 4.3 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7527 | CO-BF-26 | PLATE | P-48 | CO-BF-26-P-48 | PL2*49 | 189 | A-1011 CS | 2 |  | 14 | 0.1 | 1.1 | AMC2 | Plate | MCC |  |  | 14 | 0 | 7 | [6 empty] | 0.2 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 14 | 2026-05-07 | 0
| V17566-DWXD-7527 | CO-BF-26 | BENT PLATE | PX-6 | CO-BF-26-PX-6 | PL2*1156 | 255 | A-1011 CS | 1 |  | 7 | 4.6 | 31.9 | AMC2 | Plate | PMC |  |  | 7 | 0 | 7 | [6 empty] | 4.1 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 7 | 2026-05-07 | 0
125 | V17566-DWXD-7528 | CO-BF-27 | BENT PLATE |  |  | (835x204x51) |  |  |  | 1 |  | 3.4 | 3.4 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7528 | CO-BF-27 | PLATE | P-48 | CO-BF-27-P-48 | PL2*49 | 189 | A-1011 CS | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07 | 0
| V17566-DWXD-7528 | CO-BF-27 | BENT PLATE | PX-7 | CO-BF-27-PX-7 | PL2*835 | 255 | A-1011 CS | 1 |  | 1 | 3.3 | 3.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-1 |  | U284-07-CP030 | 1 | 2026-05-07 | 0
126 | V17566-DWXD-7529 | CO-BF-28 | BENT PLATE |  |  | (9574x90x150) |  |  |  | 16 |  | 173.2 | 2771 | AMC2 | [7 empty] | 16 | 1 |  |  |  |  | 76.1 | ADDED, thêm mới | x | o |  | ADDED, thêm mới
| V17566-DWXD-7529 | CO-BF-28 | PLATE | P-41 | CO-BF-28-P-41 | PL6*77 | 137 | A387 GR.11 CL.2 | 13 |  | 208 | 0.5 | 95.4 | AMC2 | Plate | MCC |  |  | 208 | 0 | 16 | [6 empty] | 4.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0046-3 |  | U284-07-CP035 | 208 | 2026-07-09 | 0
| V17566-DWXD-7529 | CO-BF-28 | BENT PLATE | PX-2 | CO-BF-28-PX-2 | PL10*9574 | 224 | A387 GR.11 CL.2 | 1 |  | 16 | 167.2 | 2675.6 | AMC2 | Plate | PMC |  |  | 16 | 0 | 16 | [6 empty] | 71.5 | ADDED, thêm mới |  |  |  | ADDED, thêm mới | [8 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 16 |  | 0
127 | V17566-DWXD-7530 | CO-BF-29 | BENT PLATE 110B |  |  | (1024x51x90) |  |  |  | 1 |  | 2.2 | 2.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 | ADDED, thêm mới | x | o |  |  |  | ADDED, thêm mới
| V17566-DWXD-7530 | CO-BF-29 | BENT PLATE 110B | PX-15 | CO-BF-29-PX-15 | PL2*1024 | 141 | A-1011 CS | 1 |  | 1 | 2.2 | 2.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | ADDED, thêm mới | [5 empty] | ADDED, thêm mới | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP030-3 |  | U284-05A-CP017 | 1 | 2026-05-13 | 0
128 | V17566-DWXD-7531 | CO-BF-30 | BENT PLATE 110A |  |  | (1024x51x90) |  |  |  | 1 |  | 2.2 | 2.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 | ADDED, thêm mới | x | o |  |  |  | ADDED, thêm mới
| V17566-DWXD-7531 | CO-BF-30 | BENT PLATE 110A | PX-16 | CO-BF-30-PX-16 | PL2*1024 | 141 | A-1011 CS | 1 |  | 1 | 2.2 | 2.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | ADDED, thêm mới | [5 empty] | ADDED, thêm mới | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP030-3 |  | U284-05A-CP017 | 1 | 2026-05-13 | 0
129 | V17566-DWXD-7595 | AIG-1 | PIPE |  |  | (202x136x5153) |  |  |  | 24 |  | 28.5 | 684.3 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7595 | AIG-1 | PIPE | D-17 | AIG-1-D-17 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 24 |  | 0
| V17566-DWXD-7595 | AIG-1 | PLATE | G-31 | AIG-1-G-31 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7595 | AIG-1 | PLATE | G-33 | AIG-1-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
130 | V17566-DWXD-7596 | AIG-2 | PIPE |  |  | (202x160x5153) |  |  |  | 24 |  | 28.5 | 684.3 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7596 | AIG-2 | PIPE | D-19 | AIG-2-D-19 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 24 |  | 0
| V17566-DWXD-7596 | AIG-2 | PLATE | G-31 | AIG-2-G-31 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7596 | AIG-2 | PLATE | G-33 | AIG-2-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
131 | V17566-DWXD-7597 | AIG-3 | PIPE |  |  | (202x124x5153) |  |  |  | 12 |  | 28.5 | 342.1 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7597 | AIG-3 | PIPE | D-13 | AIG-3-D-13 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 12 | 26.7 | 319.9 | AMC2 | Shape | MCC |  |  | 12 | 0 | 12 | [7 empty] | MODIFY, giảm Q.ty: 24->12, chuyển 12 sang mark mới AIG-14 RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | MODIFY, giảm Q.ty: 24->12, chuyển 12 sang mark mới AIG-14 RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 12 |  | 0
| V17566-DWXD-7597 | AIG-3 | PLATE | G-31 | AIG-3-G-31 | PL12*124 | 202 | A-240 TP304H | 1 |  | 12 | 1.5 | 18.2 | AMC2 | Plate | MCC |  |  | 12 | 0 | 12 | [7 empty] | MODIFY, giảm Q.ty: 24->12, chuyển 12 sang mark mới AIG-14 Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  | MODIFY, giảm Q.ty: 24->12, chuyển 12 sang mark mới AIG-14 Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14 | 0
| V17566-DWXD-7597 | AIG-3 | PLATE | G-33 | AIG-3-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 12 | 0.3 | 4 | AMC2 | Plate | MCC |  |  | 12 | 0 | 12 | [7 empty] | MODIFY, giảm Q.ty: 24->12, chuyển 12 sang mark mới AIG-14 | [9 empty] | ADDED, cắt mới bổ sung |  | MODIFY, giảm Q.ty: 24->12, chuyển 12 sang mark mới AIG-14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14 | 0
132 | V17566-DWXD-7598 | AIG-4 | PIPE |  |  | (202x124x5153) |  |  |  | 24 |  | 28.5 | 684.2 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7598 | AIG-4 | PIPE | D-15 | AIG-4-D-15 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 24 |  | 0
| V17566-DWXD-7598 | AIG-4 | PLATE | G-31 | AIG-4-G-31 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7598 | AIG-4 | PLATE | G-33 | AIG-4-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
133 | V17566-DWXD-7599 | AIG-5 | PIPE |  |  | (202x124x5153) |  |  |  | 24 |  | 28.5 | 684.2 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7599 | AIG-5 | PIPE | D-12 | AIG-5-D-12 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 22 chi tiết chia nối | 2 | 2026-07-14 | 22
| V17566-DWXD-7599 | AIG-5 | PLATE | G-30 | AIG-5-G-30 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7599 | AIG-5 | PLATE | G-33 | AIG-5-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
134 | V17566-DWXD-7600 | AIG-6 | PIPE |  |  | (202x124x5153) |  |  |  | 24 |  | 28.5 | 684.2 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7600 | AIG-6 | PIPE | D-14 | AIG-6-D-14 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 | 24 | 2026-07-14 | 0
| V17566-DWXD-7600 | AIG-6 | PLATE | G-30 | AIG-6-G-30 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7600 | AIG-6 | PLATE | G-33 | AIG-6-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
135 | V17566-DWXD-7601 | AIG-7 | PIPE |  |  | (202x136x5153) |  |  |  | 24 |  | 28.5 | 684.3 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7601 | AIG-7 | PIPE | D-16 | AIG-7-D-16 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 | 24 | 2026-07-14 | 0
| V17566-DWXD-7601 | AIG-7 | PLATE | G-30 | AIG-7-G-30 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7601 | AIG-7 | PLATE | G-33 | AIG-7-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
136 | V17566-DWXD-7602 | AIG-8 | PIPE |  |  | (202x160x5153) |  |  |  | 24 |  | 28.5 | 684.3 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7602 | AIG-8 | PIPE | D-18 | AIG-8-D-18 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 24 | 26.7 | 639.9 | AMC2 | Shape | MCC |  |  | 24 | 0 | 24 | [7 empty] | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-1 |  | U284-07-CP532 | 24 | 2026-07-14 | 0
| V17566-DWXD-7602 | AIG-8 | PLATE | G-30 | AIG-8-G-30 | PL12*124 | 202 | A-240 TP304H | 1 |  | 24 | 1.5 | 36.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
| V17566-DWXD-7602 | AIG-8 | PLATE | G-33 | AIG-8-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 24 | 0.3 | 7.9 | AMC2 | Plate | MCC |  |  | 24 | 0 | 24 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 24 | 2026-07-14 | 0
137 | V17566-DWXD-7603 | AIG-9 | PLATE |  |  | (51x8x75) |  |  |  | 32 |  | 0.2 | 7.7 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7603 | AIG-9 | PLATE | G-36 | AIG-9-G-36 | PL8*51 | 75 | A387 GR.11 CL.2 | 1 |  | 32 | 0.2 | 7.7 | AMC2 | Plate | MCC |  |  | 32 | 0 | 32 | [7 empty] | MODIFY, giảm Q.ty: 64->32 | [9 empty] | ADDED, cắt mới bổ sung |  | MODIFY, giảm Q.ty: 64->32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 64 | 2026-07-14 | -32
138 | V17566-DWXD-7604 | AIG-10 | PLATE |  |  | (51x8x89) |  |  |  | 32 |  | 0.3 | 9.1 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7604 | AIG-10 | PLATE | G-35 | AIG-10-G-35 | PL8*51 | 89 | A387 GR.11 CL.2 | 1 |  | 32 | 0.3 | 9.1 | AMC2 | Plate | MCC |  |  | 32 | 0 | 32 | [7 empty] | MODIFY, giảm Q.ty: 64->32 | [9 empty] | ADDED, cắt mới bổ sung |  | MODIFY, giảm Q.ty: 64->32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 64 | 2026-07-14 | -32
139 | V17566-DWXD-7605 | AIG-11 | ANGLE |  |  | (75x75x51) |  |  |  | 32 |  | 0.3 | 11.2 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | REVISED
| V17566-DWXD-7605 | AIG-11 | ANGLE | A-26 | AIG-11-A-26 | L75*75*6 | 51 | A387 GR.11 CL.2 | 1 |  | 32 | 0.3 | 11.2 | AMC2 | Shape | MCC |  |  | 0 | 32 | 0 | [7 empty] | MODIFY, giảm Q.ty: 64->32 | [9 empty] | ADDED, cắt mới bổ sung |  | MODIFY, giảm Q.ty: 64->32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 64 | 2026-07-14 | -32
140 | V17566-DWXD-7606 | AIG-12 | ANGLE |  |  | (650x157x1448) |  |  |  | 16 |  | 19.6 | 313.1 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | ADDED | x | o | [7 empty] | ADDED
| V17566-DWXD-7606 | AIG-12 | ANGLE | A-24 | AIG-12-A-24 | L75*75*6 | 1448 | A387 GR.11 CL.2 | 1 |  | 16 | 9.9 | 158.7 | AMC2 | Shape | MCC |  |  | 0 | 16 | 0 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 16 | 2026-07-14 | 0
| V17566-DWXD-7606 | AIG-12 | ANGLE | A-25 | AIG-12-A-25 | L75*75*6 | 633 | A387 GR.11 CL.2 | 2 |  | 32 | 4.3 | 138.8 | AMC2 | Shape | MCC |  |  | 0 | 32 | 0 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 32 | 2026-07-14 | 0
| V17566-DWXD-7606 | AIG-12 | PLATE | G-34 | AIG-12-G-34 | PL8*89 | 89 | A387 GR.11 CL.2 | 2 |  | 32 | 0.5 | 15.6 | AMC2 | Plate | MCC |  |  | 32 | 0 | 16 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 32 | 2026-07-14 | 0
141 | V17566-DWXD-7607 | AIG-13 | ANGLE |  |  | (650x157x1448) |  |  |  | 16 |  | 19.6 | 313.1 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | ADDED | x | o | [7 empty] | ADDED
| V17566-DWXD-7607 | AIG-13 | ANGLE | A-24 | AIG-13-A-24 | L75*75*6 | 1448 | A387 GR.11 CL.2 | 1 |  | 16 | 9.9 | 158.7 | AMC2 | Shape | MCC |  |  | 0 | 16 | 0 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 16 | 2026-07-14 | 0
| V17566-DWXD-7607 | AIG-13 | ANGLE | A-25 | AIG-13-A-25 | L75*75*6 | 633 | A387 GR.11 CL.2 | 2 |  | 32 | 4.3 | 138.8 | AMC2 | Shape | MCC |  |  | 0 | 32 | 0 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-2 L75x75x6-6000 |  | U284-07-CP533 | 32 | 2026-07-14 | 0
| V17566-DWXD-7607 | AIG-13 | PLATE | G-34 | AIG-13-G-34 | PL8*89 | 89 | A387 GR.11 CL.2 | 2 |  | 32 | 0.5 | 15.6 | AMC2 | Plate | MCC |  |  | 32 | 0 | 16 | [7 empty] | ADDED, cắt mới bổ sung | [9 empty] | ADDED, cắt mới bổ sung |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | U284-07-CP036-4 U284-07-CP036-3 |  | U284-07-CP041 | 32 | 2026-07-14 | 0
142 | V17566-DWXD-7616 | AIG-14 | PIPE |  |  | (202x124x5153) |  |  |  | 12 |  | 28.5 | 342.1 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | REVISED | x | o | [7 empty] | ADDED |  | ADDED
| V17566-DWXD-7616 | AIG-14 | PIPE | D-13 | AIG-14-D-13 | 2 1/2" SCH.10S | 5135 | A-312 TP.304 | 1 |  | 12 | 26.7 | 319.9 | AMC2 | Shape | MCC |  |  | 0 | 12 | 0 | [7 empty] | ADDED, chỉ thay đổi mark từ Assembly AIG-3 cũ RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | [9 empty] | ADDED, cắt mới bổ sung |  | ADDED, chỉ thay đổi mark từ Assembly AIG-3 cũ RELEASE HOLD, cắt theo phương án đốt sấn của đơn vị | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 12 |  | 0
| V17566-DWXD-7616 | AIG-14 | PLATE | G-31 | AIG-14-G-31 | PL12*124 | 202 | A-240 TP304H | 1 |  | 12 | 1.5 | 18.2 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [7 empty] | Cắt từ tôn PL15, lấy từ MPR : DCC26-V314-0023-21 ADDED, chỉ thay đổi mark từ Assembly AIG-3 cũ | [9 empty] | ADDED, cắt mới bổ sung |  | ADDED, chỉ thay đổi mark từ Assembly AIG-3 cũ | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14 | 0
| V17566-DWXD-7616 | AIG-14 | PLATE | G-33 | AIG-14-G-33 | PL12*67 | 67 | A-240 TP304H | 1 |  | 12 | 0.3 | 4 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [7 empty] | ADDED, chỉ thay đổi mark từ Assembly AIG-3 cũ | [9 empty] | ADDED, cắt mới bổ sung |  | ADDED, chỉ thay đổi mark từ Assembly AIG-3 cũ | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-V314-0023-21 |  | U284-07-CP040 | 12 | 2026-07-14 | 0
143 | V17566-DWXD-7608 | SR110R-1 | AIG BAFFLE 110R |  |  | (521x51x38) |  |  |  | 48 |  | 0.5 | 24.9 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7608 | SR110R-1 | AIG BAFFLE 110R | PX-21 | SR110R-1-PX-21 | PL1.5*520.7 | 89 | SS400 | 1 |  | 48 | 0.5 | 24.9 | AMC2 | Plate | PMC |  |  | 0 | 48 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 48 | 2026-07-14 | 0
144 | V17566-DWXD-7609 | SR109R-2 | AIG BAFFLE 109R |  |  | (585x51x38) |  |  |  | 1 |  | 0.6 | 0.6 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7609 | SR109R-2 | AIG BAFFLE 109R | PX-22 | SR109R-2-PX-22 | PL1.5*585 | 89 | SS400 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14 | 0
145 | V17566-DWXD-7610 | SR111R-3 | AIG BAFFLE 111R |  |  | (556x51x38) |  |  |  | 1 |  | 0.6 | 0.6 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7610 | SR111R-3 | AIG BAFFLE 111R | PX-20 | SR111R-3-PX-20 | PL1.5*556 | 89 | SS400 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14 | 0
146 | V17566-DWXD-7611 | SR109L-2 | AIG BAFFLE 109L |  |  | (585x51x38) |  |  |  | 1 |  | 0.6 | 0.6 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7611 | SR109L-2 | AIG BAFFLE 109L | PX-19 | SR109L-2-PX-19 | PL1.5*585 | 89 | SS400 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14 | 0
147 | V17566-DWXD-7612 | SR110L-1 | AIG BAFFLE 110L |  |  | (521x51x38) |  |  |  | 48 |  | 0.5 | 24.9 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7612 | SR110L-1 | AIG BAFFLE 110L | PX-18 | SR110L-1-PX-18 | PL1.5*520.7 | 89 | SS400 | 1 |  | 48 | 0.5 | 24.9 | AMC2 | Plate | PMC |  |  | 0 | 48 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 48 | 2026-07-14 | 0
148 | V17566-DWXD-7613 | SR111L-3 | AIG BAFFLE 111L |  |  | (556x51x38) |  |  |  | 1 |  | 0.6 | 0.6 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7613 | SR111L-3 | AIG BAFFLE 111L | PX-17 | SR111L-3-PX-17 | PL1.5*556 | 89 | SS400 | 1 |  | 1 | 0.6 | 0.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | U284-19A-CP019-1 DCC25-U284-0006-VTC-3/6 |  | U284-07-CP039 | 1 | 2026-07-14 | 0
149 | V17566-DWXD-7592 | SR-10103 | BATWING SHEET 101 |  |  | (127x2x1372) |  |  |  | 384 |  | 2.1 | 787.9 | AMC2 | [7 empty] | 216 | 0.5625 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7592 | SR-10103 | BATWING SHEET 101 | G-29 | SR-10103-G-29 | PL1.5*127 | 1372 | A-240 TP304H | 1 |  | 384 | 2.1 | 787.9 | AMC2 | Plate | MCC |  |  | 216 | 168 | 216 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-4 DCC26-U284-0113-VTC-1 |  | U284-07-CP038 | 384 | 2026-07-14 | 0
150 | V17566-DWXD-7593 | SR-10303 | BATWING SHEET 103 |  |  | (127x2x1901) |  |  |  | 96 |  | 2.8 | 272.9 | AMC2 | [7 empty] | 0 | 0 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7593 | SR-10303 | BATWING SHEET 103 | G-32 | SR-10303-G-32 | PL1.5*127 | 1901 | A-240 TP304H | 1 |  | 96 | 2.8 | 272.9 | AMC2 | Plate | MCC |  |  | 0 | 96 | 0 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-4 DCC26-U284-0113-VTC-1 |  | U284-07-CP038 | 96 | 2026-07-14 | 0
151 | V17566-DWXD-7594 | SR-10203 | BATWING SHEET 102 |  |  | (127x4x2132) |  |  |  | 96 |  | 3.2 | 306.2 | AMC2 | [7 empty] | 96 | 1 | [5 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | x | o | [7 empty] | ADDED | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện
| V17566-DWXD-7594 | SR-10203 | BATWING SHEET 102 | GX-1 | SR-10203-GX-1 | PL1.5*127 | 2133 | A-240 TP304H | 1 |  | 96 | 3.2 | 306.2 | AMC2 | Plate | PMC |  |  | 96 | 0 | 96 | [7 empty] | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện | [9 empty] | ADDED, cắt mới bổ sung | MODIFY, chỉ thay đổi mark Assembly theo basic để phục vụ đóng kiện |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC25-U284-0085-VTC-4 DCC26-U284-0113-VTC-1 |  | U284-07-CP038 | 96 | 2026-07-14 | 0
152 | V17566-DWXD-7614 | M-2 | U-BOLT 2 1/2"x1/2"DIA |  |  | (32x127x159) |  |  |  | 1152 |  | 0.4 | 502.2 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | ADDED | x | o | [7 empty] | ADDED
| V17566-DWXD-7614 | M-2 | U-BOLT 2 1/2"x1/2"DIA | M-29 | M-2-M-29 | D12 | 357 | A-105 | 1 |  | 1152 | 0.3 | 327.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1152 | 0 | [7 empty] | ADDED | [9 empty] | ADDED | [9 empty] | Purchasing | DCC26-U284-0086-VTP-01
| V17566-DWXD-7614 | M-2 | NUT M12 | M-30 | M-2-M-30 | NUT_M12 | 10 | A-479 TP304 | 4 |  | 4608 | 0 | 101.5 | AMC2 | Purchasing | KHO |  |  | 0 | 4608 | 0 | [7 empty] | ADDED | [9 empty] | ADDED | [9 empty] | Purchasing | DCC26-U284-0086-VTP-02
| V17566-DWXD-7614 | M-2 | U-BOLT STRAP | M-31 | M-2-M-31 | PL1.5*32 | 127 | A-240 TP304H | 1 |  | 1152 | 0 | 55.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1152 | 0 | [7 empty] | ADDED | [9 empty] | ADDED | [9 empty] | Purchasing | DCC26-U284-0086-VTP-04
| V17566-DWXD-7614 | M-2 | WASHER 1/2" DIA | M-32 | M-2-M-32 | D26 | 2 | TP304 | 2 |  | 2304 | 0 | 18.3 | AMC2 | Purchasing | KHO |  |  | 0 | 2304 | 0 | [7 empty] | ADDED | [9 empty] | ADDED | [9 empty] | Purchasing | DCC26-U284-0086-VTP-03
153 | V17566-DWXD-7615 | M-3 | U-BOLT 2 1/2"x1/2"DIA |  |  | (18x108x159) |  |  |  | 192 |  | 0.4 | 71.4 | AMC2 | [7 empty] | 0 | #DIV/0! | [5 empty] | ADDED | x | o | [7 empty] | ADDED
| V17566-DWXD-7615 | M-3 | U-BOLT 2 1/2"x1/2"DIA | M-29 | M-3-M-29 | D12 | 357 | A-105 | 1 |  | 192 | 0.3 | 54.5 | AMC2 | Purchasing | KHO |  |  | 0 | 192 | 0 | [7 empty] | ADDED | [9 empty] | ADDED | [9 empty] | Purchasing | DCC26-U284-0086-VTP-01
| V17566-DWXD-7615 | M-3 | NUT M12 | M-30 | M-3-M-30 | NUT_M12 | 10 | A-479 TP304 | 4 |  | 768 | 0 | 16.9 | AMC2 | Purchasing | KHO |  |  | 0 | 768 | 0 | [7 empty] | ADDED | [9 empty] | ADDED | [9 empty] | Purchasing | DCC26-U284-0086-VTP-02

## BTP-U284STK
U284STK
| Chủng loại | Thiết kế |  | Đã nhận |  | Còn thiếu |  |  |  | Đã nhận |  | Đồng bộ |  | Đã triển khai
|  | T.Q'ty | T.Weight | T.Q'ty | T.Weight | T.Q'ty | T.Weight |  |  | Số chi tiết | Khối lượng | Số chi tiết lớn | Khối lượng | Số chi tiết lớn | Khối lượng
| Shape | 478 | 40371.52 | 478 | 40371.52 | 0 | 0 |  | Total | 1169 | 123045.42 |  | 68220.9 |  | 0 | [5 empty] | 44
| Plate | 843 | 82717.1 | 691 | 82673.9 | 152 | 43.2
| Purchasing | 429 | 143.4 | 0 | 0 | 429 | 143.4
| Total | 1750 | 123232.02 | 1169 | 123045.42 | 581 | 186.6
Chủng loại thép hình
| Shape | #VALUE!
| Chiều dài theo thiết kế (mm) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL TK | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Đã nhận (mm) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL Nhận | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Còn thiếu (mm) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL thiếu | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu (kg) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chiều dày tôn
| Plate | 6
| Diện tích m2 theo thiết kế | 599.1316 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| SL TK | 498 | 0 | 0 | 0 | 0 | 0 | 0
| Diện tích còn thiếu( m2) | 0.9172 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Sl còn thiếu | 152 | 0 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu(kg) | 43.2 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 4812.1 | 2037.4 | 992.02 | 575.8 | 1172.5 | 6951 | 27640.2 | 613 | 5529.2 | 222.7 | 20959.8 | 0.9 | 75.8 | 14575.2 | 119.2 | 5071.7 | 6.8 | 4083.8 | 1238.9 | 206.1 | 26.7 | 96.9 | 4550.6 | 3.3 | 4141.9 | 540.2161 | 11940.3034 | 2738.1684 | 1738.2 | 16472.4 | 285 | 6075.5281 | 7.6 | 43.1954 | 753 | 401.3 | 5.7 | 0 | #VALUE!
[11 empty] | 12 | 18 | 110 | 2 | 53 | 26 | 165 | 110 | 6 | 8 | 44 | 1 | 30 | 6 | 3 | 10 | 4 | 56 | 9 | 237 | 3 | 2 | 24 | 3 | 105 | 7.7717 | 2.1539 | 2.5697 | 18 | 24 | 12 | 1.2763 | 2 | 0.22885 | 6 | 86 | 3 | 0 | #VALUE!
Chủng loại | Part No.1 | Size | Description | Length | Material | T.Q'ty | U.Weight | T.Weight | Đã nhận | Còn thiếu | 2026-05-13 | 2026-05-21 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-27 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-05 | 2026-06-06 | 2026-06-09 | 2026-06-11 | 2026-06-15 | 2026-06-23 | 2026-06-26 | 2026-06-27 | 2026-06-30 | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-16 | 2026-07-30 | 2026-08-05 | 2026-08-13 | 2026-08-14 | 2026-08-16 | 2026-08-17 | 2026-08-24 | 2026-08-25 | 2026-08-28 | 2026-09-03 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-15 | KO BB | Lấy data | Ktra nối | Tôn | Cảnh báo thừa | DVG | MPR No | Qty MPR | Cutting No. | Qty Cutting | Date Issue
Shape | BK-1-A-10 | L150*150*12 | ANGLE | 2210 | SS400 | 1 | 60.3 | 60.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-1-A-11 | L150*150*12 | ANGLE | 2210 | SS400 | 1 | 60.3 | 60.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-1-A-6 | L150*150*12 | ANGLE | 4700 | SS400 | 1 | 128.3 | 128.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-1-AY-1 | L150*150*12 | ANGLE | 4700 | SS400 | 1 | 128.3 | 128.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-1-AY-2 | L150*150*12 | ANGLE | 4700 | SS400 | 2 | 128.3 | 256.6 | 2 | 0 | 2026-08-17: 2 |  | #VALUE! |  |  |  | MCC
Plate | BK-1-G-9 | PL6*2185 | PLATE | 4861 | SS400 | 1 | 500.2 | 500.2 | 1 | 0 | [38 empty] | #VALUE! | AB | PL6 | Thừa 1 | MCC | bar: 2026-05-24; 2026-05-27
Plate | BK-1-P-13 | PL12*138 | PLATE | 138 | SS400 | 4 | 1.8 | 7.2 | 4 | 0 | 2026-06-01: 4 |  | #VALUE! |  | PL12 |  | MCC
Shape | BK-2-A-6 | L150*150*12 | ANGLE | 4700 | SS400 | 8 | 128.3 | 1026.4 | 8 | 0 | 2026-05-21: 8 |  | #VALUE! |  |  |  | MCC
Shape | BK-2-A-7 | L150*150*12 | ANGLE | 2083 | SS400 | 4 | 56.9 | 227.6 | 4 | 0 | 2026-08-17: 4 |  | #VALUE! |  |  |  | MCC
Shape | BK-2-A-8 | L150*150*12 | ANGLE | 2083 | SS400 | 4 | 56.9 | 227.6 | 4 | 0 | 2026-08-17: 4 |  | #VALUE! |  |  |  | MCC
Shape | BK-2-AY-2 | L150*150*12 | ANGLE | 4700 | SS400 | 8 | 128.3 | 1026.4 | 8 | 0 | 2026-08-17: 8 |  | #VALUE! |  |  |  | MCC
Plate | BK-2-G-10 | PL6*2083 | PLATE | 4861 | SS400 | 4 | 476.9 | 1907.6 | 4 | 0 | 2026-05-27: 8 |  | #VALUE! | 4B4A | PL6 | Thừa 4 | MCC
Plate | BK-2-P-13 | PL12*138 | PLATE | 138 | SS400 | 16 | 1.8 | 28.8 | 16 | 0 | 2026-06-01: 16 |  | #VALUE! |  | PL12 |  | MCC
Shape | BK-3-A-4 | L150*150*12 | ANGLE | 2210 | SS400 | 1 | 60.3 | 60.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-3-A-5 | L150*150*12 | ANGLE | 2210 | SS400 | 1 | 60.3 | 60.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-3-A-6 | L150*150*12 | ANGLE | 4700 | SS400 | 1 | 128.3 | 128.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-3-AY-1 | L150*150*12 | ANGLE | 4700 | SS400 | 1 | 128.3 | 128.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-21
Shape | BK-3-AY-2 | L150*150*12 | ANGLE | 4700 | SS400 | 2 | 128.3 | 256.6 | 2 | 0 | 2026-05-21: 2 |  | #VALUE! |  |  |  | MCC
Plate | BK-3-G-9 | PL6*2185 | PLATE | 4861 | SS400 | 1 | 500.2 | 500.2 | 1 | 0 | 2026-05-27: 2 |  | #VALUE! | AB | PL6 | Thừa 1 | MCC
Plate | BK-3-P-13 | PL12*138 | PLATE | 138 | SS400 | 4 | 1.8 | 7.2 | 4 | 0 | 2026-06-01: 4 |  | #VALUE! |  | PL12 |  | MCC
Shape | DR-1-D-1 | CHS88.9*5.49 | PIPE 3" SCH.40 | 3627 | SA-312 TP304 | 1 | 40.3 | 40.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-03
Purchasing | DR-1-FL-1 | PL22.3*191 | FLANGE 3" 150# SO-RF | 191 | A-182 F304 | 1 | 4.7 | 4.7 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | DR-2-D-2 | CHS88.9*5.49 | PIPE 3" SCH.40 | 3566 | SA-312 TP304 | 1 | 39.6 | 39.6 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-03
Purchasing | DR-2-EL-1 | CHS88.9*5.49 | ELBOW LR 90° 3" SCH40 | 178 | SA403-WP 304SS | 1 | 1.9 | 1.9 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | DR-4-PF-2 | PL8*7031 | PLATE | 7031 | SS400 | 1 | 2429.2 | 2429.2 | 1 | 0 | 2026-06-11: 6; 2026-06-23: 2 |  | #VALUE! | ABCDGHEF | PL8 | Thừa 7 | PMC
Shape | EX-10-E-26 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 2 | 7.1 | 14.2 | 2 | 0 | 2026-09-11: 2 |  | #VALUE! |  |  |  | MCC
Purchasing | EX-10-M-6 | PL10*10 | RUBBER SEAL TRIP | 853 | RUBBER | 2 | 0.1 | 0.2 | 0 | 2 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-11-E-28 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1174 | SS400(Galv.) | 1 | 7 | 7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Purchasing | EX-11-M-6 | PL10*10 | RUBBER SEAL TRIP | 853 | RUBBER | 1 | 0.1 | 0.1 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-12-E-25 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 1 | 7 | 7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Purchasing | EX-12-M-6 | PL10*10 | RUBBER SEAL TRIP | 853 | RUBBER | 1 | 0.1 | 0.1 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-13-E-1 | PL1.5*723 | 3/4 NO.16 Exp.Metal | 895 | SS400(Galv.) | 1 | 1.5 | 1.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-14-E-2 | PL1.5*1007 | 3/4 NO.16 Exp.Metal | 895 | SS400(Galv.) | 1 | 2.3 | 2.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-15-E-3 | PL1.5*1321 | 3/4 NO.16 Exp.Metal | 895 | SS400(Galv.) | 1 | 2.9 | 2.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-16-E-16 | PL1.5*1524.9 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 3.3 | 3.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-17-E-4 | PL1.5*742.7 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 1.7 | 1.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-18-E-11 | PL1.5*1489 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 3.2 | 3.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-19-E-21 | PL1.5*116.4 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 0.3 | 0.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-1-E-5 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 5 | 7.4 | 37 | 5 | 0 | 2026-09-11: 5 |  | #VALUE! |  |  |  | MCC
Shape | EX-20-E-18 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 5.4 | 5.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-21-E-20 | PL1.5*1284.3 | 3/4 NO.16 Exp.Metal | 895 | SS400(Galv.) | 1 | 2.8 | 2.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-22-E-14 | PL1.5*130 | 3/4 NO.16 Exp.Metal | 895 | SS400(Galv.) | 1 | 0.3 | 0.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-23-E-15 | PL1.5*1285 | 3/4 NO.16 Exp.Metal | 895 | SS400(Galv.) | 1 | 2.8 | 2.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-24-E-17 | PL1.5*1524.9 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 3.3 | 3.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-25-E-10 | PL1.5*742.7 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 1.7 | 1.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-26-E-13 | PL1.5*752.8 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 1.5 | 1.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-27-E-12 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 5.4 | 5.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-28-E-19 | PL1.5*581 | 3/4 NO.16 Exp.Metal | 876 | SS400(Galv.) | 1 | 1.3 | 1.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-29-E-31 | PL1.5*1654 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 17 | 5 | 85 | 17 | 0 | 2026-09-11: 17 |  | #VALUE! |  |  |  | MCC
Shape | EX-2-E-27 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 2 | 7.1 | 14.2 | 2 | 0 | 2026-09-11: 2 |  | #VALUE! |  |  |  | MCC
Purchasing | EX-2-M-5 | PL10*10 | RUBBER SEAL TRIP | 792 | RUBBER | 2 | 0.1 | 0.2 | 0 | 2 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-30-E-29 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 1 | 6.7 | 6.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-31-E-30 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 1 | 5.9 | 5.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-32-E-34 | PL1.5*1654 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 1 | 4.5 | 4.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Purchasing | EX-32-M-7 | PL10*10 | RUBBER SEAL TRIP | 762 | RUBBER | 2 | 0.1 | 0.2 | 0 | 2 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-33-E-33 | PL1.5*1654 | 3/4 NO.16 Exp.Metal | 1174 | SS400(Galv.) | 1 | 2.3 | 2.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-34-E-32 | PL1.5*1654 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 1 | 2.1 | 2.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-3-E-22 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 2 | 7.1 | 14.2 | 2 | 0 | 2026-09-11: 2 |  | #VALUE! |  |  |  | MCC
Purchasing | EX-3-M-5 | PL10*10 | RUBBER SEAL TRIP | 792 | RUBBER | 2 | 0.1 | 0.2 | 0 | 2 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-4-E-23 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 8 | 7.4 | 59.2 | 8 | 0 | 2026-09-11: 8 |  | #VALUE! |  |  |  | MCC
Shape | EX-5-E-8 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 2 | 7.2 | 14.4 | 2 | 0 | 2026-09-11: 2 |  | #VALUE! |  |  |  | MCC
Shape | EX-6-E-6 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 1 | 7.1 | 7.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-11
Shape | EX-7-E-24 | PL1.5*2438 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 4 | 6.7 | 26.8 | 4 | 0 | 2026-09-11: 4 |  | #VALUE! |  |  |  | MCC
Purchasing | EX-7-M-4 | PL10*10 | RUBBER SEAL TRIP | 931 | RUBBER | 8 | 0.1 | 0.8 | 0 | 8 | [38 empty] | #VALUE! |  |  |  | KHO
Shape | EX-8-E-9 | PL1.5*915 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 10 | 2.8 | 28 | 10 | 0 | 2026-09-11: 10 |  | #VALUE! |  |  |  | MCC
Shape | EX-9-E-7 | PL1.5*863 | 3/4 NO.16 Exp.Metal | 1175 | SS400(Galv.) | 10 | 2.6 | 26 | 10 | 0 | 2026-09-11: 10 |  | #VALUE! |  |  |  | MCC
Shape | FR-1-A-3 | L100*100*10 | ANGLE | 24396 | SS400 | 1 | 363.9 | 363.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | FR-1-BH-1 | BH900*350*19*25 | H BUILT-UP | 25298 | SS400 | 1 | 6682.6 | 6682.6 | 1 | 0 | 2026-08-14: 0.91316; 2026-08-16: 0.086845 |  | #VALUE! |  |  |  | WTC
Plate | FR-1-P-15 | PL10*378 | PLATE | 25298 | SS400 | 1 | 750.7 | 750.7 | 1 | 0 | 2026-08-05: 2 |  | #VALUE! | AB | PL10 | Thừa 1 | MCC
Plate | FR-1-P-19 | PL6*200 | PLATE | 200 | SS400 | 6 | 1.1 | 6.6 | 6 | 0 | 2026-05-25: 6 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-1-P-3 | PL6*166 | PLATE | 850 | SS400 | 2 | 6.6 | 13.2 | 2 | 0 | 2026-05-25: 2 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-1-P-4 | PL6*956 | PLATE | 24384 | SS400 | 1 | 1098 | 1098 | 1 | 0 | 2026-06-02: 2 |  | #VALUE! | AB | PL6 | Thừa 1 | MCC
Plate | FR-1-P-7 | PL6*131 | PLATE | 135 | SS400 | 1 | 0.4 | 0.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Shape | FR-2-A-9 | L100*100*10 | ANGLE | 12814 | SS400 | 1 | 191.1 | 191.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | FR-2-BH-2 | BH900*350*19*25 | H BUILT-UP | 13716 | SS400 | 1 | 3623.1 | 3623.1 | 1 | 0 | 2026-08-16: 0.19802; 2026-08-28: 0.80198 |  | #VALUE! |  |  |  | WTC
Plate | FR-2-P-10 | PL6*943 | PLATE | 12802 | SS400 | 1 | 568.6 | 568.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-06-02
Plate | FR-2-P-19 | PL6*200 | PLATE | 200 | SS400 | 3 | 1.1 | 3.3 | 3 | 0 | 2026-05-25: 3 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-2-P-3 | PL6*166 | PLATE | 850 | SS400 | 2 | 6.6 | 13.2 | 2 | 0 | 2026-05-25: 2 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-2-P-7 | PL6*131 | PLATE | 135 | SS400 | 1 | 0.4 | 0.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | FR-2-P-8 | PL10*378 | PLATE | 13716 | SS400 | 1 | 407 | 407 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Shape | FR-3-A-3 | L100*100*10 | ANGLE | 24396 | SS400 | 1 | 363.9 | 363.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | FR-3-BH-1 | BH900*350*19*25 | H BUILT-UP | 25298 | SS400 | 1 | 6682.6 | 6682.6 | 1 | 0 | 2026-08-14: 0.43881; 2026-08-16: 0.086845; 2026-08-28: 0.47435 |  | #VALUE! |  |  |  | WTC
Plate | FR-3-P-15 | PL10*378 | PLATE | 25298 | SS400 | 1 | 750.7 | 750.7 | 1 | 0 | 2026-08-05: 2 |  | #VALUE! | AB | PL10 | Thừa 1 | MCC
Plate | FR-3-P-19 | PL6*200 | PLATE | 200 | SS400 | 6 | 1.1 | 6.6 | 6 | 0 | 2026-05-25: 6 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-3-P-3 | PL6*166 | PLATE | 850 | SS400 | 2 | 6.6 | 13.2 | 0 | 2 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | FR-3-P-4 | PL6*956 | PLATE | 24384 | SS400 | 1 | 1098 | 1098 | 1 | 0 | 2026-06-02: 2 |  | #VALUE! | AB | PL6 | Thừa 1 | MCC
Plate | FR-3-P-7 | PL6*131 | PLATE | 135 | SS400 | 1 | 0.4 | 0.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Shape | FR-4-A-9 | L100*100*10 | ANGLE | 12814 | SS400 | 1 | 191.1 | 191.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | FR-4-BH-2 | BH900*350*19*25 | H BUILT-UP | 13716 | SS400 | 1 | 3623.1 | 3623.1 | 1 | 0 | 2026-08-14: 0.80198; 2026-08-16: 0.19802 |  | #VALUE! |  |  |  | WTC
Plate | FR-4-P-10 | PL6*943 | PLATE | 12802 | SS400 | 1 | 568.6 | 568.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-06-02
Plate | FR-4-P-19 | PL6*200 | PLATE | 200 | SS400 | 3 | 1.1 | 3.3 | 3 | 0 | 2026-05-25: 3 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-4-P-3 | PL6*166 | PLATE | 850 | SS400 | 2 | 6.6 | 13.2 | 2 | 0 | 2026-05-25: 2 |  | #VALUE! |  | PL6 |  | MCC
Plate | FR-4-P-7 | PL6*131 | PLATE | 135 | SS400 | 1 | 0.4 | 0.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | FR-4-P-8 | PL10*378 | PLATE | 13716 | SS400 | 1 | 407 | 407 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Shape | FR-5-A-2 | L100*100*10 | ANGLE | 4886 | SS400 | 2 | 72.9 | 145.8 | 2 | 0 | 2026-05-27: 2 |  | #VALUE! |  |  |  | MCC
Plate | FR-5-P-5 | PL6*964 | PLATE | 4674 | SS400 | 2 | 78.4 | 156.8 | 2 | 0 | 2026-05-27: 2 |  | #VALUE! |  | PL6 |  | MCC
Shape | FR-6-A-2 | L100*100*10 | ANGLE | 4886 | SS400 | 2 | 72.9 | 145.8 | 2 | 0 | 2026-05-27: 2 |  | #VALUE! |  |  |  | MCC
Plate | FR-6-P-9 | PL6*951 | PLATE | 4674 | SS400 | 2 | 75.6 | 151.2 | 2 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-24; 2026-05-27
Shape | LS-10-AFY-48 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-11-AFY-40 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | LS-12-CFY-2 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-13-AFY-63 | L130*130*9 | ANGLE | 509 | SS400 | 1 | 9.1 | 9.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | LS-14-CFY-12 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-15-AFY-53 | L150*150*12 | ANGLE | 511 | SS400 | 7 | 13.9 | 97.3 | 7 | 0 | 2026-05-31: 7 |  | #VALUE! |  |  |  | PMC
Shape | LS-16-AFY-59 | L130*130*9 | ANGLE | 509 | SS400 | 1 | 9.1 | 9.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Plate | LS-16-G-7 | PL10*126 | PLATE | 211 | SS400 | 1 | 1.9 | 1.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Shape | LS-17-CFY-8 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | LS-17-G-8 | PL10*152 | PLATE | 161 | SS400 | 1 | 1.9 | 1.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Shape | LS-18-AFY-13 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-19-AFY-21 | L200*200*25 | ANGLE | 514 | SS400 | 1 | 37.8 | 37.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | LS-1-AFY-57 | L150*150*12 | ANGLE | 511 | SS400 | 7 | 13.9 | 97.3 | 7 | 0 | 2026-05-31: 7 |  | #VALUE! |  |  |  | PMC
Shape | LS-20-AFY-14 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | LS-21-AFY-50 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-22-CFY-6 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-23-AFY-56 | L150*150*12 | ANGLE | 511 | SS400 | 7 | 13.9 | 97.3 | 7 | 0 | 2026-05-31: 7 |  | #VALUE! |  |  |  | PMC
Shape | LS-24-AFY-37 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | LS-25-AFY-36 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-26-AFY-8 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-27-AFY-7 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-28-AFY-45 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-29-AFY-43 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-2-AFY-27 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-30-CFY-3 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-31-AFY-62 | L130*130*9 | ANGLE | 509 | SS400 | 1 | 9.1 | 9.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Plate | LS-31-G-7 | PL10*126 | PLATE | 210 | SS400 | 1 | 1.8 | 1.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Shape | LS-32-CFY-11 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | LS-32-G-8 | PL10*152 | PLATE | 161 | SS400 | 1 | 1.9 | 1.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Shape | LS-33-AFY-54 | L150*150*12 | ANGLE | 511 | SS400 | 7 | 13.9 | 97.3 | 7 | 0 | 2026-05-31: 7 |  | #VALUE! |  |  |  | PMC
Shape | LS-34-AFY-60 | L130*130*9 | ANGLE | 509 | SS400 | 1 | 9.1 | 9.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | LS-35-CFY-9 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-36-AFY-20 | L200*200*25 | ANGLE | 514 | SS400 | 1 | 37.8 | 37.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | LS-37-AFY-12 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | LS-38-CFY-5 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | LS-38-G-4 | PL10*152 | PLATE | 162 | SS400 | 1 | 1.9 | 1.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Shape | LS-39-AFY-55 | L150*150*12 | ANGLE | 511 | SS400 | 7 | 13.9 | 97.3 | 7 | 0 | 2026-05-31: 7 |  | #VALUE! |  |  |  | PMC
Shape | LS-3-AFY-25 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-40-AFY-35 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-41-AFY-19 | L200*200*25 | ANGLE | 514 | SS400 | 1 | 37.8 | 37.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | LS-42-AFY-11 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | LS-43-AFY-47 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-44-CFY-4 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-45-AFY-61 | L130*130*9 | ANGLE | 509 | SS400 | 1 | 9.1 | 9.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | LS-46-CFY-10 | [200*80*7.5*11 | CHANNEL | 506 | SS400 | 1 | 12.4 | 12.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | LS-47-AFY-64 | L130*130*9 | ANGLE | 510 | SS400 | 2 | 9.1 | 18.2 | 2 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-23; 2026-08-25
Shape | LS-48-AFY-40 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Plate | LS-48-G-1 | PL10*125 | PLATE | 264 | SS400 | 1 | 2.3 | 2.3 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Shape | LS-4-AFY-23 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-5-AFY-4 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-6-AFY-2 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-06-27: 2 |  | #VALUE! |  |  |  | PMC
Shape | LS-7-AFY-16 | L200*200*25 | ANGLE | 514 | SS400 | 1 | 37.8 | 37.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | LS-8-AFY-6 | L150*150*12 | ANGLE | 511 | SS400 | 1 | 13.9 | 13.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | LS-9-AFY-42 | L150*150*12 | ANGLE | 511 | SS400 | 2 | 13.9 | 27.8 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | PT-1-DY-1 | CHS88.9*5.49 | PIPE 3" STD | 4574 | A106 Gr.B | 4 | 50.1 | 200.4 | 4 | 0 | 2026-08-13: 4 |  | #VALUE! |  |  |  | MCC
Plate | PT-1-P-6 | PL12*152 | PLATE | 152 | SS400 | 8 | 2.2 | 17.6 | 8 | 0 | 2026-06-01: 8 |  | #VALUE! |  | PL12 |  | MCC
Shape | PT-2-DY-3 | CHS168.3*7.11 | PIPE 6" STD | 6771 | A53 GR.B | 1 | 188.7 | 188.7 | 1 | 0 | 2026-08-13: 0.88613; 2026-09-07: 0.11446 |  | #VALUE! |  |  |  | MCC
Plate | PT-2-P-16 | PL12*200 | PLATE | 268 | SS400 | 2 | 5 | 10 | 2 | 0 | 2026-06-01: 2 |  | #VALUE! |  | PL12 |  | MCC
Shape | PT-3-DY-2 | CHS168.3*7.11 | PIPE 6" STD | 6775 | A53 GR.B | 1 | 188.8 | 188.8 | 1 | 0 | 2026-08-13: 0.88561; 2026-09-07: 0.11439 |  | #VALUE! |  |  |  | MCC
Plate | PT-3-P-16 | PL12*200 | PLATE | 268 | SS400 | 2 | 5 | 10 | 2 | 0 | 2026-06-01: 2 |  | #VALUE! |  | PL12 |  | MCC
Shape | SK1-1-A-33 | L75*75*6 | ANGLE | 1654 | SS400 | 10 | 11.3 | 113 | 10 | 0 | 2026-05-23: 10 |  | #VALUE! |  |  |  | MCC
Plate | SK1-1-G-12 | PL10*51 | PLATE | 102 | SS400 | 1 | 0.4 | 0.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Plate | SK1-1-G-13 | PL55*406 | PLATE | 762 | SM490 | 1 | 125.5 | 125.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL55 |  | MCC | bar: 2026-09-08
Plate | SK1-1-GY-1 | PL45*564 | BASE PLATE | 1918 | SS400 | 4 | 200.7 | 802.8 | 4 | 0 | 2026-07-16: 4 |  | #VALUE! |  | PL45 |  | MCC
Plate | SK1-1-GY-2 | PL45*564 | BASE PLATE | 1918 | SS400 | 1 | 200.1 | 200.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-1-GY-3 | PL45*533 | BASE PLATE | 1938 | SS400 | 4 | 179 | 716 | 4 | 0 | 2026-07-16: 4 |  | #VALUE! |  | PL45 |  | MCC
Plate | SK1-1-GY-4 | PL45*533 | BASE PLATE | 1938 | SS400 | 1 | 178.4 | 178.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-1-GY-5 | PL45*533 | BASE PLATE | 1938 | SS400 | 1 | 177.9 | 177.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-1-GY-7 | PL45*564 | BASE PLATE | 1918 | SS400 | 1 | 200.1 | 200.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-1-P-14 | PL8*225 | PLATE | 520 | SS400 | 36 | 7.3 | 262.8 | 36 | 0 | 2026-06-01: 36 |  | #VALUE! |  | PL8 |  | MCC
Plate | SK1-1-P-18 | PL6*51 | PLATE | 76 | SS400 | 40 | 0.2 | 8 | 0 | 40 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK1-1-PF-6 | PL12*508 | PLATE | 508 | SS400 | 1 | 23.8 | 23.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-03
Plate | SK1-1-SH-50 | PL12*2000 | SHELL PLATE | 11027 | SS400 | 1 | 2075.8 | 2075.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Plate | SK1-1-SH-51 | PL12*1082.6 | SHELL PLATE | 11027 | SS400 | 1 | 1120.5 | 1120.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Shape | SK1-2-A-33 | L75*75*6 | ANGLE | 1654 | SS400 | 9 | 11.3 | 101.7 | 9 | 0 | 2026-05-23: 9 |  | #VALUE! |  |  |  | MCC
Shape | SK1-2-A-34 | L75*75*6 | ANGLE | 127 | SS400 | 1 | 0.9 | 0.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK1-2-A-35 | L75*75*6 | ANGLE | 168 | SS400 | 2 | 1.1 | 2.2 | 2 | 0 | 2026-05-23: 2 |  | #VALUE! |  |  |  | MCC
Plate | SK1-2-G-12 | PL10*51 | PLATE | 102 | SS400 | 1 | 0.4 | 0.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Plate | SK1-2-G-13 | PL55*406 | PLATE | 762 | SM490 | 1 | 125.5 | 125.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL55 |  | MCC | bar: 2026-09-08
Plate | SK1-2-GF-1 | PL19*1346.1 | PAD PLATE | 1358 | SS400 | 1 | 157.3 | 157.3 | 1 | 0 | [38 empty] | #VALUE! |  | PL19 |  | PMC | bar: 2026-07-06
Plate | SK1-2-GY-1 | PL45*564 | BASE PLATE | 1918 | SS400 | 4 | 200.7 | 802.8 | 4 | 0 | 2026-07-16: 4 |  | #VALUE! |  | PL45 |  | MCC
Plate | SK1-2-GY-3 | PL45*533 | BASE PLATE | 1938 | SS400 | 4 | 179 | 716 | 4 | 0 | 2026-07-16: 4 |  | #VALUE! |  | PL45 |  | MCC
Plate | SK1-2-GY-5 | PL45*533 | BASE PLATE | 1938 | SS400 | 1 | 177.9 | 177.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-2-GY-6 | PL45*564 | BASE PLATE | 1918 | SS400 | 1 | 200.1 | 200.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-2-GY-7 | PL45*564 | BASE PLATE | 1918 | SS400 | 1 | 200.1 | 200.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-2-GY-8 | PL45*533 | BASE PLATE | 1938 | SS400 | 1 | 178.4 | 178.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL45 |  | MCC | bar: 2026-07-16
Plate | SK1-2-P-14 | PL8*225 | PLATE | 520 | SS400 | 36 | 7.3 | 262.8 | 36 | 0 | 2026-06-01: 36 |  | #VALUE! |  | PL8 |  | MCC
Plate | SK1-2-P-18 | PL6*51 | PLATE | 76 | SS400 | 41 | 0.2 | 8.2 | 0 | 41 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK1-2-PF-1 | SPD635*12 | BEND PLATE | 203 | SS400 | 1 | 37.3 | 37.3 | 1 | 0 | [38 empty] | #VALUE! |  | SPD635 |  | PMC | bar: 2026-06-15
Plate | SK1-2-PF-6 | PL12*508 | PLATE | 508 | SS400 | 1 | 23.8 | 23.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-03
Shape | SK1-2-RX-1 | D19 | ROUND BAR | 535 | SS400 | 1 | 1.1 | 1.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-07-30
Plate | SK1-2-SH-52 | PL12*1082.6 | SHELL PLATE | 11027 | SS400 | 1 | 1123.9 | 1123.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Plate | SK1-2-SH-53 | PL12*2000 | SHELL PLATE | 11027 | SS400 | 1 | 2042.9 | 2042.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Shape | SK2-1-AFY-1 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-1-AFY-15 | L200*200*25 | ANGLE | 4031 | SS400 | 1 | 296.7 | 296.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | SK2-1-AFY-3 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-1-AFY-5 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Plate | SK2-1-SH-17 | PL12*1000 | SHELL PLATE | 4405,5 | SS400 | 1 | 413.6 | 413.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-1-SH-18 | PL12*2000 | SHELL PLATE | 4405,5 | SS400 | 1 | 828.5 | 828.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-1-SH-19 | PL12*1873 | SHELL PLATE | 4405,5 | SS400 | 1 | 775.8 | 775.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-1-SH-20 | PL12*1700 | SHELL PLATE | 4405,5 | SS400 | 1 | 703.4 | 703.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Shape | SK2-2-AFY-1 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-2-AFY-15 | L200*200*25 | ANGLE | 4031 | SS400 | 1 | 296.7 | 296.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | SK2-2-AFY-3 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-2-AFY-5 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Plate | SK2-2-SH-18 | PL12*2000 | SHELL PLATE | 4405,5 | SS400 | 2 | 828.5 | 1657 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL12 |  | PMC
Plate | SK2-2-SH-29 | PL12*1700 | SHELL PLATE | 4405,5 | SS400 | 1 | 704 | 704 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-2-SH-30 | PL12*873 | SHELL PLATE | 4405,5 | SS400 | 1 | 360.3 | 360.3 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Shape | SK2-3-AFY-1 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-3-AFY-10 | L150*150*12 | ANGLE | 1570 | SS400 | 1 | 42.8 | 42.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | SK2-3-AFY-18 | L200*200*25 | ANGLE | 1633 | SS400 | 1 | 120.2 | 120.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | SK2-3-AFY-3 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Plate | SK2-3-P-1 | PL10*135 | PLATE | 840 | SS400 | 2 | 8.6 | 17.2 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK2-3-SH-17 | PL12*1000 | SHELL PLATE | 4405,5 | SS400 | 1 | 413.6 | 413.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-3-SH-25 | PL12*2000 | SHELL PLATE | 4405,5 | SS400 | 1 | 617.9 | 617.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-3-SH-26 | PL12*1873 | SHELL PLATE | 2129,5 | SS400 | 1 | 375.2 | 375.2 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-27
Plate | SK2-3-SH-27 | PL12*1700 | SHELL PLATE | 2129,5 | SS400 | 1 | 340.2 | 340.2 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Shape | SK2-4-AFY-1 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-4-AFY-15 | L200*200*25 | ANGLE | 4031 | SS400 | 1 | 296.7 | 296.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | SK2-4-AFY-3 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-4-AFY-5 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Plate | SK2-4-SH-18 | PL12*2000 | SHELL PLATE | 4405,5 | SS400 | 2 | 828.5 | 1657 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL12 |  | PMC
Plate | SK2-4-SH-21 | PL12*573 | SHELL PLATE | 4405,5 | SS400 | 1 | 236.4 | 236.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Plate | SK2-4-SH-28 | PL12*2000 | SHELL PLATE | 4405,5 | SS400 | 1 | 827.9 | 827.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Shape | SK2-5-AFY-1 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-5-AFY-17 | L200*200*25 | ANGLE | 1051 | SS400 | 1 | 77.4 | 77.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-30
Shape | SK2-5-AFY-3 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK2-5-AFY-9 | L150*150*12 | ANGLE | 992 | SS400 | 1 | 27.1 | 27.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Plate | SK2-5-P-1 | PL10*135 | PLATE | 840 | SS400 | 3 | 8.6 | 25.8 | 3 | 0 | 2026-08-05: 3 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK2-5-SH-21 | PL12*573 | SHELL PLATE | 4405,5 | SS400 | 1 | 236.4 | 236.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-08-24
Plate | SK2-5-SH-22 | PL12*2000 | SHELL PLATE | 4405,5 | SS400 | 1 | 680 | 680 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-5-SH-23 | PL12*2000 | SHELL PLATE | 1568 | SS400 | 1 | 295.5 | 295.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Plate | SK2-5-SH-24 | PL12*2000 | SHELL PLATE | 1568 | SS400 | 1 | 295.4 | 295.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-05
Shape | SK3-1-AFY-29 | L150*150*12 | ANGLE | 3186 | SS400 | 1 | 87 | 87 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-1-AFY-30 | L150*150*12 | ANGLE | 3186 | SS400 | 1 | 87 | 87 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-1-AFY-31 | L150*150*12 | ANGLE | 3186 | SS400 | 2 | 87 | 174 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Plate | SK3-1-SH-37 | PL10*1000 | SHELL PLATE | 3714,5 | SS400 | 1 | 291.4 | 291.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-1-SH-38 | PL10*2000 | SHELL PLATE | 3714,5 | SS400 | 4 | 582.9 | 2331.6 | 4 | 0 | 2026-05-13: 3; 2026-08-24: 1 |  | #VALUE! |  | PL10 |  | PMC
Plate | SK3-1-SH-39 | PL10*1800 | SHELL PLATE | 3714,5 | SS400 | 1 | 524.5 | 524.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-1-SH-40 | PL10*1371 | SHELL PLATE | 3714,5 | SS400 | 1 | 399.1 | 399.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Shape | SK3-2-AFY-22 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-2-AFY-24 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-2-AFY-26 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | SK3-2-AFY-28 | L150*150*12 | ANGLE | 1633 | SS400 | 1 | 44.6 | 44.6 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Plate | SK3-2-P-11 | PL10*135 | PLATE | 840 | SS400 | 2 | 8.6 | 17.2 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK3-2-SH-31 | PL10*2000 | SHELL PLATE | 4408 | SS400 | 1 | 691.5 | 691.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-2-SH-32 | PL10*2000 | SHELL PLATE | 4408 | SS400 | 2 | 691.1 | 1382.2 | 2 | 0 | 2026-08-24: 2 |  | #VALUE! |  | PL10 |  | PMC
Plate | SK3-2-SH-33 | PL10*2000 | SHELL PLATE | 4406,5 | SS400 | 1 | 518.7 | 518.7 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Plate | SK3-2-SH-34 | PL10*2000 | SHELL PLATE | 2193 | SS400 | 1 | 344 | 344 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-2-SH-35 | PL10*1000 | SHELL PLATE | 2193 | SS400 | 1 | 171.8 | 171.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-2-SH-36 | PL10*1171 | SHELL PLATE | 2193 | SS400 | 1 | 201.1 | 201.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Shape | SK3-3-AFY-32 | L150*150*12 | ANGLE | 3889 | SS400 | 1 | 106.2 | 106.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-3-AFY-33 | L150*150*12 | ANGLE | 3889 | SS400 | 1 | 106.2 | 106.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-3-AFY-34 | L150*150*12 | ANGLE | 3889 | SS400 | 2 | 106.2 | 212.4 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Plate | SK3-3-SH-41 | PL10*1000 | SHELL PLATE | 4399,5 | SS400 | 1 | 345 | 345 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-3-SH-42 | PL10*2000 | SHELL PLATE | 4399,5 | SS400 | 4 | 690 | 2760 | 4 | 0 | 2026-08-24: 4 |  | #VALUE! |  | PL10 |  | PMC
Plate | SK3-3-SH-43 | PL10*1800 | SHELL PLATE | 4399,5 | SS400 | 1 | 621 | 621 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Plate | SK3-3-SH-44 | PL10*1371 | SHELL PLATE | 4399,5 | SS400 | 1 | 472.4 | 472.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Shape | SK3-4-AFY-22 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-4-AFY-24 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK3-4-AFY-26 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Shape | SK3-4-AFY-38 | L150*150*12 | ANGLE | 929 | SS400 | 1 | 25.4 | 25.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-31
Plate | SK3-4-P-11 | PL10*135 | PLATE | 840 | SS400 | 3 | 8.6 | 25.8 | 3 | 0 | 2026-08-05: 3 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK3-4-SH-32 | PL10*2000 | SHELL PLATE | 4408 | SS400 | 2 | 691.1 | 1382.2 | 2 | 0 | 2026-08-24: 2 |  | #VALUE! |  | PL10 |  | PMC
Plate | SK3-4-SH-45 | PL10*1500 | SHELL PLATE | 4408 | SS400 | 1 | 518.5 | 518.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Plate | SK3-4-SH-46 | PL10*2000 | SHELL PLATE | 4408 | SS400 | 1 | 580.6 | 580.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Plate | SK3-4-SH-47 | PL10*1500 | SHELL PLATE | 1509,5 | SS400 | 2 | 177.7 | 355.4 | 2 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13; 2026-08-24
Plate | SK3-4-SH-48 | PL10*1000 | SHELL PLATE | 1509,5 | SS400 | 1 | 118.4 | 118.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-05-13
Plate | SK3-4-SH-49 | PL10*668 | SHELL PLATE | 1515,5 | SS400 | 1 | 78.9 | 78.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | PMC | bar: 2026-08-24
Shape | SK4-1-A-13 | L75*75*6 | ANGLE | 915 | SS400 | 4 | 6.3 | 25.2 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK4-1-AF-2 | L130*130*9 | ANGLE | 625 | SS400 | 1 | 11.2 | 11.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-23
Shape | SK4-1-AF-4 | L130*130*9 | ANGLE | 1345 | SS400 | 1 | 24 | 24 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-23
Shape | SK4-1-AFY-39 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-1-AFY-41 | L150*150*12 | ANGLE | 3827 | SS400 | 2 | 104.5 | 209 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | SK4-1-AFY-51 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-1-CFY-1 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | SK4-1-G-13 | PL55*406 | PLATE | 762 | SM490 | 1 | 125.5 | 125.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL55 |  | MCC | bar: 2026-09-08
Plate | SK4-1-G-2 | PL10*125 | PLATE | 229 | SS400 | 1 | 2 | 2 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Plate | SK4-1-G-3 | PL10*125 | PLATE | 211 | SS400 | 1 | 1.8 | 1.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Plate | SK4-1-G-4 | PL10*152 | PLATE | 162 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-1-P-12 | PL10*136 | PLATE | 586 | SS400 | 1 | 6 | 6 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Plate | SK4-1-P-18 | PL6*51 | PLATE | 76 | SS400 | 12 | 0.2 | 2.4 | 0 | 12 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK4-1-PF-5 | PL12*508 | PLATE | 508 | SS400 | 1 | 23.8 | 23.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-03
Plate | SK4-1-SH-54 | PL8*2000 | SHELL PLATE | 4345 | SS400 | 1 | 545.1 | 545.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-1-SH-55 | PL8*2000 | SHELL PLATE | 4345 | SS400 | 2 | 544.9 | 1089.8 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL8 |  | PMC
Plate | SK4-1-SH-56 | PL8*2000 | SHELL PLATE | 4409 | SS400 | 1 | 546.5 | 546.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-1-SH-57 | PL8*1916.4 | SHELL PLATE | 4409 | SS400 | 1 | 529.7 | 529.7 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK4-2-A-13 | L75*75*6 | ANGLE | 915 | SS400 | 4 | 6.3 | 25.2 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK4-2-AF-1 | L130*130*9 | ANGLE | 396 | SS400 | 1 | 7.1 | 7.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | SK4-2-AFY-39 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-2-AFY-44 | L150*150*12 | ANGLE | 992 | SS400 | 2 | 27.1 | 54.2 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | SK4-2-AFY-51 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-2-CFY-1 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | SK4-2-G-3 | PL10*125 | PLATE | 211 | SS400 | 1 | 1.9 | 1.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Plate | SK4-2-G-4 | PL10*152 | PLATE | 162 | SS400 | 3 | 1.9 | 5.7 | 3 | 0 | 2026-08-05: 3 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-2-G-5000 | PL10*100 | PLATE | 280 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-09-15: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-2-P-12 | PL10*136 | PLATE | 586 | SS400 | 3 | 6 | 18 | 3 | 0 | 2026-08-05: 3 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-2-P-18 | PL6*51 | PLATE | 76 | SS400 | 12 | 0.2 | 2.4 | 0 | 12 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK4-2-SH-58 | PL8*500 | SHELL PLATE | 1577 | SS400 | 1 | 49.3 | 49.3 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-2-SH-59 | PL8*1913.4 | SHELL PLATE | 1577 | SS400 | 1 | 189 | 189 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-2-SH-60 | PL8*2000 | SHELL PLATE | 1577 | SS400 | 2 | 197.5 | 395 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL8 |  | PMC
Plate | SK4-2-SH-61 | PL8*2000 | SHELL PLATE | 4409 | SS400 | 1 | 337.6 | 337.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-27
Plate | SK4-2-SH-62 | PL8*1500 | SHELL PLATE | 4409 | SS400 | 1 | 414.4 | 414.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK4-3-A-13 | L75*75*6 | ANGLE | 915 | SS400 | 4 | 6.3 | 25.2 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK4-3-AFY-39 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-3-AFY-51 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-3-CFY-1 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | SK4-3-G-1 | PL10*125 | PLATE | 264 | SS400 | 2 | 2.3 | 4.6 | 2 | 0 | 2026-06-09: 2; 2026-08-05: 2 |  | #VALUE! |  | PL10 | Thừa 2 | MCC
Plate | SK4-3-G-4 | PL10*152 | PLATE | 162 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-3-P-12 | PL10*136 | PLATE | 586 | SS400 | 3 | 6 | 18 | 3 | 0 | 2026-08-05: 3 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-3-P-18 | PL6*51 | PLATE | 76 | SS400 | 12 | 0.2 | 2.4 | 0 | 12 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK4-3-SH-70 | PL8*1913.4 | SHELL PLATE | 4409 | SS400 | 1 | 494.7 | 494.7 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-3-SH-71 | PL8*500 | SHELL PLATE | 4409 | SS400 | 1 | 137.6 | 137.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK4-4-A-13 | L75*75*6 | ANGLE | 915 | SS400 | 4 | 6.3 | 25.2 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK4-4-AF-6 | L130*130*9 | ANGLE | 969 | SS400 | 1 | 17.3 | 17.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-23
Shape | SK4-4-AFY-39 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-4-AFY-46 | L150*150*12 | ANGLE | 1570 | SS400 | 2 | 42.8 | 85.6 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | SK4-4-AFY-51 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-4-CFY-1 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | SK4-4-G-3 | PL10*125 | PLATE | 211 | SS400 | 1 | 1.8 | 1.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Plate | SK4-4-G-4 | PL10*152 | PLATE | 162 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-4-G-5000 | PL10*100 | PLATE | 280 | SS400 | 1 | 1.9 | 1.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-09-15
Plate | SK4-4-P-12 | PL10*136 | PLATE | 586 | SS400 | 2 | 6 | 12 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-4-P-18 | PL6*51 | PLATE | 76 | SS400 | 12 | 0.2 | 2.4 | 0 | 12 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK4-4-SH-57 | PL8*1916.4 | SHELL PLATE | 4409 | SS400 | 1 | 529.7 | 529.7 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-4-SH-63 | PL8*2000 | SHELL PLATE | 2139 | SS400 | 1 | 268.1 | 268.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-4-SH-64 | PL8*2000 | SHELL PLATE | 2139 | SS400 | 2 | 268 | 536 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL8 |  | PMC
Plate | SK4-4-SH-65 | PL8*2000 | SHELL PLATE | 4409 | SS400 | 1 | 320.8 | 320.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK4-5-A-13 | L75*75*6 | ANGLE | 915 | SS400 | 4 | 6.3 | 25.2 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK4-5-AF-2 | L130*130*9 | ANGLE | 625 | SS400 | 1 | 11.2 | 11.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-23
Shape | SK4-5-AF-5 | L130*130*9 | ANGLE | 770 | SS400 | 1 | 13.7 | 13.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | SK4-5-AFY-39 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-5-AFY-49 | L150*150*12 | ANGLE | 3249 | SS400 | 2 | 88.7 | 177.4 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  |  |  | PMC
Shape | SK4-5-AFY-51 | L150*150*12 | ANGLE | 4003 | SS400 | 1 | 109.3 | 109.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-27
Shape | SK4-5-CFY-1 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Plate | SK4-5-G-13 | PL55*406 | PLATE | 762 | SM490 | 1 | 125.5 | 125.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL55 |  | MCC | bar: 2026-09-08
Plate | SK4-5-G-2 | PL10*125 | PLATE | 229 | SS400 | 1 | 2 | 2 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Plate | SK4-5-G-3 | PL10*125 | PLATE | 211 | SS400 | 1 | 1.8 | 1.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 | Thừa 1 | MCC | bar: 2026-06-09; 2026-08-05
Plate | SK4-5-G-4 | PL10*152 | PLATE | 162 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK4-5-P-12 | PL10*136 | PLATE | 586 | SS400 | 1 | 6 | 6 | 1 | 0 | [38 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-05
Plate | SK4-5-P-18 | PL6*51 | PLATE | 76 | SS400 | 12 | 0.2 | 2.4 | 0 | 12 | [38 empty] | #VALUE! |  | PL6 |  | MCC
Plate | SK4-5-PF-5 | PL12*508 | PLATE | 508 | SS400 | 1 | 23.8 | 23.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-03
Plate | SK4-5-SH-62 | PL8*1500 | SHELL PLATE | 4409 | SS400 | 1 | 414.4 | 414.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-5-SH-66 | PL8*500 | SHELL PLATE | 3783 | SS400 | 1 | 118.5 | 118.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-5-SH-67 | PL8*1913.4 | SHELL PLATE | 3783 | SS400 | 1 | 453.9 | 453.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Plate | SK4-5-SH-68 | PL8*2000 | SHELL PLATE | 3783 | SS400 | 2 | 474.5 | 949 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL8 |  | PMC
Plate | SK4-5-SH-69 | PL8*2000 | SHELL PLATE | 4409 | SS400 | 1 | 505.5 | 505.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK5-1-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 3 | 109.3 | 327.9 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  |  |  | PMC
Plate | SK5-1-SH-2 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 415.4 | 415.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK5-1-SH-3 | PL6*1023 | SHELL PLATE | 4413 | SS400 | 1 | 212.4 | 212.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK5-1-SH-72 | PL6*1500 | SHELL PLATE | 4413 | SS400 | 1 | 311.6 | 311.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK5-1-SH-73 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 3 | 415.4 | 1246.2 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  | PL6 |  | PMC
Shape | SK5-2-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 3 | 109.3 | 327.9 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  |  |  | PMC
Plate | SK5-2-SH-73 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 4 | 415.4 | 1661.6 | 4 | 0 | 2026-05-31: 4 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK5-2-SH-79 | PL6*542 | SHELL PLATE | 4413 | SS400 | 1 | 112.5 | 112.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK5-2-SH-80 | PL6*1981 | SHELL PLATE | 4413 | SS400 | 1 | 411.4 | 411.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK5-3-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 6 | 109.3 | 655.8 | 6 | 0 | 2026-05-31: 6 |  | #VALUE! |  |  |  | PMC
Plate | SK5-3-SH-4 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 2 | 415.4 | 830.8 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK5-3-SH-5 | PL6*523 | SHELL PLATE | 4413 | SS400 | 2 | 108.5 | 217 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK5-3-SH-73 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 6 | 415.4 | 2492.4 | 6 | 0 | 2026-05-31: 6 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK5-3-SH-75 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 2 | 415.5 | 831 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  | PL6 |  | PMC
Shape | SK5-4-A-15 | L75*75*6 | ANGLE | 1007 | SS400 | 2 | 6.9 | 13.8 | 2 | 0 | 2026-05-23: 2 |  | #VALUE! |  |  |  | MCC
Shape | SK5-4-A-16 | L75*75*6 | ANGLE | 1321 | SS400 | 1 | 9.1 | 9.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK5-4-A-17 | L75*75*6 | ANGLE | 743 | SS400 | 3 | 5.1 | 15.3 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK5-4-A-18 | L75*75*6 | ANGLE | 1489 | SS400 | 1 | 10.2 | 10.2 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK5-4-A-19 | L75*75*6 | ANGLE | 3153 | SS400 | 2 | 21.6 | 43.2 | 2 | 0 | 2026-05-23: 2 |  | #VALUE! |  |  |  | MCC
Shape | SK5-4-A-20 | L75*75*6 | ANGLE | 129 | SS400 | 2 | 0.9 | 1.8 | 2 | 0 | 2026-05-23: 2 |  | #VALUE! |  |  |  | MCC
Shape | SK5-4-A-21 | L75*75*6 | ANGLE | 1210 | SS400 | 1 | 8.3 | 8.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK5-4-A-22 | L75*75*6 | ANGLE | 1285 | SS400 | 1 | 8.8 | 8.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK5-4-A-23 | L75*75*6 | ANGLE | 1525 | SS400 | 3 | 10.4 | 31.2 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK5-4-A-36 | L75*75*6 | ANGLE | 1221 | SS400 | 1 | 8.4 | 8.4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK5-4-AF-3 | L130*130*9 | ANGLE | 1876 | SS400 | 2 | 33.5 | 67 | 2 | 0 | 2026-08-25: 2 |  | #VALUE! |  |  |  | PMC
Shape | SK5-4-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 3 | 109.3 | 327.9 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  |  |  | PMC
Shape | SK5-4-CF-1 | [150*75*6.5*10 | CHANNEL | 1861 | SS400 | 2 | 34.6 | 69.2 | 2 | 0 | 2026-06-23: 2 |  | #VALUE! |  |  |  | PMC
Plate | SK5-4-G-11 | PL10*152 | PLATE | 304 | SS400 | 14 | 3.6 | 50.4 | 14 | 0 | 2026-08-05: 14 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK5-4-G-5 | PL10*100 | PLATE | 203 | SS400 | 2 | 1.5 | 3 | 2 | 0 | 2026-06-09: 2; 2026-08-05: 4 |  | #VALUE! |  | PL10 | Thừa 4 | MCC
Plate | SK5-4-G-5-1 | PL10*100 | PLATE | 198 | SS400 | 2 | 1.4 | 2.8 | 2 | 0 | 2026-06-09: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK5-4-G-6 | PL10*157 | PLATE | 152 | SS400 | 4 | 1.7 | 6.8 | 4 | 0 | 2026-08-05: 4 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK5-4-P-18 | PL6*51 | PLATE | 76 | SS400 | 53 | 0.2 | 10.6 | 44 | 9 | 2026-07-06: 44 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK5-4-SH-2 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 415.3 | 415.3 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK5-4-SH-73 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 3 | 415.3 | 1245.9 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK5-4-SH-76 | PL6*1042 | SHELL PLATE | 4413 | SS400 | 1 | 216.4 | 216.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK5-4-SH-77 | PL6*1481 | SHELL PLATE | 4413 | SS400 | 1 | 307.5 | 307.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK6-1-A-26 | L75*75*6 | ANGLE | 514 | SS400 | 1 | 3.52 | 3.52 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-1-A-27 | L75*75*6 | ANGLE | 2437 | SS400 | 3 | 16.7 | 50.1 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK6-1-A-30 | L75*75*6 | ANGLE | 1429 | SS400 | 1 | 9.79 | 9.79 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-1-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 4 | 109.3 | 437.2 | 4 | 0 | 2026-05-31: 4 |  | #VALUE! |  |  |  | PMC
Shape | SK6-1-AFY-58 | L130*130*9 | ANGLE | 3992 | SS400 | 1 | 71.3 | 71.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | SK6-1-CFY-7 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | SK6-1-D-5 | CHS88.9*5.49 | Pipe 3" SCH.40 | 242 | A106 Gr.B | 1 | 2.7 | 2.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-08-13
Purchasing | SK6-1-FL-10 | PL22.3*190 | FLANGE 3" 150# SO-RF | 190 | A105 | 1 | 4.2 | 4.2 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-1-FL-11 | PL22.3*190 | BLIND 3" 150# SO-RF | 190 | A105 | 1 | 5 | 5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-1-G-13 | PL55*406 | PLATE | 762 | SM490 | 1 | 125.5 | 125.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL55 |  | MCC | bar: 2026-09-08
Plate | SK6-1-G-7 | PL10*126 | PLATE | 211 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-06-09: 2; 2026-08-05: 2 |  | #VALUE! |  | PL10 | Thừa 2 | MCC
Plate | SK6-1-G-8 | PL10*152 | PLATE | 161 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Purchasing | SK6-1-GK-3 | CHS127*18.15 | GASKET 3" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.1 | 0.1 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-1-GX-1 | PL6*370 | BEND PLATE | 509 | SS400 | 1 | 8.9 | 8.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-07-08
Purchasing | SK6-1-M-1 | COUPLING 2" 3000# | COUPLING 2" 3000# | 86 | A105 | 1 | 0.7 | 0.7 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-1-M-2 | D55 | SQ HEAD PLUG 2" 3000# | 30 | A105 | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-1-P-18 | PL6*51 | PLATE | 76 | SS400 | 21 | 0.2 | 4.2 | 21 | 0 | 2026-07-06: 21 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK6-1-P-2 | PL6*138 | PLATE | 138 | SS400 | 1 | 0.9 | 0.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | SK6-1-PF-4 | PL12*508 | PLATE | 127 | SS400 | 1 | 23.8 | 23.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-03
Plate | SK6-1-SH-6 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 3 | 415.4 | 1246.2 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK6-1-SH-7 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 414.9 | 414.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-1-SH-8 | PL6*1500 | SHELL PLATE | 4413 | SS400 | 1 | 311.5 | 311.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-1-SH-9 | PL6*667 | SHELL PLATE | 4413 | SS400 | 1 | 138.4 | 138.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK6-2-A-1 | L50*50*10 | ANGLE | 38 | SS400 | 1 | 0.3 | 0.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | SK6-2-A-27 | L75*75*6 | ANGLE | 2437 | SS400 | 3 | 16.7 | 50.1 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK6-2-A-28 | L75*75*6 | ANGLE | 495 | SS400 | 1 | 3.39 | 3.39 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-2-A-29 | L75*75*6 | ANGLE | 1410 | SS400 | 1 | 9.66 | 9.66 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-2-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 4 | 109.3 | 437.2 | 4 | 0 | 2026-05-31: 4 |  | #VALUE! |  |  |  | PMC
Shape | SK6-2-AFY-58 | L130*130*9 | ANGLE | 3992 | SS400 | 1 | 71.3 | 71.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-16
Shape | SK6-2-CFY-7 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | SK6-2-D-3 | CHS168.28*7.11 | PIPE 6" SCH.40 | 242 | A106 Gr.B | 1 | 6.8 | 6.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-09
Shape | SK6-2-D-4 | CHS114.3*6.02 | PIPE 4" SCH.40 | 242 | A106 Gr.B | 1 | 3.8 | 3.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-03
Purchasing | SK6-2-FL-2 | PL23.8*279 | BLIND 6" 150# SO-RF | 279 | A105 | 1 | 11.6 | 11.6 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-2-FL-3 | PL23.8*279 | FLANGE 6" 150# SO-RF | 279 | A105 | 1 | 8.5 | 8.5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-2-FL-6 | PL22.3*229 | FLANGE 4" 150# SO-RF | 229 | A105 | 1 | 6.5 | 6.5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-2-FL-7 | PL22.3*229 | BLIND 4" 150# SO-RF | 229 | A105 | 1 | 7.3 | 7.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-2-G-14 | PL12*175 | PLATE | 203 | SS400 | 2 | 3.3 | 6.6 | 2 | 0 | 2026-06-01: 2 |  | #VALUE! |  | PL12 |  | MCC
Plate | SK6-2-G-7 | PL10*126 | PLATE | 211 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-06-09: 2; 2026-08-05: 2 |  | #VALUE! |  | PL10 | Thừa 2 | MCC
Plate | SK6-2-G-8 | PL10*152 | PLATE | 161 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Purchasing | SK6-2-GK-1 | CHS215.9*22.6 | GASKET 6" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-2-GK-2 | CHS157.2*20.55 | GASKET 4" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.2 | 0.2 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-2-GX-1 | PL6*370 | BEND PLATE | 509 | SS400 | 1 | 8.9 | 8.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-07-08
Shape | SK6-2-HY-1 | H150*150*7*10 | H-BEAM | 1436 | SS400 | 1 | 44.7 | 44.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-15
Purchasing | SK6-2-M-1 | COUPLING 2" 3000# | COUPLING 2" 3000# | 86 | A105 | 1 | 0.7 | 0.7 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-2-M-2 | D55 | SQ HEAD PLUG 2" 3000# | 30 | A105 | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-2-P-17 | PL6*70 | PLATE | 130 | SS400 | 8 | 0.4 | 3.2 | 8 | 0 | 2026-07-06: 8 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK6-2-P-18 | PL6*51 | PLATE | 76 | SS400 | 21 | 0.2 | 4.2 | 21 | 0 | 2026-07-06: 21 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK6-2-P-2 | PL6*138 | PLATE | 138 | SS400 | 1 | 0.9 | 0.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | SK6-2-SH-14 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 413.6 | 413.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-2-SH-15 | PL6*1700 | SHELL PLATE | 4413 | SS400 | 1 | 353.1 | 353.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-2-SH-16 | PL6*967 | SHELL PLATE | 4413 | SS400 | 1 | 200.8 | 200.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-2-SH-6 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 2 | 415.4 | 830.8 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK6-2-SH-8 | PL6*1500 | SHELL PLATE | 4413 | SS400 | 1 | 311.5 | 311.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK6-3-A-1 | L50*50*10 | ANGLE | 38 | SS400 | 1 | 0.3 | 0.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | SK6-3-A-27 | L75*75*6 | ANGLE | 2437 | SS400 | 3 | 16.7 | 50.1 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK6-3-A-28 | L75*75*6 | ANGLE | 495 | SS400 | 1 | 3.39 | 3.39 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-3-A-29 | L75*75*6 | ANGLE | 1410 | SS400 | 1 | 9.66 | 9.66 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-3-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 4 | 109.3 | 437.2 | 4 | 0 | 2026-05-31: 4 |  | #VALUE! |  |  |  | PMC
Shape | SK6-3-AFY-58 | L130*130*9 | ANGLE | 3992 | SS400 | 1 | 71.3 | 71.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-16
Shape | SK6-3-CFY-7 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | SK6-3-D-3 | CHS168.28*7.11 | PIPE 6" SCH.40 | 242 | A106 Gr.B | 1 | 6.8 | 6.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-09
Shape | SK6-3-D-4 | CHS114.3*6.02 | PIPE 4" SCH.40 | 242 | A106 Gr.B | 1 | 3.8 | 3.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-09-03
Purchasing | SK6-3-FL-2 | PL23.8*279 | BLIND 6" 150# SO-RF | 279 | A105 | 1 | 11.6 | 11.6 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-3-FL-3 | PL23.8*279 | FLANGE 6" 150# SO-RF | 279 | A105 | 1 | 8.5 | 8.5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-3-FL-4 | PL22.3*229 | FLANGE 4" 150# SO-RF | 229 | A105 | 1 | 6.5 | 6.5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-3-FL-5 | PL22.3*229 | BLIND 4" 150# SO-RF | 229 | A105 | 1 | 7.3 | 7.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-3-G-7 | PL10*126 | PLATE | 211 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-06-09: 2; 2026-08-05: 3 |  | #VALUE! |  | PL10 | Thừa 3 | MCC
Plate | SK6-3-G-8 | PL10*152 | PLATE | 161 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Purchasing | SK6-3-GK-1 | CHS215.9*22.6 | GASKET 6" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-3-GK-2 | CHS157.2*20.55 | GASKET 4" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.2 | 0.2 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-3-GX-1 | PL6*370 | BEND PLATE | 509 | SS400 | 1 | 8.9 | 8.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-07-08
Purchasing | SK6-3-M-1 | COUPLING 2" 3000# | COUPLING 2" 3000# | 86 | A105 | 1 | 0.7 | 0.7 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-3-M-2 | D55 | SQ HEAD PLUG 2" 3000# | 30 | A105 | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-3-P-18 | PL6*51 | PLATE | 76 | SS400 | 21 | 0.2 | 4.2 | 21 | 0 | 2026-07-06: 21 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK6-3-P-2 | PL6*138 | PLATE | 138 | SS400 | 1 | 0.9 | 0.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | SK6-3-SH-10 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 413.6 | 413.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-3-SH-6 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 3 | 415.3 | 1245.9 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK6-3-SH-8 | PL6*1500 | SHELL PLATE | 4413 | SS400 | 1 | 311.5 | 311.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-3-SH-9 | PL6*667 | SHELL PLATE | 4413 | SS400 | 1 | 138.4 | 138.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK6-4-A-1 | L50*50*10 | ANGLE | 38 | SS400 | 1 | 0.3 | 0.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | SK6-4-A-27 | L75*75*6 | ANGLE | 2437 | SS400 | 4 | 16.7 | 66.8 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK6-4-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 4 | 109.3 | 437.2 | 4 | 0 | 2026-05-31: 4 |  | #VALUE! |  |  |  | PMC
Shape | SK6-4-AFY-58 | L130*130*9 | ANGLE | 3992 | SS400 | 1 | 71.3 | 71.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-06-23
Shape | SK6-4-CFY-7 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | SK6-4-D-3 | CHS168.28*7.11 | PIPE 6" SCH.40 | 242 | A106 Gr.B | 1 | 6.8 | 6.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-09
Purchasing | SK6-4-FL-2 | PL23.8*279 | BLIND 6" 150# SO-RF | 279 | A105 | 1 | 11.6 | 11.6 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-4-FL-3 | PL23.8*279 | FLANGE 6" 150# SO-RF | 279 | A105 | 1 | 8.5 | 8.5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-4-G-7 | PL10*126 | PLATE | 211 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-06-09: 2; 2026-08-05: 2 |  | #VALUE! |  | PL10 | Thừa 2 | MCC
Plate | SK6-4-G-8 | PL10*152 | PLATE | 161 | SS400 | 2 | 1.9 | 3.8 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Purchasing | SK6-4-GK-1 | CHS215.9*22.6 | GASKET 6" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-4-M-1 | COUPLING 2" 3000# | COUPLING 2" 3000# | 86 | A105 | 1 | 0.7 | 0.7 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-4-M-2 | D55 | SQ HEAD PLUG 2" 3000# | 30 | A105 | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-4-P-18 | PL6*51 | PLATE | 76 | SS400 | 20 | 0.2 | 4 | 20 | 0 | 2026-07-06: 20 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK6-4-SH-13 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 414.1 | 414.1 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-4-SH-6 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 3 | 415.4 | 1246.2 | 3 | 0 | 2026-05-31: 3 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK6-4-SH-8 | PL6*1500 | SHELL PLATE | 4413 | SS400 | 1 | 311.5 | 311.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-4-SH-9 | PL6*667 | SHELL PLATE | 4413 | SS400 | 1 | 138.4 | 138.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK6-5-A-1 | L50*50*10 | ANGLE | 38 | SS400 | 1 | 0.3 | 0.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-27
Shape | SK6-5-A-22 | L75*75*6 | ANGLE | 1284 | SS400 | 1 | 8.8 | 8.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-5-A-24 | L75*75*6 | ANGLE | 2516 | SS400 | 2 | 17.2 | 34.4 | 2 | 0 | 2026-05-23: 2 |  | #VALUE! |  |  |  | MCC
Shape | SK6-5-A-25 | L75*75*6 | ANGLE | 581 | SS400 | 1 | 4 | 4 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-5-A-26 | L75*75*6 | ANGLE | 514 | SS400 | 1 | 3.52 | 3.52 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-5-A-27 | L75*75*6 | ANGLE | 2437 | SS400 | 3 | 16.7 | 50.1 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK6-5-A-30 | L75*75*6 | ANGLE | 1429 | SS400 | 1 | 9.79 | 9.79 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-5-A-32 | L75*75*6 | ANGLE | 1184 | SS400 | 1 | 8.1 | 8.1 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Shape | SK6-5-AFY-52 | L150*150*12 | ANGLE | 4003 | SS400 | 4 | 109.3 | 437.2 | 4 | 0 | 2026-05-31: 4 |  | #VALUE! |  |  |  | PMC
Shape | SK6-5-AFY-58 | L130*130*9 | ANGLE | 3992 | SS400 | 1 | 71.3 | 71.3 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-08-25
Shape | SK6-5-CFY-7 | [200*80*7.5*11 | CHANNEL | 3964 | SS400 | 1 | 97.5 | 97.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-05-25
Shape | SK6-5-D-3 | CHS168.28*7.11 | PIPE 6" SCH.40 | 242 | A106 Gr.B | 1 | 6.8 | 6.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-09
Shape | SK6-5-D-5 | CHS88.9*5.49 | Pipe 3" SCH.40 | 242 | A106 Gr.B | 1 | 2.7 | 2.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-08-13
Purchasing | SK6-5-FL-2 | PL23.8*279 | BLIND 6" 150# SO-RF | 279 | A105 | 1 | 11.6 | 11.6 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-5-FL-3 | PL23.8*279 | FLANGE 6" 150# SO-RF | 279 | A105 | 1 | 8.5 | 8.5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-5-FL-8 | PL22.3*190 | FLANGE 3" 150# SO-RF | 190 | A105 | 1 | 4.2 | 4.2 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-5-FL-9 | PL22.3*190 | BLIND 3" 150# SO-RF | 190 | A105 | 1 | 5 | 5 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-5-G-11 | PL10*152 | PLATE | 304 | SS400 | 4 | 3.6 | 14.4 | 4 | 0 | 2026-08-05: 4 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK6-5-G-13 | PL55*406 | PLATE | 762 | SM490 | 1 | 125.5 | 125.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL55 |  | MCC | bar: 2026-09-08
Plate | SK6-5-G-7 | PL10*126 | PLATE | 212 | SS400 | 3 | 1.9 | 5.7 | 3 | 0 | 2026-06-09: 3; 2026-08-05: 2 |  | #VALUE! |  | PL10 | Thừa 2 | MCC
Plate | SK6-5-G-8 | PL10*152 | PLATE | 161 | SS400 | 3 | 1.9 | 5.7 | 3 | 0 | 2026-08-05: 3 |  | #VALUE! |  | PL10 |  | MCC
Purchasing | SK6-5-GK-1 | CHS215.9*22.6 | GASKET 6" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.3 | 0.3 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Purchasing | SK6-5-GK-3 | CHS127*18.15 | GASKET 3" 150# SO-RF | 3 | NON-METALLIC | 1 | 0.1 | 0.1 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK6-5-GX-1 | PL6*370 | BEND PLATE | 509 | SS400 | 1 | 8.9 | 8.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | SK6-5-P-18 | PL6*51 | PLATE | 76 | SS400 | 39 | 0.2 | 7.8 | 39 | 0 | 2026-07-06: 39 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK6-5-P-2 | PL6*138 | PLATE | 138 | SS400 | 1 | 0.9 | 0.9 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-05-25
Plate | SK6-5-PF-3 | PL12*508 | PLATE | 127 | SS400 | 1 | 23.8 | 23.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-06-03
Plate | SK6-5-SH-11 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 414 | 414 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-5-SH-12 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 1 | 415.4 | 415.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-5-SH-6 | PL6*2000 | SHELL PLATE | 4413 | SS400 | 2 | 415.3 | 830.6 | 2 | 0 | 2026-05-31: 2 |  | #VALUE! |  | PL6 |  | PMC
Plate | SK6-5-SH-8 | PL6*1500 | SHELL PLATE | 4413 | SS400 | 1 | 311.5 | 311.5 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Plate | SK6-5-SH-9 | PL6*667 | SHELL PLATE | 4413 | SS400 | 1 | 138.4 | 138.4 | 1 | 0 | [38 empty] | #VALUE! |  | PL6 |  | PMC | bar: 2026-05-31
Shape | SK7-1-A-12 | L75*75*6 | ANGLE | 863 | SS400 | 3 | 5.9 | 17.7 | 3 | 0 | 2026-05-23: 3 |  | #VALUE! |  |  |  | MCC
Shape | SK7-1-A-31 | L75*75*6 | ANGLE | 120 | SS400 | 1 | 0.8 | 0.8 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-05-23
Plate | SK7-1-DF-1 | SPD634*12 | BEND PLATE | 203 | SS400 | 1 | 37.2 | 37.2 | 1 | 0 | [38 empty] | #VALUE! |  | SPD634 |  | PMC | bar: 2026-06-15
Plate | SK7-1-G-15 | PL16*832 | PLATE | 832 | SS400 | 1 | 28.6 | 28.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL16 |  | MCC | bar: 2026-07-10
Plate | SK7-1-G-16 | PL19*92 | PLATE | 196 | SS400 | 4 | 1.7 | 6.8 | 4 | 0 | 2026-06-26: 4 |  | #VALUE! |  | PL19 |  | MCC
Plate | SK7-1-G-17 | PL10*76 | PLATE | 270 | SS400 | 2 | 1.6 | 3.2 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK7-1-G-18 | PL16*832 | PLATE | 832 | SS400 | 1 | 68.3 | 68.3 | 1 | 0 | [38 empty] | #VALUE! |  | PL16 |  | MCC | bar: 2026-07-10
Plate | SK7-1-GF-2 | PL12*1300 | PAD PLATE | 1200 | SS400 | 1 | 70.8 | 70.8 | 1 | 0 | [38 empty] | #VALUE! |  | PL12 |  | PMC | bar: 2026-05-31
Purchasing | SK7-1-GK-4 | CHS746*55.5 | GASKET OD.746 ID.635 | 3 | NON-METALLIC | 1 | 2.8 | 2.8 | 0 | 1 | [38 empty] | #VALUE! |  |  |  | KHO
Plate | SK7-1-P-18 | PL6*51 | PLATE | 76 | SS400 | 10 | 0.2 | 2 | 10 | 0 | 2026-07-06: 10 |  | #VALUE! |  | PL6 |  | MCC
Shape | SK7-1-R-1 | D19 | ROUND BAR | 448 | SS400 | 1 | 0.9 | 0.9 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | MCC | bar: 2026-06-06
Shape | SK7-1-RX-2 | D19 | ROUND BAR | 839 | SS400 | 1 | 1.7 | 1.7 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-07-30
Shape | SK7-1-RX-3 | D19 | ROUND BAR | 271 | SS400 | 1 | 0.5 | 0.5 | 1 | 0 | [38 empty] | #VALUE! |  |  |  | PMC | bar: 2026-07-30
Plate | SK7-1-SH-78 | PL8*1651 | SHELL PLATE | 4410,5 | SS400 | 1 | 436.6 | 436.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK7-2-A-12 | L75*75*6 | ANGLE | 863 | SS400 | 4 | 5.9 | 23.6 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Plate | SK7-2-P-18 | PL6*51 | PLATE | 76 | SS400 | 12 | 0.2 | 2.4 | 12 | 0 | 2026-07-06: 12 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK7-2-SH-74 | PL8*1651 | SHELL PLATE | 4413 | SS400 | 1 | 456.6 | 456.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Shape | SK7-3-A-12 | L75*75*6 | ANGLE | 863 | SS400 | 8 | 5.9 | 47.2 | 8 | 0 | 2026-05-23: 8 |  | #VALUE! |  |  |  | MCC
Plate | SK7-3-P-18 | PL6*51 | PLATE | 76 | SS400 | 24 | 0.2 | 4.8 | 24 | 0 | 2026-07-06: 24 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK7-3-SH-1 | PL8*1651 | SHELL PLATE | 4410,5 | SS400 | 2 | 456.6 | 913.2 | 2 | 0 | 2026-06-05: 2 |  | #VALUE! |  | PL8 |  | PMC
Shape | SK7-4-A-12 | L75*75*6 | ANGLE | 863 | SS400 | 4 | 5.9 | 23.6 | 4 | 0 | 2026-05-23: 4 |  | #VALUE! |  |  |  | MCC
Shape | SK7-4-A-14 | L75*75*6 | ANGLE | 723 | SS400 | 2 | 5 | 10 | 2 | 0 | 2026-05-23: 2 |  | #VALUE! |  |  |  | MCC
Plate | SK7-4-G-11 | PL10*152 | PLATE | 304 | SS400 | 2 | 3.6 | 7.2 | 2 | 0 | 2026-08-05: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SK7-4-P-18 | PL6*51 | PLATE | 76 | SS400 | 16 | 0.2 | 3.2 | 16 | 0 | 2026-07-06: 16 |  | #VALUE! |  | PL6 |  | MCC
Plate | SK7-4-SH-74 | PL8*1651 | SHELL PLATE | 4413 | SS400 | 1 | 456.6 | 456.6 | 1 | 0 | [38 empty] | #VALUE! |  | PL8 |  | PMC | bar: 2026-06-05
Purchasing | SR-1-M-3 | NUT_M6 | SELF-DRILLING HEX M6 | 32 | SS400(Galv.) | 376 | 0 | 0 | 0 | 376 | [38 empty] | #VALUE! |  |  |  | KHO

## U284STK
ASSEMBLY PART LIST
Project name / Tên Dự án : V17566 Tallgrass_HRSG NPP
Item Name / Tên Hạng mục : Outlet Stack
Contract No. / Số Hợp đồng : U284 |  | U284STK | [76 empty] | chi tiết chia nối
Prepared By / Chuẩn bị : TTTV-TK | [31 empty] | DCC | [8 empty] | DCC
Document No. / Số Tài liệu : U284-01-APL-001 | [7 empty] | Rev./ Số Sửa đổi: 3 | [13 empty] | 68220.9 | #DIV/0! | [5 empty] | Date: 01-06-2026 |  |  | PAINTING INSIDE | [8 empty] | PAINTING OUTSIDE | [17 empty] | Content Rev. | [9 empty] | Type Fabrication | [6 empty] | Type | Document Cutting
DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | DCC | DCC | DCC | DCC | DCC | DCC | DCC | 1st |  |  | 2nd |  |  | Top Coat (3rd) |  |  | 1st |  |  | 2nd |  |  | Top Coat (3rd) |  |  | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC-F | DCC-X | DCC-Y | DCC-Z | DCC-J | DCC-BH | DCC | Unit 1
No. | Drawing Number | Assembly No. | Description | Part No. |  | Size | Length | Material | Q'ty | Set | T.Q'ty | U.Weight | T.Weight | Scope of Steel Work | Chung loai | Dang | Phan giao to | Ngay giao | Da nhan | Con thieu | Lam tron | Dong bo | Ti le dong bo | Fitup | Inspection | Clear | Loose Part | Total Area (m2) | Remark | AS Symbol | Delivery item | D.F.T (㎛) | Painting Name & Color Code | Total Area (m2) | D.F.T (㎛) | Painting Name & Color Code | Total Area (m2) | D.F.T (㎛) | Painting Name & Color Code | Total Area (m2) | D.F.T (㎛) | Painting Name & Color Code | Total Area (m2) | D.F.T (㎛) | Painting Name & Color Code | Total Area (m2) | D.F.T (㎛) | Painting Name & Color Code | Total Area (m2) | %Hao phí (Theo từng loại KCT- PMBs) | %Hao phí (Theo thực tế Quyết toán) | Paint Brand (Hãng sơn) | Scope of Painting Work Unit-1 | Scope of Painting Work Unit-2 | Scope of Painting Work Unit-3 | Scope of Painting Work Unit-4 | Scope of Painting Work Unit-5 | Scope of Painting Work Unit-6 | Rev.1 (dd/mm/yyyy) | Rev.2 (05/05/2026) | Rev.3 (01/06/2026) | Rev.4 (dd/mm/yyyy) | Rev.5 (dd/mm/yyyy) | Rev.6 (dd/mm/yyyy) | Rev.7 (dd/mm/yyyy) | Rev.8 (dd/mm/yyyy) | Rev.9 (dd/mm/yyyy) | Rev.10 (dd/mm/yyyy) | Khoan Lỗ | Lốc tròn (Uốn cong) | Sấn | Vát mép & Cắt miệng | Gia công cơ khí (Không thay đổi chiều dày) | Gia công cơ khí (Có thay đổi chiều dày) | Tổ hợp | Fabrication or Purchasing | MPR No. | Q'Ty in MPR Bolt & Fitting | Cutting No. | Q'TY | Date Issue
1 | 2 | 3 | 4 | 5A (Marking as Dwg.) | 5B (Marking as Cutting) | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [5 empty] | 20 | 21 | 22 | 23 | 24 |  |  |  | 14 | 17 | 18 | 19 | 20 | 21A | 21B | 21C | 22A | 22B | 22C | 23A | 23B | 23C | 24A | 24B | 24C | 25A | 25B | 25C | 26A | 26B | 26C | 27A | 27B | 28 | 29A | 29B | 29C | 29D | 29E | 29F | 30A | 30B | 30C | 30D | 30E | 30F | 30G | 30H | 30I | 30J | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
1 | V17566-SKXD-7001 | BK-1 | BLANKING PLATE |  |  | (2235x156x4861) |  |  |  | 1 |  | 1141.1 | 1141.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 35.2 |  | x | o | [21 empty] | PAC
2 | V17566-SKXD-7001 | BK-1 | ANGLE | A-6 | BK-1-A-6 | L150*150*12 | 4700 | SS400 | 1 |  | 1 | 128.3 | 128.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 |  |  |  | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
3 | V17566-SKXD-7001 | BK-1 | ANGLE | A-10 | BK-1-A-10 | L150*150*12 | 2210 | SS400 | 1 |  | 1 | 60.3 | 60.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
4 | V17566-SKXD-7001 | BK-1 | ANGLE | A-11 | BK-1-A-11 | L150*150*12 | 2210 | SS400 | 1 |  | 1 | 60.3 | 60.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
5 | V17566-SKXD-7001 | BK-1 | ANGLE | AY-1 | BK-1-AY-1 | L150*150*12 | 4700 | SS400 | 1 |  | 1 | 128.3 | 128.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 |  |  |  | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
6 | V17566-SKXD-7001 | BK-1 | ANGLE | AY-2 | BK-1-AY-2 | L150*150*12 | 4700 | SS400 | 2 |  | 2 | 128.3 | 256.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 5.5 |  |  |  | 75 | Greenish Grey, Grey | 2.75 | [6 empty] | 75 | Greenish Grey, Grey | 2.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
7 | V17566-SKXD-7001 | BK-1 | PLATE | G-9 | BK-1-G-9 | PL6*2185 | 4861 | SS400 | 1 |  | 1 | 500.2 | 500.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 21.3 |  |  |  | 75 | Greenish Grey, Grey | 10.65 | [6 empty] | 75 | Greenish Grey, Grey | 10.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
8 | V17566-SKXD-7001 | BK-1 | PLATE | P-13 | BK-1-P-13 | PL12*138 | 138 | SS400 | 4 |  | 4 | 1.8 | 7.1 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
10 | V17566-SKXD-7002 | BK-2 | BLANKING PLATE |  |  | (2134x156x4861) |  |  |  | 4 |  | 1110.9 | 4443.8 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 136.1 |  | x | o | [21 empty] | PAC
11 | V17566-SKXD-7002 | BK-2 | ANGLE | A-6 | BK-2-A-6 | L150*150*12 | 4700 | SS400 | 2 |  | 8 | 128.3 | 1026.4 | AMC2 | Shape | MCC |  |  | 8 | 0 | 4 | [6 empty] | 22.1 |  |  |  | 75 | Greenish Grey, Grey | 11.05 | [6 empty] | 75 | Greenish Grey, Grey | 11.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
12 | V17566-SKXD-7002 | BK-2 | ANGLE | A-7 | BK-2-A-7 | L150*150*12 | 2083 | SS400 | 1 |  | 4 | 56.9 | 227.4 | AMC2 | Shape | MCC |  |  | 4 | 0 | 4 | [6 empty] | 4.9 |  |  |  | 75 | Greenish Grey, Grey | 2.45 | [6 empty] | 75 | Greenish Grey, Grey | 2.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
13 | V17566-SKXD-7002 | BK-2 | ANGLE | A-8 | BK-2-A-8 | L150*150*12 | 2083 | SS400 | 1 |  | 4 | 56.9 | 227.4 | AMC2 | Shape | MCC |  |  | 4 | 0 | 4 | [6 empty] | 4.9 |  |  |  | 75 | Greenish Grey, Grey | 2.45 | [6 empty] | 75 | Greenish Grey, Grey | 2.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
14 | V17566-SKXD-7002 | BK-2 | ANGLE | AY-2 | BK-2-AY-2 | L150*150*12 | 4700 | SS400 | 2 |  | 8 | 128.3 | 1026.4 | AMC2 | Shape | MCC |  |  | 8 | 0 | 4 | [6 empty] | 22.1 |  |  |  | 75 | Greenish Grey, Grey | 11.05 | [6 empty] | 75 | Greenish Grey, Grey | 11.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
15 | V17566-SKXD-7002 | BK-2 | PLATE | G-10 | BK-2-G-10 | PL6*2083 | 4861 | SS400 | 1 |  | 4 | 476.9 | 1907.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 81.3 |  |  |  | 75 | Greenish Grey, Grey | 40.65 | [6 empty] | 75 | Greenish Grey, Grey | 40.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
16 | V17566-SKXD-7002 | BK-2 | PLATE | P-13 | BK-2-P-13 | PL12*138 | 138 | SS400 | 4 |  | 16 | 1.8 | 28.4 | AMC2 | Plate | MCC |  |  | 16 | 0 | 4 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
19 | V17566-SKXD-7003 | BK-3 | BLANKING PLATE |  |  | (2235x156x4861) |  |  |  | 1 |  | 1141.1 | 1141.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 35.2 |  | x | o | [21 empty] | PAC
20 | V17566-SKXD-7003 | BK-3 | ANGLE | A-4 | BK-3-A-4 | L150*150*12 | 2210 | SS400 | 1 |  | 1 | 60.3 | 60.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
21 | V17566-SKXD-7003 | BK-3 | ANGLE | A-5 | BK-3-A-5 | L150*150*12 | 2210 | SS400 | 1 |  | 1 | 60.3 | 60.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
22 | V17566-SKXD-7003 | BK-3 | ANGLE | A-6 | BK-3-A-6 | L150*150*12 | 4700 | SS400 | 1 |  | 1 | 128.3 | 128.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 |  |  |  | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
23 | V17566-SKXD-7003 | BK-3 | ANGLE | AY-1 | BK-3-AY-1 | L150*150*12 | 4700 | SS400 | 1 |  | 1 | 128.3 | 128.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 |  |  |  | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 75 | Greenish Grey, Grey | 1.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
24 | V17566-SKXD-7003 | BK-3 | ANGLE | AY-2 | BK-3-AY-2 | L150*150*12 | 4700 | SS400 | 2 |  | 2 | 128.3 | 256.6 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 5.5 |  |  |  | 75 | Greenish Grey, Grey | 2.75 | [6 empty] | 75 | Greenish Grey, Grey | 2.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
25 | V17566-SKXD-7003 | BK-3 | PLATE | G-9 | BK-3-G-9 | PL6*2185 | 4861 | SS400 | 1 |  | 1 | 500.2 | 500.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 21.3 |  |  |  | 75 | Greenish Grey, Grey | 10.65 | [6 empty] | 75 | Greenish Grey, Grey | 10.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
26 | V17566-SKXD-7003 | BK-3 | PLATE | P-13 | BK-3-P-13 | PL12*138 | 138 | SS400 | 4 |  | 4 | 1.8 | 7.1 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
29 | V17566-SKXD-7004 | DR-1 | DRAIN PIPE |  |  | (3633x191x191) |  |  |  | 1 |  | 45 | 45 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 1.1 |  | x | o | [21 empty] | PAC
30 | V17566-SKXD-7004 | DR-1 | PIPE 3" SCH.40 | D-1 | DR-1-D-1 | CHS88.9*5.49 | 3627 | SA-312 TP304 | 1 |  | 1 | 40.3 | 40.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 |  |  |  | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
31 | V17566-SKXD-7004 | DR-1 | FLANGE 3" 150# SO-RF | FL-1 | DR-1-FL-1 | PL22.3*191 | 191 | A-182 F304 | 1 |  | 1 | 4.7 | 4.7 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
32 | V17566-SKXD-7005 | DR-2 | DRAIN PIPE |  |  | (3724x158x89) |  |  |  | 1 |  | 41.5 | 41.5 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 1 |  | x | o | [21 empty] | PAC
33 | V17566-SKXD-7005 | DR-2 | PIPE 3" SCH.40 | D-2 | DR-2-D-2 | CHS88.9*5.49 | 3566 | SA-312 TP304 | 1 |  | 1 | 39.6 | 39.6 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 |  |  |  | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
34 | V17566-SKXD-7005 | DR-2 | ELBOW LR 90° 3" SCH40 | EL-1 | DR-2-EL-1 | CHS88.9*5.49 | 178 | SA403-WP 304SS | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
35 | V17566-SKXD-7193 | DR-4 | DRAIN PAN |  |  | (7008x580x6984) |  |  |  | 1 |  | 2429.2 | 2429.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 77.6 |  | x | o | [21 empty] | PAC
36 | V17566-SKXD-7193 | DR-4 | PLATE | PF-2 | DR-4-PF-2 | PL8*7031 | 7031 | SS400 | 1 |  | 1 | 2429.2 | 2429.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 77.6 |  |  |  | 75 | Greenish Grey, Grey | 38.8 | [6 empty] | 75 | Greenish Grey, Grey | 38.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
37 | V17566-SKXD-7006 | EX-1 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 5 |  | 7.4 | 37 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 28.6 |  | x | o | [21 empty] | PAC
38 | V17566-SKXD-7006 | EX-1 | 3/4 NO.16 Exp.Metal | E-5 | EX-1-E-5 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 5 | 7.4 | 37 | AMC2 | Shape | MCC |  |  | 5 | 0 | 5 | [5 empty] | Loose Part | 28.6 |  |  |  |  | Hot Dip Galvanized | 14.3 | [7 empty] | Hot Dip Galvanized | 14.3 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
39 | V17566-SKXD-7007 | EX-2 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 2 |  | 7.2 | 14.3 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 11 |  | x | o | [21 empty] | PAC
40 | V17566-SKXD-7007 | EX-2 | 3/4 NO.16 Exp.Metal | E-27 | EX-2-E-27 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 2 | 7.1 | 14.1 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 10.9 |  |  |  |  | Hot Dip Galvanized | 5.45 | [7 empty] | Hot Dip Galvanized | 5.45 | [9 empty] | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
41 | V17566-SKXD-7007 | EX-2 | RUBBER SEAL TRIP | M-5 | EX-2-M-5 | PL10*10 | 792 | RUBBER | 1 |  | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.1 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
42 | V17566-SKXD-7008 | EX-3 | EXPANDED METAL |  |  | (1172x200x2438) |  |  |  | 2 |  | 7.3 | 14.5 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 11.1 |  | x | o | [21 empty] | PAC
43 | V17566-SKXD-7008 | EX-3 | 3/4 NO.16 Exp.Metal | E-22 | EX-3-E-22 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 2 | 7.1 | 14.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 11.1 |  |  |  |  | Hot Dip Galvanized | 5.55 | [7 empty] | Hot Dip Galvanized | 5.55 | [9 empty] | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
44 | V17566-SKXD-7008 | EX-3 | RUBBER SEAL TRIP | M-5 | EX-3-M-5 | PL10*10 | 792 | RUBBER | 1 |  | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.1 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
45 | V17566-SKXD-7009 | EX-4 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 8 |  | 7.4 | 59.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 45.7 |  | x | o | [21 empty] | PAC
46 | V17566-SKXD-7009 | EX-4 | 3/4 NO.16 Exp.Metal | E-23 | EX-4-E-23 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 8 | 7.4 | 59.1 | AMC2 | Shape | MCC |  |  | 8 | 0 | 8 | [5 empty] | Loose Part | 45.7 |  |  |  |  | Hot Dip Galvanized | 22.85 | [7 empty] | Hot Dip Galvanized | 22.85 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
47 | V17566-SKXD-7010 | EX-5 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 2 |  | 7.2 | 14.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 11.1 |  | x | o | [21 empty] | PAC
48 | V17566-SKXD-7010 | EX-5 | 3/4 NO.16 Exp.Metal | E-8 | EX-5-E-8 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 2 | 7.2 | 14.4 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 11.1 |  |  |  |  | Hot Dip Galvanized | 5.55 | [7 empty] | Hot Dip Galvanized | 5.55 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
49 | V17566-SKXD-7011 | EX-6 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 1 |  | 7.1 | 7.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 5.5 |  | x | o | [21 empty] | PAC
50 | V17566-SKXD-7011 | EX-6 | 3/4 NO.16 Exp.Metal | E-6 | EX-6-E-6 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 1 | 7.1 | 7.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 5.5 |  |  |  |  | Hot Dip Galvanized | 2.75 | [7 empty] | Hot Dip Galvanized | 2.75 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
51 | V17566-SKXD-7012 | EX-7 | EXPANDED METAL |  |  | (1153x203x2438) |  |  |  | 4 |  | 6.9 | 27.7 | AMC2 | [7 empty] | 0 | 0.33333 |  |  |  |  | 20.9 |  | x | o | [21 empty] | PAC
52 | V17566-SKXD-7012 | EX-7 | 3/4 NO.16 Exp.Metal | E-24 | EX-7-E-24 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 4 | 6.7 | 26.6 | AMC2 | Shape | MCC |  |  | 4 | 0 | 4 | [6 empty] | 20.6 |  |  |  |  | Hot Dip Galvanized | 10.3 | [7 empty] | Hot Dip Galvanized | 10.3 | [9 empty] | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
53 | V17566-SKXD-7012 | EX-7 | RUBBER SEAL TRIP | M-4 | EX-7-M-4 | PL10*10 | 931 | RUBBER | 2 |  | 8 | 0.1 | 1.1 | AMC2 | Purchasing | KHO |  |  | 0 | 8 | 0 | [6 empty] | 0.3 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
54 | V17566-SKXD-7013 | EX-8 | EXPANDED METAL |  |  | (1153x196x915) |  |  |  | 10 |  | 2.8 | 27.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 21.4 |  | x | o | [21 empty] | PAC
55 | V17566-SKXD-7013 | EX-8 | 3/4 NO.16 Exp.Metal | E-9 | EX-8-E-9 | PL1.5*915 | 1175 | SS400(Galv.) | 1 |  | 10 | 2.8 | 27.6 | AMC2 | Shape | MCC |  |  | 10 | 0 | 10 | [5 empty] | Loose Part | 21.4 |  |  |  |  | Hot Dip Galvanized | 10.7 | [7 empty] | Hot Dip Galvanized | 10.7 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
56 | V17566-SKXD-7014 | EX-9 | EXPANDED METAL |  |  | (1153x196x863) |  |  |  | 10 |  | 2.6 | 26 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 20.1 |  | x | o | [21 empty] | PAC
57 | V17566-SKXD-7014 | EX-9 | 3/4 NO.16 Exp.Metal | E-7 | EX-9-E-7 | PL1.5*863 | 1175 | SS400(Galv.) | 1 |  | 10 | 2.6 | 26 | AMC2 | Shape | MCC |  |  | 10 | 0 | 10 | [5 empty] | Loose Part | 20.1 |  |  |  |  | Hot Dip Galvanized | 10.05 | [7 empty] | Hot Dip Galvanized | 10.05 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
58 | V17566-SKXD-7015 | EX-10 | EXPANDED METAL |  |  | (1172x200x2438) |  |  |  | 2 |  | 7.2 | 14.5 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 11.1 |  | x | o | [21 empty] | PAC
59 | V17566-SKXD-7015 | EX-10 | 3/4 NO.16 Exp.Metal | E-26 | EX-10-E-26 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 2 | 7.1 | 14.2 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 11 |  |  |  |  | Hot Dip Galvanized | 5.5 | [7 empty] | Hot Dip Galvanized | 5.5 | [9 empty] | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
60 | V17566-SKXD-7015 | EX-10 | RUBBER SEAL TRIP | M-6 | EX-10-M-6 | PL10*10 | 853 | RUBBER | 1 |  | 2 | 0.1 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.1 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
61 | V17566-SKXD-7016 | EX-11 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 1 |  | 7.1 | 7.1 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 5.5 |  | x | o | [21 empty] | PAC
62 | V17566-SKXD-7016 | EX-11 | 3/4 NO.16 Exp.Metal | E-28 | EX-11-E-28 | PL1.5*2438 | 1174 | SS400(Galv.) | 1 |  | 1 | 7 | 7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 5.4 |  |  |  |  | Hot Dip Galvanized | 2.7 | [7 empty] | Hot Dip Galvanized | 2.7 | [9 empty] | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
63 | V17566-SKXD-7016 | EX-11 | RUBBER SEAL TRIP | M-6 | EX-11-M-6 | PL10*10 | 853 | RUBBER | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
64 | V17566-SKXD-7017 | EX-12 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 1 |  | 7.1 | 7.1 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | 5.5 |  | x | o | [21 empty] | PAC
65 | V17566-SKXD-7017 | EX-12 | 3/4 NO.16 Exp.Metal | E-25 | EX-12-E-25 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 1 | 7 | 7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 5.4 |  |  |  |  | Hot Dip Galvanized | 2.7 | [7 empty] | Hot Dip Galvanized | 2.7 | [9 empty] | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
66 | V17566-SKXD-7017 | EX-12 | RUBBER SEAL TRIP | M-6 | EX-12-M-6 | PL10*10 | 853 | RUBBER | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
67 | V17566-SKXD-7018 | EX-13 | EXPANDED METAL |  |  | (887x111x723) |  |  |  | 1 |  | 1.5 | 1.5 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.2 |  | x | o | [21 empty] | PAC
68 | V17566-SKXD-7018 | EX-13 | 3/4 NO.16 Exp.Metal | E-1 | EX-13-E-1 | PL1.5*723 | 895 | SS400(Galv.) | 1 |  | 1 | 1.5 | 1.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.2 |  |  |  |  | Hot Dip Galvanized | 0.6 | [7 empty] | Hot Dip Galvanized | 0.6 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
69 | V17566-SKXD-7019 | EX-14 | EXPANDED METAL |  |  | (887x111x1007) |  |  |  | 1 |  | 2.3 | 2.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.8 |  | x | o | [21 empty] | PAC
70 | V17566-SKXD-7019 | EX-14 | 3/4 NO.16 Exp.Metal | E-2 | EX-14-E-2 | PL1.5*1007 | 895 | SS400(Galv.) | 1 |  | 1 | 2.3 | 2.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.8 |  |  |  |  | Hot Dip Galvanized | 0.9 | [7 empty] | Hot Dip Galvanized | 0.9 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
71 | V17566-SKXD-7020 | EX-15 | EXPANDED METAL |  |  | (887x111x1321) |  |  |  | 1 |  | 2.9 | 2.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.2 |  | x | o | [21 empty] | PAC
72 | V17566-SKXD-7020 | EX-15 | 3/4 NO.16 Exp.Metal | E-3 | EX-15-E-3 | PL1.5*1321 | 895 | SS400(Galv.) | 1 |  | 1 | 2.9 | 2.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 2.2 |  |  |  |  | Hot Dip Galvanized | 1.1 | [7 empty] | Hot Dip Galvanized | 1.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
73 | V17566-SKXD-7021 | EX-16 | EXPANDED METAL |  |  | (869x107x1525) |  |  |  | 1 |  | 3.3 | 3.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.6 |  | x | o | [21 empty] | PAC
74 | V17566-SKXD-7021 | EX-16 | 3/4 NO.16 Exp.Metal | E-16 | EX-16-E-16 | PL1.5*1524.9 | 876 | SS400(Galv.) | 1 |  | 1 | 3.3 | 3.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 2.6 |  |  |  |  | Hot Dip Galvanized | 1.3 | [7 empty] | Hot Dip Galvanized | 1.3 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
75 | V17566-SKXD-7022 | EX-17 | EXPANDED METAL |  |  | (869x107x743) |  |  |  | 1 |  | 1.7 | 1.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.3 |  | x | o | [21 empty] | PAC
76 | V17566-SKXD-7022 | EX-17 | 3/4 NO.16 Exp.Metal | E-4 | EX-17-E-4 | PL1.5*742.7 | 876 | SS400(Galv.) | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.3 |  |  |  |  | Hot Dip Galvanized | 0.65 | [7 empty] | Hot Dip Galvanized | 0.65 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
77 | V17566-SKXD-7023 | EX-18 | EXPANDED METAL |  |  | (869x107x1489) |  |  |  | 1 |  | 3.2 | 3.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.5 |  | x | o | [21 empty] | PAC
78 | V17566-SKXD-7023 | EX-18 | 3/4 NO.16 Exp.Metal | E-11 | EX-18-E-11 | PL1.5*1489 | 876 | SS400(Galv.) | 1 |  | 1 | 3.2 | 3.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 2.5 |  |  |  |  | Hot Dip Galvanized | 1.25 | [7 empty] | Hot Dip Galvanized | 1.25 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
79 | V17566-SKXD-7024 | EX-19 | EXPANDED METAL |  |  | (869x107x116) |  |  |  | 1 |  | 0.3 | 0.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.2 |  | x | o | [21 empty] | PAC
80 | V17566-SKXD-7024 | EX-19 | 3/4 NO.16 Exp.Metal | E-21 | EX-19-E-21 | PL1.5*116.4 | 876 | SS400(Galv.) | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.2 |  |  |  |  | Hot Dip Galvanized | 0.1 | [7 empty] | Hot Dip Galvanized | 0.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
81 | V17566-SKXD-7025 | EX-20 | EXPANDED METAL |  |  | (869x107x2438) |  |  |  | 1 |  | 5.4 | 5.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 4.2 |  | x | o | [21 empty] | PAC
82 | V17566-SKXD-7025 | EX-20 | 3/4 NO.16 Exp.Metal | E-18 | EX-20-E-18 | PL1.5*2438 | 876 | SS400(Galv.) | 1 |  | 1 | 5.4 | 5.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 4.2 |  |  |  |  | Hot Dip Galvanized | 2.1 | [7 empty] | Hot Dip Galvanized | 2.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
83 | V17566-SKXD-7026 | EX-21 | EXPANDED METAL |  |  | (887x111x1284) |  |  |  | 1 |  | 2.8 | 2.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.2 |  | x | o | [21 empty] | PAC
84 | V17566-SKXD-7026 | EX-21 | 3/4 NO.16 Exp.Metal | E-20 | EX-21-E-20 | PL1.5*1284.3 | 895 | SS400(Galv.) | 1 |  | 1 | 2.8 | 2.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 2.2 |  |  |  |  | Hot Dip Galvanized | 1.1 | [7 empty] | Hot Dip Galvanized | 1.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
85 | V17566-SKXD-7027 | EX-22 | EXPANDED METAL |  |  | (887x111x130) |  |  |  | 1 |  | 0.3 | 0.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.2 |  | x | o | [21 empty] | PAC
86 | V17566-SKXD-7027 | EX-22 | 3/4 NO.16 Exp.Metal | E-14 | EX-22-E-14 | PL1.5*130 | 895 | SS400(Galv.) | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.2 |  |  |  |  | Hot Dip Galvanized | 0.1 | [7 empty] | Hot Dip Galvanized | 0.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
87 | V17566-SKXD-7028 | EX-23 | EXPANDED METAL |  |  | (887x111x1285) |  |  |  | 1 |  | 2.8 | 2.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.2 |  | x | o | [21 empty] | PAC
88 | V17566-SKXD-7028 | EX-23 | 3/4 NO.16 Exp.Metal | E-15 | EX-23-E-15 | PL1.5*1285 | 895 | SS400(Galv.) | 1 |  | 1 | 2.8 | 2.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 2.2 |  |  |  |  | Hot Dip Galvanized | 1.1 | [7 empty] | Hot Dip Galvanized | 1.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
89 | V17566-SKXD-7029 | EX-24 | EXPANDED METAL |  |  | (869x111x1525) |  |  |  | 1 |  | 3.3 | 3.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.6 |  | x | o | [21 empty] | PAC
90 | V17566-SKXD-7029 | EX-24 | 3/4 NO.16 Exp.Metal | E-17 | EX-24-E-17 | PL1.5*1524.9 | 876 | SS400(Galv.) | 1 |  | 1 | 3.3 | 3.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 2.6 |  |  |  |  | Hot Dip Galvanized | 1.3 | [7 empty] | Hot Dip Galvanized | 1.3 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
91 | V17566-SKXD-7030 | EX-25 | EXPANDED METAL |  |  | (869x111x743) |  |  |  | 1 |  | 1.7 | 1.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.3 |  | x | o | [21 empty] | PAC
92 | V17566-SKXD-7030 | EX-25 | 3/4 NO.16 Exp.Metal | E-10 | EX-25-E-10 | PL1.5*742.7 | 876 | SS400(Galv.) | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.3 |  |  |  |  | Hot Dip Galvanized | 0.65 | [7 empty] | Hot Dip Galvanized | 0.65 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
93 | V17566-SKXD-7031 | EX-26 | EXPANDED METAL |  |  | (869x111x753) |  |  |  | 1 |  | 1.5 | 1.5 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.2 |  | x | o | [21 empty] | PAC
94 | V17566-SKXD-7031 | EX-26 | 3/4 NO.16 Exp.Metal | E-13 | EX-26-E-13 | PL1.5*752.8 | 876 | SS400(Galv.) | 1 |  | 1 | 1.5 | 1.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.2 |  |  |  |  | Hot Dip Galvanized | 0.6 | [7 empty] | Hot Dip Galvanized | 0.6 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
95 | V17566-SKXD-7032 | EX-27 | EXPANDED METAL |  |  | (869x111x2438) |  |  |  | 1 |  | 5.4 | 5.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 4.2 |  | x | o | [21 empty] | PAC
96 | V17566-SKXD-7032 | EX-27 | 3/4 NO.16 Exp.Metal | E-12 | EX-27-E-12 | PL1.5*2438 | 876 | SS400(Galv.) | 1 |  | 1 | 5.4 | 5.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 4.2 |  |  |  |  | Hot Dip Galvanized | 2.1 | [7 empty] | Hot Dip Galvanized | 2.1 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
97 | V17566-SKXD-7033 | EX-28 | EXPANDED METAL |  |  | (869x111x581) |  |  |  | 1 |  | 1.3 | 1.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1 |  | x | o | [21 empty] | PAC
98 | V17566-SKXD-7033 | EX-28 | 3/4 NO.16 Exp.Metal | E-19 | EX-28-E-19 | PL1.5*581 | 876 | SS400(Galv.) | 1 |  | 1 | 1.3 | 1.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1 |  |  |  |  | Hot Dip Galvanized | 0.5 | [7 empty] | Hot Dip Galvanized | 0.5 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
99 | V17566-SKXD-7178 | EX-29 | EXPANDED METAL |  |  | (1153x196x1654) |  |  |  | 17 |  | 5 | 85.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 65.9 |  | x | o | [21 empty] | PAC
100 | V17566-SKXD-7178 | EX-29 | 3/4 NO.16 Exp.Metal | E-31 | EX-29-E-31 | PL1.5*1654 | 1175 | SS400(Galv.) | 1 |  | 17 | 5 | 85.1 | AMC2 | Shape | MCC |  |  | 17 | 0 | 17 | [5 empty] | Loose Part | 65.9 |  |  |  |  | Hot Dip Galvanized | 32.95 | [7 empty] | Hot Dip Galvanized | 32.95 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
101 | V17566-SKXD-7179 | EX-30 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 1 |  | 6.7 | 6.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 5.2 |  | x | o | [21 empty] | PAC
102 | V17566-SKXD-7179 | EX-30 | 3/4 NO.16 Exp.Metal | E-29 | EX-30-E-29 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 1 | 6.7 | 6.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 5.2 |  |  |  |  | Hot Dip Galvanized | 2.6 | [7 empty] | Hot Dip Galvanized | 2.6 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
103 | V17566-SKXD-7180 | EX-31 | EXPANDED METAL |  |  | (1153x196x2438) |  |  |  | 1 |  | 5.9 | 5.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 4.5 |  | x | o | [21 empty] | PAC
104 | V17566-SKXD-7180 | EX-31 | 3/4 NO.16 Exp.Metal | E-30 | EX-31-E-30 | PL1.5*2438 | 1175 | SS400(Galv.) | 1 |  | 1 | 5.9 | 5.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 4.5 |  |  |  |  | Hot Dip Galvanized | 2.25 | [7 empty] | Hot Dip Galvanized | 2.25 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
105 | V17566-SKXD-7181 | EX-32 | EXPANDED METAL |  |  | (1153x196x1654) |  |  |  | 1 |  | 4.7 | 4.7 | AMC2 | [7 empty] | 0 | 0.33333 |  |  |  |  | 3.6 |  | x | o | [21 empty] | PAC
106 | V17566-SKXD-7181 | EX-32 | 3/4 NO.16 Exp.Metal | E-34 | EX-32-E-34 | PL1.5*1654 | 1175 | SS400(Galv.) | 1 |  | 1 | 4.5 | 4.5 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.5 |  |  |  |  | Hot Dip Galvanized | 1.75 | [7 empty] | Hot Dip Galvanized | 1.75 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
107 | V17566-SKXD-7181 | EX-32 | RUBBER SEAL TRIP | M-7 | EX-32-M-7 | PL10*10 | 762 | RUBBER | 2 |  | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | 0.1 |  |  |  |  | No paint | [8 empty] | No paint | [10 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
108 | V17566-SKXD-7182 | EX-33 | EXPANDED METAL |  |  | (1153x196x1654) |  |  |  | 1 |  | 2.3 | 2.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.8 |  | x | o | [21 empty] | PAC
109 | V17566-SKXD-7182 | EX-33 | 3/4 NO.16 Exp.Metal | E-33 | EX-33-E-33 | PL1.5*1654 | 1174 | SS400(Galv.) | 1 |  | 1 | 2.3 | 2.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.8 |  |  |  |  | Hot Dip Galvanized | 0.9 | [7 empty] | Hot Dip Galvanized | 0.9 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
110 | V17566-SKXD-7183 | EX-34 | EXPANDED METAL |  |  | (1153x196x1654) |  |  |  | 1 |  | 2.1 | 2.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 1.6 |  | x | o | [21 empty] | PAC
111 | V17566-SKXD-7183 | EX-34 | 3/4 NO.16 Exp.Metal | E-32 | EX-34-E-32 | PL1.5*1654 | 1175 | SS400(Galv.) | 1 |  | 1 | 2.1 | 2.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 1.6 |  |  |  |  | Hot Dip Galvanized | 0.8 | [7 empty] | Hot Dip Galvanized | 0.8 | [9 empty] | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
112 | V17566-SKXD-7034 | FR-1 | FRAME |  |  | (25304x366x1373) |  |  |  | 1 |  | 8915.1 | 8915.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 157 |  | x | o | [21 empty] | PAC
113 | V17566-SKXD-7034 | FR-1 | ANGLE | A-3 | FR-1-A-3 | L100*100*10 | 24396 | SS400 | 1 |  | 1 | 363.9 | 363.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 9.5 |  |  |  | 75 | Greenish Grey, Grey | 4.75 | [6 empty] | 75 | Greenish Grey, Grey | 4.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
114 | V17566-SKXD-7034 | FR-1 | H BUILT-UP | BH-1 | FR-1-BH-1 | BH900*350*19*25 | 25298 | SS400 | 1 |  | 1 | 6682.6 | 6682.6 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 80.1 |  |  |  | 75 | Greenish Grey, Grey | 40.05 | [6 empty] | 75 | Greenish Grey, Grey | 40.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication
115 | V17566-SKXD-7034 | FR-1 | PLATE | P-3 | FR-1-P-3 | PL6*166 | 850 | SS400 | 2 |  | 2 | 6.6 | 13.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
116 | V17566-SKXD-7034 | FR-1 | PLATE | P-4 | FR-1-P-4 | PL6*956 | 24384 | SS400 | 1 |  | 1 | 1098 | 1098 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 46.9 |  |  |  | 75 | Greenish Grey, Grey | 23.45 | [6 empty] | 75 | Greenish Grey, Grey | 23.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
117 | V17566-SKXD-7034 | FR-1 | PLATE | P-7 | FR-1-P-7 | PL6*131 | 135 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
118 | V17566-SKXD-7034 | FR-1 | PLATE | P-15 | FR-1-P-15 | PL10*378 | 25298 | SS400 | 1 |  | 1 | 750.7 | 750.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 19.6 |  |  |  | 75 | Greenish Grey, Grey | 9.8 | [6 empty] | 75 | Greenish Grey, Grey | 9.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
119 | V17566-SKXD-7034 | FR-1 | PLATE | P-19 | FR-1-P-19 | PL6*200 | 200 | SS400 | 6 |  | 6 | 1.1 | 6.3 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
120 | V17566-SKXD-7035 | FR-2 | FRAME |  |  | (13722x366x1366) |  |  |  | 1 |  | 4806.6 | 4806.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 84.1 |  | x | o | [21 empty] | PAC
121 | V17566-SKXD-7035 | FR-2 | ANGLE | A-9 | FR-2-A-9 | L100*100*10 | 12814 | SS400 | 1 |  | 1 | 191.1 | 191.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 5 |  |  |  | 75 | Greenish Grey, Grey | 2.5 | [6 empty] | 75 | Greenish Grey, Grey | 2.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
122 | V17566-SKXD-7035 | FR-2 | H BUILT-UP | BH-2 | FR-2-BH-2 | BH900*350*19*25 | 13716 | SS400 | 1 |  | 1 | 3623.1 | 3623.1 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 43.4 |  |  |  | 75 | Greenish Grey, Grey | 21.7 | [6 empty] | 75 | Greenish Grey, Grey | 21.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication
123 | V17566-SKXD-7035 | FR-2 | PLATE | P-3 | FR-2-P-3 | PL6*166 | 850 | SS400 | 2 |  | 2 | 6.6 | 13.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
124 | V17566-SKXD-7035 | FR-2 | PLATE | P-7 | FR-2-P-7 | PL6*131 | 135 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
125 | V17566-SKXD-7035 | FR-2 | PLATE | P-8 | FR-2-P-8 | PL10*378 | 13716 | SS400 | 1 |  | 1 | 407 | 407 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 10.7 |  |  |  | 75 | Greenish Grey, Grey | 5.35 | [6 empty] | 75 | Greenish Grey, Grey | 5.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
126 | V17566-SKXD-7035 | FR-2 | PLATE | P-10 | FR-2-P-10 | PL6*943 | 12802 | SS400 | 1 |  | 1 | 568.6 | 568.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 24.3 |  |  |  | 75 | Greenish Grey, Grey | 12.15 | [6 empty] | 75 | Greenish Grey, Grey | 12.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
127 | V17566-SKXD-7035 | FR-2 | PLATE | P-19 | FR-2-P-19 | PL6*200 | 200 | SS400 | 3 |  | 3 | 1.1 | 3.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
128 | V17566-SKXD-7036 | FR-3 | FRAME |  |  | (25304x366x1373) |  |  |  | 1 |  | 8915.1 | 8915.1 | AMC2 | [7 empty] | 0 | 0.84615 |  |  |  |  | 157 |  | x | o | [21 empty] | PAC
129 | V17566-SKXD-7036 | FR-3 | ANGLE | A-3 | FR-3-A-3 | L100*100*10 | 24396 | SS400 | 1 |  | 1 | 363.9 | 363.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 9.5 |  |  |  | 75 | Greenish Grey, Grey | 4.75 | [6 empty] | 75 | Greenish Grey, Grey | 4.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
130 | V17566-SKXD-7036 | FR-3 | H BUILT-UP | BH-1 | FR-3-BH-1 | BH900*350*19*25 | 25298 | SS400 | 1 |  | 1 | 6682.6 | 6682.6 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 80.1 |  |  |  | 75 | Greenish Grey, Grey | 40.05 | [6 empty] | 75 | Greenish Grey, Grey | 40.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication
131 | V17566-SKXD-7036 | FR-3 | PLATE | P-3 | FR-3-P-3 | PL6*166 | 850 | SS400 | 2 |  | 2 | 6.6 | 13.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
132 | V17566-SKXD-7036 | FR-3 | PLATE | P-4 | FR-3-P-4 | PL6*956 | 24384 | SS400 | 1 |  | 1 | 1098 | 1098 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 46.9 |  |  |  | 75 | Greenish Grey, Grey | 23.45 | [6 empty] | 75 | Greenish Grey, Grey | 23.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
133 | V17566-SKXD-7036 | FR-3 | PLATE | P-7 | FR-3-P-7 | PL6*131 | 135 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
134 | V17566-SKXD-7036 | FR-3 | PLATE | P-15 | FR-3-P-15 | PL10*378 | 25298 | SS400 | 1 |  | 1 | 750.7 | 750.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 19.6 |  |  |  | 75 | Greenish Grey, Grey | 9.8 | [6 empty] | 75 | Greenish Grey, Grey | 9.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
135 | V17566-SKXD-7036 | FR-3 | PLATE | P-19 | FR-3-P-19 | PL6*200 | 200 | SS400 | 6 |  | 6 | 1.1 | 6.3 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
136 | V17566-SKXD-7037 | FR-4 | FRAME |  |  | (13722x366x1366) |  |  |  | 1 |  | 4806.6 | 4806.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 84.1 |  | x | o | [21 empty] | PAC
137 | V17566-SKXD-7037 | FR-4 | ANGLE | A-9 | FR-4-A-9 | L100*100*10 | 12814 | SS400 | 1 |  | 1 | 191.1 | 191.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 5 |  |  |  | 75 | Greenish Grey, Grey | 2.5 | [6 empty] | 75 | Greenish Grey, Grey | 2.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
138 | V17566-SKXD-7037 | FR-4 | H BUILT-UP | BH-2 | FR-4-BH-2 | BH900*350*19*25 | 13716 | SS400 | 1 |  | 1 | 3623.1 | 3623.1 | AMC2 | Shape | WTC |  |  | 1 | 0 | 1 | [6 empty] | 43.4 |  |  |  | 75 | Greenish Grey, Grey | 21.7 | [6 empty] | 75 | Greenish Grey, Grey | 21.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Fabrication
139 | V17566-SKXD-7037 | FR-4 | PLATE | P-3 | FR-4-P-3 | PL6*166 | 850 | SS400 | 2 |  | 2 | 6.6 | 13.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
140 | V17566-SKXD-7037 | FR-4 | PLATE | P-7 | FR-4-P-7 | PL6*131 | 135 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
141 | V17566-SKXD-7037 | FR-4 | PLATE | P-8 | FR-4-P-8 | PL10*378 | 13716 | SS400 | 1 |  | 1 | 407 | 407 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 10.7 |  |  |  | 75 | Greenish Grey, Grey | 5.35 | [6 empty] | 75 | Greenish Grey, Grey | 5.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
142 | V17566-SKXD-7037 | FR-4 | PLATE | P-10 | FR-4-P-10 | PL6*943 | 12802 | SS400 | 1 |  | 1 | 568.6 | 568.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 24.3 |  |  |  | 75 | Greenish Grey, Grey | 12.15 | [6 empty] | 75 | Greenish Grey, Grey | 12.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
143 | V17566-SKXD-7037 | FR-4 | PLATE | P-19 | FR-4-P-19 | PL6*200 | 200 | SS400 | 3 |  | 3 | 1.1 | 3.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
144 | V17566-SKXD-7038 | FR-5 | FRAME |  |  | (1002x106x4886) |  |  |  | 2 |  | 151.3 | 302.7 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 10.6 |  | x | o | [21 empty] | PAC
145 | V17566-SKXD-7038 | FR-5 | ANGLE | A-2 | FR-5-A-2 | L100*100*10 | 4886 | SS400 | 1 |  | 2 | 72.9 | 145.8 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 3.8 |  |  |  | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
146 | V17566-SKXD-7038 | FR-5 | PLATE | P-5 | FR-5-P-5 | PL6*964 | 4674 | SS400 | 1 |  | 2 | 78.4 | 156.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 6.8 |  |  |  | 75 | Greenish Grey, Grey | 3.4 | [6 empty] | 75 | Greenish Grey, Grey | 3.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
147 | V17566-SKXD-7039 | FR-6 | FRAME |  |  | (995x106x4886) |  |  |  | 2 |  | 148.5 | 296.9 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 10.4 |  | x | o | [21 empty] | PAC
148 | V17566-SKXD-7039 | FR-6 | ANGLE | A-2 | FR-6-A-2 | L100*100*10 | 4886 | SS400 | 1 |  | 2 | 72.9 | 145.8 | AMC2 | Shape | MCC |  |  | 2 | 0 | 2 | [6 empty] | 3.8 |  |  |  | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
149 | V17566-SKXD-7039 | FR-6 | PLATE | P-9 | FR-6-P-9 | PL6*951 | 4674 | SS400 | 1 |  | 2 | 75.6 | 151.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 6.6 |  |  |  | 75 | Greenish Grey, Grey | 3.3 | [6 empty] | 75 | Greenish Grey, Grey | 3.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
150 | V17566-SKXD-7040 | LS-1 | LOOSE PART |  |  | (519x170x150) |  |  |  | 7 |  | 13.9 | 97.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.1 |  | x | o | [21 empty] | PAC
151 | V17566-SKXD-7040 | LS-1 | ANGLE | AFY-57 | LS-1-AFY-57 | L150*150*12 | 511 | SS400 | 1 |  | 7 | 13.9 | 97.6 | AMC2 | Shape | PMC |  |  | 7 | 0 | 7 | [5 empty] | Loose Part | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
152 | V17566-SKXD-7041 | LS-2 | LOOSE PART |  |  | (519x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
153 | V17566-SKXD-7041 | LS-2 | ANGLE | AFY-27 | LS-2-AFY-27 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
154 | V17566-SKXD-7042 | LS-3 | LOOSE PART |  |  | (521x150x170) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
155 | V17566-SKXD-7042 | LS-3 | ANGLE | AFY-25 | LS-3-AFY-25 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
156 | V17566-SKXD-7043 | LS-4 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
157 | V17566-SKXD-7043 | LS-4 | ANGLE | AFY-23 | LS-4-AFY-23 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
158 | V17566-SKXD-7044 | LS-5 | LOOSE PART |  |  | (521x150x170) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
159 | V17566-SKXD-7044 | LS-5 | ANGLE | AFY-4 | LS-5-AFY-4 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
160 | V17566-SKXD-7045 | LS-6 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
161 | V17566-SKXD-7045 | LS-6 | ANGLE | AFY-2 | LS-6-AFY-2 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
162 | V17566-SKXD-7046 | LS-7 | LOOSE PART |  |  | (524x220x200) |  |  |  | 1 |  | 37.8 | 37.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
163 | V17566-SKXD-7046 | LS-7 | ANGLE | AFY-16 | LS-7-AFY-16 | L200*200*25 | 514 | SS400 | 1 |  | 1 | 37.8 | 37.8 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
164 | V17566-SKXD-7047 | LS-8 | LOOSE PART |  |  | (519x170x150) |  |  |  | 1 |  | 13.9 | 13.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
165 | V17566-SKXD-7047 | LS-8 | ANGLE | AFY-6 | LS-8-AFY-6 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
166 | V17566-SKXD-7048 | LS-9 | LOOSE PART |  |  | (519x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
167 | V17566-SKXD-7048 | LS-9 | ANGLE | AFY-42 | LS-9-AFY-42 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
168 | V17566-SKXD-7049 | LS-10 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
169 | V17566-SKXD-7049 | LS-10 | ANGLE | AFY-48 | LS-10-AFY-48 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
170 | V17566-SKXD-7050 | LS-11 | LOOSE PART |  |  | (521x150x170) |  |  |  | 1 |  | 13.9 | 13.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
171 | V17566-SKXD-7050 | LS-11 | ANGLE | AFY-40 | LS-11-AFY-40 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
172 | V17566-SKXD-7051 | LS-12 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
173 | V17566-SKXD-7051 | LS-12 | CHANNEL | CFY-2 | LS-12-CFY-2 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
174 | V17566-SKXD-7052 | LS-13 | LOOSE PART |  |  | (518x150x130) |  |  |  | 1 |  | 9.1 | 9.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
175 | V17566-SKXD-7052 | LS-13 | ANGLE | AFY-63 | LS-13-AFY-63 | L130*130*9 | 509 | SS400 | 1 |  | 1 | 9.1 | 9.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
176 | V17566-SKXD-7053 | LS-14 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
177 | V17566-SKXD-7053 | LS-14 | CHANNEL | CFY-12 | LS-14-CFY-12 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
178 | V17566-SKXD-7054 | LS-15 | LOOSE PART |  |  | (519x170x150) |  |  |  | 7 |  | 13.9 | 97.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.1 |  | x | o | [21 empty] | PAC
179 | V17566-SKXD-7054 | LS-15 | ANGLE | AFY-53 | LS-15-AFY-53 | L150*150*12 | 511 | SS400 | 1 |  | 7 | 13.9 | 97.6 | AMC2 | Shape | PMC |  |  | 7 | 0 | 7 | [5 empty] | Loose Part | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
180 | V17566-SKXD-7055 | LS-16 | LOOSE PART |  |  | (518x217x208) |  |  |  | 1 |  | 10.9 | 10.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
181 | V17566-SKXD-7055 | LS-16 | ANGLE | AFY-59 | LS-16-AFY-59 | L130*130*9 | 509 | SS400 | 1 |  | 1 | 9.1 | 9.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
182 | V17566-SKXD-7055 | LS-16 | PLATE | G-7 | LS-16-G-7 | PL10*126 | 211 | SS400 | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
183 | V17566-SKXD-7056 | LS-17 | LOOSE PART |  |  | (511x177x200) |  |  |  | 1 |  | 14.4 | 14.4 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
184 | V17566-SKXD-7056 | LS-17 | CHANNEL | CFY-8 | LS-17-CFY-8 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
185 | V17566-SKXD-7056 | LS-17 | PLATE | G-8 | LS-17-G-8 | PL10*152 | 161 | SS400 | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
186 | V17566-SKXD-7057 | LS-18 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
187 | V17566-SKXD-7057 | LS-18 | ANGLE | AFY-13 | LS-18-AFY-13 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
188 | V17566-SKXD-7058 | LS-19 | LOOSE PART |  |  | (524x220x200) |  |  |  | 1 |  | 37.8 | 37.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
189 | V17566-SKXD-7058 | LS-19 | ANGLE | AFY-21 | LS-19-AFY-21 | L200*200*25 | 514 | SS400 | 1 |  | 1 | 37.8 | 37.8 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
190 | V17566-SKXD-7059 | LS-20 | LOOSE PART |  |  | (519x170x150) |  |  |  | 1 |  | 13.9 | 13.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
191 | V17566-SKXD-7059 | LS-20 | ANGLE | AFY-14 | LS-20-AFY-14 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
192 | V17566-SKXD-7060 | LS-21 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
193 | V17566-SKXD-7060 | LS-21 | ANGLE | AFY-50 | LS-21-AFY-50 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
194 | V17566-SKXD-7061 | LS-22 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
195 | V17566-SKXD-7061 | LS-22 | CHANNEL | CFY-6 | LS-22-CFY-6 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
196 | V17566-SKXD-7062 | LS-23 | LOOSE PART |  |  | (519x170x150) |  |  |  | 7 |  | 13.9 | 97.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.1 |  | x | o | [21 empty] | PAC
197 | V17566-SKXD-7062 | LS-23 | ANGLE | AFY-56 | LS-23-AFY-56 | L150*150*12 | 511 | SS400 | 1 |  | 7 | 13.9 | 97.6 | AMC2 | Shape | PMC |  |  | 7 | 0 | 7 | [5 empty] | Loose Part | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
198 | V17566-SKXD-7063 | LS-24 | LOOSE PART |  |  | (519x170x150) |  |  |  | 1 |  | 13.9 | 13.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
199 | V17566-SKXD-7063 | LS-24 | ANGLE | AFY-37 | LS-24-AFY-37 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
200 | V17566-SKXD-7064 | LS-25 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
201 | V17566-SKXD-7064 | LS-25 | ANGLE | AFY-36 | LS-25-AFY-36 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
202 | V17566-SKXD-7065 | LS-26 | LOOSE PART |  |  | (521x150x170) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
203 | V17566-SKXD-7065 | LS-26 | ANGLE | AFY-8 | LS-26-AFY-8 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
204 | V17566-SKXD-7066 | LS-27 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
205 | V17566-SKXD-7066 | LS-27 | ANGLE | AFY-7 | LS-27-AFY-7 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
206 | V17566-SKXD-7067 | LS-28 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
207 | V17566-SKXD-7067 | LS-28 | ANGLE | AFY-45 | LS-28-AFY-45 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
208 | V17566-SKXD-7068 | LS-29 | LOOSE PART |  |  | (521x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
209 | V17566-SKXD-7068 | LS-29 | ANGLE | AFY-43 | LS-29-AFY-43 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
210 | V17566-SKXD-7069 | LS-30 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
211 | V17566-SKXD-7069 | LS-30 | CHANNEL | CFY-3 | LS-30-CFY-3 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
212 | V17566-SKXD-7070 | LS-31 | LOOSE PART |  |  | (518x227x208) |  |  |  | 1 |  | 10.9 | 10.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
213 | V17566-SKXD-7070 | LS-31 | ANGLE | AFY-62 | LS-31-AFY-62 | L130*130*9 | 509 | SS400 | 1 |  | 1 | 9.1 | 9.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
214 | V17566-SKXD-7070 | LS-31 | PLATE | G-7 | LS-31-G-7 | PL10*126 | 210 | SS400 | 1 |  | 1 | 1.8 | 1.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
215 | V17566-SKXD-7071 | LS-32 | LOOSE PART |  |  | (511x186x200) |  |  |  | 1 |  | 14.4 | 14.4 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
216 | V17566-SKXD-7071 | LS-32 | CHANNEL | CFY-11 | LS-32-CFY-11 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
217 | V17566-SKXD-7071 | LS-32 | PLATE | G-8 | LS-32-G-8 | PL10*152 | 161 | SS400 | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
218 | V17566-SKXD-7072 | LS-33 | LOOSE PART |  |  | (519x170x150) |  |  |  | 7 |  | 13.9 | 97.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.1 |  | x | o | [21 empty] | PAC
219 | V17566-SKXD-7072 | LS-33 | ANGLE | AFY-54 | LS-33-AFY-54 | L150*150*12 | 511 | SS400 | 1 |  | 7 | 13.9 | 97.6 | AMC2 | Shape | PMC |  |  | 7 | 0 | 7 | [5 empty] | Loose Part | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
220 | V17566-SKXD-7073 | LS-34 | LOOSE PART |  |  | (518x150x130) |  |  |  | 1 |  | 9.1 | 9.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
221 | V17566-SKXD-7073 | LS-34 | ANGLE | AFY-60 | LS-34-AFY-60 | L130*130*9 | 509 | SS400 | 1 |  | 1 | 9.1 | 9.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
222 | V17566-SKXD-7074 | LS-35 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
223 | V17566-SKXD-7074 | LS-35 | CHANNEL | CFY-9 | LS-35-CFY-9 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
224 | V17566-SKXD-7075 | LS-36 | LOOSE PART |  |  | (524x220x200) |  |  |  | 1 |  | 37.8 | 37.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
225 | V17566-SKXD-7075 | LS-36 | ANGLE | AFY-20 | LS-36-AFY-20 | L200*200*25 | 514 | SS400 | 1 |  | 1 | 37.8 | 37.8 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
226 | V17566-SKXD-7076 | LS-37 | LOOSE PART |  |  | (519x170x150) |  |  |  | 1 |  | 13.9 | 13.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
227 | V17566-SKXD-7076 | LS-37 | ANGLE | AFY-12 | LS-37-AFY-12 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
228 | V17566-SKXD-7077 | LS-38 | LOOSE PART |  |  | (511x183x200) |  |  |  | 1 |  | 14.4 | 14.4 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
229 | V17566-SKXD-7077 | LS-38 | CHANNEL | CFY-5 | LS-38-CFY-5 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
230 | V17566-SKXD-7077 | LS-38 | PLATE | G-4 | LS-38-G-4 | PL10*152 | 162 | SS400 | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
231 | V17566-SKXD-7078 | LS-39 | LOOSE PART |  |  | (519x170x150) |  |  |  | 7 |  | 13.9 | 97.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 2.1 |  | x | o | [21 empty] | PAC
232 | V17566-SKXD-7078 | LS-39 | ANGLE | AFY-55 | LS-39-AFY-55 | L150*150*12 | 511 | SS400 | 1 |  | 7 | 13.9 | 97.6 | AMC2 | Shape | PMC |  |  | 7 | 0 | 7 | [5 empty] | Loose Part | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
233 | V17566-SKXD-7079 | LS-40 | LOOSE PART |  |  | (519x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
234 | V17566-SKXD-7079 | LS-40 | ANGLE | AFY-35 | LS-40-AFY-35 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
235 | V17566-SKXD-7080 | LS-41 | LOOSE PART |  |  | (524x220x200) |  |  |  | 1 |  | 37.8 | 37.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
236 | V17566-SKXD-7080 | LS-41 | ANGLE | AFY-19 | LS-41-AFY-19 | L200*200*25 | 514 | SS400 | 1 |  | 1 | 37.8 | 37.8 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
237 | V17566-SKXD-7081 | LS-42 | LOOSE PART |  |  | (519x170x150) |  |  |  | 1 |  | 13.9 | 13.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
238 | V17566-SKXD-7081 | LS-42 | ANGLE | AFY-11 | LS-42-AFY-11 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
239 | V17566-SKXD-7082 | LS-43 | LOOSE PART |  |  | (519x170x150) |  |  |  | 2 |  | 13.9 | 27.9 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.6 |  | x | o | [21 empty] | PAC
240 | V17566-SKXD-7082 | LS-43 | ANGLE | AFY-47 | LS-43-AFY-47 | L150*150*12 | 511 | SS400 | 1 |  | 2 | 13.9 | 27.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
241 | V17566-SKXD-7083 | LS-44 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
242 | V17566-SKXD-7083 | LS-44 | CHANNEL | CFY-4 | LS-44-CFY-4 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
243 | V17566-SKXD-7084 | LS-45 | LOOSE PART |  |  | (518x150x130) |  |  |  | 1 |  | 9.1 | 9.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
244 | V17566-SKXD-7084 | LS-45 | ANGLE | AFY-61 | LS-45-AFY-61 | L130*130*9 | 509 | SS400 | 1 |  | 1 | 9.1 | 9.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
245 | V17566-SKXD-7085 | LS-46 | LOOSE PART |  |  | (511x100x200) |  |  |  | 1 |  | 12.4 | 12.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.3 |  | x | o | [21 empty] | PAC
246 | V17566-SKXD-7085 | LS-46 | CHANNEL | CFY-10 | LS-46-CFY-10 | [200*80*7.5*11 | 506 | SS400 | 1 |  | 1 | 12.4 | 12.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [5 empty] | Loose Part | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
247 | V17566-SKXD-7184 | LS-47 | LOOSE PART |  |  | (518x150x130) |  |  |  | 2 |  | 9.1 | 18.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | 0.5 |  | x | o | [21 empty] | PAC
248 | V17566-SKXD-7184 | LS-47 | ANGLE | AFY-64 | LS-47-AFY-64 | L130*130*9 | 510 | SS400 | 1 |  | 2 | 9.1 | 18.2 | AMC2 | Shape | PMC |  |  | 2 | 0 | 2 | [5 empty] | Loose Part | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
249 | V17566-SKXD-7185 | LS-48 | LOOSE PART |  |  | (521x360x241) |  |  |  | 1 |  | 17.7 | 17.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 0.4 |  | x | o | [21 empty] | PAC
250 | V17566-SKXD-7185 | LS-48 | ANGLE | AFY-40 | LS-48-AFY-40 | L150*150*12 | 511 | SS400 | 1 |  | 1 | 13.9 | 13.9 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
251 | V17566-SKXD-7185 | LS-48 | PLATE | G-1 | LS-48-G-1 | PL10*125 | 264 | SS400 | 1 |  | 1 | 2.3 | 2.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
252 | V17566-SKXD-7086 | PT-1 | PIPE BRACE |  |  | (4674x152x89) |  |  |  | 4 |  | 54.4 | 217.8 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 5.5 |  | x | o | [21 empty] | PAC
253 | V17566-SKXD-7086 | PT-1 | PIPE 3" STD | DY-1 | PT-1-DY-1 | CHS88.9*5.49 | 4574 | A106 Gr.B | 1 |  | 4 | 50.1 | 200.4 | AMC2 | Shape | MCC |  |  | 4 | 0 | 4 | [6 empty] | 5.1 |  |  |  | 75 | Greenish Grey, Grey | 2.55 | [6 empty] | 75 | Greenish Grey, Grey | 2.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
254 | V17566-SKXD-7086 | PT-1 | PLATE | P-6 | PT-1-P-6 | PL12*152 | 152 | SS400 | 2 |  | 8 | 2.2 | 17.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 4 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
255 | V17566-SKXD-7087 | PT-2 | PIPE BRACE |  |  | (6871x168x268) |  |  |  | 1 |  | 198.8 | 198.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 3.8 |  | x | o | [21 empty] | PAC
256 | V17566-SKXD-7087 | PT-2 | PIPE 6" STD | DY-3 | PT-2-DY-3 | CHS168.3*7.11 | 6771 | A53 GR.B | 1 |  | 1 | 188.7 | 188.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.6 |  |  |  | 75 | Greenish Grey, Grey | 1.8 | [6 empty] | 75 | Greenish Grey, Grey | 1.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
257 | V17566-SKXD-7087 | PT-2 | PLATE | P-16 | PT-2-P-16 | PL12*200 | 268 | SS400 | 2 |  | 2 | 5 | 10.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
258 | V17566-SKXD-7088 | PT-3 | PIPE BRACE |  |  | (6875x168x268) |  |  |  | 1 |  | 198.9 | 198.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 3.8 |  | x | o | [21 empty] | PAC
259 | V17566-SKXD-7088 | PT-3 | PIPE 6" STD | DY-2 | PT-3-DY-2 | CHS168.3*7.11 | 6775 | A53 GR.B | 1 |  | 1 | 188.8 | 188.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.6 |  |  |  | 75 | Greenish Grey, Grey | 1.8 | [6 empty] | 75 | Greenish Grey, Grey | 1.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
260 | V17566-SKXD-7088 | PT-3 | PLATE | P-16 | PT-3-P-16 | PL12*200 | 268 | SS400 | 2 |  | 2 | 5 | 10.1 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
261 | V17566-SKXD-7089 | SK1-1 | SHELL PLATE |  |  | (4921x7393x3436) |  |  |  | 1 |  | 6005.7 | 6005.7 | AMC2 | [7 empty] | 0 | 0.61165 |  |  |  |  | 99 |  | x | o | [21 empty] | PAC
262 | V17566-SKXD-7089 | SK1-1 | ANGLE | A-33 | SK1-1-A-33 | L75*75*6 | 1654 | SS400 | 10 |  | 10 | 11.3 | 113.3 | AMC2 | Shape | MCC |  |  | 10 | 0 | 1 | [6 empty] | 4.8 |  |  |  | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
263 | V17566-SKXD-7089 | SK1-1 | PLATE | G-12 | SK1-1-G-12 | PL10*51 | 102 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
264 | V17566-SKXD-7089 | SK1-1 | PLATE | G-13 | SK1-1-G-13 | PL55*406 | 762 | SM490 | 1 |  | 1 | 125.5 | 125.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
265 | V17566-SKXD-7089 | SK1-1 | BASE PLATE | GY-1 | SK1-1-GY-1 | PL45*564 | 1918 | SS400 | 4 |  | 4 | 200.7 | 802.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 5.3 |  |  |  | 75 | Greenish Grey, Grey | 2.65 | [6 empty] | 75 | Greenish Grey, Grey | 2.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
266 | V17566-SKXD-7089 | SK1-1 | BASE PLATE | GY-2 | SK1-1-GY-2 | PL45*564 | 1918 | SS400 | 1 |  | 1 | 200.1 | 200.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
267 | V17566-SKXD-7089 | SK1-1 | BASE PLATE | GY-3 | SK1-1-GY-3 | PL45*533 | 1938 | SS400 | 4 |  | 4 | 179 | 715.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 4.8 |  |  |  | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
268 | V17566-SKXD-7089 | SK1-1 | BASE PLATE | GY-4 | SK1-1-GY-4 | PL45*533 | 1938 | SS400 | 1 |  | 1 | 178.4 | 178.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 |  |  |  | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
269 | V17566-SKXD-7089 | SK1-1 | BASE PLATE | GY-5 | SK1-1-GY-5 | PL45*533 | 1938 | SS400 | 1 |  | 1 | 177.9 | 177.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 |  |  |  | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
270 | V17566-SKXD-7089 | SK1-1 | BASE PLATE | GY-7 | SK1-1-GY-7 | PL45*564 | 1918 | SS400 | 1 |  | 1 | 200.1 | 200.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
271 | V17566-SKXD-7089 | SK1-1 | PLATE | P-14 | SK1-1-P-14 | PL8*225 | 520 | SS400 | 36 |  | 36 | 7.3 | 264.1 | AMC2 | Plate | MCC |  |  | 36 | 0 | 1 | [6 empty] | 8.8 |  |  |  | 75 | Greenish Grey, Grey | 4.4 | [6 empty] | 75 | Greenish Grey, Grey | 4.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
272 | V17566-SKXD-7089 | SK1-1 | PLATE | P-18 | SK1-1-P-18 | PL6*51 | 76 | SS400 | 40 |  | 40 | 0.2 | 7.3 | AMC2 | Plate | MCC |  |  | 0 | 40 | 0 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
273 | V17566-SKXD-7089 | SK1-1 | PLATE | PF-6 | SK1-1-PF-6 | PL12*508 | 508 | SS400 | 1 |  | 1 | 23.8 | 23.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
274 | V17566-SKXD-7089 | SK1-1 | SHELL PLATE | SH-50 | SK1-1-SH-50 | PL12*2000 | 11027 | SS400 | 1 |  | 1 | 2075.8 | 2075.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 44.4 |  |  |  | 75 | Greenish Grey, Grey | 22.2 | [6 empty] | 75 | Greenish Grey, Grey | 22.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
275 | V17566-SKXD-7089 | SK1-1 | SHELL PLATE | SH-51 | SK1-1-SH-51 | PL12*1082.6 | 11027 | SS400 | 1 |  | 1 | 1120.5 | 1120.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 24.1 |  |  |  | 75 | Greenish Grey, Grey | 12.05 | [6 empty] | 75 | Greenish Grey, Grey | 12.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
276 | V17566-SKXD-7093 | SK1-2 | SHELL PLATE |  |  | (4921x7393x3436) |  |  |  | 1 |  | 6164 | 6164 | AMC2 | [7 empty] | 0 | 0.62385 |  |  |  |  | 100.7 |  | x | o | [21 empty] | PAC
277 | V17566-SKXD-7093 | SK1-2 | ANGLE | A-33 | SK1-2-A-33 | L75*75*6 | 1654 | SS400 | 9 |  | 9 | 11.3 | 102 | AMC2 | Shape | MCC |  |  | 9 | 0 | 1 | [6 empty] | 4.4 |  |  |  | 75 | Greenish Grey, Grey | 2.2 | [6 empty] | 75 | Greenish Grey, Grey | 2.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
278 | V17566-SKXD-7093 | SK1-2 | ANGLE | A-34 | SK1-2-A-34 | L75*75*6 | 127 | SS400 | 1 |  | 1 | 0.9 | 0.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
279 | V17566-SKXD-7093 | SK1-2 | ANGLE | A-35 | SK1-2-A-35 | L75*75*6 | 168 | SS400 | 2 |  | 2 | 1.1 | 2.3 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
280 | V17566-SKXD-7093 | SK1-2 | PLATE | G-12 | SK1-2-G-12 | PL10*51 | 102 | SS400 | 1 |  | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
281 | V17566-SKXD-7093 | SK1-2 | PLATE | G-13 | SK1-2-G-13 | PL55*406 | 762 | SM490 | 1 |  | 1 | 125.5 | 125.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
282 | V17566-SKXD-7093 | SK1-2 | PAD PLATE | GF-1 | SK1-2-GF-1 | PL19*1346.1 | 1358 | SS400 | 1 |  | 1 | 157.3 | 157.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.2 |  |  |  | 75 | Greenish Grey, Grey | 1.1 | [6 empty] | 75 | Greenish Grey, Grey | 1.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
283 | V17566-SKXD-7093 | SK1-2 | BASE PLATE | GY-1 | SK1-2-GY-1 | PL45*564 | 1918 | SS400 | 4 |  | 4 | 200.7 | 802.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 5.3 |  |  |  | 75 | Greenish Grey, Grey | 2.65 | [6 empty] | 75 | Greenish Grey, Grey | 2.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
284 | V17566-SKXD-7093 | SK1-2 | BASE PLATE | GY-3 | SK1-2-GY-3 | PL45*533 | 1938 | SS400 | 4 |  | 4 | 179 | 715.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 4.8 |  |  |  | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
285 | V17566-SKXD-7093 | SK1-2 | BASE PLATE | GY-5 | SK1-2-GY-5 | PL45*533 | 1938 | SS400 | 1 |  | 1 | 177.9 | 177.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 |  |  |  | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
286 | V17566-SKXD-7093 | SK1-2 | BASE PLATE | GY-6 | SK1-2-GY-6 | PL45*564 | 1918 | SS400 | 1 |  | 1 | 200.1 | 200.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
287 | V17566-SKXD-7093 | SK1-2 | BASE PLATE | GY-7 | SK1-2-GY-7 | PL45*564 | 1918 | SS400 | 1 |  | 1 | 200.1 | 200.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
288 | V17566-SKXD-7093 | SK1-2 | BASE PLATE | GY-8 | SK1-2-GY-8 | PL45*533 | 1938 | SS400 | 1 |  | 1 | 178.4 | 178.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 |  |  |  | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
289 | V17566-SKXD-7093 | SK1-2 | PLATE | P-14 | SK1-2-P-14 | PL8*225 | 520 | SS400 | 36 |  | 36 | 7.3 | 264.1 | AMC2 | Plate | MCC |  |  | 36 | 0 | 1 | [6 empty] | 8.8 |  |  |  | 75 | Greenish Grey, Grey | 4.4 | [6 empty] | 75 | Greenish Grey, Grey | 4.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
290 | V17566-SKXD-7093 | SK1-2 | PLATE | P-18 | SK1-2-P-18 | PL6*51 | 76 | SS400 | 41 |  | 41 | 0.2 | 7.5 | AMC2 | Plate | MCC |  |  | 0 | 41 | 0 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
291 | V17566-SKXD-7093 | SK1-2 | BEND PLATE | PF-1 | SK1-2-PF-1 | SPD635*12 | 203 | SS400 | 1 |  | 1 | 37.3 | 37.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
292 | V17566-SKXD-7093 | SK1-2 | PLATE | PF-6 | SK1-2-PF-6 | PL12*508 | 508 | SS400 | 1 |  | 1 | 23.8 | 23.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
293 | V17566-SKXD-7093 | SK1-2 | ROUND BAR | RX-1 | SK1-2-RX-1 | D19 | 535 | SS400 | 1 |  | 1 | 1.1 | 1.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
294 | V17566-SKXD-7093 | SK1-2 | SHELL PLATE | SH-52 | SK1-2-SH-52 | PL12*1082.6 | 11027 | SS400 | 1 |  | 1 | 1123.9 | 1123.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 24.2 |  |  |  | 75 | Greenish Grey, Grey | 12.1 | [6 empty] | 75 | Greenish Grey, Grey | 12.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
295 | V17566-SKXD-7093 | SK1-2 | SHELL PLATE | SH-53 | SK1-2-SH-53 | PL12*2000 | 11027 | SS400 | 1 |  | 1 | 2042.9 | 2042.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 43.7 |  |  |  | 75 | Greenish Grey, Grey | 21.85 | [6 empty] | 75 | Greenish Grey, Grey | 21.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
296 | V17566-SKXD-7098 | SK2-1 | SHELL PLATE |  |  | (3534x2485x6582) |  |  |  | 1 |  | 3345.8 | 3345.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 68.6 |  | x | o | [21 empty] | PAC
297 | V17566-SKXD-7098 | SK2-1 | ANGLE | AFY-1 | SK2-1-AFY-1 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
298 | V17566-SKXD-7098 | SK2-1 | ANGLE | AFY-3 | SK2-1-AFY-3 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
299 | V17566-SKXD-7098 | SK2-1 | ANGLE | AFY-5 | SK2-1-AFY-5 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
300 | V17566-SKXD-7098 | SK2-1 | ANGLE | AFY-15 | SK2-1-AFY-15 | L200*200*25 | 4031 | SS400 | 1 |  | 1 | 296.7 | 296.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.2 |  |  |  | 75 | Greenish Grey, Grey | 1.6 | [6 empty] | 75 | Greenish Grey, Grey | 1.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
301 | V17566-SKXD-7098 | SK2-1 | SHELL PLATE | SH-17 | SK2-1-SH-17 | PL12*1000 | 4405.5 | SS400 | 1 |  | 1 | 413.6 | 413.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.9 |  |  |  | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
302 | V17566-SKXD-7098 | SK2-1 | SHELL PLATE | SH-18 | SK2-1-SH-18 | PL12*2000 | 4405.5 | SS400 | 1 |  | 1 | 828.5 | 828.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.8 |  |  |  | 75 | Greenish Grey, Grey | 8.9 | [6 empty] | 75 | Greenish Grey, Grey | 8.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
303 | V17566-SKXD-7098 | SK2-1 | SHELL PLATE | SH-19 | SK2-1-SH-19 | PL12*1873 | 4405.5 | SS400 | 1 |  | 1 | 775.8 | 775.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 16.6 |  |  |  | 75 | Greenish Grey, Grey | 8.3 | [6 empty] | 75 | Greenish Grey, Grey | 8.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
304 | V17566-SKXD-7098 | SK2-1 | SHELL PLATE | SH-20 | SK2-1-SH-20 | PL12*1700 | 4405.5 | SS400 | 1 |  | 1 | 703.4 | 703.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 15.1 |  |  |  | 75 | Greenish Grey, Grey | 7.55 | [6 empty] | 75 | Greenish Grey, Grey | 7.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
305 | V17566-SKXD-7102 | SK2-2 | SHELL PLATE |  |  | (3534x2485x6582) |  |  |  | 1 |  | 3345.9 | 3345.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 68.6 |  | x | o | [21 empty] | PAC
306 | V17566-SKXD-7102 | SK2-2 | ANGLE | AFY-1 | SK2-2-AFY-1 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
307 | V17566-SKXD-7102 | SK2-2 | ANGLE | AFY-3 | SK2-2-AFY-3 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
308 | V17566-SKXD-7102 | SK2-2 | ANGLE | AFY-5 | SK2-2-AFY-5 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
309 | V17566-SKXD-7102 | SK2-2 | ANGLE | AFY-15 | SK2-2-AFY-15 | L200*200*25 | 4031 | SS400 | 1 |  | 1 | 296.7 | 296.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.2 |  |  |  | 75 | Greenish Grey, Grey | 1.6 | [6 empty] | 75 | Greenish Grey, Grey | 1.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
310 | V17566-SKXD-7102 | SK2-2 | SHELL PLATE | SH-18 | SK2-2-SH-18 | PL12*2000 | 4405.5 | SS400 | 2 |  | 2 | 828.5 | 1657 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 35.5 |  |  |  | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
311 | V17566-SKXD-7102 | SK2-2 | SHELL PLATE | SH-29 | SK2-2-SH-29 | PL12*1700 | 4405.5 | SS400 | 1 |  | 1 | 704 | 704 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 15.1 |  |  |  | 75 | Greenish Grey, Grey | 7.55 | [6 empty] | 75 | Greenish Grey, Grey | 7.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
312 | V17566-SKXD-7102 | SK2-2 | SHELL PLATE | SH-30 | SK2-2-SH-30 | PL12*873 | 4405.5 | SS400 | 1 |  | 1 | 360.3 | 360.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 7.8 |  |  |  | 75 | Greenish Grey, Grey | 3.9 | [6 empty] | 75 | Greenish Grey, Grey | 3.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
313 | V17566-SKXD-7106 | SK2-3 | SHELL PLATE |  |  | (3534x2435x6582) |  |  |  | 1 |  | 2145.7 | 2145.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 45 |  | x | o | [21 empty] | PAC
314 | V17566-SKXD-7106 | SK2-3 | ANGLE | AFY-1 | SK2-3-AFY-1 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
315 | V17566-SKXD-7106 | SK2-3 | ANGLE | AFY-3 | SK2-3-AFY-3 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
316 | V17566-SKXD-7106 | SK2-3 | ANGLE | AFY-10 | SK2-3-AFY-10 | L150*150*12 | 1570 | SS400 | 1 |  | 1 | 42.8 | 42.8 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 |  |  |  | 75 | Greenish Grey, Grey | 0.45 | [6 empty] | 75 | Greenish Grey, Grey | 0.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
317 | V17566-SKXD-7106 | SK2-3 | ANGLE | AFY-18 | SK2-3-AFY-18 | L200*200*25 | 1633 | SS400 | 1 |  | 1 | 120.2 | 120.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
318 | V17566-SKXD-7106 | SK2-3 | PLATE | P-1 | SK2-3-P-1 | PL10*135 | 840 | SS400 | 2 |  | 2 | 8.6 | 17.3 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
319 | V17566-SKXD-7106 | SK2-3 | SHELL PLATE | SH-17 | SK2-3-SH-17 | PL12*1000 | 4405.5 | SS400 | 1 |  | 1 | 413.6 | 413.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.9 |  |  |  | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
320 | V17566-SKXD-7106 | SK2-3 | SHELL PLATE | SH-25 | SK2-3-SH-25 | PL12*2000 | 4405.5 | SS400 | 1 |  | 1 | 617.9 | 617.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
321 | V17566-SKXD-7106 | SK2-3 | SHELL PLATE | SH-26 | SK2-3-SH-26 | PL12*1873 | 2129.5 | SS400 | 1 |  | 1 | 375.2 | 375.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.1 |  |  |  | 75 | Greenish Grey, Grey | 4.05 | [6 empty] | 75 | Greenish Grey, Grey | 4.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
322 | V17566-SKXD-7106 | SK2-3 | SHELL PLATE | SH-27 | SK2-3-SH-27 | PL12*1700 | 2129.5 | SS400 | 1 |  | 1 | 340.2 | 340.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 7.3 |  |  |  | 75 | Greenish Grey, Grey | 3.65 | [6 empty] | 75 | Greenish Grey, Grey | 3.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
323 | V17566-SKXD-7110 | SK2-4 | SHELL PLATE |  |  | (3534x2485x6582) |  |  |  | 1 |  | 3345.8 | 3345.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 68.6 |  | x | o | [21 empty] | PAC
324 | V17566-SKXD-7110 | SK2-4 | ANGLE | AFY-1 | SK2-4-AFY-1 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
325 | V17566-SKXD-7110 | SK2-4 | ANGLE | AFY-3 | SK2-4-AFY-3 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
326 | V17566-SKXD-7110 | SK2-4 | ANGLE | AFY-5 | SK2-4-AFY-5 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
327 | V17566-SKXD-7110 | SK2-4 | ANGLE | AFY-15 | SK2-4-AFY-15 | L200*200*25 | 4031 | SS400 | 1 |  | 1 | 296.7 | 296.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.2 |  |  |  | 75 | Greenish Grey, Grey | 1.6 | [6 empty] | 75 | Greenish Grey, Grey | 1.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
328 | V17566-SKXD-7110 | SK2-4 | SHELL PLATE | SH-18 | SK2-4-SH-18 | PL12*2000 | 4405.5 | SS400 | 2 |  | 2 | 828.5 | 1657 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 35.5 |  |  |  | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
329 | V17566-SKXD-7110 | SK2-4 | SHELL PLATE | SH-21 | SK2-4-SH-21 | PL12*573 | 4405.5 | SS400 | 1 |  | 1 | 236.4 | 236.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.1 |  |  |  | 75 | Greenish Grey, Grey | 2.55 | [6 empty] | 75 | Greenish Grey, Grey | 2.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
330 | V17566-SKXD-7110 | SK2-4 | SHELL PLATE | SH-28 | SK2-4-SH-28 | PL12*2000 | 4405.5 | SS400 | 1 |  | 1 | 827.9 | 827.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
331 | V17566-SKXD-7114 | SK2-5 | SHELL PLATE |  |  | (3488x2485x6582) |  |  |  | 1 |  | 1856.1 | 1856.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 39.3 |  | x | o | [21 empty] | PAC
332 | V17566-SKXD-7114 | SK2-5 | ANGLE | AFY-1 | SK2-5-AFY-1 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
333 | V17566-SKXD-7114 | SK2-5 | ANGLE | AFY-3 | SK2-5-AFY-3 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
334 | V17566-SKXD-7114 | SK2-5 | ANGLE | AFY-9 | SK2-5-AFY-9 | L150*150*12 | 992 | SS400 | 1 |  | 1 | 27.1 | 27.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
335 | V17566-SKXD-7114 | SK2-5 | ANGLE | AFY-17 | SK2-5-AFY-17 | L200*200*25 | 1051 | SS400 | 1 |  | 1 | 77.4 | 77.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 |  |  |  | 75 | Greenish Grey, Grey | 0.4 | [6 empty] | 75 | Greenish Grey, Grey | 0.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
336 | V17566-SKXD-7114 | SK2-5 | PLATE | P-1 | SK2-5-P-1 | PL10*135 | 840 | SS400 | 3 |  | 3 | 8.6 | 25.9 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
337 | V17566-SKXD-7114 | SK2-5 | SHELL PLATE | SH-21 | SK2-5-SH-21 | PL12*573 | 4405.5 | SS400 | 1 |  | 1 | 236.4 | 236.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.1 |  |  |  | 75 | Greenish Grey, Grey | 2.55 | [6 empty] | 75 | Greenish Grey, Grey | 2.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
338 | V17566-SKXD-7114 | SK2-5 | SHELL PLATE | SH-22 | SK2-5-SH-22 | PL12*2000 | 4405.5 | SS400 | 1 |  | 1 | 680 | 680 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 14.6 |  |  |  | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
339 | V17566-SKXD-7114 | SK2-5 | SHELL PLATE | SH-23 | SK2-5-SH-23 | PL12*2000 | 1568 | SS400 | 1 |  | 1 | 295.5 | 295.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 6.4 |  |  |  | 75 | Greenish Grey, Grey | 3.2 | [6 empty] | 75 | Greenish Grey, Grey | 3.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
340 | V17566-SKXD-7114 | SK2-5 | SHELL PLATE | SH-24 | SK2-5-SH-24 | PL12*2000 | 1568 | SS400 | 1 |  | 1 | 295.4 | 295.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 6.4 |  |  |  | 75 | Greenish Grey, Grey | 3.2 | [6 empty] | 75 | Greenish Grey, Grey | 3.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
341 | V17566-SKXD-7118 | SK3-1 | SHELL PLATE |  |  | (3143x1815x12189) |  |  |  | 1 |  | 3894.5 | 3894.5 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 98.7 |  | x | o | [21 empty] | PAC
342 | V17566-SKXD-7118 | SK3-1 | ANGLE | AFY-29 | SK3-1-AFY-29 | L150*150*12 | 3186 | SS400 | 1 |  | 1 | 87 | 87 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 1.9 |  |  |  | 75 | Greenish Grey, Grey | 0.95 | [6 empty] | 75 | Greenish Grey, Grey | 0.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
343 | V17566-SKXD-7118 | SK3-1 | ANGLE | AFY-30 | SK3-1-AFY-30 | L150*150*12 | 3186 | SS400 | 1 |  | 1 | 87 | 87 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 1.9 |  |  |  | 75 | Greenish Grey, Grey | 0.95 | [6 empty] | 75 | Greenish Grey, Grey | 0.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
344 | V17566-SKXD-7118 | SK3-1 | ANGLE | AFY-31 | SK3-1-AFY-31 | L150*150*12 | 3186 | SS400 | 2 |  | 2 | 87 | 173.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 3.7 |  |  |  | 75 | Greenish Grey, Grey | 1.85 | [6 empty] | 75 | Greenish Grey, Grey | 1.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
345 | V17566-SKXD-7118 | SK3-1 | SHELL PLATE | SH-37 | SK3-1-SH-37 | PL10*1000 | 3714.5 | SS400 | 1 |  | 1 | 291.4 | 291.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 7.5 |  |  |  | 75 | Greenish Grey, Grey | 3.75 | [6 empty] | 75 | Greenish Grey, Grey | 3.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
346 | V17566-SKXD-7118 | SK3-1 | SHELL PLATE | SH-38 | SK3-1-SH-38 | PL10*2000 | 3714.5 | SS400 | 4 |  | 4 | 582.9 | 2331.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 1 | [6 empty] | 59.9 |  |  |  | 75 | Greenish Grey, Grey | 29.95 | [6 empty] | 75 | Greenish Grey, Grey | 29.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
347 | V17566-SKXD-7118 | SK3-1 | SHELL PLATE | SH-39 | SK3-1-SH-39 | PL10*1800 | 3714.5 | SS400 | 1 |  | 1 | 524.5 | 524.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.5 |  |  |  | 75 | Greenish Grey, Grey | 6.75 | [6 empty] | 75 | Greenish Grey, Grey | 6.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
348 | V17566-SKXD-7118 | SK3-1 | SHELL PLATE | SH-40 | SK3-1-SH-40 | PL10*1371 | 3714.5 | SS400 | 1 |  | 1 | 399.1 | 399.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 10.3 |  |  |  | 75 | Greenish Grey, Grey | 5.15 | [6 empty] | 75 | Greenish Grey, Grey | 5.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
349 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE |  |  | (3488x2435x12189) |  |  |  | 1 |  | 3698.8 | 3698.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 93.6 |  | x | o | [21 empty] | PAC
350 | V17566-SKXD-7121 | SK3-2 | ANGLE | AFY-22 | SK3-2-AFY-22 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
351 | V17566-SKXD-7121 | SK3-2 | ANGLE | AFY-24 | SK3-2-AFY-24 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
352 | V17566-SKXD-7121 | SK3-2 | ANGLE | AFY-26 | SK3-2-AFY-26 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
353 | V17566-SKXD-7121 | SK3-2 | ANGLE | AFY-28 | SK3-2-AFY-28 | L150*150*12 | 1633 | SS400 | 1 |  | 1 | 44.6 | 44.6 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 1 |  |  |  | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
354 | V17566-SKXD-7121 | SK3-2 | PLATE | P-11 | SK3-2-P-11 | PL10*135 | 840 | SS400 | 2 |  | 2 | 8.6 | 17.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
355 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE | SH-31 | SK3-2-SH-31 | PL10*2000 | 4408 | SS400 | 1 |  | 1 | 691.5 | 691.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
356 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE | SH-32 | SK3-2-SH-32 | PL10*2000 | 4408 | SS400 | 2 |  | 2 | 691.1 | 1382.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 35.5 |  |  |  | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
357 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE | SH-33 | SK3-2-SH-33 | PL10*2000 | 4406.5 | SS400 | 1 |  | 1 | 518.7 | 518.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.4 |  |  |  | 75 | Greenish Grey, Grey | 6.7 | [6 empty] | 75 | Greenish Grey, Grey | 6.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
358 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE | SH-34 | SK3-2-SH-34 | PL10*2000 | 2193 | SS400 | 1 |  | 1 | 344 | 344 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.9 |  |  |  | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
359 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE | SH-35 | SK3-2-SH-35 | PL10*1000 | 2193 | SS400 | 1 |  | 1 | 171.8 | 171.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 4.4 |  |  |  | 75 | Greenish Grey, Grey | 2.2 | [6 empty] | 75 | Greenish Grey, Grey | 2.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
360 | V17566-SKXD-7121 | SK3-2 | SHELL PLATE | SH-36 | SK3-2-SH-36 | PL10*1171 | 2193 | SS400 | 1 |  | 1 | 201.1 | 201.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.2 |  |  |  | 75 | Greenish Grey, Grey | 2.6 | [6 empty] | 75 | Greenish Grey, Grey | 2.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
361 | V17566-SKXD-7125 | SK3-3 | SHELL PLATE |  |  | (3486x2429x12189) |  |  |  | 1 |  | 4623.1 | 4623.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 117.1 |  | x | o | [21 empty] | PAC
362 | V17566-SKXD-7125 | SK3-3 | ANGLE | AFY-32 | SK3-3-AFY-32 | L150*150*12 | 3889 | SS400 | 1 |  | 1 | 106.2 | 106.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.3 |  |  |  | 75 | Greenish Grey, Grey | 1.15 | [6 empty] | 75 | Greenish Grey, Grey | 1.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
363 | V17566-SKXD-7125 | SK3-3 | ANGLE | AFY-33 | SK3-3-AFY-33 | L150*150*12 | 3889 | SS400 | 1 |  | 1 | 106.2 | 106.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.3 |  |  |  | 75 | Greenish Grey, Grey | 1.15 | [6 empty] | 75 | Greenish Grey, Grey | 1.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
364 | V17566-SKXD-7125 | SK3-3 | ANGLE | AFY-34 | SK3-3-AFY-34 | L150*150*12 | 3889 | SS400 | 2 |  | 2 | 106.2 | 212.3 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.6 |  |  |  | 75 | Greenish Grey, Grey | 2.3 | [6 empty] | 75 | Greenish Grey, Grey | 2.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
365 | V17566-SKXD-7125 | SK3-3 | SHELL PLATE | SH-41 | SK3-3-SH-41 | PL10*1000 | 4399.5 | SS400 | 1 |  | 1 | 345 | 345 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.9 |  |  |  | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 75 | Greenish Grey, Grey | 4.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
366 | V17566-SKXD-7125 | SK3-3 | SHELL PLATE | SH-42 | SK3-3-SH-42 | PL10*2000 | 4399.5 | SS400 | 4 |  | 4 | 690 | 2760.2 | AMC2 | Plate | PMC |  |  | 4 | 0 | 1 | [6 empty] | 70.9 |  |  |  | 75 | Greenish Grey, Grey | 35.45 | [6 empty] | 75 | Greenish Grey, Grey | 35.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
367 | V17566-SKXD-7125 | SK3-3 | SHELL PLATE | SH-43 | SK3-3-SH-43 | PL10*1800 | 4399.5 | SS400 | 1 |  | 1 | 621 | 621 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 16 |  |  |  | 75 | Greenish Grey, Grey | 8 | [6 empty] | 75 | Greenish Grey, Grey | 8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
368 | V17566-SKXD-7125 | SK3-3 | SHELL PLATE | SH-44 | SK3-3-SH-44 | PL10*1371 | 4399.5 | SS400 | 1 |  | 1 | 472.4 | 472.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 12.2 |  |  |  | 75 | Greenish Grey, Grey | 6.1 | [6 empty] | 75 | Greenish Grey, Grey | 6.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
369 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE |  |  | (3488x2435x12189) |  |  |  | 1 |  | 3412.8 | 3412.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 86.4 |  | x | o | [21 empty] | PAC
370 | V17566-SKXD-7128 | SK3-4 | ANGLE | AFY-22 | SK3-4-AFY-22 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
371 | V17566-SKXD-7128 | SK3-4 | ANGLE | AFY-24 | SK3-4-AFY-24 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
372 | V17566-SKXD-7128 | SK3-4 | ANGLE | AFY-26 | SK3-4-AFY-26 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
373 | V17566-SKXD-7128 | SK3-4 | ANGLE | AFY-38 | SK3-4-AFY-38 | L150*150*12 | 929 | SS400 | 1 |  | 1 | 25.4 | 25.4 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
374 | V17566-SKXD-7128 | SK3-4 | PLATE | P-11 | SK3-4-P-11 | PL10*135 | 840 | SS400 | 3 |  | 3 | 8.6 | 25.8 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
375 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE | SH-32 | SK3-4-SH-32 | PL10*2000 | 4408 | SS400 | 2 |  | 2 | 691.1 | 1382.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 35.5 |  |  |  | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 75 | Greenish Grey, Grey | 17.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
376 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE | SH-45 | SK3-4-SH-45 | PL10*1500 | 4408 | SS400 | 1 |  | 1 | 518.5 | 518.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
377 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE | SH-46 | SK3-4-SH-46 | PL10*2000 | 4408 | SS400 | 1 |  | 1 | 580.6 | 580.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 14.9 |  |  |  | 75 | Greenish Grey, Grey | 7.45 | [6 empty] | 75 | Greenish Grey, Grey | 7.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
378 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE | SH-47 | SK3-4-SH-47 | PL10*1500 | 1509.5 | SS400 | 2 |  | 2 | 177.7 | 355.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 9.2 |  |  |  | 75 | Greenish Grey, Grey | 4.6 | [6 empty] | 75 | Greenish Grey, Grey | 4.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
379 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE | SH-48 | SK3-4-SH-48 | PL10*1000 | 1509.5 | SS400 | 1 |  | 1 | 118.4 | 118.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.1 |  |  |  | 75 | Greenish Grey, Grey | 1.55 | [6 empty] | 75 | Greenish Grey, Grey | 1.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
380 | V17566-SKXD-7128 | SK3-4 | SHELL PLATE | SH-49 | SK3-4-SH-49 | PL10*668 | 1515.5 | SS400 | 1 |  | 1 | 78.9 | 78.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
381 | V17566-SKXD-7132 | SK4-1 | SHELL PLATE |  |  | (3488x2434x10233) |  |  |  | 1 |  | 3463.5 | 3463.5 | AMC2 | [7 empty] | 0 | 0.65714 |  |  |  |  | 102.6 |  | x | o | [21 empty] | PAC
382 | V17566-SKXD-7132 | SK4-1 | ANGLE | A-13 | SK4-1-A-13 | L75*75*6 | 915 | SS400 | 4 |  | 4 | 6.3 | 25.1 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.1 |  |  |  | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
383 | V17566-SKXD-7132 | SK4-1 | ANGLE | AF-2 | SK4-1-AF-2 | L130*130*9 | 625 | SS400 | 1 |  | 1 | 11.2 | 11.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Fabrication
384 | V17566-SKXD-7132 | SK4-1 | ANGLE | AF-4 | SK4-1-AF-4 | L130*130*9 | 1345 | SS400 | 1 |  | 1 | 24 | 24 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
385 | V17566-SKXD-7132 | SK4-1 | ANGLE | AFY-39 | SK4-1-AFY-39 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
386 | V17566-SKXD-7132 | SK4-1 | ANGLE | AFY-41 | SK4-1-AFY-41 | L150*150*12 | 3827 | SS400 | 2 |  | 2 | 104.5 | 208.9 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.5 |  |  |  | 75 | Greenish Grey, Grey | 2.25 | [6 empty] | 75 | Greenish Grey, Grey | 2.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
387 | V17566-SKXD-7132 | SK4-1 | ANGLE | AFY-51 | SK4-1-AFY-51 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
388 | V17566-SKXD-7132 | SK4-1 | CHANNEL | CFY-1 | SK4-1-CFY-1 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
389 | V17566-SKXD-7132 | SK4-1 | PLATE | G-2 | SK4-1-G-2 | PL10*125 | 229 | SS400 | 1 |  | 1 | 2 | 2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
390 | V17566-SKXD-7132 | SK4-1 | PLATE | G-3 | SK4-1-G-3 | PL10*125 | 211 | SS400 | 1 |  | 1 | 1.8 | 1.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
391 | V17566-SKXD-7132 | SK4-1 | PLATE | G-4 | SK4-1-G-4 | PL10*152 | 162 | SS400 | 2 |  | 2 | 1.9 | 3.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
392 | V17566-SKXD-7132 | SK4-1 | PLATE | G-13 | SK4-1-G-13 | PL55*406 | 762 | SM490 | 1 |  | 1 | 125.5 | 125.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
393 | V17566-SKXD-7132 | SK4-1 | PLATE | P-12 | SK4-1-P-12 | PL10*136 | 586 | SS400 | 1 |  | 1 | 6 | 6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
394 | V17566-SKXD-7132 | SK4-1 | PLATE | P-18 | SK4-1-P-18 | PL6*51 | 76 | SS400 | 12 |  | 12 | 0.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
395 | V17566-SKXD-7132 | SK4-1 | PLATE | PF-5 | SK4-1-PF-5 | PL12*508 | 508 | SS400 | 1 |  | 1 | 23.8 | 23.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
396 | V17566-SKXD-7132 | SK4-1 | SHELL PLATE | SH-54 | SK4-1-SH-54 | PL8*2000 | 4345 | SS400 | 1 |  | 1 | 545.1 | 545.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.5 |  |  |  | 75 | Greenish Grey, Grey | 8.75 | [6 empty] | 75 | Greenish Grey, Grey | 8.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
397 | V17566-SKXD-7132 | SK4-1 | SHELL PLATE | SH-55 | SK4-1-SH-55 | PL8*2000 | 4345 | SS400 | 2 |  | 2 | 544.9 | 1089.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 34.9 |  |  |  | 75 | Greenish Grey, Grey | 17.45 | [6 empty] | 75 | Greenish Grey, Grey | 17.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
398 | V17566-SKXD-7132 | SK4-1 | SHELL PLATE | SH-56 | SK4-1-SH-56 | PL8*2000 | 4409 | SS400 | 1 |  | 1 | 546.5 | 546.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.5 |  |  |  | 75 | Greenish Grey, Grey | 8.75 | [6 empty] | 75 | Greenish Grey, Grey | 8.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
399 | V17566-SKXD-7132 | SK4-1 | SHELL PLATE | SH-57 | SK4-1-SH-57 | PL8*1916.4 | 4409 | SS400 | 1 |  | 1 | 529.7 | 529.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17 |  |  |  | 75 | Greenish Grey, Grey | 8.5 | [6 empty] | 75 | Greenish Grey, Grey | 8.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
400 | V17566-SKXD-7136 | SK4-2 | SHELL PLATE |  |  | (3491x2553x9928) |  |  |  | 1 |  | 1816.7 | 1816.7 | AMC2 | [7 empty] | 0 | 0.67568 |  |  |  |  | 55.3 |  | x | o | [21 empty] | PAC
401 | V17566-SKXD-7136 | SK4-2 | ANGLE | A-13 | SK4-2-A-13 | L75*75*6 | 915 | SS400 | 4 |  | 4 | 6.3 | 25.1 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.1 |  |  |  | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
402 | V17566-SKXD-7136 | SK4-2 | ANGLE | AF-1 | SK4-2-AF-1 | L130*130*9 | 396 | SS400 | 1 |  | 1 | 7.1 | 7.1 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
403 | V17566-SKXD-7136 | SK4-2 | ANGLE | AFY-39 | SK4-2-AFY-39 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
404 | V17566-SKXD-7136 | SK4-2 | ANGLE | AFY-44 | SK4-2-AFY-44 | L150*150*12 | 992 | SS400 | 2 |  | 2 | 27.1 | 54.1 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 1.2 |  |  |  | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 75 | Greenish Grey, Grey | 0.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
405 | V17566-SKXD-7136 | SK4-2 | ANGLE | AFY-51 | SK4-2-AFY-51 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
406 | V17566-SKXD-7136 | SK4-2 | CHANNEL | CFY-1 | SK4-2-CFY-1 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
407 | V17566-SKXD-7136 | SK4-2 | PLATE | G-3 | SK4-2-G-3 | PL10*125 | 211 | SS400 | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
408 | V17566-SKXD-7136 | SK4-2 | PLATE | G-4 | SK4-2-G-4 | PL10*152 | 162 | SS400 | 3 |  | 3 | 1.9 | 5.8 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
409 | V17566-SKXD-7136 | SK4-2 | PLATE | G-5000 | SK4-2-G-5000 | PL10*100 | 280 | SS400 | 2 |  | 2 | 1.9 | 3.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [24 empty] | PAC | [7 empty] | Chi tiết thêm mới | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
410 | V17566-SKXD-7136 | SK4-2 | PLATE | P-12 | SK4-2-P-12 | PL10*136 | 586 | SS400 | 3 |  | 3 | 6 | 17.9 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
411 | V17566-SKXD-7136 | SK4-2 | PLATE | P-18 | SK4-2-P-18 | PL6*51 | 76 | SS400 | 12 |  | 12 | 0.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
412 | V17566-SKXD-7136 | SK4-2 | SHELL PLATE | SH-58 | SK4-2-SH-58 | PL8*500 | 1577 | SS400 | 1 |  | 1 | 49.3 | 49.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 1.6 |  |  |  | 75 | Greenish Grey, Grey | 0.8 | [6 empty] | 75 | Greenish Grey, Grey | 0.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
413 | V17566-SKXD-7136 | SK4-2 | SHELL PLATE | SH-59 | SK4-2-SH-59 | PL8*1913.4 | 1577 | SS400 | 1 |  | 1 | 189 | 189 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 6.1 |  |  |  | 75 | Greenish Grey, Grey | 3.05 | [6 empty] | 75 | Greenish Grey, Grey | 3.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
414 | V17566-SKXD-7136 | SK4-2 | SHELL PLATE | SH-60 | SK4-2-SH-60 | PL8*2000 | 1577 | SS400 | 2 |  | 2 | 197.5 | 395.1 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 12.7 |  |  |  | 75 | Greenish Grey, Grey | 6.35 | [6 empty] | 75 | Greenish Grey, Grey | 6.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
415 | V17566-SKXD-7136 | SK4-2 | SHELL PLATE | SH-61 | SK4-2-SH-61 | PL8*2000 | 4409 | SS400 | 1 |  | 1 | 337.6 | 337.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 10.9 |  |  |  | 75 | Greenish Grey, Grey | 5.45 | [6 empty] | 75 | Greenish Grey, Grey | 5.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
416 | V17566-SKXD-7136 | SK4-2 | SHELL PLATE | SH-62 | SK4-2-SH-62 | PL8*1500 | 4409 | SS400 | 1 |  | 1 | 414.4 | 414.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
417 | V17566-SKXD-7139 | SK4-3 | SHELL PLATE |  |  | (3488x2434x2290) |  |  |  | 1 |  | 1004.9 | 1004.9 | AMC2 | [7 empty] | 0 | 0.57143 |  |  |  |  | 29.7 |  | x | o | [21 empty] | PAC
418 | V17566-SKXD-7139 | SK4-3 | ANGLE | A-13 | SK4-3-A-13 | L75*75*6 | 915 | SS400 | 4 |  | 4 | 6.3 | 25.1 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.1 |  |  |  | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
419 | V17566-SKXD-7139 | SK4-3 | ANGLE | AFY-39 | SK4-3-AFY-39 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
420 | V17566-SKXD-7139 | SK4-3 | ANGLE | AFY-51 | SK4-3-AFY-51 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
421 | V17566-SKXD-7139 | SK4-3 | CHANNEL | CFY-1 | SK4-3-CFY-1 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
422 | V17566-SKXD-7139 | SK4-3 | PLATE | G-1 | SK4-3-G-1 | PL10*125 | 264 | SS400 | 2 |  | 2 | 2.3 | 4.5 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
423 | V17566-SKXD-7139 | SK4-3 | PLATE | G-4 | SK4-3-G-4 | PL10*152 | 162 | SS400 | 2 |  | 2 | 1.9 | 3.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
424 | V17566-SKXD-7139 | SK4-3 | PLATE | P-12 | SK4-3-P-12 | PL10*136 | 586 | SS400 | 3 |  | 3 | 6 | 17.9 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
425 | V17566-SKXD-7139 | SK4-3 | PLATE | P-18 | SK4-3-P-18 | PL6*51 | 76 | SS400 | 12 |  | 12 | 0.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
426 | V17566-SKXD-7139 | SK4-3 | SHELL PLATE | SH-70 | SK4-3-SH-70 | PL8*1913.4 | 4409 | SS400 | 1 |  | 1 | 494.7 | 494.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 15.9 |  |  |  | 75 | Greenish Grey, Grey | 7.95 | [6 empty] | 75 | Greenish Grey, Grey | 7.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
427 | V17566-SKXD-7139 | SK4-3 | SHELL PLATE | SH-71 | SK4-3-SH-71 | PL8*500 | 4409 | SS400 | 1 |  | 1 | 137.6 | 137.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 4.5 |  |  |  | 75 | Greenish Grey, Grey | 2.25 | [6 empty] | 75 | Greenish Grey, Grey | 2.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
428 | V17566-SKXD-7142 | SK4-4 | SHELL PLATE |  |  | (3488x2434x9928) |  |  |  | 1 |  | 2119.8 | 2119.8 | AMC2 | [7 empty] | 0 | 0.63636 |  |  |  |  | 64.6 |  | x | o | [21 empty] | PAC
429 | V17566-SKXD-7142 | SK4-4 | ANGLE | A-13 | SK4-4-A-13 | L75*75*6 | 915 | SS400 | 4 |  | 4 | 6.3 | 25.1 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.1 |  |  |  | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
430 | V17566-SKXD-7142 | SK4-4 | ANGLE | AF-6 | SK4-4-AF-6 | L130*130*9 | 969 | SS400 | 1 |  | 1 | 17.3 | 17.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
431 | V17566-SKXD-7142 | SK4-4 | ANGLE | AFY-39 | SK4-4-AFY-39 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
432 | V17566-SKXD-7142 | SK4-4 | ANGLE | AFY-46 | SK4-4-AFY-46 | L150*150*12 | 1570 | SS400 | 2 |  | 2 | 42.8 | 85.7 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 1.8 |  |  |  | 75 | Greenish Grey, Grey | 0.9 | [6 empty] | 75 | Greenish Grey, Grey | 0.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
433 | V17566-SKXD-7142 | SK4-4 | ANGLE | AFY-51 | SK4-4-AFY-51 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
434 | V17566-SKXD-7142 | SK4-4 | CHANNEL | CFY-1 | SK4-4-CFY-1 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
435 | V17566-SKXD-7142 | SK4-4 | PLATE | G-3 | SK4-4-G-3 | PL10*125 | 211 | SS400 | 1 |  | 1 | 1.8 | 1.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
436 | V17566-SKXD-7142 | SK4-4 | PLATE | G-4 | SK4-4-G-4 | PL10*152 | 162 | SS400 | 2 |  | 2 | 1.9 | 3.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
437 | V17566-SKXD-7142 | SK4-4 | PLATE | G-5000 | SK4-4-G-5000 | PL10*100 | 280 | SS400 | 1 |  | 1 | 1.9 | 1.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | [24 empty] | PAC | [7 empty] | Chi tiết thêm mới | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
438 | V17566-SKXD-7142 | SK4-4 | PLATE | P-12 | SK4-4-P-12 | PL10*136 | 586 | SS400 | 2 |  | 2 | 6 | 11.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
439 | V17566-SKXD-7142 | SK4-4 | PLATE | P-18 | SK4-4-P-18 | PL6*51 | 76 | SS400 | 12 |  | 12 | 0.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
440 | V17566-SKXD-7142 | SK4-4 | SHELL PLATE | SH-57 | SK4-4-SH-57 | PL8*1916.4 | 4409 | SS400 | 1 |  | 1 | 529.7 | 529.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17 |  |  |  | 75 | Greenish Grey, Grey | 8.5 | [6 empty] | 75 | Greenish Grey, Grey | 8.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
441 | V17566-SKXD-7142 | SK4-4 | SHELL PLATE | SH-63 | SK4-4-SH-63 | PL8*2000 | 2139 | SS400 | 1 |  | 1 | 268.1 | 268.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.6 |  |  |  | 75 | Greenish Grey, Grey | 4.3 | [6 empty] | 75 | Greenish Grey, Grey | 4.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
442 | V17566-SKXD-7142 | SK4-4 | SHELL PLATE | SH-64 | SK4-4-SH-64 | PL8*2000 | 2139 | SS400 | 2 |  | 2 | 268 | 536 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 17.2 |  |  |  | 75 | Greenish Grey, Grey | 8.6 | [6 empty] | 75 | Greenish Grey, Grey | 8.6 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
443 | V17566-SKXD-7142 | SK4-4 | SHELL PLATE | SH-65 | SK4-4-SH-65 | PL8*2000 | 4409 | SS400 | 1 |  | 1 | 320.8 | 320.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 10.3 |  |  |  | 75 | Greenish Grey, Grey | 5.15 | [6 empty] | 75 | Greenish Grey, Grey | 5.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
444 | V17566-SKXD-7145 | SK4-5 | SHELL PLATE |  |  | (3488x2498x10233) |  |  |  | 1 |  | 3152 | 3152 | AMC2 | [7 empty] | 0 | 0.66667 |  |  |  |  | 93.1 |  | x | o | [21 empty] | PAC
445 | V17566-SKXD-7145 | SK4-5 | ANGLE | A-13 | SK4-5-A-13 | L75*75*6 | 915 | SS400 | 4 |  | 4 | 6.3 | 25.1 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.1 |  |  |  | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
446 | V17566-SKXD-7145 | SK4-5 | ANGLE | AF-2 | SK4-5-AF-2 | L130*130*9 | 625 | SS400 | 1 |  | 1 | 11.2 | 11.2 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Fabrication
447 | V17566-SKXD-7145 | SK4-5 | ANGLE | AF-5 | SK4-5-AF-5 | L130*130*9 | 770 | SS400 | 1 |  | 1 | 13.7 | 13.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
448 | V17566-SKXD-7145 | SK4-5 | ANGLE | AFY-39 | SK4-5-AFY-39 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
449 | V17566-SKXD-7145 | SK4-5 | ANGLE | AFY-49 | SK4-5-AFY-49 | L150*150*12 | 3249 | SS400 | 2 |  | 2 | 88.7 | 177.3 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 3.8 |  |  |  | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
450 | V17566-SKXD-7145 | SK4-5 | ANGLE | AFY-51 | SK4-5-AFY-51 | L150*150*12 | 4003 | SS400 | 1 |  | 1 | 109.3 | 109.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.4 |  |  |  | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 75 | Greenish Grey, Grey | 1.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
451 | V17566-SKXD-7145 | SK4-5 | CHANNEL | CFY-1 | SK4-5-CFY-1 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
452 | V17566-SKXD-7145 | SK4-5 | PLATE | G-2 | SK4-5-G-2 | PL10*125 | 229 | SS400 | 1 |  | 1 | 2 | 2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
453 | V17566-SKXD-7145 | SK4-5 | PLATE | G-3 | SK4-5-G-3 | PL10*125 | 211 | SS400 | 1 |  | 1 | 1.8 | 1.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
454 | V17566-SKXD-7145 | SK4-5 | PLATE | G-4 | SK4-5-G-4 | PL10*152 | 162 | SS400 | 2 |  | 2 | 1.9 | 3.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
455 | V17566-SKXD-7145 | SK4-5 | PLATE | G-13 | SK4-5-G-13 | PL55*406 | 762 | SM490 | 1 |  | 1 | 125.5 | 125.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
456 | V17566-SKXD-7145 | SK4-5 | PLATE | P-12 | SK4-5-P-12 | PL10*136 | 586 | SS400 | 1 |  | 1 | 6 | 6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
457 | V17566-SKXD-7145 | SK4-5 | PLATE | P-18 | SK4-5-P-18 | PL6*51 | 76 | SS400 | 12 |  | 12 | 0.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 12 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
458 | V17566-SKXD-7145 | SK4-5 | PLATE | PF-5 | SK4-5-PF-5 | PL12*508 | 508 | SS400 | 1 |  | 1 | 23.8 | 23.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
459 | V17566-SKXD-7145 | SK4-5 | SHELL PLATE | SH-62 | SK4-5-SH-62 | PL8*1500 | 4409 | SS400 | 1 |  | 1 | 414.4 | 414.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
460 | V17566-SKXD-7145 | SK4-5 | SHELL PLATE | SH-66 | SK4-5-SH-66 | PL8*500 | 3783 | SS400 | 1 |  | 1 | 118.5 | 118.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.8 |  |  |  | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 75 | Greenish Grey, Grey | 1.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
461 | V17566-SKXD-7145 | SK4-5 | SHELL PLATE | SH-67 | SK4-5-SH-67 | PL8*1913.4 | 3783 | SS400 | 1 |  | 1 | 453.9 | 453.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 14.6 |  |  |  | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
462 | V17566-SKXD-7145 | SK4-5 | SHELL PLATE | SH-68 | SK4-5-SH-68 | PL8*2000 | 3783 | SS400 | 2 |  | 2 | 474.5 | 948.9 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 30.4 |  |  |  | 75 | Greenish Grey, Grey | 15.2 | [6 empty] | 75 | Greenish Grey, Grey | 15.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
463 | V17566-SKXD-7145 | SK4-5 | SHELL PLATE | SH-69 | SK4-5-SH-69 | PL8*2000 | 4409 | SS400 | 1 |  | 1 | 505.5 | 505.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 16.2 |  |  |  | 75 | Greenish Grey, Grey | 8.1 | [6 empty] | 75 | Greenish Grey, Grey | 8.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
464 | V17566-SKXD-7149 | SK5-1 | SHELL PLATE |  |  | (3488x2433x10538) |  |  |  | 1 |  | 2513.3 | 2513.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 100.3 |  | x | o | [21 empty] | PAC
465 | V17566-SKXD-7149 | SK5-1 | ANGLE | AFY-52 | SK5-1-AFY-52 | L150*150*12 | 4003 | SS400 | 3 |  | 3 | 109.3 | 327.8 | AMC2 | Shape | PMC |  |  | 3 | 0 | 1 | [6 empty] | 7.1 |  |  |  | 75 | Greenish Grey, Grey | 3.55 | [6 empty] | 75 | Greenish Grey, Grey | 3.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
466 | V17566-SKXD-7149 | SK5-1 | SHELL PLATE | SH-2 | SK5-1-SH-2 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 415.4 | 415.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
467 | V17566-SKXD-7149 | SK5-1 | SHELL PLATE | SH-3 | SK5-1-SH-3 | PL6*1023 | 4413 | SS400 | 1 |  | 1 | 212.4 | 212.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 9.1 |  |  |  | 75 | Greenish Grey, Grey | 4.55 | [6 empty] | 75 | Greenish Grey, Grey | 4.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
468 | V17566-SKXD-7149 | SK5-1 | SHELL PLATE | SH-72 | SK5-1-SH-72 | PL6*1500 | 4413 | SS400 | 1 |  | 1 | 311.6 | 311.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
469 | V17566-SKXD-7149 | SK5-1 | SHELL PLATE | SH-73 | SK5-1-SH-73 | PL6*2000 | 4413 | SS400 | 3 |  | 3 | 415.4 | 1246.2 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | 53.1 |  |  |  | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
470 | V17566-SKXD-7151 | SK5-2 | SHELL PLATE |  |  | (3488x2433x10538) |  |  |  | 1 |  | 2513.3 | 2513.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 100.3 |  | x | o | [21 empty] | PAC
471 | V17566-SKXD-7151 | SK5-2 | ANGLE | AFY-52 | SK5-2-AFY-52 | L150*150*12 | 4003 | SS400 | 3 |  | 3 | 109.3 | 327.8 | AMC2 | Shape | PMC |  |  | 3 | 0 | 1 | [6 empty] | 7.1 |  |  |  | 75 | Greenish Grey, Grey | 3.55 | [6 empty] | 75 | Greenish Grey, Grey | 3.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
472 | V17566-SKXD-7151 | SK5-2 | SHELL PLATE | SH-73 | SK5-2-SH-73 | PL6*2000 | 4413 | SS400 | 4 |  | 4 | 415.4 | 1661.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 1 | [6 empty] | 70.9 |  |  |  | 75 | Greenish Grey, Grey | 35.45 | [6 empty] | 75 | Greenish Grey, Grey | 35.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
473 | V17566-SKXD-7151 | SK5-2 | SHELL PLATE | SH-79 | SK5-2-SH-79 | PL6*542 | 4413 | SS400 | 1 |  | 1 | 112.5 | 112.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 4.8 |  |  |  | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 75 | Greenish Grey, Grey | 2.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
474 | V17566-SKXD-7151 | SK5-2 | SHELL PLATE | SH-80 | SK5-2-SH-80 | PL6*1981 | 4413 | SS400 | 1 |  | 1 | 411.4 | 411.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.5 |  |  |  | 75 | Greenish Grey, Grey | 8.75 | [6 empty] | 75 | Greenish Grey, Grey | 8.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
475 | V17566-SKXD-7153 | SK5-3 | SHELL PLATE |  |  | (3488x2433x10538) |  |  |  | 2 |  | 2513.3 | 5026.4 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 200.6 |  | x | o | [21 empty] | PAC
476 | V17566-SKXD-7153 | SK5-3 | ANGLE | AFY-52 | SK5-3-AFY-52 | L150*150*12 | 4003 | SS400 | 3 |  | 6 | 109.3 | 655.6 | AMC2 | Shape | PMC |  |  | 6 | 0 | 2 | [6 empty] | 14.1 |  |  |  | 75 | Greenish Grey, Grey | 7.05 | [6 empty] | 75 | Greenish Grey, Grey | 7.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
477 | V17566-SKXD-7153 | SK5-3 | SHELL PLATE | SH-4 | SK5-3-SH-4 | PL6*2000 | 4413 | SS400 | 1 |  | 2 | 415.4 | 830.7 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 35.4 |  |  |  | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
478 | V17566-SKXD-7153 | SK5-3 | SHELL PLATE | SH-5 | SK5-3-SH-5 | PL6*523 | 4413 | SS400 | 1 |  | 2 | 108.5 | 217 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 9.3 |  |  |  | 75 | Greenish Grey, Grey | 4.65 | [6 empty] | 75 | Greenish Grey, Grey | 4.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
479 | V17566-SKXD-7153 | SK5-3 | SHELL PLATE | SH-73 | SK5-3-SH-73 | PL6*2000 | 4413 | SS400 | 3 |  | 6 | 415.4 | 2492.2 | AMC2 | Plate | PMC |  |  | 6 | 0 | 2 | [6 empty] | 106.3 |  |  |  | 75 | Greenish Grey, Grey | 53.15 | [6 empty] | 75 | Greenish Grey, Grey | 53.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
480 | V17566-SKXD-7153 | SK5-3 | SHELL PLATE | SH-75 | SK5-3-SH-75 | PL6*2000 | 4413 | SS400 | 1 |  | 2 | 415.5 | 830.9 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 35.4 |  |  |  | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
481 | V17566-SKXD-7155 | SK5-4 | SHELL PLATE |  |  | (3488x2433x10538) |  |  |  | 1 |  | 2872.7 | 2872.7 | AMC2 | [7 empty] | 0 | 0.91429 |  |  |  |  | 113 |  | x | o | [21 empty] | PAC
482 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-15 | SK5-4-A-15 | L75*75*6 | 1007 | SS400 | 2 |  | 2 | 6.9 | 13.8 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.6 |  |  |  | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 75 | Greenish Grey, Grey | 0.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
483 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-16 | SK5-4-A-16 | L75*75*6 | 1321 | SS400 | 1 |  | 1 | 9.1 | 9.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
484 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-17 | SK5-4-A-17 | L75*75*6 | 743 | SS400 | 3 |  | 3 | 5.1 | 15.3 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
485 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-18 | SK5-4-A-18 | L75*75*6 | 1489 | SS400 | 1 |  | 1 | 10.2 | 10.2 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
486 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-19 | SK5-4-A-19 | L75*75*6 | 3153 | SS400 | 2 |  | 2 | 21.6 | 43.2 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.8 |  |  |  | 75 | Greenish Grey, Grey | 0.9 | [6 empty] | 75 | Greenish Grey, Grey | 0.9 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
487 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-20 | SK5-4-A-20 | L75*75*6 | 129 | SS400 | 2 |  | 2 | 0.9 | 1.8 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
488 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-21 | SK5-4-A-21 | L75*75*6 | 1210 | SS400 | 1 |  | 1 | 8.3 | 8.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
489 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-22 | SK5-4-A-22 | L75*75*6 | 1285 | SS400 | 1 |  | 1 | 8.8 | 8.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
490 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-23 | SK5-4-A-23 | L75*75*6 | 1525 | SS400 | 3 |  | 3 | 10.4 | 31.3 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
491 | V17566-SKXD-7155 | SK5-4 | ANGLE | A-36 | SK5-4-A-36 | L75*75*6 | 1221 | SS400 | 1 |  | 1 | 8.4 | 8.4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
492 | V17566-SKXD-7155 | SK5-4 | ANGLE | AF-3 | SK5-4-AF-3 | L130*130*9 | 1876 | SS400 | 2 |  | 2 | 33.5 | 67 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 1.9 |  |  |  | 75 | Greenish Grey, Grey | 0.95 | [6 empty] | 75 | Greenish Grey, Grey | 0.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
493 | V17566-SKXD-7155 | SK5-4 | ANGLE | AFY-52 | SK5-4-AFY-52 | L150*150*12 | 4003 | SS400 | 3 |  | 3 | 109.3 | 327.8 | AMC2 | Shape | PMC |  |  | 3 | 0 | 1 | [6 empty] | 7.1 |  |  |  | 75 | Greenish Grey, Grey | 3.55 | [6 empty] | 75 | Greenish Grey, Grey | 3.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
494 | V17566-SKXD-7155 | SK5-4 | CHANNEL | CF-1 | SK5-4-CF-1 | [150*75*6.5*10 | 1861 | SS400 | 2 |  | 2 | 34.6 | 69.3 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
495 | V17566-SKXD-7155 | SK5-4 | PLATE | G-5 | SK5-4-G-5 | PL10*100 | 203 | SS400 | 2 |  | 2 | 1.5 | 2.9 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 | [24 empty] | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
496 | V17566-SKXD-7155 | SK5-4 | PLATE | G-5-1 | SK5-4-G-5-1 | PL10*100 | 198 | SS400 | 2 |  | 2 | 1.4 | 2.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
497 | V17566-SKXD-7155 | SK5-4 | PLATE | G-6 | SK5-4-G-6 | PL10*157 | 152 | SS400 | 4 |  | 4 | 1.7 | 6.9 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
498 | V17566-SKXD-7155 | SK5-4 | PLATE | G-11 | SK5-4-G-11 | PL10*152 | 304 | SS400 | 14 |  | 14 | 3.6 | 50.8 | AMC2 | Plate | MCC |  |  | 14 | 0 | 1 | [6 empty] | 1.4 |  |  |  | 75 | Greenish Grey, Grey | 0.7 | [6 empty] | 75 | Greenish Grey, Grey | 0.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
499 | V17566-SKXD-7155 | SK5-4 | PLATE | P-18 | SK5-4-P-18 | PL6*51 | 76 | SS400 | 53 |  | 53 | 0.2 | 9.7 | AMC2 | Plate | MCC |  |  | 44 | 9 | 0 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
500 | V17566-SKXD-7155 | SK5-4 | SHELL PLATE | SH-2 | SK5-4-SH-2 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 415.3 | 415.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
501 | V17566-SKXD-7155 | SK5-4 | SHELL PLATE | SH-73 | SK5-4-SH-73 | PL6*2000 | 4413 | SS400 | 3 |  | 3 | 415.3 | 1246 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | 53.1 |  |  |  | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
502 | V17566-SKXD-7155 | SK5-4 | SHELL PLATE | SH-76 | SK5-4-SH-76 | PL6*1042 | 4413 | SS400 | 1 |  | 1 | 216.4 | 216.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 9.3 |  |  |  | 75 | Greenish Grey, Grey | 4.65 | [6 empty] | 75 | Greenish Grey, Grey | 4.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
503 | V17566-SKXD-7155 | SK5-4 | SHELL PLATE | SH-77 | SK5-4-SH-77 | PL6*1481 | 4413 | SS400 | 1 |  | 1 | 307.5 | 307.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.1 |  |  |  | 75 | Greenish Grey, Grey | 6.55 | [6 empty] | 75 | Greenish Grey, Grey | 6.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
504 | V17566-SKXD-7160 | SK6-1 | SHELL PLATE |  |  | (3488x2441x10487) |  |  |  | 1 |  | 2963.6 | 2963.6 | AMC2 | [7 empty] | 0 | 0.90385 |  |  |  |  | 109.3 |  | x | o | [21 empty] | PAC
505 | V17566-SKXD-7160 | SK6-1 | ANGLE | A-26 | SK6-1-A-26 | L75*75*6 | 514 | SS400 | 1 |  | 1 | 3.52 | 3.52 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.15 |  |  |  | 75 | Greenish Grey, Grey | 0.075 | [6 empty] | 75 | Greenish Grey, Grey | 0.075 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( tăng chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
506 | V17566-SKXD-7160 | SK6-1 | ANGLE | A-27 | SK6-1-A-27 | L75*75*6 | 2437 | SS400 | 3 |  | 3 | 16.7 | 50.1 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
507 | V17566-SKXD-7160 | SK6-1 | ANGLE | A-30 | SK6-1-A-30 | L75*75*6 | 1429 | SS400 | 1 |  | 1 | 9.79 | 9.79 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.42 |  |  |  | 75 | Greenish Grey, Grey | 0.21 | [6 empty] | 75 | Greenish Grey, Grey | 0.21 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( giảm chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
508 | V17566-SKXD-7160 | SK6-1 | ANGLE | AFY-52 | SK6-1-AFY-52 | L150*150*12 | 4003 | SS400 | 4 |  | 4 | 109.3 | 437.1 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 9.4 |  |  |  | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
509 | V17566-SKXD-7160 | SK6-1 | ANGLE | AFY-58 | SK6-1-AFY-58 | L130*130*9 | 3992 | SS400 | 1 |  | 1 | 71.3 | 71.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2 |  |  |  | 75 | Greenish Grey, Grey | 1 | [6 empty] | 75 | Greenish Grey, Grey | 1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
510 | V17566-SKXD-7160 | SK6-1 | CHANNEL | CFY-7 | SK6-1-CFY-7 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
511 | V17566-SKXD-7160 | SK6-1 | Pipe 3" SCH.40 | D-5 | SK6-1-D-5 | CHS88.9*5.49 | 242 | A106 Gr.B | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
512 | V17566-SKXD-7160 | SK6-1 | FLANGE 3" 150# SO-RF | FL-10 | SK6-1-FL-10 | PL22.3*190 | 190 | A105 | 1 |  | 1 | 4.2 | 4.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
513 | V17566-SKXD-7160 | SK6-1 | BLIND 3" 150# SO-RF | FL-11 | SK6-1-FL-11 | PL22.3*190 | 190 | A105 | 1 |  | 1 | 5 | 5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
514 | V17566-SKXD-7160 | SK6-1 | PLATE | G-7 | SK6-1-G-7 | PL10*126 | 211 | SS400 | 2 |  | 2 | 1.9 | 3.7 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
515 | V17566-SKXD-7160 | SK6-1 | PLATE | G-8 | SK6-1-G-8 | PL10*152 | 161 | SS400 | 2 |  | 2 | 1.9 | 3.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
516 | V17566-SKXD-7160 | SK6-1 | PLATE | G-13 | SK6-1-G-13 | PL55*406 | 762 | SM490 | 1 |  | 1 | 125.5 | 125.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
517 | V17566-SKXD-7160 | SK6-1 | GASKET 3" 150# SO-RF | GK-3 | SK6-1-GK-3 | CHS127*18.15 | 3 | NON-METALLIC | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
518 | V17566-SKXD-7160 | SK6-1 | BEND PLATE | GX-1 | SK6-1-GX-1 | PL6*370 | 509 | SS400 | 1 |  | 1 | 8.9 | 8.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
519 | V17566-SKXD-7160 | SK6-1 | COUPLING 2" 3000# | M-1 | SK6-1-M-1 | COUPLING 2" 3000# | 86 | A105 | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
520 | V17566-SKXD-7160 | SK6-1 | SQ HEAD PLUG 2" 3000# | M-2 | SK6-1-M-2 | D55 | 30 | A105 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
521 | V17566-SKXD-7160 | SK6-1 | PLATE | P-2 | SK6-1-P-2 | PL6*138 | 138 | SS400 | 1 |  | 1 | 0.9 | 0.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
522 | V17566-SKXD-7160 | SK6-1 | PLATE | P-18 | SK6-1-P-18 | PL6*51 | 76 | SS400 | 21 |  | 21 | 0.2 | 3.8 | AMC2 | Plate | MCC |  |  | 21 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
523 | V17566-SKXD-7160 | SK6-1 | PLATE | PF-4 | SK6-1-PF-4 | PL12*508 | 127 | SS400 | 1 |  | 1 | 23.8 | 23.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
524 | V17566-SKXD-7160 | SK6-1 | SHELL PLATE | SH-6 | SK6-1-SH-6 | PL6*2000 | 4413 | SS400 | 3 |  | 3 | 415.4 | 1246.2 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | 53.1 |  |  |  | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
525 | V17566-SKXD-7160 | SK6-1 | SHELL PLATE | SH-7 | SK6-1-SH-7 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 414.9 | 414.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
526 | V17566-SKXD-7160 | SK6-1 | SHELL PLATE | SH-8 | SK6-1-SH-8 | PL6*1500 | 4413 | SS400 | 1 |  | 1 | 311.5 | 311.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
527 | V17566-SKXD-7160 | SK6-1 | SHELL PLATE | SH-9 | SK6-1-SH-9 | PL6*667 | 4413 | SS400 | 1 |  | 1 | 138.4 | 138.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.9 |  |  |  | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
529 | V17566-SKXD-7164 | SK6-2 | SHELL PLATE |  |  | (3488x2772x10182) |  |  |  | 1 |  | 2900.7 | 2900.7 | AMC2 | [7 empty] | 0 | 0.87879 |  |  |  |  | 110.1 |  | x | o | [21 empty] | PAC
530 | V17566-SKXD-7164 | SK6-2 | ANGLE | A-1 | SK6-2-A-1 | L50*50*10 | 38 | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
531 | V17566-SKXD-7164 | SK6-2 | ANGLE | A-27 | SK6-2-A-27 | L75*75*6 | 2437 | SS400 | 3 |  | 3 | 16.7 | 50.1 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
532 | V17566-SKXD-7164 | SK6-2 | ANGLE | A-28 | SK6-2-A-28 | L75*75*6 | 495 | SS400 | 1 |  | 1 | 3.39 | 3.39 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.14 |  |  |  | 75 | Greenish Grey, Grey | 0.07 | [6 empty] | 75 | Greenish Grey, Grey | 0.07 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( tăng chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
533 | V17566-SKXD-7164 | SK6-2 | ANGLE | A-29 | SK6-2-A-29 | L75*75*6 | 1410 | SS400 | 1 |  | 1 | 9.66 | 9.66 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.41 |  |  |  | 75 | Greenish Grey, Grey | 0.205 | [6 empty] | 75 | Greenish Grey, Grey | 0.205 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( giảm chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
534 | V17566-SKXD-7164 | SK6-2 | ANGLE | AFY-52 | SK6-2-AFY-52 | L150*150*12 | 4003 | SS400 | 4 |  | 4 | 109.3 | 437.1 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 9.4 |  |  |  | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
535 | V17566-SKXD-7164 | SK6-2 | ANGLE | AFY-58 | SK6-2-AFY-58 | L130*130*9 | 3992 | SS400 | 1 |  | 1 | 71.3 | 71.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2 |  |  |  | 75 | Greenish Grey, Grey | 1 | [6 empty] | 75 | Greenish Grey, Grey | 1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
536 | V17566-SKXD-7164 | SK6-2 | CHANNEL | CFY-7 | SK6-2-CFY-7 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
537 | V17566-SKXD-7164 | SK6-2 | PIPE 6" SCH.40 | D-3 | SK6-2-D-3 | CHS168.28*7.11 | 242 | A106 Gr.B | 1 |  | 1 | 6.8 | 6.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
538 | V17566-SKXD-7164 | SK6-2 | PIPE 4" SCH.40 | D-4 | SK6-2-D-4 | CHS114.3*6.02 | 242 | A106 Gr.B | 1 |  | 1 | 3.8 | 3.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
539 | V17566-SKXD-7164 | SK6-2 | BLIND 6" 150# SO-RF | FL-2 | SK6-2-FL-2 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 11.6 | 11.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
540 | V17566-SKXD-7164 | SK6-2 | FLANGE 6" 150# SO-RF | FL-3 | SK6-2-FL-3 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 8.5 | 8.5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
541 | V17566-SKXD-7164 | SK6-2 | FLANGE 4" 150# SO-RF | FL-6 | SK6-2-FL-6 | PL22.3*229 | 229 | A105 | 1 |  | 1 | 6.5 | 6.5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
542 | V17566-SKXD-7164 | SK6-2 | BLIND 4" 150# SO-RF | FL-7 | SK6-2-FL-7 | PL22.3*229 | 229 | A105 | 1 |  | 1 | 7.3 | 7.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
543 | V17566-SKXD-7164 | SK6-2 | PLATE | G-7 | SK6-2-G-7 | PL10*126 | 211 | SS400 | 2 |  | 2 | 1.9 | 3.7 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
544 | V17566-SKXD-7164 | SK6-2 | PLATE | G-8 | SK6-2-G-8 | PL10*152 | 161 | SS400 | 2 |  | 2 | 1.9 | 3.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
545 | V17566-SKXD-7164 | SK6-2 | PLATE | G-14 | SK6-2-G-14 | PL12*175 | 203 | SS400 | 2 |  | 2 | 3.3 | 6.7 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
546 | V17566-SKXD-7164 | SK6-2 | GASKET 6" 150# SO-RF | GK-1 | SK6-2-GK-1 | CHS215.9*22.6 | 3 | NON-METALLIC | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
547 | V17566-SKXD-7164 | SK6-2 | GASKET 4" 150# SO-RF | GK-2 | SK6-2-GK-2 | CHS157.2*20.55 | 3 | NON-METALLIC | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
548 | V17566-SKXD-7164 | SK6-2 | BEND PLATE | GX-1 | SK6-2-GX-1 | PL6*370 | 509 | SS400 | 1 |  | 1 | 8.9 | 8.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
549 | V17566-SKXD-7164 | SK6-2 | H-BEAM | HY-1 | SK6-2-HY-1 | H150*150*7*10 | 1436 | SS400 | 1 |  | 1 | 44.7 | 44.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 |  |  |  | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 75 | Greenish Grey, Grey | 0.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication
550 | V17566-SKXD-7164 | SK6-2 | COUPLING 2" 3000# | M-1 | SK6-2-M-1 | COUPLING 2" 3000# | 86 | A105 | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
551 | V17566-SKXD-7164 | SK6-2 | SQ HEAD PLUG 2" 3000# | M-2 | SK6-2-M-2 | D55 | 30 | A105 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
552 | V17566-SKXD-7164 | SK6-2 | PLATE | P-2 | SK6-2-P-2 | PL6*138 | 138 | SS400 | 1 |  | 1 | 0.9 | 0.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
553 | V17566-SKXD-7164 | SK6-2 | PLATE | P-17 | SK6-2-P-17 | PL6*70 | 130 | SS400 | 8 |  | 8 | 0.4 | 3.4 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
554 | V17566-SKXD-7164 | SK6-2 | PLATE | P-18 | SK6-2-P-18 | PL6*51 | 76 | SS400 | 21 |  | 21 | 0.2 | 3.8 | AMC2 | Plate | MCC |  |  | 21 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
555 | V17566-SKXD-7164 | SK6-2 | SHELL PLATE | SH-6 | SK6-2-SH-6 | PL6*2000 | 4413 | SS400 | 2 |  | 2 | 415.4 | 830.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 35.4 |  |  |  | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
556 | V17566-SKXD-7164 | SK6-2 | SHELL PLATE | SH-8 | SK6-2-SH-8 | PL6*1500 | 4413 | SS400 | 1 |  | 1 | 311.5 | 311.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
557 | V17566-SKXD-7164 | SK6-2 | SHELL PLATE | SH-14 | SK6-2-SH-14 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 413.6 | 413.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.6 |  |  |  | 75 | Greenish Grey, Grey | 8.8 | [6 empty] | 75 | Greenish Grey, Grey | 8.8 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
558 | V17566-SKXD-7164 | SK6-2 | SHELL PLATE | SH-15 | SK6-2-SH-15 | PL6*1700 | 4413 | SS400 | 1 |  | 1 | 353.1 | 353.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 15.1 |  |  |  | 75 | Greenish Grey, Grey | 7.55 | [6 empty] | 75 | Greenish Grey, Grey | 7.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
559 | V17566-SKXD-7164 | SK6-2 | SHELL PLATE | SH-16 | SK6-2-SH-16 | PL6*967 | 4413 | SS400 | 1 |  | 1 | 200.8 | 200.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 8.6 |  |  |  | 75 | Greenish Grey, Grey | 4.3 | [6 empty] | 75 | Greenish Grey, Grey | 4.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
562 | V17566-SKXD-7168 | SK6-3 | SHELL PLATE |  |  | (3754x4742x10182) |  |  |  | 1 |  | 2847.6 | 2847.6 | AMC2 | [7 empty] | 0 | 0.85455 |  |  |  |  | 108.6 |  | x | o | [21 empty] | PAC
563 | V17566-SKXD-7168 | SK6-3 | ANGLE | A-1 | SK6-3-A-1 | L50*50*10 | 38 | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
564 | V17566-SKXD-7168 | SK6-3 | ANGLE | A-27 | SK6-3-A-27 | L75*75*6 | 2437 | SS400 | 3 |  | 3 | 16.7 | 50.1 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
565 | V17566-SKXD-7168 | SK6-3 | ANGLE | A-28 | SK6-3-A-28 | L75*75*6 | 495 | SS400 | 1 |  | 1 | 3.39 | 3.39 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.14 |  |  |  | 75 | Greenish Grey, Grey | 0.07 | [6 empty] | 75 | Greenish Grey, Grey | 0.07 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( tăng chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
566 | V17566-SKXD-7168 | SK6-3 | ANGLE | A-29 | SK6-3-A-29 | L75*75*6 | 1410 | SS400 | 1 |  | 1 | 9.66 | 9.66 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.41 |  |  |  | 75 | Greenish Grey, Grey | 0.205 | [6 empty] | 75 | Greenish Grey, Grey | 0.205 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( giảm chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
567 | V17566-SKXD-7168 | SK6-3 | ANGLE | AFY-52 | SK6-3-AFY-52 | L150*150*12 | 4003 | SS400 | 4 |  | 4 | 109.3 | 437.1 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 9.4 |  |  |  | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
568 | V17566-SKXD-7168 | SK6-3 | ANGLE | AFY-58 | SK6-3-AFY-58 | L130*130*9 | 3992 | SS400 | 1 |  | 1 | 71.3 | 71.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2 |  |  |  | 75 | Greenish Grey, Grey | 1 | [6 empty] | 75 | Greenish Grey, Grey | 1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
569 | V17566-SKXD-7168 | SK6-3 | CHANNEL | CFY-7 | SK6-3-CFY-7 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
570 | V17566-SKXD-7168 | SK6-3 | PIPE 6" SCH.40 | D-3 | SK6-3-D-3 | CHS168.28*7.11 | 242 | A106 Gr.B | 1 |  | 1 | 6.8 | 6.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
571 | V17566-SKXD-7168 | SK6-3 | PIPE 4" SCH.40 | D-4 | SK6-3-D-4 | CHS114.3*6.02 | 242 | A106 Gr.B | 1 |  | 1 | 3.8 | 3.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
572 | V17566-SKXD-7168 | SK6-3 | BLIND 6" 150# SO-RF | FL-2 | SK6-3-FL-2 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 11.6 | 11.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
573 | V17566-SKXD-7168 | SK6-3 | FLANGE 6" 150# SO-RF | FL-3 | SK6-3-FL-3 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 8.5 | 8.5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
574 | V17566-SKXD-7168 | SK6-3 | FLANGE 4" 150# SO-RF | FL-4 | SK6-3-FL-4 | PL22.3*229 | 229 | A105 | 1 |  | 1 | 6.5 | 6.5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
575 | V17566-SKXD-7168 | SK6-3 | BLIND 4" 150# SO-RF | FL-5 | SK6-3-FL-5 | PL22.3*229 | 229 | A105 | 1 |  | 1 | 7.3 | 7.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
576 | V17566-SKXD-7168 | SK6-3 | PLATE | G-7 | SK6-3-G-7 | PL10*126 | 211 | SS400 | 2 |  | 2 | 1.9 | 3.7 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
577 | V17566-SKXD-7168 | SK6-3 | PLATE | G-8 | SK6-3-G-8 | PL10*152 | 161 | SS400 | 2 |  | 2 | 1.9 | 3.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
578 | V17566-SKXD-7168 | SK6-3 | GASKET 6" 150# SO-RF | GK-1 | SK6-3-GK-1 | CHS215.9*22.6 | 3 | NON-METALLIC | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
579 | V17566-SKXD-7168 | SK6-3 | GASKET 4" 150# SO-RF | GK-2 | SK6-3-GK-2 | CHS157.2*20.55 | 3 | NON-METALLIC | 1 |  | 1 | 0.2 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
580 | V17566-SKXD-7168 | SK6-3 | BEND PLATE | GX-1 | SK6-3-GX-1 | PL6*370 | 509 | SS400 | 1 |  | 1 | 8.9 | 8.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
581 | V17566-SKXD-7168 | SK6-3 | COUPLING 2" 3000# | M-1 | SK6-3-M-1 | COUPLING 2" 3000# | 86 | A105 | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
582 | V17566-SKXD-7168 | SK6-3 | SQ HEAD PLUG 2" 3000# | M-2 | SK6-3-M-2 | D55 | 30 | A105 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
583 | V17566-SKXD-7168 | SK6-3 | PLATE | P-2 | SK6-3-P-2 | PL6*138 | 138 | SS400 | 1 |  | 1 | 0.9 | 0.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
584 | V17566-SKXD-7168 | SK6-3 | PLATE | P-18 | SK6-3-P-18 | PL6*51 | 76 | SS400 | 21 |  | 21 | 0.2 | 3.8 | AMC2 | Plate | MCC |  |  | 21 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
585 | V17566-SKXD-7168 | SK6-3 | SHELL PLATE | SH-6 | SK6-3-SH-6 | PL6*2000 | 4413 | SS400 | 3 |  | 3 | 415.3 | 1246 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | 53.1 |  |  |  | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
586 | V17566-SKXD-7168 | SK6-3 | SHELL PLATE | SH-8 | SK6-3-SH-8 | PL6*1500 | 4413 | SS400 | 1 |  | 1 | 311.5 | 311.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
587 | V17566-SKXD-7168 | SK6-3 | SHELL PLATE | SH-9 | SK6-3-SH-9 | PL6*667 | 4413 | SS400 | 1 |  | 1 | 138.4 | 138.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.9 |  |  |  | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
588 | V17566-SKXD-7168 | SK6-3 | SHELL PLATE | SH-10 | SK6-3-SH-10 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 413.6 | 413.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.6 |  |  |  | 75 | Greenish Grey, Grey | 8.8 | [6 empty] | 75 | Greenish Grey, Grey | 8.8 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
591 | V17566-SKXD-7171 | SK6-4 | SHELL PLATE |  |  | (3488x2473x10182) |  |  |  | 1 |  | 2822.4 | 2822.4 | AMC2 | [7 empty] | 0 | 0.89362 |  |  |  |  | 107.9 |  | x | o | [21 empty] | PAC
592 | V17566-SKXD-7171 | SK6-4 | ANGLE | A-1 | SK6-4-A-1 | L50*50*10 | 38 | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
593 | V17566-SKXD-7171 | SK6-4 | ANGLE | A-27 | SK6-4-A-27 | L75*75*6 | 2437 | SS400 | 4 |  | 4 | 16.7 | 66.8 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 2.9 |  |  |  | 75 | Greenish Grey, Grey | 1.45 | [6 empty] | 75 | Greenish Grey, Grey | 1.45 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
594 | V17566-SKXD-7171 | SK6-4 | ANGLE | AFY-52 | SK6-4-AFY-52 | L150*150*12 | 4003 | SS400 | 4 |  | 4 | 109.3 | 437.1 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 9.4 |  |  |  | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
595 | V17566-SKXD-7171 | SK6-4 | ANGLE | AFY-58 | SK6-4-AFY-58 | L130*130*9 | 3992 | SS400 | 1 |  | 1 | 71.3 | 71.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2 |  |  |  | 75 | Greenish Grey, Grey | 1 | [6 empty] | 75 | Greenish Grey, Grey | 1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
596 | V17566-SKXD-7171 | SK6-4 | CHANNEL | CFY-7 | SK6-4-CFY-7 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
597 | V17566-SKXD-7171 | SK6-4 | PIPE 6" SCH.40 | D-3 | SK6-4-D-3 | CHS168.28*7.11 | 242 | A106 Gr.B | 1 |  | 1 | 6.8 | 6.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
598 | V17566-SKXD-7171 | SK6-4 | BLIND 6" 150# SO-RF | FL-2 | SK6-4-FL-2 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 11.6 | 11.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
599 | V17566-SKXD-7171 | SK6-4 | FLANGE 6" 150# SO-RF | FL-3 | SK6-4-FL-3 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 8.5 | 8.5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
600 | V17566-SKXD-7171 | SK6-4 | PLATE | G-7 | SK6-4-G-7 | PL10*126 | 211 | SS400 | 2 |  | 2 | 1.9 | 3.7 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
601 | V17566-SKXD-7171 | SK6-4 | PLATE | G-8 | SK6-4-G-8 | PL10*152 | 161 | SS400 | 2 |  | 2 | 1.9 | 3.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
602 | V17566-SKXD-7171 | SK6-4 | GASKET 6" 150# SO-RF | GK-1 | SK6-4-GK-1 | CHS215.9*22.6 | 3 | NON-METALLIC | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
603 | V17566-SKXD-7171 | SK6-4 | COUPLING 2" 3000# | M-1 | SK6-4-M-1 | COUPLING 2" 3000# | 86 | A105 | 1 |  | 1 | 0.7 | 0.7 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
604 | V17566-SKXD-7171 | SK6-4 | SQ HEAD PLUG 2" 3000# | M-2 | SK6-4-M-2 | D55 | 30 | A105 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
605 | V17566-SKXD-7171 | SK6-4 | PLATE | P-18 | SK6-4-P-18 | PL6*51 | 76 | SS400 | 20 |  | 20 | 0.2 | 3.7 | AMC2 | Plate | MCC |  |  | 20 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
606 | V17566-SKXD-7171 | SK6-4 | SHELL PLATE | SH-6 | SK6-4-SH-6 | PL6*2000 | 4413 | SS400 | 3 |  | 3 | 415.4 | 1246.2 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | 53.1 |  |  |  | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 75 | Greenish Grey, Grey | 26.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
607 | V17566-SKXD-7171 | SK6-4 | SHELL PLATE | SH-8 | SK6-4-SH-8 | PL6*1500 | 4413 | SS400 | 1 |  | 1 | 311.5 | 311.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
608 | V17566-SKXD-7171 | SK6-4 | SHELL PLATE | SH-9 | SK6-4-SH-9 | PL6*667 | 4413 | SS400 | 1 |  | 1 | 138.4 | 138.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.9 |  |  |  | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
609 | V17566-SKXD-7171 | SK6-4 | SHELL PLATE | SH-13 | SK6-4-SH-13 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 414.1 | 414.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
611 | V17566-SKXD-7174 | SK6-5 | SHELL PLATE |  |  | (3822x2433x10487) |  |  |  | 1 |  | 3064.1 | 3064.1 | AMC2 | [7 empty] | 0 | 0.92857 |  |  |  |  | 112.6 |  | x | o | [21 empty] | PAC
612 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-1 | SK6-5-A-1 | L50*50*10 | 38 | SS400 | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
613 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-22 | SK6-5-A-22 | L75*75*6 | 1284 | SS400 | 1 |  | 1 | 8.8 | 8.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
614 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-24 | SK6-5-A-24 | L75*75*6 | 2516 | SS400 | 2 |  | 2 | 17.2 | 34.5 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.5 |  |  |  | 75 | Greenish Grey, Grey | 0.75 | [6 empty] | 75 | Greenish Grey, Grey | 0.75 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
615 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-25 | SK6-5-A-25 | L75*75*6 | 581 | SS400 | 1 |  | 1 | 4 | 4 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
616 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-26 | SK6-5-A-26 | L75*75*6 | 514 | SS400 | 1 |  | 1 | 3.52 | 3.52 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.15 |  |  |  | 75 | Greenish Grey, Grey | 0.075 | [6 empty] | 75 | Greenish Grey, Grey | 0.075 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( tăng chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
617 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-27 | SK6-5-A-27 | L75*75*6 | 2437 | SS400 | 3 |  | 3 | 16.7 | 50.1 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 2.1 |  |  |  | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 75 | Greenish Grey, Grey | 1.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
618 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-30 | SK6-5-A-30 | L75*75*6 | 1429 | SS400 | 1 |  | 1 | 9.79 | 9.79 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.42 |  |  |  | 75 | Greenish Grey, Grey | 0.21 | [6 empty] | 75 | Greenish Grey, Grey | 0.21 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi chiều dài ( giảm chiều dài) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
619 | V17566-SKXD-7174 | SK6-5 | ANGLE | A-32 | SK6-5-A-32 | L75*75*6 | 1184 | SS400 | 1 |  | 1 | 8.1 | 8.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 |  |  |  | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 75 | Greenish Grey, Grey | 0.15 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
620 | V17566-SKXD-7174 | SK6-5 | ANGLE | AFY-52 | SK6-5-AFY-52 | L150*150*12 | 4003 | SS400 | 4 |  | 4 | 109.3 | 437.1 | AMC2 | Shape | PMC |  |  | 4 | 0 | 1 | [6 empty] | 9.4 |  |  |  | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 75 | Greenish Grey, Grey | 4.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
621 | V17566-SKXD-7174 | SK6-5 | ANGLE | AFY-58 | SK6-5-AFY-58 | L130*130*9 | 3992 | SS400 | 1 |  | 1 | 71.3 | 71.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2 |  |  |  | 75 | Greenish Grey, Grey | 1 | [6 empty] | 75 | Greenish Grey, Grey | 1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
622 | V17566-SKXD-7174 | SK6-5 | CHANNEL | CFY-7 | SK6-5-CFY-7 | [200*80*7.5*11 | 3964 | SS400 | 1 |  | 1 | 97.5 | 97.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 2.7 |  |  |  | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 75 | Greenish Grey, Grey | 1.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
623 | V17566-SKXD-7174 | SK6-5 | PIPE 6" SCH.40 | D-3 | SK6-5-D-3 | CHS168.28*7.11 | 242 | A106 Gr.B | 1 |  | 1 | 6.8 | 6.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
624 | V17566-SKXD-7174 | SK6-5 | Pipe 3" SCH.40 | D-5 | SK6-5-D-5 | CHS88.9*5.49 | 242 | A106 Gr.B | 1 |  | 1 | 2.7 | 2.7 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
625 | V17566-SKXD-7174 | SK6-5 | BLIND 6" 150# SO-RF | FL-2 | SK6-5-FL-2 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 11.6 | 11.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
626 | V17566-SKXD-7174 | SK6-5 | FLANGE 6" 150# SO-RF | FL-3 | SK6-5-FL-3 | PL23.8*279 | 279 | A105 | 1 |  | 1 | 8.5 | 8.5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
627 | V17566-SKXD-7174 | SK6-5 | FLANGE 3" 150# SO-RF | FL-8 | SK6-5-FL-8 | PL22.3*190 | 190 | A105 | 1 |  | 1 | 4.2 | 4.2 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
628 | V17566-SKXD-7174 | SK6-5 | BLIND 3" 150# SO-RF | FL-9 | SK6-5-FL-9 | PL22.3*190 | 190 | A105 | 1 |  | 1 | 5 | 5 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
629 | V17566-SKXD-7174 | SK6-5 | PLATE | G-7 | SK6-5-G-7 | PL10*126 | 212 | SS400 | 3 |  | 3 | 1.9 | 5.6 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [6 empty] | Chi tiết thay đổi biên dạng | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
630 | V17566-SKXD-7174 | SK6-5 | PLATE | G-8 | SK6-5-G-8 | PL10*152 | 161 | SS400 | 3 |  | 3 | 1.9 | 5.8 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
631 | V17566-SKXD-7174 | SK6-5 | PLATE | G-11 | SK6-5-G-11 | PL10*152 | 304 | SS400 | 4 |  | 4 | 3.6 | 14.5 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
632 | V17566-SKXD-7174 | SK6-5 | PLATE | G-13 | SK6-5-G-13 | PL55*406 | 762 | SM490 | 1 |  | 1 | 125.5 | 125.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 |  |  |  | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 75 | Greenish Grey, Grey | 0.35 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
633 | V17566-SKXD-7174 | SK6-5 | GASKET 6" 150# SO-RF | GK-1 | SK6-5-GK-1 | CHS215.9*22.6 | 3 | NON-METALLIC | 1 |  | 1 | 0.3 | 0.3 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
634 | V17566-SKXD-7174 | SK6-5 | GASKET 3" 150# SO-RF | GK-3 | SK6-5-GK-3 | CHS127*18.15 | 3 | NON-METALLIC | 1 |  | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
635 | V17566-SKXD-7174 | SK6-5 | BEND PLATE | GX-1 | SK6-5-GX-1 | PL6*370 | 509 | SS400 | 1 |  | 1 | 8.9 | 8.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
636 | V17566-SKXD-7174 | SK6-5 | PLATE | P-2 | SK6-5-P-2 | PL6*138 | 138 | SS400 | 1 |  | 1 | 0.9 | 0.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
637 | V17566-SKXD-7174 | SK6-5 | PLATE | P-18 | SK6-5-P-18 | PL6*51 | 76 | SS400 | 39 |  | 39 | 0.2 | 7.1 | AMC2 | Plate | MCC |  |  | 39 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
638 | V17566-SKXD-7174 | SK6-5 | PLATE | PF-3 | SK6-5-PF-3 | PL12*508 | 127 | SS400 | 1 |  | 1 | 23.8 | 23.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
639 | V17566-SKXD-7174 | SK6-5 | SHELL PLATE | SH-6 | SK6-5-SH-6 | PL6*2000 | 4413 | SS400 | 2 |  | 2 | 415.3 | 830.7 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 35.4 |  |  |  | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 75 | Greenish Grey, Grey | 17.7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
640 | V17566-SKXD-7174 | SK6-5 | SHELL PLATE | SH-8 | SK6-5-SH-8 | PL6*1500 | 4413 | SS400 | 1 |  | 1 | 311.5 | 311.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 13.3 |  |  |  | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 75 | Greenish Grey, Grey | 6.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
641 | V17566-SKXD-7174 | SK6-5 | SHELL PLATE | SH-9 | SK6-5-SH-9 | PL6*667 | 4413 | SS400 | 1 |  | 1 | 138.4 | 138.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 5.9 |  |  |  | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 75 | Greenish Grey, Grey | 2.95 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
642 | V17566-SKXD-7174 | SK6-5 | SHELL PLATE | SH-11 | SK6-5-SH-11 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 414 | 414 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [7 empty] | Chi tiết thay đổi vị trí lỗ khoét | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
643 | V17566-SKXD-7174 | SK6-5 | SHELL PLATE | SH-12 | SK6-5-SH-12 | PL6*2000 | 4413 | SS400 | 1 |  | 1 | 415.4 | 415.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 17.7 |  |  |  | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 75 | Greenish Grey, Grey | 8.85 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
646 | V17566-SKXD-7186 | SK7-1 | SHELL PLATE |  |  | (3531x2386x1651) |  |  |  | 1 |  | 677.6 | 677.6 | AMC2 | [7 empty] | 0 | 0.96552 |  |  |  |  | 19 |  | x | o | [21 empty] | PAC
647 | V17566-SKXD-7186 | SK7-1 | ANGLE | A-12 | SK7-1-A-12 | L75*75*6 | 863 | SS400 | 3 |  | 3 | 5.9 | 17.7 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | 0.8 |  |  |  | 75 | Greenish Grey, Grey | 0.4 | [6 empty] | 75 | Greenish Grey, Grey | 0.4 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
648 | V17566-SKXD-7186 | SK7-1 | ANGLE | A-31 | SK7-1-A-31 | L75*75*6 | 120 | SS400 | 1 |  | 1 | 0.8 | 0.8 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
649 | V17566-SKXD-7186 | SK7-1 | BEND PLATE | DF-1 | SK7-1-DF-1 | SPD634*12 | 203 | SS400 | 1 |  | 1 | 37.2 | 37.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
650 | V17566-SKXD-7186 | SK7-1 | PLATE | G-15 | SK7-1-G-15 | PL16*832 | 832 | SS400 | 1 |  | 1 | 28.6 | 28.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.5 |  |  |  | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 75 | Greenish Grey, Grey | 0.25 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
651 | V17566-SKXD-7186 | SK7-1 | PLATE | G-16 | SK7-1-G-16 | PL19*92 | 196 | SS400 | 4 |  | 4 | 1.7 | 6.7 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
652 | V17566-SKXD-7186 | SK7-1 | PLATE | G-17 | SK7-1-G-17 | PL10*76 | 270 | SS400 | 2 |  | 2 | 1.6 | 3.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
653 | V17566-SKXD-7186 | SK7-1 | PLATE | G-18 | SK7-1-G-18 | PL16*832 | 832 | SS400 | 1 |  | 1 | 68.3 | 68.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.1 |  |  |  | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 75 | Greenish Grey, Grey | 0.55 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
654 | V17566-SKXD-7186 | SK7-1 | PAD PLATE | GF-2 | SK7-1-GF-2 | PL12*1300 | 1200 | SS400 | 1 |  | 1 | 70.8 | 70.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 1.6 |  |  |  | 75 | Greenish Grey, Grey | 0.8 | [6 empty] | 75 | Greenish Grey, Grey | 0.8 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication
655 | V17566-SKXD-7186 | SK7-1 | GASKET OD.746 ID.635 | GK-4 | SK7-1-GK-4 | CHS746*55.5 | 3 | NON-METALLIC | 1 |  | 1 | 2.8 | 2.8 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing
656 | V17566-SKXD-7186 | SK7-1 | PLATE | P-18 | SK7-1-P-18 | PL6*51 | 76 | SS400 | 10 |  | 10 | 0.2 | 1.8 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
657 | V17566-SKXD-7186 | SK7-1 | ROUND BAR | R-1 | SK7-1-R-1 | D19 | 448 | SS400 | 1 |  | 1 | 0.9 | 0.9 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
658 | V17566-SKXD-7186 | SK7-1 | ROUND BAR | RX-2 | SK7-1-RX-2 | D19 | 839 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
659 | V17566-SKXD-7186 | SK7-1 | ROUND BAR | RX-3 | SK7-1-RX-3 | D19 | 271 | SS400 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | 0 |  |  |  | 75 | Greenish Grey, Grey | 0 | [6 empty] | 75 | Greenish Grey, Grey | 0 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
660 | V17566-SKXD-7186 | SK7-1 | SHELL PLATE | SH-78 | SK7-1-SH-78 | PL8*1651 | 4410.5 | SS400 | 1 |  | 1 | 436.6 | 436.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 14 |  |  |  | 75 | Greenish Grey, Grey | 7 | [6 empty] | 75 | Greenish Grey, Grey | 7 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
662 | V17566-SKXD-7188 | SK7-2 | SHELL PLATE |  |  | (3445x2386x1651) |  |  |  | 1 |  | 482.4 | 482.4 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 15.8 |  | x | o | [21 empty] | PAC
663 | V17566-SKXD-7188 | SK7-2 | ANGLE | A-12 | SK7-2-A-12 | L75*75*6 | 863 | SS400 | 4 |  | 4 | 5.9 | 23.6 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1 |  |  |  | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
664 | V17566-SKXD-7188 | SK7-2 | PLATE | P-18 | SK7-2-P-18 | PL6*51 | 76 | SS400 | 12 |  | 12 | 0.2 | 2.2 | AMC2 | Plate | MCC |  |  | 12 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
665 | V17566-SKXD-7188 | SK7-2 | SHELL PLATE | SH-74 | SK7-2-SH-74 | PL8*1651 | 4413 | SS400 | 1 |  | 1 | 456.6 | 456.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 14.6 |  |  |  | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
666 | V17566-SKXD-7190 | SK7-3 | SHELL PLATE |  |  | (3445x2385x1651) |  |  |  | 2 |  | 482.4 | 964.9 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 31.5 |  | x | o | [21 empty] | PAC
667 | V17566-SKXD-7190 | SK7-3 | ANGLE | A-12 | SK7-3-A-12 | L75*75*6 | 863 | SS400 | 4 |  | 8 | 5.9 | 47.3 | AMC2 | Shape | MCC |  |  | 8 | 0 | 2 | [6 empty] | 2 |  |  |  | 75 | Greenish Grey, Grey | 1 | [6 empty] | 75 | Greenish Grey, Grey | 1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
668 | V17566-SKXD-7190 | SK7-3 | PLATE | P-18 | SK7-3-P-18 | PL6*51 | 76 | SS400 | 12 |  | 24 | 0.2 | 4.4 | AMC2 | Plate | MCC |  |  | 24 | 0 | 2 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
669 | V17566-SKXD-7190 | SK7-3 | SHELL PLATE | SH-1 | SK7-3-SH-1 | PL8*1651 | 4410.5 | SS400 | 1 |  | 2 | 456.6 | 913.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 29.3 |  |  |  | 75 | Greenish Grey, Grey | 14.65 | [6 empty] | 75 | Greenish Grey, Grey | 14.65 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
670 | V17566-SKXD-7192 | SK7-4 | SHELL PLATE |  |  | (3445x2385x1651) |  |  |  | 1 |  | 500.3 | 500.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 16.4 |  | x | o | [21 empty] | PAC
671 | V17566-SKXD-7192 | SK7-4 | ANGLE | A-12 | SK7-4-A-12 | L75*75*6 | 863 | SS400 | 4 |  | 4 | 5.9 | 23.6 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1 |  |  |  | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 75 | Greenish Grey, Grey | 0.5 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
672 | V17566-SKXD-7192 | SK7-4 | ANGLE | A-14 | SK7-4-A-14 | L75*75*6 | 723 | SS400 | 2 |  | 2 | 5 | 9.9 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.4 |  |  |  | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 75 | Greenish Grey, Grey | 0.2 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
673 | V17566-SKXD-7192 | SK7-4 | PLATE | G-11 | SK7-4-G-11 | PL10*152 | 304 | SS400 | 2 |  | 2 | 3.6 | 7.3 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.2 |  |  |  | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 75 | Greenish Grey, Grey | 0.1 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
674 | V17566-SKXD-7192 | SK7-4 | PLATE | P-18 | SK7-4-P-18 | PL6*51 | 76 | SS400 | 16 |  | 16 | 0.2 | 2.9 | AMC2 | Plate | MCC |  |  | 16 | 0 | 1 | [6 empty] | 0.1 |  |  |  | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 75 | Greenish Grey, Grey | 0.05 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
675 | V17566-SKXD-7192 | SK7-4 | SHELL PLATE | SH-74 | SK7-4-SH-74 | PL8*1651 | 4413 | SS400 | 1 |  | 1 | 456.6 | 456.6 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 14.6 |  |  |  | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 75 | Greenish Grey, Grey | 7.3 | [6 empty] | 40 |  | Jotun | PAC | [15 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication
677 | V17566-SKXD-7194 | SR-1 | SELF-DRILLING HEX M6 | M-3 | SR-1-M-3 | NUT_M6 | 32 | SS400(Galv.) | 1 |  | 376 | 0 | 1 | AMC2 | Purchasing | KHO |  |  | 0 | 376 | 0 | [5 empty] | Loose Part | 0.5 |  |  |  |  | Hot Dip Galvanized | 0.25 | [7 empty] | Hot Dip Galvanized | 0.25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchasing

## U284BRSTK
ASSEMBLY PART LIST
Project name / Tên Dự án : JOHN S RAINEY GENETATING STATION
Item Name / Tên Hạng mục : Bracing&Lifting Lug for Outlet Stack
Contract No. / Số Hợp đồng : U284
Prepared By / Chuẩn bị : Design Consultant Center
Document No. / Số Tài liệu : U284-SFR-APL-019 | [7 empty] | Rev./ Số Sửa đổi: 1 | [10 empty] | Date: 25-06-2026 |  |  | Content Rev. | [9 empty] | Type Fabrication | [6 empty] | Type
DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC |  |  |  | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC-F | DCC-X | DCC-Y | DCC-Z | DCC-J | DCC-BH | DCC
No. | Drawing Number | Assembly No. | Description | Part No. |  | Size | Length | Material | Q'ty | Set | T.Q'ty | U.Weight | T.Weight |  |  |  | Loose Part | Total Area (m2) | Remark | AS Symbol | Delivery item | Rev.1 (18/06/2026) | Rev.2 (dd/mm/yyyy) | Rev.3 (dd/mm/yyyy) | Rev.4 (dd/mm/yyyy) | Rev.5 (dd/mm/yyyy) | Rev.6 (dd/mm/yyyy) | Rev.7 (dd/mm/yyyy) | Rev.8 (dd/mm/yyyy) | Rev.9 (dd/mm/yyyy) | Rev.10 (dd/mm/yyyy) | Khoan Lỗ | Lốc tròn (Uốn cong) | Sấn | Vát mép & Cắt miệng | Gia công cơ khí (Không thay đổi chiều dày) | Gia công cơ khí (Có thay đổi chiều dày) | Tổ hợp | Fabrication or Purchasing
1 | 2 | 3 | 4 | 5A (Marking as Dwg.) | 5B (Marking as Cutting) | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |  | 14 | 17 | 18 | 19 | 20 | 30A | 30B | 30C | 30D | 30E | 30F | 30G | 30H | 30I | 30J | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
1 | V17566-SKXD-AS-OS-BR-1 | OS-BR-1 | CV |  |  | (2146x10x100) |  |  |  | 5 |  | 16.8 | 84.2 | AMC2 |  |  |  | 2.4 |  | x | o
2 | V17566-SKXD-AS-OS-BR-1 | OS-BR-1 | PLATE | P-5001 | OS-BR-1-P-5001 | PL10*100 | 2146 | SS400 | 1 |  | 5 | 16.8 | 84.2 | AMC2 | Plate | MCC | Loose Part | 2.4 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
3 | V17566-SKXD-AS-OS-BR-2 | OS-BR-2 | CV |  |  | (3378x8x1981) |  |  |  | 28 |  | 37.7 | 1055.6 | AMC2 |  |  |  | 35.5 |  | x | o
4 | V17566-SKXD-AS-OS-BR-2 | OS-BR-2 | PLATE | P-22 | OS-BR-2-P-22 | PL8*150 | 4003 | SS400 | 1 |  | 28 | 37.7 | 1055.6 | AMC2 | Plate | MCC | Loose Part | 35.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
5 | V17566-SKXD-AS-OS-BR-3 | OS-BR-3 | CV |  |  | (1400x10x100) |  |  |  | 10 |  | 11 | 109.9 | AMC2 |  |  |  | 3.1 |  | x | o
6 | V17566-SKXD-AS-OS-BR-3 | OS-BR-3 | PLATE | P-5007 | OS-BR-3-P-5007 | PL10*100 | 1400 | SS400 | 1 |  | 10 | 11 | 109.9 | AMC2 | Plate | MCC | Loose Part | 3.1 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
7 | V17566-SKXD-AS-OS-BR-4 | OS-BR-4 | CV |  |  | (9800x10x100) |  |  |  | 25 |  | 76.9 | 1923.2 | AMC2 |  |  |  | 53.9 |  | x | o
8 | V17566-SKXD-AS-OS-BR-4 | OS-BR-4 | PLATE | P-5000 | OS-BR-4-P-5000 | PL10*100 | 9800 | SS400 | 1 |  | 25 | 76.9 | 1923.2 | AMC2 | Plate | MCC | Loose Part | 53.9 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
9 | V17566-SKXD-AS-OS-BR-5 | OS-BR-5 | CV |  |  | (3371x8x2185) |  |  |  | 10 |  | 38.9 | 388.6 | AMC2 |  |  |  | 13.1 |  | x | o
10 | V17566-SKXD-AS-OS-BR-5 | OS-BR-5 | PLATE | P-29 | OS-BR-5-P-29 | PL8*150 | 4127 | SS400 | 1 |  | 10 | 38.9 | 388.6 | AMC2 | Plate | MCC | Loose Part | 13.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
11 | V17566-SKXD-AS-OS-BR-6 | OS-BR-6 | CV |  |  | (1263x8x313) |  |  |  | 3 |  | 11.8 | 35.4 | AMC2 |  |  |  | 1.2 |  | x | o
12 | V17566-SKXD-AS-OS-BR-6 | OS-BR-6 | PLATE | P-23 | OS-BR-6-P-23 | PL8*150 | 1254 | SS400 | 1 |  | 3 | 11.8 | 35.4 | AMC2 | Plate | MCC | Loose Part | 1.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
13 | V17566-SKXD-AS-OS-BR-7 | OS-BR-7 | CV |  |  | (8554x60x100) |  |  |  | 1 |  | 57.3 | 57.3 | AMC2 |  |  |  | 3.7 |  | x | o
14 | V17566-SKXD-AS-OS-BR-7 | OS-BR-7 | PLATE | 1C100-1 | OS-BR-7-1C100-1 | PL4*56 | 92 | SS400 | 2 |  | 2 | 0.2 | 0.3 | AMC2 | Plate | MCC |  | 0 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
16 | V17566-SKXD-AS-OS-BR-8 | OS-BR-8 | CV |  |  | (6400x10x100) |  |  |  | 8 |  | 50.2 | 401.9 | AMC2 |  |  |  | 11.3 |  | x | o
17 | V17566-SKXD-AS-OS-BR-8 | OS-BR-8 | PLATE | P-5005 | OS-BR-8-P-5005 | PL10*100 | 6400 | SS400 | 1 |  | 8 | 50.2 | 401.9 | AMC2 | Plate | MCC | Loose Part | 11.3 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
18 | V17566-SKXD-AS-OS-BR-9 | OS-BR-9 | CV |  |  | (5120x60x100) |  |  |  | 1 |  | 34.4 | 34.4 | AMC2 |  |  |  | 2.2 | Revised | x | o | Giảm Q'ty(Cũ:2)
19 | V17566-SKXD-AS-OS-BR-9 | OS-BR-9 | PLATE | 1C100-1 | OS-BR-9-1C100-1 | PL4*56 | 92 | SS400 | 2 |  | 2 | 0.2 | 0.3 | AMC2 | Plate | MCC |  | 0 | Revised |  |  | Giảm Q'ty(Cũ:4) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
20 | V17566-SKXD-AS-OS-BR-9 | OS-BR-9 | BENT CHANNEL | CX-5 | OS-BR-9-CX-5 | C100*60*4 | 5120 | SS400 | 1 |  | 1 | 34.1 | 34.1 | AMC2 | Shape | PMC |  | 2.2 | Revised |  |  | Giảm Q'ty(Cũ:2) | [9 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
21 | V17566-SKXD-AS-OS-BR-10 | OS-BR-10 | CV |  |  | (2756x8x1239) |  |  |  | 1 |  | 28.3 | 28.3 | AMC2 |  |  |  | 1 |  | x | o
22 | V17566-SKXD-AS-OS-BR-10 | OS-BR-10 | PLATE | P-27 | OS-BR-10-P-27 | PL8*150 | 3005 | SS400 | 1 |  | 1 | 28.3 | 28.3 | AMC2 | Plate | MCC | Loose Part | 1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
23 | V17566-SKXD-AS-OS-BR-11 | OS-BR-11 | CV |  |  | (1810x10x100) |  |  |  | 2 |  | 14.2 | 28.4 | AMC2 |  |  |  | 0.8 |  | x | o
24 | V17566-SKXD-AS-OS-BR-11 | OS-BR-11 | PLATE | P-5006 | OS-BR-11-P-5006 | PL10*100 | 1810 | SS400 | 1 |  | 2 | 14.2 | 28.4 | AMC2 | Plate | MCC | Loose Part | 0.8 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
25 | V17566-SKXD-AS-OS-BR-12 | OS-BR-12 | CV |  |  | (2242x8x830) |  |  |  | 1 |  | 22.1 | 22.1 | AMC2 |  |  |  | 0.7 |  | x | o
26 | V17566-SKXD-AS-OS-BR-12 | OS-BR-12 | PLATE | P-28 | OS-BR-12-P-28 | PL8*150 | 2348 | SS400 | 1 |  | 1 | 22.1 | 22.1 | AMC2 | Plate | MCC | Loose Part | 0.7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
27 | V17566-SKXD-AS-OS-BR-13 | OS-BR-13 | CV |  |  | (1788x8x516) |  |  |  | 3 |  | 17 | 51.1 | AMC2 |  |  |  | 1.7 |  | x | o
28 | V17566-SKXD-AS-OS-BR-13 | OS-BR-13 | PLATE | P-24 | OS-BR-13-P-24 | PL8*150 | 1809 | SS400 | 1 |  | 3 | 17 | 51.1 | AMC2 | Plate | MCC | Loose Part | 1.7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
29 | V17566-SKXD-AS-OS-BR-14 | OS-BR-14 | CV |  |  | (8000x10x100) |  |  |  | 1 |  | 62.8 | 62.8 | AMC2 |  |  |  | 2 |  | x | o
30 | V17566-SKXD-AS-OS-BR-14 | OS-BR-14 | PLATE | P-5002 | OS-BR-14-P-5002 | PL10*100 | 8000 | SS400 | 1 |  | 1 | 62.8 | 62.8 | AMC2 | Plate | MCC | Loose Part | 2 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
31 | V17566-SKXD-AS-OS-BR-15 | OS-BR-15 | CV |  |  | (8375x60x100) |  |  |  | 1 |  | 56.1 | 56.1 | AMC2 |  |  |  | 3.6 |  | x | o
32 | V17566-SKXD-AS-OS-BR-15 | OS-BR-15 | PLATE | 1C100-1 | OS-BR-15-1C100-1 | PL4*56 | 92 | SS400 | 2 |  | 2 | 0.2 | 0.3 | AMC2 | Plate | MCC |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
33 | V17566-SKXD-AS-OS-BR-15 | OS-BR-15 | BENT CHANNEL | CX-3 | OS-BR-15-CX-3 | C100*60*4 | 8375 | SS400 | 1 |  | 1 | 55.8 | 55.8 | AMC2 | Shape | PMC |  | 3.6 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
34 | V17566-SKXD-AS-OS-BR-16 | OS-BR-16 | CV |  |  | (3069x8x1526) |  |  |  | 1 |  | 32.5 | 32.5 | AMC2 |  |  |  | 1.1 |  | x | o
35 | V17566-SKXD-AS-OS-BR-16 | OS-BR-16 | PLATE | P-25 | OS-BR-16-P-25 | PL8*150 | 3448 | SS400 | 1 |  | 1 | 32.5 | 32.5 | AMC2 | Plate | MCC | Loose Part | 1.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
36 | V17566-SKXD-AS-OS-BR-18 | OS-BR-18 | CV |  |  | (12000x10x100) |  |  |  | 4 |  | 94.2 | 376.8 | AMC2 |  |  |  | 10.6 |  | x | o
37 | V17566-SKXD-AS-OS-BR-18 | OS-BR-18 | PLATE | P-5004 | OS-BR-18-P-5004 | PL10*100 | 12000 | SS400 | 1 |  | 4 | 94.2 | 376.8 | AMC2 | Plate | MCC | Loose Part | 10.6 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
38 | V17566-SKXD-AS-OS-BR-19 | OS-BR-19 | CV |  |  | (2901x8x1535) |  |  |  | 2 |  | 31 | 61.9 | AMC2 |  |  |  | 2.1 |  | x | o
39 | V17566-SKXD-AS-OS-BR-19 | OS-BR-19 | PLATE | P-26 | OS-BR-19-P-26 | PL8*150 | 3288 | SS400 | 1 |  | 2 | 31 | 61.9 | AMC2 | Plate | MCC | Loose Part | 2.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
40 | V17566-SKXD-AS-OS-BR-20 | OS-BR-20 | CV |  |  | (6850x10x100) |  |  |  | 2 |  | 53.8 | 107.5 | AMC2 |  |  |  | 3 |  | x | o
41 | V17566-SKXD-AS-OS-BR-20 | OS-BR-20 | PLATE | P-5003 | OS-BR-20-P-5003 | PL10*100 | 6850 | SS400 | 1 |  | 2 | 53.8 | 107.5 | AMC2 | Plate | MCC | Loose Part | 3 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
42 | V17566-SKXD-AS-OS-BR-21 | OS-BR-21 | CV |  |  | (6364x60x100) |  |  |  | 1 |  | 42.7 | 42.7 | AMC2 |  |  |  | 2.8 | Revised | x | o | Giảm Q'ty(Cũ:2)
43 | V17566-SKXD-AS-OS-BR-21 | OS-BR-21 | PLATE | 1C100-1 | OS-BR-21-1C100-1 | PL4*56 | 92 | SS400 | 2 |  | 2 | 0.2 | 0.3 | AMC2 | Plate | MCC |  | 0 | Revised |  |  | Giảm Q'ty(Cũ:4) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
44 | V17566-SKXD-AS-OS-BR-21 | OS-BR-21 | BENT CHANNEL | CX-2 | OS-BR-21-CX-2 | C100*60*4 | 6364 | SS400 | 1 |  | 1 | 42.4 | 42.4 | AMC2 | Shape | PMC |  | 2.8 | Revised |  |  | Giảm Q'ty(Cũ:2) | [9 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
45 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | CV |  |  | (7005x150x2529) |  |  |  | 2 |  | 247.4 | 494.7 | AMC2 |  |  |  | 15.9 |  | x | o
46 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | PLATE | 1H150-1 | OS-BR-23-1H150-1 | PL4*70 | 130 | SS400 | 2 |  | 4 | 0.3 | 1.1 | AMC2 | Plate | MCC |  | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
47 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | BENT ANGLE | AX-9 | OS-BR-23-AX-9 | L65*65*4 | 3182 | SS400 | 2 |  | 4 | 12.6 | 50.4 | AMC2 | Shape | PMC |  | 3.3 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
48 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | BENT CHANNEL | CX-1 | OS-BR-23-CX-1 | H150*150*7*10 | 6950 | SS400 | 1 |  | 2 | 216.3 | 432.6 | AMC2 | Shape | PMC |  | 12.1 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
49 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | PLATE | P-30 | OS-BR-23-P-30 | PL4*124 | 248 | SS400 | 1 |  | 2 | 0.9 | 1.8 | AMC2 | Plate | MCC |  | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
50 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | PLATE | P-31 | OS-BR-23-P-31 | PL10*120 | 183 | SS400 | 2 |  | 4 | 1.7 | 6.8 | AMC2 | Plate | MCC |  | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
51 | V17566-SKXD-AS-OS-BR-23 | OS-BR-23 | PLATE | P-32 | OS-BR-23-P-32 | PL6*80 | 139 | SS400 | 2 |  | 4 | 0.5 | 2.1 | AMC2 | Plate | MCC |  | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
52 | V17566-SKXD-AS-OS-BR-24 | OS-BR-24 | CV |  |  | (7005x150x3404) |  |  |  | 1 |  | 232 | 232 | AMC2 |  |  |  | 7 |  | x | o
53 | V17566-SKXD-AS-OS-BR-24 | OS-BR-24 | PLATE | 1H150-1 | OS-BR-24-1H150-1 | PL4*70 | 130 | SS400 | 2 |  | 2 | 0.3 | 0.6 | AMC2 | Plate | MCC |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
54 | V17566-SKXD-AS-OS-BR-24 | OS-BR-24 | BENT ANGLE | AX-10 | OS-BR-24-AX-10 | L65*65*4 | 3220 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  | 0.8 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
55 | V17566-SKXD-AS-OS-BR-24 | OS-BR-24 | BENT CHANNEL | CX-6 | OS-BR-24-CX-6 | H150*150*7*10 | 6900 | SS400 | 1 |  | 1 | 214.8 | 214.8 | AMC2 | Shape | PMC |  | 6 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
56 | V17566-SKXD-AS-OS-BR-24 | OS-BR-24 | PLATE | P-31 | OS-BR-24-P-31 | PL10*120 | 183 | SS400 | 2 |  | 2 | 1.7 | 3.4 | AMC2 | Plate | MCC |  | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
57 | V17566-SKXD-AS-OS-BR-24 | OS-BR-24 | PLATE | P-33 | OS-BR-24-P-33 | PL6*80 | 139 | SS400 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Plate | MCC |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
58 | V17566-SKXD-AS-OS-BR-25 | OS-BR-25 | CV |  |  | (7017x150x3404) |  |  |  | 1 |  | 232 | 232 | AMC2 |  |  |  | 7 |  | x | o
59 | V17566-SKXD-AS-OS-BR-25 | OS-BR-25 | PLATE | 1H150-1 | OS-BR-25-1H150-1 | PL4*70 | 130 | SS400 | 2 |  | 2 | 0.3 | 0.6 | AMC2 | Plate | MCC |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
60 | V17566-SKXD-AS-OS-BR-25 | OS-BR-25 | BENT ANGLE | AX-10 | OS-BR-25-AX-10 | L65*65*4 | 3220 | SS400 | 1 |  | 1 | 12.7 | 12.7 | AMC2 | Shape | PMC |  | 0.8 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
61 | V17566-SKXD-AS-OS-BR-25 | OS-BR-25 | BENT CHANNEL | CX-6 | OS-BR-25-CX-6 | H150*150*7*10 | 6900 | SS400 | 1 |  | 1 | 214.8 | 214.8 | AMC2 | Shape | PMC |  | 6 | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
62 | V17566-SKXD-AS-OS-BR-25 | OS-BR-25 | PLATE | P-31 | OS-BR-25-P-31 | PL10*120 | 183 | SS400 | 2 |  | 2 | 1.7 | 3.4 | AMC2 | Plate | MCC |  | 0.1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
63 | V17566-SKXD-AS-OS-BR-25 | OS-BR-25 | PLATE | P-33 | OS-BR-25-P-33 | PL6*80 | 139 | SS400 | 1 |  | 1 | 0.5 | 0.5 | AMC2 | Plate | MCC |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
64 | V17566-SKXD-AS-OS-BR-26 | OS-BR-26 | CV |  |  | (5468x737x220) |  |  |  | 1 |  | 82.2 | 82.2 | AMC2 |  |  |  | 3.6 | Added | x | o | Thêm mới
65 | V17566-SKXD-AS-OS-BR-26 | OS-BR-26 | PLATE | 1C100-4 | OS-BR-26-1C100-4 | PL4*54 | 88 | SS400 | 4 |  | 4 | 0.1 | 0.6 | AMC2 | Plate | MCC |  | 0 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
66 | V17566-SKXD-AS-OS-BR-26 | OS-BR-26 | BENT CHANNEL | CX-27 | OS-BR-26-CX-27 | C100*60*6 | 5120 | SS400 | 1 |  | 1 | 50.2 | 50.2 | AMC2 | Shape | PMC |  | 2.2 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
67 | V17566-SKXD-AS-OS-BR-26 | OS-BR-26 | BENT CHANNEL | CX-30 | OS-BR-26-CX-30 | C100*60*6 | 3180 | SS400 | 1 |  | 1 | 29.8 | 29.8 | AMC2 | Shape | PMC |  | 1.3 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
68 | V17566-SKXD-AS-OS-BR-26 | OS-BR-26 | PLATE | P-53 | OS-BR-26-P-53 | PL10*141 | 150 | SS400 | 1 |  | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  | 0 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
69 | V17566-SKXD-AS-OS-BR-27 | OS-BR-27 | CV |  |  | (8564x60x100) |  |  |  | 1 |  | 84.2 | 84.2 | AMC2 |  |  |  | 3.7 | Added | x | o | Thêm mới
70 | V17566-SKXD-AS-OS-BR-27 | OS-BR-27 | PLATE | 1C100-4 | OS-BR-27-1C100-4 | PL4*54 | 88 | SS400 | 2 |  | 2 | 0.1 | 0.3 | AMC2 | Plate | MCC |  | 0 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
71 | V17566-SKXD-AS-OS-BR-27 | OS-BR-27 | BENT CHANNEL | CX-20 | OS-BR-27-CX-20 | C100*60*6 | 8564 | SS400 | 1 |  | 1 | 83.9 | 83.9 | AMC2 | Shape | PMC |  | 3.7 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication
72 | V17566-SKXD-AS-OS-BR-28 | OS-BR-28 | CV |  |  | (12000x10x100) |  |  |  | 2 |  | 94.2 | 188.4 | AMC2 |  |  |  | 5.3 | Added | x | o | Thêm mới
73 | V17566-SKXD-AS-OS-BR-28 | OS-BR-28 | PLATE | P-5008 | OS-BR-28-P-5008 | PL10*100 | 12000 | SS400 | 1 |  | 2 | 94.2 | 188.4 | AMC2 | Plate | MCC | Loose Part | 5.3 | Added |  |  | Thêm mới | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
74 | V17566-SKXD-AS-OS-LT-3 | OS-LT-3 | LIFTTING LUG |  |  | (250x25x150) |  |  |  | 2 |  | 6.4 | 12.9 | AMC2 |  |  |  | 0.2 |  | x | o
75 | V17566-SKXD-AS-OS-LT-3 | OS-LT-3 | PLATE | P-34 | OS-LT-3-P-34 | PL25*150 | 250 | SS400 | 1 |  | 2 | 6.4 | 12.9 | AMC2 | Plate | MCC | Loose Part | 0.2 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
76 | V17566-SKXD-AS-OS-LT-4 | OS-LT-4 | LIFTTING LUG |  |  | (220x101x200) |  |  |  | 55 |  | 4.4 | 241.7 | AMC2 |  |  |  | 6.3 |  | x | o
77 | V17566-SKXD-AS-OS-LT-4 | OS-LT-4 | PLATE | P-20 | OS-LT-4-P-20 | PL10*200 | 220 | SS400 | 1 |  | 55 | 3.5 | 190 | AMC2 | Plate | MCC |  | 5.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
78 | V17566-SKXD-AS-OS-LT-4 | OS-LT-4 | PLATE | P-21 | OS-LT-4-P-21 | PL20*85 | 90 | SS400 | 1 |  | 55 | 0.9 | 51.6 | AMC2 | Plate | MCC |  | 1 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
79 | V17566-SKXD-AS-OS-LT-5 | OS-LT-5 | LIFTTING LUG |  |  | (220x101x200) |  |  |  | 2 |  | 4.4 | 8.8 | AMC2 |  |  |  | 0.2 |  | x | o
80 | V17566-SKXD-AS-OS-LT-5 | OS-LT-5 | PLATE | P-20 | OS-LT-5-P-20 | PL10*200 | 220 | SS400 | 1 |  | 2 | 3.5 | 6.9 | AMC2 | Plate | MCC |  | 0.2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication
81 | V17566-SKXD-AS-OS-LT-5 | OS-LT-5 | PLATE | P-21 | OS-LT-5-P-21 | PL20*85 | 90 | SS400 | 1 |  | 2 | 0.9 | 1.9 | AMC2 | Plate | MCC |  | 0 | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication

## BTP-U284BRSTK
U284BRSTK
| Chủng loại | Thiết kế |  | Đã nhận |  | Còn thiếu |  |  |  | Đã nhận |  | Đồng bộ |  | Đã triển khai
|  | T.Q'ty | T.Weight | T.Q'ty | T.Weight | T.Q'ty | T.Weight |  |  | Số chi tiết | Khối lượng | Số chi tiết lớn | Khối lượng | Số chi tiết lớn | Khối lượng
| Shape | 16 | 1234.2 | 7 | 1026.1 | 9 | 208.1 |  | Total | 270 | 6272.4 |  | 0 |  | 0
| Plate | 263 | 5246.3 | 263 | 5246.3 | 0 | 0
| Purchasing | 0 | 0 | 0 | 0 | 0 | 0
| Total | 279 | 6480.5 | 270 | 6272.4 | 9 | 208.1 | [20 empty] | 450000
Chủng loại thép hình
| Shape | C100*60*4 | L65*65*4
| Chiều dài theo thiết kế (mm) | 19859 | 19168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL TK | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Đã nhận (mm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL Nhận | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Còn thiếu (mm) | 19859 | 19168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL thiếu | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu (kg) | 132.3 | 75.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chiều dày tôn
| Plate | #VALUE!
| Diện tích m2 theo thiết kế | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| SL TK | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0
| Diện tích còn thiếu( m2) | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Sl còn thiếu | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu(kg) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 862.2 | 64.1 | 11.9 | 1653.2 | 1590.1 | 3282.1 | 213.1 | 163.9 | 0 | 0 | 0 | 0 | #VALUE!
[11 empty] | 4 | 59 | 35 | 47 | 44 | 59 | 65 | 3 | 0 | 0 | 0 | 0 | #VALUE!
Chủng loại | Part No.1 | Size | Description | Length | Material | T.Q'ty | U.Weight | T.Weight | Đã nhận | Còn thiếu | 2026-07-06 | 2026-08-09 | 2026-08-11 | 2026-08-13 | 2026-08-16 | 2026-08-17 | 2026-09-20 | 2026-09-25 |  |  |  | KO BB | Lấy data | Ktra nối | Tôn | Cảnh báo thừa | DVG | MPR No | Qty MPR | Cutting No. | Qty Cutting | Date Issue
Plate | OS-BR-10-P-27 | PL8*150 | PLATE | 3005 | SS400 | 1 | 28.3 | 28.3 | 1 | 0 | 2026-08-13: 2 |  |  |  |  | #VALUE! | AB | PL8 | Thừa 1 | MCC
Plate | OS-BR-11-P-5006 | PL10*100 | PLATE | 1810 | SS400 | 2 | 14.2 | 28.4 | 2 | 0 | 2026-08-17: 2 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 3620 | 3620
Plate | OS-BR-12-P-28 | PL8*150 | PLATE | 2348 | SS400 | 1 | 22.1 | 22.1 | 1 | 0 | [12 empty] | #VALUE! |  | PL8 |  | MCC | bar: 2026-08-13
Plate | OS-BR-13-P-24 | PL8*150 | PLATE | 1809 | SS400 | 3 | 17 | 51 | 3 | 0 | 2026-08-16: 3 |  |  |  |  | #VALUE! |  | PL8 |  | MCC
Plate | OS-BR-14-P-5002 | PL10*100 | PLATE | 8000 | SS400 | 1 | 62.8 | 62.8 | 1 | 0 | [12 empty] | #VALUE! |  | PL10 |  | MCC | 8000 | 8000 | bar: 2026-08-17
Plate | OS-BR-15-1C100-1 | PL4*56 | PLATE | 92 | SS400 | 2 | 0.2 | 0.4 | 2 | 0 | 2026-08-11: 2 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Shape | OS-BR-15-CX-3 | C100*60*4 | BENT CHANNEL | 8375 | SS400 | 1 | 55.8 | 55.8 | 0 | 1 | [12 empty] | #VALUE! |  |  |  | PMC
Plate | OS-BR-16-P-25 | PL8*150 | PLATE | 3448 | SS400 | 1 | 32.5 | 32.5 | 1 | 0 | [12 empty] | #VALUE! | BA | PL8 | Thừa 1 | MCC | bar: 2026-08-13 to 2026-08-16
Plate | OS-BR-18-P-5004 | PL10*100 | PLATE | 12000 | SS400 | 4 | 94.2 | 376.8 | 4 | 0 | 2026-08-17: 4 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 48000 | 48000
Plate | OS-BR-19-P-26 | PL8*150 | PLATE | 3288 | SS400 | 2 | 31 | 62 | 2 | 0 | 2026-08-13: 2; 2026-08-16: 2 |  |  |  |  | #VALUE! | 2B2A | PL8 | Thừa 2 | MCC
Plate | OS-BR-1-P-5001 | PL10*100 | PLATE | 2146 | SS400 | 5 | 16.8 | 84 | 5 | 0 | 2026-08-17: 5 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 10730 | 10730
Plate | OS-BR-20-P-5003 | PL10*100 | PLATE | 6850 | SS400 | 2 | 53.8 | 107.6 | 2 | 0 | 2026-08-17: 2 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 13700 | 13700
Plate | OS-BR-21-1C100-1 | PL4*56 | PLATE | 92 | SS400 | 2 | 0.2 | 0.4 | 2 | 0 | 2026-08-11: 4 |  |  |  |  | #VALUE! |  | PL4 | Thừa 2 | MCC
Shape | OS-BR-21-CX-2 | C100*60*4 | BENT CHANNEL | 6364 | SS400 | 1 | 42.4 | 42.4 | 0 | 1 | [12 empty] | #VALUE! |  |  |  | PMC
Plate | OS-BR-23-1H150-1 | PL4*70 | PLATE | 130 | SS400 | 4 | 0.3 | 1.2 | 4 | 0 | 2026-08-11: 4 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Shape | OS-BR-23-AX-9 | L65*65*4 | BENT ANGLE | 3182 | SS400 | 4 | 12.6 | 50.4 | 0 | 4 | [12 empty] | #VALUE! |  |  |  | PMC
Shape | OS-BR-23-CX-1 | H150*150*7*10 | BENT CHANNEL | 6950 | SS400 | 2 | 216.3 | 432.6 | 2 | 0 | 2026-07-06: 2 |  |  |  |  | #VALUE! |  |  |  | PMC
Plate | OS-BR-23-P-30 | PL4*124 | PLATE | 248 | SS400 | 2 | 0.9 | 1.8 | 2 | 0 | 2026-08-11: 2 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Plate | OS-BR-23-P-31 | PL10*120 | PLATE | 183 | SS400 | 4 | 1.7 | 6.8 | 4 | 0 | 2026-09-20: 4 |  |  |  |  | #VALUE! |  | PL10 |  | MCC
Plate | OS-BR-23-P-32 | PL6*80 | PLATE | 139 | SS400 | 4 | 0.5 | 2 | 4 | 0 | 2026-08-11: 4 |  |  |  |  | #VALUE! |  | PL6 |  | MCC
Plate | OS-BR-24-1H150-1 | PL4*70 | PLATE | 130 | SS400 | 2 | 0.3 | 0.6 | 2 | 0 | 2026-08-11: 2 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Shape | OS-BR-24-AX-10 | L65*65*4 | BENT ANGLE | 3220 | SS400 | 1 | 12.7 | 12.7 | 0 | 1 | [12 empty] | #VALUE! |  |  |  | PMC
Shape | OS-BR-24-CX-6 | H150*150*7*10 | BENT CHANNEL | 6900 | SS400 | 1 | 214.8 | 214.8 | 1 | 0 | [12 empty] | #VALUE! |  |  |  | PMC | bar: 2026-07-06
Plate | OS-BR-24-P-31 | PL10*120 | PLATE | 183 | SS400 | 2 | 1.7 | 3.4 | 2 | 0 | 2026-09-20: 2 |  |  |  |  | #VALUE! |  | PL10 |  | MCC
Plate | OS-BR-24-P-33 | PL6*80 | PLATE | 139 | SS400 | 1 | 0.5 | 0.5 | 1 | 0 | [12 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-08-11
Plate | OS-BR-25-1H150-1 | PL4*70 | PLATE | 130 | SS400 | 2 | 0.3 | 0.6 | 2 | 0 | 2026-08-11: 2 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Shape | OS-BR-25-AX-10 | L65*65*4 | BENT ANGLE | 3220 | SS400 | 1 | 12.7 | 12.7 | 0 | 1 | [12 empty] | #VALUE! |  |  |  | PMC
Shape | OS-BR-25-CX-6 | H150*150*7*10 | BENT CHANNEL | 6900 | SS400 | 1 | 214.8 | 214.8 | 1 | 0 | [12 empty] | #VALUE! |  |  |  | PMC | bar: 2026-07-06
Plate | OS-BR-25-P-31 | PL10*120 | PLATE | 183 | SS400 | 2 | 1.7 | 3.4 | 2 | 0 | 2026-09-20: 2 |  |  |  |  | #VALUE! |  | PL10 |  | MCC
Plate | OS-BR-25-P-33 | PL6*80 | PLATE | 139 | SS400 | 1 | 0.5 | 0.5 | 1 | 0 | [12 empty] | #VALUE! |  | PL6 |  | MCC | bar: 2026-08-11
Plate | OS-BR-26-1C100-4 | PL4*54 | PLATE | 88 | SS400 | 4 | 0.1 | 0.4 | 4 | 0 | 2026-08-11: 4 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Shape | OS-BR-26-CX-27 | C100*60*6 | BENT CHANNEL | 5120 | SS400 | 1 | 50.2 | 50.2 | 1 | 0 | [12 empty] | #VALUE! |  |  |  | PMC | bar: 2026-09-25
Shape | OS-BR-26-CX-30 | C100*60*6 | BENT CHANNEL | 3180 | SS400 | 1 | 29.8 | 29.8 | 1 | 0 | [12 empty] | #VALUE! |  |  |  | PMC | bar: 2026-09-25
Plate | OS-BR-26-P-53 | PL10*141 | PLATE | 150 | SS400 | 1 | 1.7 | 1.7 | 1 | 0 | [12 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-08-11
Plate | OS-BR-27-1C100-4 | PL4*54 | PLATE | 88 | SS400 | 2 | 0.1 | 0.2 | 2 | 0 | 2026-08-11: 2 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Shape | OS-BR-27-CX-20 | C100*60*6 | BENT CHANNEL | 8564 | SS400 | 1 | 83.9 | 83.9 | 1 | 0 | [12 empty] | #VALUE! |  |  |  | PMC | bar: 2026-09-25
Plate | OS-BR-28-P-5008 | PL10*100 | PLATE | 12000 | SS400 | 2 | 94.2 | 188.4 | 2 | 0 | 2026-08-17: 2 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 24000 | 24000
Plate | OS-BR-2-P-22 | PL8*150 | PLATE | 4003 | SS400 | 28 | 37.7 | 1055.6 | 28 | 0 | 2026-08-13: 28; 2026-08-16: 28 |  |  |  |  | #VALUE! | 28B28A | PL8 | Thừa 28 | MCC
Plate | OS-BR-3-P-5007 | PL10*100 | PLATE | 1400 | SS400 | 10 | 11 | 110 | 10 | 0 | 2026-08-17: 10 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 14000 | 14000
Plate | OS-BR-4-P-5000 | PL10*100 | PLATE | 9800 | SS400 | 25 | 76.9 | 1922.5 | 25 | 0 | 2026-08-17: 25 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 245000 | 245000
Plate | OS-BR-5-P-29 | PL8*150 | PLATE | 4127 | SS400 | 10 | 38.9 | 389 | 10 | 0 | 2026-08-13: 10; 2026-08-16: 10 |  |  |  |  | #VALUE! | 10B10A | PL8 | Thừa 10 | MCC
Plate | OS-BR-6-P-23 | PL8*150 | PLATE | 1254 | SS400 | 3 | 11.8 | 35.4 | 3 | 0 | 2026-08-13: 3 |  |  |  |  | #VALUE! |  | PL8 |  | MCC
Plate | OS-BR-7-1C100-1 | PL4*56 | PLATE | 92 | SS400 | 2 | 0.2 | 0.4 | 2 | 0 | 2026-08-11: 2 |  |  |  |  | #VALUE! |  | PL4 |  | MCC
Plate | OS-BR-8-P-5005 | PL10*100 | PLATE | 6400 | SS400 | 8 | 50.2 | 401.6 | 8 | 0 | 2026-08-17: 8 |  |  |  |  | #VALUE! |  | PL10 |  | MCC | 51200 | 51200
Plate | OS-BR-9-1C100-1 | PL4*56 | PLATE | 92 | SS400 | 2 | 0.2 | 0.4 | 2 | 0 | 2026-08-11: 4 |  |  |  |  | #VALUE! |  | PL4 | Thừa 2 | MCC
Shape | OS-BR-9-CX-5 | C100*60*4 | BENT CHANNEL | 5120 | SS400 | 1 | 34.1 | 34.1 | 0 | 1 | [12 empty] | #VALUE! |  |  |  | PMC
Plate | OS-LT-3-P-34 | PL25*150 | PLATE | 250 | SS400 | 2 | 6.4 | 12.8 | 2 | 0 | 2026-08-09: 2 |  |  |  |  | #VALUE! |  | PL25 |  | MCC
Plate | OS-LT-4-P-20 | PL10*200 | PLATE | 220 | SS400 | 55 | 3.5 | 192.5 | 55 | 0 | 2026-09-20: 55 |  |  |  |  | #VALUE! |  | PL10 |  | MCC
Plate | OS-LT-4-P-21 | PL20*85 | PLATE | 90 | SS400 | 55 | 0.9 | 49.5 | 55 | 0 | 2026-08-09: 55 |  |  |  |  | #VALUE! |  | PL20 |  | MCC
Plate | OS-LT-5-P-20 | PL10*200 | PLATE | 220 | SS400 | 2 | 3.5 | 7 | 2 | 0 | 2026-09-20: 2 |  |  |  |  | #VALUE! |  | PL10 |  | MCC
Plate | OS-LT-5-P-21 | PL20*85 | PLATE | 90 | SS400 | 2 | 0.9 | 1.8 | 2 | 0 | 2026-08-09: 2 |  |  |  |  | #VALUE! |  | PL20 |  | MCC