## Cover
TÌNH TRẠNG DỰ ÁN
TT | Dự án/Project | Hạng mục/Item | Khối lượng/TW | Tiếp nhận/ Reveived | Còn thiếu/ Remain | Đồng bộ | % | Đã triển khai | KL còn lại có thể triển khai
X | A320 | Kuo Kuang Combined Cycle Power Plant Unit 2 | 334037.2634 | 248099.2906 | 85937.9728 | 64387.9453 | 74.27% | 51008.607 | 13379.3383
1 | A320 | M4120 | 140087.6 | 119323.4 | 20764.2 |  | 85.18% |  | 0
2 | A320 | M4130 | 193949.6634 | 128775.8906 | 65173.7728 | 64387.9453 | 66.4% | 51008.607 | 13379.3383
3 |  |  |  |  | 0 |  |  |  | 0
4 |  |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
0

## BTP-A320M4120
A320M4120
| Chủng loại | Thiết kế |  | Đã nhận |  | Còn thiếu |  |  |  | Đã nhận |  | Đồng bộ |  | Đã triển khai
|  | T.Q'ty | T.Weight | T.Q'ty | T.Weight | T.Q'ty | T.Weight |  |  | Số chi tiết | Khối lượng | Số chi tiết lớn | Khối lượng | Số chi tiết lớn | Khối lượng
| Shape | 0 | 0 | 0 | 0 | 0 | 0 |  | Total | 575 | 119323.4 |  | 0 |  | 0
| Plate | 765 | 140087.6 | 575 | 119323.4 | 190 | 20764.2
| Purchasing | 0 | 0 | 0 | 0 | 0 | 0
| Total | 765 | 140087.6 | 575 | 119323.4 | 190 | 20764.2
Chủng loại thép hình
| Shape | #VALUE!
| Chiều dài theo thiết kế (mm) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL TK | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Đã nhận (mm) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL Nhận | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Còn thiếu (mm) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SL thiếu | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu (kg) | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chiều dày tôn
| Plate | 25 | 15 | 20 | #VALUE! | 12 | 10 | 30 | 3 | 5
| Diện tích m2 theo thiết kế | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SL TK | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Diện tích còn thiếu( m2) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Sl còn thiếu | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| KL còn thiếu(kg) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[11 empty] | 2393 | 2610.7 | 1733 | 2066.9 | 204.1 | 14.8 | 45286.8 | 1663.8 | 51 | 20.5 | 5724.5 | 20015.1 | 2116 | 61.3 | 274.3 | 1953.3 | 3143.7 | 3438.6 | 3860.4 | 1424.4 | 7531.7 | 1426.3 | 4202.7 | 48070.8 | 1485.9 | 2158.3 | 580.5 | 45765.9 | 7128.8 | 10285.7 | 48.8 | 177.6 | 404.8 | 43622.8 | 1830.4 | 32421.8 | 3849 | 356.2 | 0 | #VALUE!
[11 empty] | 17 | 28 | 45 | 24 | 4 | 2 | 28 | 15 | 3 | 1 | 100 | 41 | 36 | 3 | 11 | 12 | 2 | 2 | 6 | 1 | 5 | 1 | 3 | 32 | 3 | 37 | 16 | 33 | 98 | 7 | 2 | 3 | 12 | 27 | 41 | 23 | 7 | 21 | 0 | #VALUE!
Chủng loại | Part No.1 | Size | Description | Length | Material | T.Q'ty | U.Weight | T.Weight | Đã nhận | Còn thiếu | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-25 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-05 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-08-16 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-07 | 2026-09-19 | 2026-09-21 | 2026-09-22 | 2026-09-24 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-28 | 2026-10-30 | KO BB | Lấy data | Ktra nối | Tôn | Cảnh báo thừa | DVG | MPR No | Qty MPR | Cutting No. | Qty Cutting | Date Issue
Plate | SD_A0044_P0134 | PL10*50 | Plate | 11567 | A36 | 4 | 45.4 | 181.6 | 4 | 0 | 2026-09-28: 16 |  | #VALUE! |  | PL10 | 4A4B4C4D | MCC |  |  | chi tiết chia nối | 12
Plate | SD_A0044_P0222 | PL10 Dev.~9456 | Plate | 3272 | A36 | 2 | 1233.4 | 2466.8 | 2 | 0 | 2026-10-09: 2 |  | #VALUE! | 2B | #VALUE! |  | PMC |  |  | chi tiết chia nối | 6
Plate | SD_A0044_P0223 | PL10*485 | Plate | 11493 | A36 | 2 | 437.3 | 874.6 | 2 | 0 | 2026-09-24: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_A0044_P0224 | PL10*505.9 | Plate | 509 | A36 | 4 | 17.6 | 70.4 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0225 | PL10 Dev.~9456 | Plate | 3435 | A36 | 2 | 1353.9 | 2707.8 | 2 | 0 | 2026-09-21: 1; 2026-10-09: 2 |  | #VALUE! | A2B | #VALUE! | Thừa 1 | PMC |  |  | chi tiết chia nối | 6
Plate | SD_A0044_P0226 | PL10*485 | Plate | 4243 | A36 | 2 | 161.5 | 323 | 2 | 0 | 2026-09-29: 2 |  | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_A0044_P0231 | PL10*505.9 | Plate | 768 | A36 | 4 | 29.1 | 116.4 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0232 | PL10*505.9 | Plate | 1041 | A36 | 4 | 40.4 | 161.6 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0233 | PL10*505.9 | Plate | 1223 | A36 | 4 | 47.9 | 191.6 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0234 | PL10*505.9 | Plate | 1345 | A36 | 4 | 52.9 | 211.6 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0235 | PL10*505.9 | Plate | 1429 | A36 | 4 | 56.4 | 225.6 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0236 | PL10*505.9 | Plate | 1477 | A36 | 4 | 58.4 | 233.6 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0237 | PL10*505.9 | Plate | 1494 | A36 | 4 | 59.2 | 236.8 | 4 | 0 | 2026-10-14: 3; 2026-10-23: 1 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0238 | PL10*505.9 | Plate | 1451 | A36 | 4 | 57.1 | 228.4 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0239 | PL10*505.9 | Plate | 1276 | A36 | 4 | 49.7 | 198.8 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0044_P0240 | PL10*505.9 | Plate | 890 | A36 | 4 | 33.3 | 133.2 | 4 | 0 | 2026-10-23: 4 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_A0159_P0491 | PL20*505 | Plate | 3981 | A36 | 1 | 205.8 | 205.8 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-11
Plate | SD_A0159_P0492 | PL20*118.1 | Plate | 450 | A36 | 2 | 8.3 | 16.6 | 2 | 0 | 2026-07-11: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_A0159_P0493 | PL20*569.5 | Plate | 3981 | A36 | 1 | 229.3 | 229.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-11
Plate | SD_A0162_P0522 | PL20*1299.6 | Plate | 1983 | A36 | 1 | 215.7 | 215.7 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-12
Plate | SD_A0163_P0523 | PL20*1348.8 | Plate | 2024 | A36 | 2 | 229.5 | 459 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_A0164_P0527 | PL25*1525.1 | Plate | 2567 | A36 | 4 | 386.6 | 1546.4 | 2 | 2 | 2026-07-12: 2 |  | #VALUE! |  | PL25 |  | MCC | DCC26-A320-0002-10 |  | A320-03-CP009 | 2 | 2026-06-23
Plate | SD_A0165_P0528 | PL15*200 | Plate | 722 | A36 | 48 | 17 | 816 | 32 | 16 | 2026-07-29: 4; 2026-07-30: 3; 2026-08-03: 5; 2026-08-05: 4; 2026-09-29: 11; 2026-10-30: 5 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28
Plate | SD_A0165_P0529 | PL15*170 | Plate | 722 | A36 | 48 | 13.1 | 628.8 | 32 | 16 | 2026-08-03: 8; 2026-08-05: 4; 2026-08-06: 4; 2026-10-01: 2; 2026-10-30: 14 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28
Plate | SD_A0171_P0535 | PL15*200 | Plate | 873 | A36 | 16 | 20.5 | 328 | 16 | 0 | 2026-07-29: 2; 2026-07-31: 1; 2026-08-03: 5; 2026-08-05: 6; 2026-08-12: 2 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28
Plate | SD_A0171_P0536 | PL15*170 | Plate | 873 | A36 | 16 | 15.8 | 252.8 | 15 | 1 | 2026-08-03: 13; 2026-08-05: 2 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28
Plate | SD_A0174_P0540 | PL15*300 | Plate | 578 | A36 | 4 | 20.4 | 81.6 | 0 | 4 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_A0174_P0541 | PL15*270 | Plate | 578 | A36 | 4 | 17.3 | 69.2 | 0 | 4 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_A0176_P0552 | PL25*1341.6 | Plate | 2041 | A36 | 2 | 281.3 | 562.6 | 0 | 2 | [39 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-A320-0002-10 |  | A320-03-CP009 | 1 | 2026-06-23
Plate | SD_A0177_P0554 | PL25*1206.2 | Plate | 1984 | A36 | 4 | 249.3 | 997.2 | 0 | 4 | [39 empty] | #VALUE! |  | PL25 |  | MCC | DCC26-A320-0002-10 |  | A320-03-CP009 | 2 | 2026-06-23
Plate | SD_A0178_P0563 | PL20*1385.5 | Plate | 2311 | A36 | 1 | 263.2 | 263.2 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29
Plate | SD_A0179_P0564 | PL20*1433.2 | Plate | 2354 | A36 | 2 | 279.3 | 558.6 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_A0187_P0585 | PL20*2374.4 | Plate | 4923 | A36 | 2 | 607.9 | 1215.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC |  |  | chi tiết chia nối | 2
Plate | SD_A0188_P0586 | PL20*206.2 | Plate | 1250 | A36 | 2 | 38.7 | 77.4 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_A0189_P0587 | PL20*2517.7 | Plate | 3413 | A36 | 2 | 444.8 | 889.6 | 2 | 0 | 2026-08-27: 2 |  | #VALUE! | 2A | PL20 |  | MCC |  |  | chi tiết chia nối | 2
Plate | SD_A0190_P0588 | PL20*1095 | Plate | 3975 | A36 | 2 | 683.4 | 1366.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_A0191_P0589 | PL20*1994.1 | Plate | 4132 | A36 | 2 | 742.7 | 1485.4 | 2 | 0 | 2026-08-27: 4 |  | #VALUE! | 2A 2B | PL20 | Thừa 2 | MCC |  |  | chi tiết chia nối | 2
Plate | SD_A0192_P0590 | PL20*206.2 | Plate | 1250 | A36 | 2 | 38.7 | 77.4 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_A0193_P0591 | PL15*1694.2 | Plate | 2687 | A36 | 2 | 252.8 | 505.6 | 2 | 0 | 2026-07-29: 4 |  | #VALUE! | AABB | PL15 | Thừa 2 | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28
Plate | SD_B0001_A0035_P0060 | PL15*150 | Plate | 2490 | A36 | 12 | 43.9 | 526.8 | 12 | 0 | 2026-08-03: 3; 2026-08-06: 21 |  | #VALUE! | 3B 12A 9B | PL15 | Thừa 12 | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 12 | 2026-06-28
Plate | SD_B0001_A0035_P0061 | PL15*168 | Plate | 2476 | A36 | 4 | 48.9 | 195.6 | 4 | 0 | 2026-08-05: 8 |  | #VALUE! | 4A 4B | PL15 | Thừa 4 | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 4 | 2026-06-28
Plate | SD_B0001_A0035_P0102 | PL10 Dev. ~2454.1 | Plate | 9185 | A36 | 4 | 1695.9 | 6783.6 | 4 | 0 | 2026-07-25: 18; 2026-10-09: 2 |  | #VALUE! | 4A4B3C3D4ECD | #VALUE! | Thừa 16 | PMC |  |  | chi tiết chia nối | 4
Plate | SD_B0001_A0035_P0103 | PL10*50 | Plate | 9185 | A36 | 4 | 36.1 | 144.4 | 4 | 0 | 2026-07-13: 4 |  | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28
Plate | SD_B0002_A0036_P0096 | PL15*220 | Plate | 5258 | A36 | 1 | 136.1 | 136.1 | 1 | 0 | 2026-08-03: 1; 2026-08-06: 2 |  | #VALUE! | BAC | PL15 | Thừa 2 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0036_P0104 | PL10 Dev. ~9556 | Plate | 3450 | A36 | 1 | 1719.3 | 1719.3 | 1 | 0 | 2026-08-24: 1; 2026-08-25: 2; 2026-09-07: 1; 2026-10-09: 1 |  | #VALUE! | ABECD | #VALUE! | Thừa 4 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0036_P0105 | PL12 Dev. ~4935.8 | Plate | 5897 | A36 | 1 | 1000.2 | 1000.2 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0036_P0113 | PL10 Dev. ~3853.3 | Plate | 3917 | A36 | 1 | 140.9 | 140.9 | 1 | 0 | 2026-09-30: 6 |  | #VALUE! | ABCDEF | #VALUE! | Thừa 5 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0036_P0116 | PL12*240 | Plate | 392 | A36 | 2 | 7.4 | 14.8 | 2 | 0 | 2026-07-20: 2 |  | #VALUE! |  | PL12 |  | MCC | DCC26-A320-0007-3/6 DCC26-A320-0007-3/5 DCC26-A320-0007-3/4 DCC26-A320-0007-6/7 DCC26-A320-0007-3/3 DCC26-A320-0007-3/2 DCC26-A320-0007-3/1 |  | A320-03-CP007 | 2 | 2026-06-23
Plate | SD_B0002_A0036_P0332 | PL15*200 | Plate | 3213 | A36 | 2 | 75.2 | 150.4 | 2 | 0 | 2026-08-03: 2 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28
Plate | SD_B0002_A0036_P0336 | PL15*200 | Plate | 10116 | A36 | 1 | 220.6 | 220.6 | 1 | 0 | 2026-08-03: 5 |  | #VALUE! | ABCDE | PL15 | Thừa 4 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0036_P0344 | PL15*200 | Plate | 2007 | A36 | 2 | 46.1 | 92.2 | 2 | 0 | 2026-08-06: 2 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28
Plate | SD_B0002_A0036_P0561 | PL20*1961.5 | Plate | 2606 | A36 | 1 | 353 | 353 | 1 | 0 | 2026-07-14: 2 |  | #VALUE! | A B | PL20 | Thừa 1 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0036_P0562 | PL20*1166.9 | Plate | 1311 | A36 | 2 | 115.1 | 230.2 | 1 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0002_A0036_P0603 | PL12*156.3 | Plate | 2595 | A36 | 1 | 37.4 | 37.4 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | PMC | DCC26-A320-0007-3/6 DCC26-A320-0007-3/5 DCC26-A320-0007-3/4 DCC26-A320-0007-6/7 DCC26-A320-0007-3/3 DCC26-A320-0007-3/2 DCC26-A320-0007-3/1 |  | A320-03-CP007 | 1 | 2026-06-23
Plate | SD_B0002_A0036_P0604 | PL12*156.3 | Plate | 2595 | A36 | 1 | 37.4 | 37.4 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | PMC | DCC26-A320-0007-3/6 DCC26-A320-0007-3/5 DCC26-A320-0007-3/4 DCC26-A320-0007-6/7 DCC26-A320-0007-3/3 DCC26-A320-0007-3/2 DCC26-A320-0007-3/1 |  | A320-03-CP007 | 1 | 2026-06-23
Plate | SD_B0002_A0037_P0097 | PL15*220 | Plate | 1502 | A36 | 1 | 38.9 | 38.9 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0002_A0037_P0106 | PL12 Dev. ~2305.5 | Plate | 5868 | A36 | 1 | 856.7 | 856.7 | 1 | 0 | [39 empty] | #VALUE! | B | #VALUE! |  | PMC |  |  | chi tiết chia nối | 1 | bar: 2026-09-30
Plate | SD_B0002_A0037_P0107 | PL10*60 | Plate | 1127 | A36 | 1 | 5.3 | 5.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0037_P0108 | PL10*60 | Plate | 1410 | A36 | 1 | 6.6 | 6.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0037_P0109 | PL10*60 | Plate | 1100 | A36 | 1 | 5.2 | 5.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0037_P0110 | PL10*60 | Plate | 1979 | A36 | 1 | 9.3 | 9.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0037_P0112 | PL10*60 | Plate | 5562 | A36 | 1 | 26.2 | 26.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-08-05
Plate | SD_B0002_A0037_P0342 | PL15*200 | Plate | 1679 | A36 | 1 | 39.5 | 39.5 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0002_A0037_P0559 | PL20*200 | Plate | 1889 | A36 | 1 | 59.2 | 59.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0002_A0037_P0560 | PL20*200 | Plate | 1941 | A36 | 1 | 60.8 | 60.8 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-13
Plate | SD_B0002_A0038_P0097 | PL15*220 | Plate | 1502 | A36 | 1 | 38.9 | 38.9 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0002_A0038_P0107 | PL10*60 | Plate | 1127 | A36 | 1 | 5.3 | 5.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0038_P0108 | PL10*60 | Plate | 1410 | A36 | 1 | 6.6 | 6.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0038_P0109 | PL10*60 | Plate | 1100 | A36 | 1 | 5.2 | 5.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0038_P0110 | PL10*60 | Plate | 1979 | A36 | 1 | 9.3 | 9.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0002_A0038_P0112 | PL10*60 | Plate | 5562 | A36 | 1 | 26.2 | 26.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-08-05
Plate | SD_B0002_A0038_P0114 | PL12 Dev. ~2305.5 | Plate | 5868 | A36 | 1 | 856.7 | 856.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0038_P0342 | PL15*200 | Plate | 1679 | A36 | 1 | 39.5 | 39.5 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0002_A0038_P0559 | PL20*200 | Plate | 1889 | A36 | 1 | 59.2 | 59.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-13
Plate | SD_B0002_A0038_P0560 | PL20*200 | Plate | 1941 | A36 | 1 | 60.8 | 60.8 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0002_A0039_P0096 | PL15*220 | Plate | 5258 | A36 | 1 | 136.1 | 136.1 | 1 | 0 | 2026-08-03: 1; 2026-08-06: 2 |  | #VALUE! | ABC | PL15 | Thừa 2 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0039_P0111 | PL12 Dev. ~4986.1 | Plate | 6006 | A36 | 1 | 2259.1 | 2259.1 | 1 | 0 | 2026-09-30: 3 |  | #VALUE! | CAB | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0039_P0343 | PL15*200 | Plate | 4773 | A36 | 1 | 112.3 | 112.3 | 1 | 0 | 2026-08-03: 1; 2026-08-06: 2 |  | #VALUE! | BAC | PL15 | Thừa 2 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0002_A0116_P0372 | PL20*400 | Plate | 400 | A36 | 2 | 25.1 | 50.2 | 2 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-12 to 2026-07-13
Plate | SD_B0002_A0116_P0374 | PL3*250 | Plate | 800 | AISI304 | 4 | 4.7 | 18.8 | 4 | 0 | 2026-08-12: 4 |  | #VALUE! |  | PL3 |  | MCC | E275-01-CP131-1 A320-01-CP004-1 |  | A320-03-CP003 | 4 | 2026-06-23
Plate | SD_B0002_A0116_P0378 | PL20*400 | Plate | 970 | A36 | 2 | 60.9 | 121.8 | 2 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-11; 2026-08-10
Plate | SD_B0002_A0116_P0382 | PL20*265 | Plate | 400 | A36 | 4 | 16.6 | 66.4 | 4 | 0 | 2026-07-11: 1; 2026-07-12: 1; 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29
Plate | SD_B0002_A0116_P0390 | PL30*1020 | Plate | 3080 | A36 | 1 | 739.8 | 739.8 | 1 | 0 | [39 empty] | #VALUE! |  | PL30 |  | MCC | M304-04-CP009-1 M304-04-CP014-2 M305-01-CP032-3 DCC26-A320-0002-11 M304-04-CP014-1 M305-11-CP032-3 A320-01-CP013-1 M305-01-CP032-1 |  | A320-03-CP010 | 1 | 2026-06-23 | bar: 2026-07-11
Plate | SD_B0002_A0116_P0414 | PL20*965.9 | Plate | 1505 | A36 | 2 | 116.6 | 233.2 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0116_P0415 | PL20*400 | Plate | 1028 | A36 | 2 | 63.9 | 127.8 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0116_P0416 | PL20*400 | Plate | 699 | A36 | 2 | 43.7 | 87.4 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0116_P0419 | PL20*265 | Plate | 690 | A36 | 2 | 28.6 | 57.2 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0116_P0420 | PL20*265 | Plate | 1004 | A36 | 2 | 41.5 | 83 | 2 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-11 to 2026-07-12
Plate | SD_B0002_A0116_P0421 | PL20*265 | Plate | 706 | A36 | 2 | 29.2 | 58.4 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0116_P0422 | PL20*265 | Plate | 1046 | A36 | 2 | 43.2 | 86.4 | 2 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-12 to 2026-07-13
Plate | SD_B0002_A0116_P0423 | PL20*926.5 | Plate | 1477 | A36 | 2 | 116 | 232 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0116_P0618 | PL5*50 | Plate | 100 | AISI304 | 1 | 0.2 | 0.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL5 |  | MCC | E275-01-CP039-2 |  | A320-03-CP006 | 1 | 2026-06-23 | bar: 2026-08-10
Plate | SD_B0002_A0133_P0412 | PL20*408.8 | Plate | 420 | A36 | 1 | 27 | 27 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-12
Plate | SD_B0002_A0133_P0418 | PL20*603.9 | Plate | 1550 | A36 | 1 | 115.2 | 115.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-13
Plate | SD_B0002_A0133_P0424 | PL20*420 | Plate | 455 | A36 | 2 | 30 | 60 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0134_P0413 | PL20*380 | Plate | 454 | A36 | 2 | 25.3 | 50.6 | 2 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-14 to 2026-07-15
Plate | SD_B0002_A0135_P0417 | PL20*608.6 | Plate | 970 | A36 | 2 | 91.7 | 183.4 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0002_A0136_P0425 | PL20*365 | Plate | 598 | A36 | 2 | 29.8 | 59.6 | 2 | 0 | 2026-07-14: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0003_A0009_P0016 | PL15*220 | Plate | 2254 | A36 | 6 | 58.3 | 349.8 | 6 | 0 | 2026-08-03: 6 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 6 | 2026-06-28
Plate | SD_B0003_A0009_P0017 | PL15*200 | Plate | 2264 | A36 | 12 | 53.2 | 638.4 | 12 | 0 | 2026-08-03: 12 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 12 | 2026-06-28
Plate | SD_B0003_A0009_P0094 | PL12 Dev. ~2243 | Plate | 7345 | A36 | 6 | 1481.8 | 8890.8 | 6 | 0 | 2026-07-25: 9; 2026-08-05: 13; 2026-09-07: 2 |  | #VALUE! | 4A 4B 1C 6D 2B 5C 2A | #VALUE! | Thừa 18 | PMC |  |  | chi tiết chia nối | 6
Plate | SD_B0003_A0009_P0095 | PL10*50 | Plate | 7345 | A36 | 6 | 28.8 | 172.8 | 0 | 6 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 6 | 2026-06-28
Plate | SD_B0005_A0066_P0201 | PL10*44.8 | Plate | 6766 | A36 | 1 | 23.7 | 23.7 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0066_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0066_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0066_P0261 | PL15*250 | Plate | 1851 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0066_P0265 | PL18 Dev. ~2053.9 | Plate | 6991 | A36 | 1 | 1614.4 | 1614.4 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | ABC | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0068_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0068_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0068_P0205 | PL10*43.8 | Plate | 6833 | A36 | 1 | 23.4 | 23.4 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28
Plate | SD_B0005_A0068_P0262 | PL15*250 | Plate | 1851 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0068_P0266 | PL18 Dev. ~2074.3 | Plate | 6834 | A36 | 1 | 1620.9 | 1620.9 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | CAB | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0070_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0070_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0070_P0213 | PL10*48.4 | Plate | 6445 | A36 | 1 | 24.5 | 24.5 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0070_P0263 | PL15*250 | Plate | 1848 | A36 | 1 | 54.3 | 54.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0070_P0269 | PL18 Dev. ~2028.3 | Plate | 6673 | A36 | 1 | 1451.9 | 1451.9 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | BAC | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0072_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0072_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0072_P0215 | PL10*49.7 | Plate | 6223 | A36 | 1 | 24.3 | 24.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-10-12
Plate | SD_B0005_A0072_P0263 | PL15*250 | Plate | 1848 | A36 | 1 | 54.3 | 54.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0072_P0270 | PL18 Dev. ~2053.7 | Plate | 6375 | A36 | 1 | 1428 | 1428 | 1 | 0 | 2026-09-22: 1; 2026-10-01: 2 |  | #VALUE! | A BC | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0074_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0074_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0074_P0217 | PL10*50 | Plate | 6048 | A36 | 1 | 23.7 | 23.7 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0074_P0263 | PL15*250 | Plate | 1847 | A36 | 1 | 54.3 | 54.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0074_P0271 | PL18 Dev. ~2078.6 | Plate | 6038 | A36 | 1 | 1426.3 | 1426.3 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | CBA | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0076_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0076_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0076_P0219 | PL10*49.9 | Plate | 5977 | A36 | 1 | 23.4 | 23.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0076_P0263 | PL15*250 | Plate | 1848 | A36 | 1 | 54.3 | 54.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0076_P0272 | PL18 Dev. ~2063.9 | Plate | 6180 | A36 | 1 | 1426.8 | 1426.8 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | ABC | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0078_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0078_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0078_P0230 | PL10*48.8 | Plate | 6389 | A36 | 1 | 24.5 | 24.5 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | bar: 2026-10-12
Plate | SD_B0005_A0078_P0264 | PL15*250 | Plate | 1849 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0078_P0275 | PL18 Dev. ~1965.5 | Plate | 7009 | A36 | 1 | 1492.4 | 1492.4 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | BAC | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0080_P0202 | PL15*276 | Plate | 2153 | A36 | 1 | 70 | 70 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0080_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0080_P0260 | PL10*46.9 | Plate | 6605 | A36 | 1 | 24.3 | 24.3 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28
Plate | SD_B0005_A0080_P0261 | PL15*250 | Plate | 1851 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0080_P0276 | PL18 Dev. ~2006.7 | Plate | 7076 | A36 | 1 | 1561.3 | 1561.3 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | CBA | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0082_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-14
Plate | SD_B0005_A0082_P0207 | PL10*44.5 | Plate | 6792 | A36 | 1 | 23.6 | 23.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0082_P0208 | PL15*276 | Plate | 2297 | A36 | 1 | 74.6 | 74.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0082_P0262 | PL15*250 | Plate | 1851 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0082_P0267 | PL18 Dev. ~2060.4 | Plate | 6882 | A36 | 1 | 1577 | 1577 | 1 | 0 | 2026-09-22: 2 |  | #VALUE! | AC | #VALUE! | Thừa 1 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0084_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-15
Plate | SD_B0005_A0084_P0208 | PL15*276 | Plate | 2297 | A36 | 1 | 74.6 | 74.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0084_P0221 | PL10*50 | Plate | 6021 | A36 | 1 | 23.6 | 23.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0084_P0263 | PL15*250 | Plate | 1848 | A36 | 1 | 54.3 | 54.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0084_P0273 | PL18 Dev. ~2011.7 | Plate | 6500 | A36 | 1 | 1426.3 | 1426.3 | 1 | 0 | 2026-09-19: 1; 2026-09-22: 2 |  | #VALUE! | B CA | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0086_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-15
Plate | SD_B0005_A0086_P0210 | PL10*46.4 | Plate | 6651 | A36 | 1 | 24.1 | 24.1 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0086_P0211 | PL15*276 | Plate | 2009 | A36 | 1 | 65.3 | 65.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0086_P0262 | PL15*250 | Plate | 1851 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0086_P0268 | PL18 Dev. ~2033.9 | Plate | 6854 | A36 | 1 | 1508.3 | 1508.3 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | CBA | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0005_A0088_P0203 | PL20*276 | Plate | 1377 | A36 | 1 | 59.6 | 59.6 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-15
Plate | SD_B0005_A0088_P0211 | PL15*276 | Plate | 2010 | A36 | 1 | 65.3 | 65.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0088_P0227 | PL10*49.8 | Plate | 6173 | A36 | 1 | 24.1 | 24.1 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-13
Plate | SD_B0005_A0088_P0264 | PL15*250 | Plate | 1849 | A36 | 1 | 54.4 | 54.4 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0005_A0088_P0274 | PL18 Dev. ~1965.9 | Plate | 6802 | A36 | 1 | 1443.1 | 1443.1 | 1 | 0 | 2026-09-22: 3 |  | #VALUE! | BAC | #VALUE! | Thừa 2 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0011_A0005_P0001 | PL10*50 | Plate | 7090 | A36 | 4 | 27.8 | 111.2 | 3 | 1 | 2026-10-28: 3 |  | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0011_A0005_P0010 | PL10 Dev. ~2611.1 | Plate | 7090 | A36 | 4 | 1396.5 | 5586 | 4 | 0 | 2026-10-24: 12 |  | #VALUE! | 4A4B4C | #VALUE! | Thừa 8 | PMC
Plate | SD_B0011_A0005_P0012 | PL15*150 | Plate | 2647 | A36 | 8 | 46.7 | 373.6 | 0 | 8 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_B0011_A0005_P0013 | PL15*168 | Plate | 2633 | A36 | 4 | 52 | 208 | 0 | 4 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_B0012_A0006_P0014 | PL15*168 | Plate | 2925 | A36 | 1 | 57.8 | 57.8 | 0 | 1 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_B0012_A0006_P0043 | PL10 Dev. ~3038.5 | Plate | 6418 | A36 | 1 | 1158.7 | 1158.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0012_A0006_P0044 | PL10*50 | Plate | 4042 | A36 | 1 | 15.9 | 15.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0012_A0006_P0045 | PL10*50 | Plate | 2051 | A36 | 1 | 8.1 | 8.1 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0012_A0006_P0325 | PL12*200 | Plate | 2921 | A36 | 1 | 54.9 | 54.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0006_P0503 | PL12*200 | Plate | 2531 | A36 | 1 | 47.6 | 47.6 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0006_P0506 | PL20*200 | Plate | 973 | A36 | 1 | 30.5 | 30.5 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | bar: 2026-09-29
Plate | SD_B0012_A0006_P0510 | PL20*200 | Plate | 1051 | A36 | 1 | 32.9 | 32.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0007_P0014 | PL15*168 | Plate | 2925 | A36 | 1 | 57.8 | 57.8 | 0 | 1 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_B0012_A0007_P0044 | PL10*50 | Plate | 4042 | A36 | 1 | 15.9 | 15.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0012_A0007_P0045 | PL10*50 | Plate | 2051 | A36 | 1 | 8.1 | 8.1 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0012_A0007_P0046 | PL10*50 | Plate | 6024 | A36 | 1 | 22.6 | 22.6 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0012_A0007_P0047 | PL10 Dev. ~3038.5 | Plate | 6418 | A36 | 1 | 1158.7 | 1158.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0012_A0007_P0504 | PL12*200 | Plate | 2541 | A36 | 1 | 47.8 | 47.8 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0007_P0506 | PL20*200 | Plate | 973 | A36 | 1 | 30.5 | 30.5 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0007_P0510 | PL20*200 | Plate | 1051 | A36 | 1 | 32.9 | 32.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0007_P0622 | PL12*200 | Plate | 2921 | A36 | 1 | 54.9 | 54.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0011 | PL15*168 | Plate | 4680 | A36 | 1 | 92.5 | 92.5 | 0 | 1 | [39 empty] | #VALUE! |  | PL15 |  | MCC
Plate | SD_B0012_A0040_P0025 | PL10 Dev. ~6463 | Plate | 4383 | A36 | 1 | 955.7 | 955.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0012_A0040_P0041 | PL10 Dev. ~8614 | Plate | 3640 | A36 | 1 | 1964.7 | 1964.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0012_A0040_P0042 | PL12*200 | Plate | 9174 | A36 | 1 | 172.7 | 172.7 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0048 | PL10 Dev. ~3801 | Plate | 3555 | A36 | 1 | 139.9 | 139.9 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0012_A0040_P0115 | PL12*240 | Plate | 365 | A36 | 2 | 7.2 | 14.4 | 0 | 2 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0324 | PL12*200 | Plate | 3210 | A36 | 2 | 60 | 120 | 0 | 2 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0326 | PL12*200 | Plate | 1726 | A36 | 2 | 32 | 64 | 0 | 2 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0502 | PL12*200 | Plate | 3228 | A36 | 1 | 60.7 | 60.7 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0505 | PL20*200 | Plate | 3027 | A36 | 1 | 94.8 | 94.8 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0040_P0509 | PL20*200 | Plate | 3130 | A36 | 1 | 98.1 | 98.1 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0040_P0511 | PL12*400 | Plate | 1359 | A36 | 1 | 46.4 | 46.4 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0512 | PL12*760.4 | Plate | 983 | A36 | 1 | 34.8 | 34.8 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0513 | PL12*420.4 | Plate | 434 | A36 | 1 | 11.1 | 11.1 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0514 | PL12*400 | Plate | 1471 | A36 | 2 | 50.2 | 100.4 | 0 | 2 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0515 | PL12*866.6 | Plate | 1087 | A36 | 2 | 41.9 | 83.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0516 | PL12*524.7 | Plate | 547 | A36 | 2 | 17.3 | 34.6 | 0 | 2 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0012_A0040_P0597 | PL12*156.3 | Plate | 2220 | A36 | 1 | 31.9 | 31.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | PMC
Plate | SD_B0012_A0040_P0598 | PL12*156.3 | Plate | 2220 | A36 | 1 | 31.9 | 31.9 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | PMC
Plate | SD_B0012_A0113_P0370 | PL30*1020 | Plate | 2150 | A36 | 1 | 516.5 | 516.5 | 0 | 1 | [39 empty] | #VALUE! |  | PL30 |  | MCC
Plate | SD_B0012_A0113_P0372 | PL20*400 | Plate | 400 | A36 | 2 | 25.1 | 50.2 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0374 | PL3*250 | Plate | 800 | AISI304 | 4 | 4.7 | 18.8 | 0 | 4 | [39 empty] | #VALUE! |  | PL3 |  | MCC
Plate | SD_B0012_A0113_P0378 | PL20*400 | Plate | 970 | A36 | 2 | 60.9 | 121.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0382 | PL20*265 | Plate | 400 | A36 | 4 | 16.6 | 66.4 | 0 | 4 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0403 | PL20*400 | Plate | 753 | A36 | 2 | 46.8 | 93.6 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0404 | PL20*400 | Plate | 509 | A36 | 2 | 31.9 | 63.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0407 | PL20*265 | Plate | 506 | A36 | 2 | 21 | 42 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0408 | PL20*265 | Plate | 736 | A36 | 2 | 30.4 | 60.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0409 | PL20*265 | Plate | 512 | A36 | 2 | 21.2 | 42.4 | 1 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC | bar: 2026-09-28
Plate | SD_B0012_A0113_P0410 | PL20*265 | Plate | 766 | A36 | 2 | 31.6 | 63.2 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0411 | PL20*883.5 | Plate | 1068 | A36 | 2 | 80.8 | 161.6 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0508 | PL20*900.4 | Plate | 1055 | A36 | 2 | 79.9 | 159.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0113_P0618 | PL5*50 | Plate | 100 | AISI304 | 1 | 0.2 | 0.2 | 0 | 1 | [39 empty] | #VALUE! |  | PL5 |  | MCC
Plate | SD_B0012_A0131_P0402 | PL20*407.2 | Plate | 420 | A36 | 1 | 26.8 | 26.8 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0131_P0406 | PL20*453.2 | Plate | 620 | A36 | 1 | 41.5 | 41.5 | 0 | 1 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0132_P0405 | PL20*453.9 | Plate | 970 | A36 | 2 | 68.9 | 137.8 | 0 | 2 | [39 empty] | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0012_A0161_P0507 | PL20*300 | Plate | 451 | A36 | 2 | 20 | 40 | 2 | 0 | 2026-09-29: 2 |  | #VALUE! |  | PL20 |  | MCC
Plate | SD_B0014_A0043_P0132 | PL10 Dev.~9456 | Plate | 3430 | A36 | 1 | 1424.4 | 1424.4 | 1 | 0 | [39 empty] | #VALUE! | ADCB | #VALUE! | Thừa 3 | PMC |  |  | chi tiết chia nối | 1 | bar: 2026-07-25; 2026-08-24; 2026-08-28 to 2026-09-07
Plate | SD_B0014_A0043_P0133 | PL10*678 | Plate | 11493 | A36 | 1 | 611.3 | 611.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-09-24
Plate | SD_B0014_A0043_P0134 | PL10*50 | Plate | 11567 | A36 | 2 | 45.4 | 90.8 | 2 | 0 | 2026-08-16: 8 |  | #VALUE! | ABCD | PL10 | Thừa 6 | MCC |  |  | chi tiết chia nối | 2
Plate | SD_B0014_A0043_P0135 | PL10*756.6 | Plate | 644 | A36 | 2 | 32.3 | 64.6 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0136 | PL10*756.6 | Plate | 851 | A36 | 2 | 46.9 | 93.8 | 2 | 0 | [39 empty] | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 | bar: 2026-09-28; 2026-09-30
Plate | SD_B0014_A0043_P0137 | PL10*756.6 | Plate | 1096 | A36 | 2 | 62.6 | 125.2 | 2 | 0 | [39 empty] | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 | bar: 2026-09-28; 2026-09-30
Plate | SD_B0014_A0043_P0138 | PL10*756.6 | Plate | 1260 | A36 | 2 | 73.1 | 146.2 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0139 | PL10*756.6 | Plate | 1372 | A36 | 2 | 80.2 | 160.4 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0140 | PL10*756.6 | Plate | 1445 | A36 | 2 | 84.9 | 169.8 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0141 | PL10*756.6 | Plate | 1484 | A36 | 2 | 87.6 | 175.2 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0142 | PL10*756.6 | Plate | 1495 | A36 | 2 | 88.5 | 177 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0143 | PL10*756.6 | Plate | 1451 | A36 | 2 | 84.8 | 169.6 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0144 | PL10*756.6 | Plate | 1276 | A36 | 2 | 72.8 | 145.6 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0145 | PL10*756.6 | Plate | 890 | A36 | 2 | 46.4 | 92.8 | 2 | 0 | 2026-09-28: 2 |  | #VALUE! |  | PL10 |  | PMC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0146 | PL10 Dev.~9456 | Plate | 3530 | A36 | 1 | 1424.4 | 1424.4 | 1 | 0 | 2026-08-16: 1; 2026-09-07: 1; 2026-09-21: 2 |  | #VALUE! | A D BC | #VALUE! | Thừa 3 | PMC |  |  | chi tiết chia nối | 1
Plate | SD_B0014_A0043_P0147 | PL10*678 | Plate | 4243 | A36 | 1 | 225.8 | 225.8 | 1 | 0 | [39 empty] | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 | bar: 2026-07-29
Plate | SD_B0014_A0043_P0319 | PL15*150 | Plate | 4619 | A36 | 1 | 80.9 | 80.9 | 1 | 0 | 2026-07-29: 1; 2026-08-03: 2 |  | #VALUE! | BAC | PL15 | Thừa 2 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0014_A0043_P0320 | PL15*150 | Plate | 5305 | A36 | 1 | 93.5 | 93.5 | 1 | 0 | 2026-08-06: 3 |  | #VALUE! | ABC | PL15 | Thừa 2 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0014_A0043_P0321 | PL15*150 | Plate | 985 | A36 | 2 | 17 | 34 | 2 | 0 | 2026-08-03: 2 |  | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28
Plate | SD_B0014_A0043_P0322 | PL15*150 | Plate | 1397 | A36 | 2 | 22.8 | 45.6 | 2 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28 | bar: 2026-08-03 to 2026-08-05
Plate | SD_B0014_A0043_P0337 | PL15*150 | Plate | 410 | A36 | 1 | 7.2 | 7.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0014_A0043_P0338 | PL15*150 | Plate | 678 | A36 | 1 | 10.3 | 10.3 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-05
Plate | SD_B0014_A0043_P0339 | PL15*150 | Plate | 510 | A36 | 1 | 7.2 | 7.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-08-03
Plate | SD_B0014_A0043_P0340 | PL15*150 | Plate | 1761 | A36 | 1 | 31.1 | 31.1 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-07-29
Plate | SD_B0014_A0043_P0341 | PL15*300 | Plate | 383 | A36 | 1 | 10.1 | 10.1 | 1 | 0 | [39 empty] | #VALUE! |  | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 | bar: 2026-07-29
Plate | SD_B0014_A0043_P0556 | PL20*150 | Plate | 3213 | A36 | 2 | 72.7 | 145.4 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0043_P0558 | PL20*150 | Plate | 3252 | A36 | 2 | 73 | 146 | 2 | 0 | 2026-07-11: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0043_P0596 | PL15*168 | Plate | 9902 | A36 | 1 | 195.7 | 195.7 | 1 | 0 | 2026-07-29: 1; 2026-08-03: 3; 2026-08-12: 1 |  | #VALUE! | EACDB | PL15 | Thừa 4 | MCC |  |  | chi tiết chia nối | 1
Plate | SD_B0014_A0115_P0372 | PL20*400 | Plate | 400 | A36 | 2 | 25.1 | 50.2 | 2 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 | bar: 2026-07-11 to 2026-07-12
Plate | SD_B0014_A0115_P0374 | PL3*250 | Plate | 800 | AISI304 | 4 | 4.7 | 18.8 | 4 | 0 | 2026-08-12: 4 |  | #VALUE! |  | PL3 |  | MCC | E275-01-CP131-1 A320-01-CP004-1 |  | A320-03-CP003 | 4 | 2026-06-23
Plate | SD_B0014_A0115_P0378 | PL20*400 | Plate | 970 | A36 | 2 | 60.9 | 121.8 | 2 | 0 | 2026-07-11: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0115_P0382 | PL20*265 | Plate | 400 | A36 | 4 | 16.6 | 66.4 | 4 | 0 | 2026-07-11: 3; 2026-07-12: 1 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29
Plate | SD_B0014_A0115_P0390 | PL30*1020 | Plate | 3080 | A36 | 1 | 739.8 | 739.8 | 1 | 0 | [39 empty] | #VALUE! |  | PL30 |  | MCC | M304-04-CP009-1 M304-04-CP014-2 M305-01-CP032-3 DCC26-A320-0002-11 M304-04-CP014-1 M305-11-CP032-3 A320-01-CP013-1 M305-01-CP032-1 |  | A320-03-CP010 | 1 | 2026-06-23 | bar: 2026-07-11
Plate | SD_B0014_A0115_P0393 | PL20*400 | Plate | 1119 | A36 | 2 | 70.3 | 140.6 | 2 | 0 | 2026-07-14: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0115_P0394 | PL20*400 | Plate | 730 | A36 | 2 | 45.8 | 91.6 | 2 | 0 | 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0115_P0397 | PL20*265 | Plate | 730 | A36 | 4 | 30.4 | 121.6 | 4 | 0 | 2026-07-12: 2; 2026-07-13: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29
Plate | SD_B0014_A0115_P0398 | PL20*265 | Plate | 1119 | A36 | 2 | 46.6 | 93.2 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0115_P0399 | PL20*265 | Plate | 1119 | A36 | 2 | 45 | 90 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0115_P0555 | PL20*715.8 | Plate | 1241 | A36 | 4 | 104.3 | 417.2 | 4 | 0 | 2026-07-14: 3; 2026-08-16: 1 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29
Plate | SD_B0014_A0115_P0618 | PL5*50 | Plate | 100 | AISI304 | 1 | 0.2 | 0.2 | 1 | 0 | [39 empty] | #VALUE! |  | PL5 |  | MCC | E275-01-CP039-2 |  | A320-03-CP006 | 1 | 2026-06-23 | bar: 2026-08-10
Plate | SD_B0014_A0127_P0391 | PL20*410 | Plate | 420 | A36 | 1 | 27 | 27 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-12
Plate | SD_B0014_A0127_P0396 | PL20*624.2 | Plate | 1550 | A36 | 1 | 117.1 | 117.1 | 1 | 0 | [39 empty] | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 | bar: 2026-07-12
Plate | SD_B0014_A0127_P0400 | PL20*420 | Plate | 461 | A36 | 2 | 30.4 | 60.8 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0128_P0392 | PL20*380 | Plate | 461 | A36 | 2 | 25.5 | 51 | 2 | 0 | 2026-07-14: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0129_P0395 | PL20*624 | Plate | 970 | A36 | 2 | 95 | 190 | 2 | 0 | 2026-07-12: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0014_A0130_P0401 | PL20*365 | Plate | 624 | A36 | 2 | 30.7 | 61.4 | 2 | 0 | 2026-08-16: 2 |  | #VALUE! |  | PL20 |  | MCC | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29
Plate | SD_B0020_A0016_P0026 | PL10 Dev.~4247 | Plate | 821 | A36 | 1 | 240.6 | 240.6 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0020_A0016_P0028 | PL10*50 | Plate | 550 | A36 | 1 | 2.2 | 2.2 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0016_P0030 | PL12*218 | Plate | 4558 | A36 | 1 | 93.5 | 93.5 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0020_A0016_P0031 | PL10 Dev.~4247 | Plate | 2142 | A36 | 1 | 647.7 | 647.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0020_A0016_P0033 | PL10*50 | Plate | 1601 | A36 | 1 | 6.3 | 6.3 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0016_P0034 | PL12*200 | Plate | 4587 | A36 | 1 | 86.3 | 86.3 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0020_A0016_P0036 | PL10 Dev.~4247 | Plate | 1171 | A36 | 1 | 323.9 | 323.9 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0020_A0016_P0038 | PL10*50 | Plate | 901 | A36 | 1 | 3.1 | 3.1 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0016_P0040 | PL10*50 | Plate | 4335 | A36 | 2 | 17 | 34 | 0 | 2 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0017_P0027 | PL10 Dev.~4247 | Plate | 550 | A36 | 1 | 126.1 | 126.1 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0020_A0017_P0029 | PL10*50 | Plate | 548 | A36 | 1 | 2.2 | 2.2 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0017_P0030 | PL12*218 | Plate | 4558 | A36 | 1 | 93.5 | 93.5 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0020_A0017_P0032 | PL10 Dev.~4247 | Plate | 1601 | A36 | 1 | 418.7 | 418.7 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0020_A0017_P0034 | PL12*200 | Plate | 4587 | A36 | 1 | 86.3 | 86.3 | 0 | 1 | [39 empty] | #VALUE! |  | PL12 |  | MCC
Plate | SD_B0020_A0017_P0035 | PL10*50 | Plate | 1597 | A36 | 1 | 6.3 | 6.3 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0017_P0037 | PL10 Dev.~4247 | Plate | 900 | A36 | 1 | 209.4 | 209.4 | 0 | 1 | [39 empty] | #VALUE! |  | #VALUE! |  | MCC
Plate | SD_B0020_A0017_P0039 | PL10*50 | Plate | 899 | A36 | 1 | 3.1 | 3.1 | 0 | 1 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0020_A0017_P0040 | PL10*50 | Plate | 4335 | A36 | 2 | 17 | 34 | 0 | 2 | [39 empty] | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0023_A0022_P0058 | PL10 Dev. ~2454.1 | Plate | 9985 | A36 | 8 | 1843.6 | 14748.8 | 8 | 0 | 2026-09-30: 5; 2026-10-22: 15; 2026-10-24: 3; 2026-10-28: 2 |  | #VALUE! | C4E 4A4B3C4D D 2E 2F | #VALUE! | Thừa 17 | PMC
Plate | SD_B0023_A0022_P0059 | PL10*50 | Plate | 9985 | A36 | 8 | 39.2 | 313.6 | 6 | 2 | 2026-10-16: 4; 2026-10-28: 2 |  | #VALUE! |  | PL10 |  | MCC
Plate | SD_B0023_A0022_P0060 | PL15*150 | Plate | 2490 | A36 | 32 | 43.9 | 1404.8 | 32 | 0 | 2026-10-01: 32 |  | #VALUE! | 16A16B | PL15 |  | MCC
Plate | SD_B0023_A0022_P0061 | PL15*168 | Plate | 2476 | A36 | 8 | 48.9 | 391.2 | 8 | 0 | 2026-10-01: 8 |  | #VALUE! | 4A4B | PL15 |  | MCC
Plate | SD_B0024_A0023_P0058 | PL10 Dev. ~2454.1 | Plate | 9985 | A36 | 8 | 1843.6 | 14748.8 | 8 | 0 | 2026-09-30: 14; 2026-10-22: 4; 2026-10-24: 2 |  | #VALUE! | 2A4B4C4E 4D A F | #VALUE! | Thừa 12 | PMC |  |  | chi tiết chia nối | 16
Plate | SD_B0024_A0023_P0059 | PL10*50 | Plate | 9985 | A36 | 8 | 39.2 | 313.6 | 4 | 4 | 2026-10-16: 4 |  | #VALUE! |  | PL10 |  | MCC | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 8 | 2026-06-28
Plate | SD_B0024_A0023_P0060 | PL15*150 | Plate | 2490 | A36 | 24 | 43.9 | 1053.6 | 24 | 0 | 2026-10-01: 22; 2026-10-30: 2 |  | #VALUE! | 12A 10B 2B | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 24 | 2026-06-28
Plate | SD_B0024_A0023_P0061 | PL15*168 | Plate | 2476 | A36 | 8 | 48.9 | 391.2 | 8 | 0 | 2026-10-01: 8 |  | #VALUE! | 4A4B | PL15 |  | MCC | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 8 | 2026-06-28
Plate | SD_B0028_A0029_P0060 | PL15*150 | Plate | 2490 | A36 | 16 | 43.9 | 702.4 | 16 | 0 | 2026-10-01: 16 |  | #VALUE! | 8A8B | PL15 |  | MCC
Plate | SD_B0028_A0029_P0061 | PL15*168 | Plate | 2476 | A36 | 8 | 48.9 | 391.2 | 8 | 0 | 2026-10-01: 8 |  | #VALUE! | 4A4B | PL15 |  | MCC
Plate | SD_B0028_A0029_P0085 | PL10 Dev. ~2454.1 | Plate | 5819 | A36 | 8 | 1074.3 | 8594.4 | 8 | 0 | 2026-09-30: 2; 2026-10-22: 8; 2026-10-24: 6 |  | #VALUE! | 2C4A4B 4C1 2C2 | #VALUE! | Thừa 8 | PMC
Plate | SD_B0028_A0029_P0087 | PL10*50 | Plate | 5819 | A36 | 8 | 22.8 | 182.4 | 4 | 4 | 2026-10-16: 4 |  | #VALUE! |  | PL10 |  | MCC

## A320M4120
ASSEMBLY PART LIST
Project name / Tên Dự án : Kuo Kuang Combined Cycle Power Plant Unit 2 | [72 empty] | chi tiết chia nối
Item Name / Tên Hạng mục : M4120 - Steam Duct (SD)
Contract No. / Số Hợp đồng : A320 |  | A320M4120
Prepared By / Chuẩn bị : Design Consultant Center 2
Document No. / Số Tài liệu : A320-01-APL-001 | [7 empty] | Rev./ Số Sửa đổi: 3 | [13 empty] | 0 | #DIV/0! | [5 empty] | Date: 06-Jul-2026 | [29 empty] | Content Rev. |  |  |  | Type Fabrication | [6 empty] | Type | Document Cutting
DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | DCC | DCC | DCC | DCC | DCC | DCC | L1 | L1 | L1 | L1 | L1 | L2 | L2 | L2 | L2 | L2 | L3 | L3 | L3 | L3 | L3 | L4 | L4 | L4 | L4 | L4 | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC-F | DCC-X | DCC-Y | DCC-Z | DCC-J | DCC-BH | DCC | DCC |  | DCC | DCC | DCC | DCC | DCC | DCC | DCC
No. | Drawing Number | Assembly No. | Description |  |  | Size | Length | Material | Q'ty | Set | T.Q'ty | U.Weight | T.Weight | Scope of Steel Work | Chung loai | Dang | Phan giao to | Ngay giao | Da nhan | Con thieu | Lam tron | Dong bo | Ti le dong bo | Fitup | Inspection | Clear | Loose Part | Total Area (m2) | Remark | AS Symbol | Scope of Steel Work LOT 1 | SL L1 | T'Qty L1 | Da nhan | Con thieu | Scope of Steel Work LOT 2 | SL L2 | T'L2 | Da nhan | Con thieu | Scope of Steel Work LOT 3 | SL L3 | T'L3 | Da nhan | Con thieu | Scope of Steel Work LOT 4 | SL L4 | T'L4 | Da nhan | Con thieu | Loose Part | Scope of Steel Work - LOT 1 | Scope of Steel Work - LOT 2 | Scope of Steel Work - LOT 3 | Scope of Steel Work - LOT 4 | Unit Area (m2) | Delivery item | Scope of Painting Work | Rev.1 (28/05/2026) | Rev.2 (09/06/2026) | Rev.3 (19/06/2026) | Rev.4 (09/07/2026) | Khoan Lỗ | Lốc tròn (Uốn cong) | Sấn | Vát mép & Cắt miệng | Gia công cơ khí (Không thay đổi chiều dày) | Gia công cơ khí (Có thay đổi chiều dày) | Tổ hợp | Fabrication or Purchasing | MPR No. | Q'Ty in MPR Bolt & Fitting | Cutting No. | Q'TY | Date Issue | Cutting No. | Q'TY | Date Issue | Remain (T'Qty-Q'Ty)
1 | 2 | 3 | 4 | 5A (Marking as Dwg.) | 5B (Marking as Cutting) | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [5 empty] | 20 | 21 | 22 | 23 | 24 |  |  |  |  | 17 | 18 | 19 | [20 empty] | 14 | 15A | 15 | 15 | 15 | 16 | 20 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
17 | 24D066-00-M4120_0.0 Sh.21 | 24D066-M4120#A0005#B0011#A0005 | [7 empty] | 4 |  |  | 6278.9 | AMC2 | [7 empty] | 0 | 0.35 |  |  |  |  | 157.5 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 4 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 39.4
18 | 24D066-00-M4120_0.0 Sh.21 | 24D066-M4120#A0005#B0011#A0005 | Plate | M4120_P0001 | SD_B0011_A0005_P0001 | PL10*50 | 7090 | A36 | 1 | 4 | 4 | 27.8 | 111.2 | AMC2 | Plate | MCC |  |  | 3 | 1 | 3 | [6 empty] | 0.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 4 | 4 | 3 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.9; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
19 | 24D066-00-M4120_0.0 Sh.21 | 24D066-M4120#A0005#B0011#A0005 | Plate | M4120_P0010 | SD_B0011_A0005_P0010 | PL10 Dev. ~2611.1 | 7090 | A36 | 1 | 4 | 4 | 1396.5 | 5586 | AMC2 | Plate | PMC |  |  | 4 | 0 | 4 | [6 empty] | 35.8 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 35.8; 33: Added, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
20 | 24D066-00-M4120_0.0 Sh.21 | 24D066-M4120#A0005#B0011#A0005 | Plate | M4120_P0012 | SD_B0011_A0005_P0012 | PL15*150 | 2647 | A36 | 2 | 4 | 8 | 46.7 | 373.6 | AMC2 | Plate | MCC |  |  | 0 | 8 | 0 | [6 empty] | 1.8 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 4 | 8 | 0 | 8 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.9; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
21 | 24D066-00-M4120_0.0 Sh.21 | 24D066-M4120#A0005#B0011#A0005 | Plate | M4120_P0013 | SD_B0011_A0005_P0013 | PL15*168 | 2633 | A36 | 1 | 4 | 4 | 52 | 208 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | 1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
22 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | [7 empty] | 1 |  |  | 1406.4 | AMC2 | [7 empty] | 0 | 0.125 |  |  |  |  | 34.7 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 34.7
23 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0014 | SD_B0012_A0006_P0014 | PL15*168 | 2925 | A36 | 1 | 1 | 1 | 57.8 | 57.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
24 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0043 | SD_B0012_A0006_P0043 | PL10 Dev. ~3038.5 | 6418 | A36 | 1 | 1 | 1 | 1158.7 | 1158.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 29.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 29.7; 41: Fabrication; 50: 1
25 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0044 | SD_B0012_A0006_P0044 | PL10*50 | 4042 | A36 | 1 | 1 | 1 | 15.9 | 15.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.5 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.5; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
26 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0045 | SD_B0012_A0006_P0045 | PL10*50 | 2051 | A36 | 1 | 1 | 1 | 8.1 | 8.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
27 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0325 | SD_B0012_A0006_P0325 | PL12*200 | 2921 | A36 | 1 | 1 | 1 | 54.9 | 54.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
28 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0503 | SD_B0012_A0006_P0503 | PL12*200 | 2531 | A36 | 1 | 1 | 1 | 47.6 | 47.6 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
29 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0506 | SD_B0012_A0006_P0506 | PL20*200 | 973 | A36 | 1 | 1 | 1 | 30.5 | 30.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
30 | 24D066-00-M4120_0.0 Sh.22 | 24D066-M4120#A0006#B0012#A0006 | Plate | M4120_P0510 | SD_B0012_A0006_P0510 | PL20*200 | 1051 | A36 | 1 | 1 | 1 | 32.9 | 32.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.5 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.5; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
31 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | [7 empty] | 1 |  |  | 1429.2 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 35.4 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 35.4
32 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0014 | SD_B0012_A0007_P0014 | PL15*168 | 2925 | A36 | 1 | 1 | 1 | 57.8 | 57.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
33 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0044 | SD_B0012_A0007_P0044 | PL10*50 | 4042 | A36 | 1 | 1 | 1 | 15.9 | 15.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.5 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.5; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
34 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0045 | SD_B0012_A0007_P0045 | PL10*50 | 2051 | A36 | 1 | 1 | 1 | 8.1 | 8.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
35 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0046 | SD_B0012_A0007_P0046 | PL10*50 | 6024 | A36 | 1 | 1 | 1 | 22.6 | 22.6 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.7; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
36 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0047 | SD_B0012_A0007_P0047 | PL10 Dev. ~3038.5 | 6418 | A36 | 1 | 1 | 1 | 1158.7 | 1158.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 29.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 29.7; 41: Fabrication; 50: 1
37 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0504 | SD_B0012_A0007_P0504 | PL12*200 | 2541 | A36 | 1 | 1 | 1 | 47.8 | 47.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
38 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0506 | SD_B0012_A0007_P0506 | PL20*200 | 973 | A36 | 1 | 1 | 1 | 30.5 | 30.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
39 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0510 | SD_B0012_A0007_P0510 | PL20*200 | 1051 | A36 | 1 | 1 | 1 | 32.9 | 32.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.5 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.5; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
40 | 24D066-00-M4120_0.0 Sh.23 | 24D066-M4120#A0007#B0012#A0007 | Plate | M4120_P0622 | SD_B0012_A0007_P0622 | PL12*200 | 2921 | A36 | 1 | 1 | 1 | 54.9 | 54.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
46 | 24D066-00-M4120_0.0 Sh.25 | 24D066-M4120#A0009#B0003#A0009 | [7 empty] | 6 |  |  | 10052.9 | AMC2 | [7 empty] | 0 | 0.8 |  |  |  |  | 213.6 | LOT 1 | x | AMC 2-S3 | 6 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 35.6
47 | 24D066-00-M4120_0.0 Sh.25 | 24D066-M4120#A0009#B0003#A0009 | Plate | M4120_P0016 | SD_B0003_A0009_P0016 | PL15*220 | 2254 | A36 | 1 | 6 | 6 | 58.3 | 349.8 | AMC2 | Plate | MCC |  |  | 6 | 0 | 6 | [6 empty] | 1.1 | LOT 1 |  | AMC 2-S3 | 6 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 6 | 2026-06-28 |  |  |  | 0
48 | 24D066-00-M4120_0.0 Sh.25 | 24D066-M4120#A0009#B0003#A0009 | Plate | M4120_P0017 | SD_B0003_A0009_P0017 | PL15*200 | 2264 | A36 | 2 | 6 | 12 | 53.2 | 638.4 | AMC2 | Plate | MCC |  |  | 12 | 0 | 6 | [6 empty] | 2 | LOT 1 |  | AMC 2-S3 | 6 | 12 | 12 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 12 | 2026-06-28 |  |  |  | 0
49 | 24D066-00-M4120_0.0 Sh.25 | 24D066-M4120#A0009#B0003#A0009 | Plate | M4120_P0094 | SD_B0003_A0009_P0094 | PL12 Dev. ~2243 | 7345 | A36 | 1 | 6 | 6 | 1481.8 | 8890.8 | AMC2 | Plate | PMC |  |  | 6 | 0 | 6 | [6 empty] | 31.7 | LOT 1 |  | AMC 2-S3 | 6 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 31.7; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 6; 50: 0
50 | 24D066-00-M4120_0.0 Sh.25 | 24D066-M4120#A0009#B0003#A0009 | Plate | M4120_P0095 | SD_B0003_A0009_P0095 | PL10*50 | 7345 | A36 | 1 | 6 | 6 | 28.8 | 172.8 | AMC2 | Plate | MCC |  |  | 0 | 6 | 0 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S3 | 6 | 6 | 0 | 6 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 6 | 2026-06-28 |  |  |  | 0
97 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | [7 empty] | 1 |  |  | 1437.6 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 36.7 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 36.7
98 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0026 | SD_B0020_A0016_P0026 | PL10 Dev.~4247 | 821 | A36 | 1 | 1 | 1 | 240.6 | 240.6 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 6.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 6.2; 41: Fabrication; 50: 1
99 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0028 | SD_B0020_A0016_P0028 | PL10*50 | 550 | A36 | 1 | 1 | 1 | 2.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
100 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0030 | SD_B0020_A0016_P0030 | PL12*218 | 4558 | A36 | 1 | 1 | 1 | 93.5 | 93.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 2.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 2.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
101 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0031 | SD_B0020_A0016_P0031 | PL10 Dev.~4247 | 2142 | A36 | 1 | 1 | 1 | 647.7 | 647.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 16.6 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 16.6; 41: Fabrication; 50: 1
102 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0033 | SD_B0020_A0016_P0033 | PL10*50 | 1601 | A36 | 1 | 1 | 1 | 6.3 | 6.3 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
103 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0034 | SD_B0020_A0016_P0034 | PL12*200 | 4587 | A36 | 1 | 1 | 1 | 86.3 | 86.3 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.9; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
104 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0036 | SD_B0020_A0016_P0036 | PL10 Dev.~4247 | 1171 | A36 | 1 | 1 | 1 | 323.9 | 323.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 8.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 8.4; 41: Fabrication; 50: 1
105 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0038 | SD_B0020_A0016_P0038 | PL10*50 | 901 | A36 | 1 | 1 | 1 | 3.1 | 3.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
106 | 24D066-00-M4120_0.0 Sh.32 | 24D066-M4120#A0016#B0020#A0016 | Plate | M4120_P0040 | SD_B0020_A0016_P0040 | PL10*50 | 4335 | A36 | 2 | 1 | 2 | 17 | 34 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.5; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
107 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | [7 empty] | 1 |  |  | 979.5 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 25 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 25
108 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0027 | SD_B0020_A0017_P0027 | PL10 Dev.~4247 | 550 | A36 | 1 | 1 | 1 | 126.1 | 126.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 3.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 3.3; 41: Fabrication; 50: 1
109 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0029 | SD_B0020_A0017_P0029 | PL10*50 | 548 | A36 | 1 | 1 | 1 | 2.2 | 2.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
110 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0030 | SD_B0020_A0017_P0030 | PL12*218 | 4558 | A36 | 1 | 1 | 1 | 93.5 | 93.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 2.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 2.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
111 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0032 | SD_B0020_A0017_P0032 | PL10 Dev.~4247 | 1601 | A36 | 1 | 1 | 1 | 418.7 | 418.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 10.8 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 10.8; 41: Fabrication; 50: 1
112 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0034 | SD_B0020_A0017_P0034 | PL12*200 | 4587 | A36 | 1 | 1 | 1 | 86.3 | 86.3 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.9; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
113 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0035 | SD_B0020_A0017_P0035 | PL10*50 | 1597 | A36 | 1 | 1 | 1 | 6.3 | 6.3 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
114 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0037 | SD_B0020_A0017_P0037 | PL10 Dev.~4247 | 900 | A36 | 1 | 1 | 1 | 209.4 | 209.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 5.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 5.4; 41: Fabrication; 50: 1
115 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0039 | SD_B0020_A0017_P0039 | PL10*50 | 899 | A36 | 1 | 1 | 1 | 3.1 | 3.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
116 | 24D066-00-M4120_0.0 Sh.33 | 24D066-M4120#A0017#B0020#A0017 | Plate | M4120_P0040 | SD_B0020_A0017_P0040 | PL10*50 | 4335 | A36 | 2 | 1 | 2 | 17 | 34 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.5; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
141 | 24D066-00-M4120_0.0 Sh.38 | 24D066-M4120#A0022#B0023#A0022 | [7 empty] | 8 |  |  | 16858.1 | AMC2 | [7 empty] | 6 | 0.96429 |  |  |  |  | 421.2 | LOT 2(Qty:4), LOT 3(Qty:4) | x | N/A | 0 |  |  |  | AMC 2-S2 | 4 |  |  |  | AMC 2-S2 | 4 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 52.7; 31: Modify: LOT2,3 (Qty:1->4)
142 | 24D066-00-M4120_0.0 Sh.38 | 24D066-M4120#A0022#B0023#A0022 | Plate | M4120_P0058 | SD_B0023_A0022_P0058 | PL10 Dev. ~2454.1 | 9985 | A36 | 1 | 8 | 8 | 1843.6 | 14748.8 | AMC2 | Plate | PMC |  |  | 8 | 0 | 8 | [6 empty] | 47.2 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 47.2; 31: Added: thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
143 | 24D066-00-M4120_0.0 Sh.38 | 24D066-M4120#A0022#B0023#A0022 | Plate | M4120_P0059 | SD_B0023_A0022_P0059 | PL10*50 | 9985 | A36 | 1 | 8 | 8 | 39.2 | 313.6 | AMC2 | Plate | MCC |  |  | 6 | 2 | 6 | [6 empty] | 1.2 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 1.2; 31: Added: thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
144 | 24D066-00-M4120_0.0 Sh.38 | 24D066-M4120#A0022#B0023#A0022 | Plate | M4120_P0060 | SD_B0023_A0022_P0060 | PL15*150 | 2490 | A36 | 4 | 8 | 32 | 43.9 | 1404.8 | AMC2 | Plate | MCC |  |  | 32 | 0 | 8 | [6 empty] | 3.3 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 16 | 4 | 12 | AMC 2-S2 | 4 | 16 | 16 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 0.8; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 32
145 | 24D066-00-M4120_0.0 Sh.38 | 24D066-M4120#A0022#B0023#A0022 | Plate | M4120_P0061 | SD_B0023_A0022_P0061 | PL15*168 | 2476 | A36 | 1 | 8 | 8 | 48.9 | 391.2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 8 | [6 empty] | 0.9 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 0.9; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
146 | 24D066-00-M4120_0.0 Sh.39 | 24D066-M4120#A0023#B0024#A0023 | [7 empty] | 8 |  |  | 33014.1 | AMC2 | [7 empty] | 4 | 0.91667 |  |  |  |  | 829.3 | LOT 1(Qty:8), LOT 2(Qty:4), LOT 3(Qty:4) | x | N/A | 0 |  |  |  | AMC 2-S2 | 4 |  |  |  | AMC 2-S2 | 4 |  |  |  | N/A | 0 |  |  |  | 15A: FAC 2; 15: AMC 2; 15: AMC 2; 15: -; 16: 51.8; 31: Modify: LOT1 (Qty:2->8); LOT2,3 (Qty:1->4)
147 | 24D066-00-M4120_0.0 Sh.39 | 24D066-M4120#A0023#B0024#A0023 | Plate | M4120_P0058 | SD_B0024_A0023_P0058 | PL10 Dev. ~2454.1 | 9985 | A36 | 1 | 8 | 8 | 1843.6 | 14748.8 | AMC2 | Plate | PMC |  |  | 8 | 0 | 8 | [6 empty] | 47.2 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | AMC 2 | - | 47.2 |  |  |  | Added: thêm nguyên công | MODIFY, bổ sung cho Lot1 |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication |  |  | chi tiết chia nối | 16 |  |  |  |  | -8
148 | 24D066-00-M4120_0.0 Sh.39 | 24D066-M4120#A0023#B0024#A0023 | Plate | M4120_P0059 | SD_B0024_A0023_P0059 | PL10*50 | 9985 | A36 | 1 | 8 | 8 | 39.2 | 313.6 | AMC2 | Plate | MCC |  |  | 4 | 4 | 4 | [6 empty] | 1.2 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | AMC 2 | - | 1.2 |  |  |  | Added: thêm nguyên công | MODIFY, bổ sung cho Lot1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 8 | 2026-06-28 |  |  |  | 0
149 | 24D066-00-M4120_0.0 Sh.39 | 24D066-M4120#A0023#B0024#A0023 | Plate | M4120_P0060 | SD_B0024_A0023_P0060 | PL15*150 | 2490 | A36 | 3 | 8 | 24 | 43.9 | 1053.6 | AMC2 | Plate | MCC |  |  | 24 | 0 | 8 | [6 empty] | 2.5 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 12 | 4 | 8 | AMC 2-S2 | 4 | 12 | 12 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | AMC 2 | - | 0.8 |  |  |  |  | MODIFY, bổ sung cho Lot1 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 24 | 2026-06-28 |  |  |  | 0
150 | 24D066-00-M4120_0.0 Sh.39 | 24D066-M4120#A0023#B0024#A0023 | Plate | M4120_P0061 | SD_B0024_A0023_P0061 | PL15*168 | 2476 | A36 | 1 | 8 | 8 | 48.9 | 391.2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 8 | [6 empty] | 0.9 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | AMC 2 | - | 0.9 |  |  |  |  | MODIFY, bổ sung cho Lot1 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 8 | 2026-06-28 |  |  |  | 0
176 | 24D066-00-M4120_0.0 Sh.45 | 24D066-M4120#A0029#B0028#A0029 | [7 empty] | 8 |  |  | 9870.8 | AMC2 | [7 empty] | 4 | 0.9 |  |  |  |  | 246.5 | LOT 2(Qty:4), LOT 3(Qty:4) | x | N/A | 0 |  |  |  | AMC 2-S2 | 4 |  |  |  | AMC 2-S2 | 4 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 30.8; 31: Modify: LOT2,3 (Qty:1->4)
177 | 24D066-00-M4120_0.0 Sh.45 | 24D066-M4120#A0029#B0028#A0029 | Plate | M4120_P0060 | SD_B0028_A0029_P0060 | PL15*150 | 2490 | A36 | 2 | 8 | 16 | 43.9 | 702.4 | AMC2 | Plate | MCC |  |  | 16 | 0 | 8 | [6 empty] | 1.6 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 8 | 4 | 4 | AMC 2-S2 | 4 | 8 | 8 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 0.8; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 16
178 | 24D066-00-M4120_0.0 Sh.45 | 24D066-M4120#A0029#B0028#A0029 | Plate | M4120_P0061 | SD_B0028_A0029_P0061 | PL15*168 | 2476 | A36 | 1 | 8 | 8 | 48.9 | 391.2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 8 | [6 empty] | 0.9 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 0.9; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
179 | 24D066-00-M4120_0.0 Sh.45 | 24D066-M4120#A0029#B0028#A0029 | Plate | M4120_P0085 | SD_B0028_A0029_P0085 | PL10 Dev. ~2454.1 | 5819 | A36 | 1 | 8 | 8 | 1074.3 | 8594.4 | AMC2 | Plate | PMC |  |  | 8 | 0 | 8 | [6 empty] | 27.6 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 27.6; 31: Added: thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
180 | 24D066-00-M4120_0.0 Sh.45 | 24D066-M4120#A0029#B0028#A0029 | Plate | M4120_P0087 | SD_B0028_A0029_P0087 | PL10*50 | 5819 | A36 | 1 | 8 | 8 | 22.8 | 182.4 | AMC2 | Plate | MCC |  |  | 4 | 4 | 4 | [6 empty] | 0.7 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 4 | 4 | 4 | 0 | AMC 2-S2 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: AMC 2; 15: AMC 2; 15: -; 16: 0.7; 31: Added: thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 8
213 | 24D066-00-M4120_0.0 Sh.51 | 24D066-M4120#A0035#B0001#A0035 | [7 empty] | 4 |  |  | 7650.1 | AMC2 | [7 empty] | 4 | 1 |  |  |  |  | 191.8 | LOT 1 | x | AMC 2-S1 | 4 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 48
214 | 24D066-00-M4120_0.0 Sh.51 | 24D066-M4120#A0035#B0001#A0035 | Plate | M4120_P0060 | SD_B0001_A0035_P0060 | PL15*150 | 2490 | A36 | 3 | 4 | 12 | 43.9 | 526.8 | AMC2 | Plate | MCC |  |  | 12 | 0 | 4 | [6 empty] | 2.5 | LOT 1 |  | AMC 2-S1 | 4 | 12 | 12 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 12 | 2026-06-28 |  |  |  | 0
215 | 24D066-00-M4120_0.0 Sh.51 | 24D066-M4120#A0035#B0001#A0035 | Plate | M4120_P0061 | SD_B0001_A0035_P0061 | PL15*168 | 2476 | A36 | 1 | 4 | 4 | 48.9 | 195.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 4 | 2026-06-28 |  |  |  | 0
216 | 24D066-00-M4120_0.0 Sh.51 | 24D066-M4120#A0035#B0001#A0035 | Plate | M4120_P0102 | SD_B0001_A0035_P0102 | PL10 Dev. ~2454.1 | 9185 | A36 | 1 | 4 | 4 | 1695.9 | 6783.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 4 | [6 empty] | 43.5 | LOT 1 |  | AMC 2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 43.5; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 4; 50: 0
217 | 24D066-00-M4120_0.0 Sh.51 | 24D066-M4120#A0035#B0001#A0035 | Plate | M4120_P0103 | SD_B0001_A0035_P0103 | PL10*50 | 9185 | A36 | 1 | 4 | 4 | 36.1 | 144.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | 1.1 | LOT 1 |  | AMC 2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
218 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | [7 empty] | 1 |  |  | 4132.4 | AMC2 | [7 empty] | 0 | 0.75 |  |  |  |  | 90.5 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 90.5
219 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0096 | SD_B0002_A0036_P0096 | PL15*220 | 5258 | A36 | 1 | 1 | 1 | 136.1 | 136.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 2.5; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
220 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0104 | SD_B0002_A0036_P0104 | PL10 Dev. ~9556 | 3450 | A36 | 1 | 1 | 1 | 1719.3 | 1719.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 44.1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 44.1; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
221 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0105 | SD_B0002_A0036_P0105 | PL12 Dev. ~4935.8 | 5897 | A36 | 1 | 1 | 1 | 1000.2 | 1000.2 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 21.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 21.7; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
222 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0113 | SD_B0002_A0036_P0113 | PL10 Dev. ~3853.3 | 3917 | A36 | 1 | 1 | 1 | 140.9 | 140.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 3.9 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 3.9; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
223 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0116 | SD_B0002_A0036_P0116 | PL12*240 | 392 | A36 | 2 | 1 | 2 | 7.4 | 14.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0007-3/6 DCC26-A320-0007-3/5 DCC26-A320-0007-3/4 DCC26-A320-0007-6/7 DCC26-A320-0007-3/3 DCC26-A320-0007-3/2 DCC26-A320-0007-3/1 |  | A320-03-CP007 | 2 | 2026-06-23 |  |  |  | 0
224 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0332 | SD_B0002_A0036_P0332 | PL15*200 | 3213 | A36 | 2 | 1 | 2 | 75.2 | 150.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.8 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28 |  |  |  | 0
225 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0336 | SD_B0002_A0036_P0336 | PL15*200 | 10116 | A36 | 1 | 1 | 1 | 220.6 | 220.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 4.1; 30: Modify: cập nhật nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
226 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0344 | SD_B0002_A0036_P0344 | PL15*200 | 2007 | A36 | 2 | 1 | 2 | 46.1 | 92.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28 |  |  |  | 0
227 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0561 | SD_B0002_A0036_P0561 | PL20*1961.5 | 2606 | A36 | 1 | 1 | 1 | 353 | 353 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 4.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 4.7; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
228 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0562 | SD_B0002_A0036_P0562 | PL20*1166.9 | 1311 | A36 | 2 | 1 | 2 | 115.1 | 230.2 | AMC2 | Plate | MCC |  |  | 1 | 1 | 0 | [6 empty] | 3.1 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.5 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
229 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0603 | SD_B0002_A0036_P0603 | PL12*156.3 | 2595 | A36 | 1 | 1 | 1 | 37.4 | 37.4 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0007-3/6 DCC26-A320-0007-3/5 DCC26-A320-0007-3/4 DCC26-A320-0007-6/7 DCC26-A320-0007-3/3 DCC26-A320-0007-3/2 DCC26-A320-0007-3/1 |  | A320-03-CP007 | 1 | 2026-06-23 |  |  |  | 0
230 | 24D066-00-M4120_0.0 Sh.52 | 24D066-M4120#A0036#B0002#A0036 | Plate | M4120_P0604 | SD_B0002_A0036_P0604 | PL12*156.3 | 2595 | A36 | 1 | 1 | 1 | 37.4 | 37.4 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0007-3/6 DCC26-A320-0007-3/5 DCC26-A320-0007-3/4 DCC26-A320-0007-6/7 DCC26-A320-0007-3/3 DCC26-A320-0007-3/2 DCC26-A320-0007-3/1 |  | A320-03-CP007 | 1 | 2026-06-23 |  |  |  | 0
231 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | [7 empty] | 1 |  |  | 1107.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 23.1 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 23.1
232 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0097 | SD_B0002_A0037_P0097 | PL15*220 | 1502 | A36 | 1 | 1 | 1 | 38.9 | 38.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
233 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0106 | SD_B0002_A0037_P0106 | PL12 Dev. ~2305.5 | 5868 | A36 | 1 | 1 | 1 | 856.7 | 856.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 18.4 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 18.4; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
234 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0107 | SD_B0002_A0037_P0107 | PL10*60 | 1127 | A36 | 1 | 1 | 1 | 5.3 | 5.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
235 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0108 | SD_B0002_A0037_P0108 | PL10*60 | 1410 | A36 | 1 | 1 | 1 | 6.6 | 6.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
236 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0109 | SD_B0002_A0037_P0109 | PL10*60 | 1100 | A36 | 1 | 1 | 1 | 5.2 | 5.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
237 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0110 | SD_B0002_A0037_P0110 | PL10*60 | 1979 | A36 | 1 | 1 | 1 | 9.3 | 9.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
238 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0112 | SD_B0002_A0037_P0112 | PL10*60 | 5562 | A36 | 1 | 1 | 1 | 26.2 | 26.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
239 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0342 | SD_B0002_A0037_P0342 | PL15*200 | 1679 | A36 | 1 | 1 | 1 | 39.5 | 39.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
240 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0559 | SD_B0002_A0037_P0559 | PL20*200 | 1889 | A36 | 1 | 1 | 1 | 59.2 | 59.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
241 | 24D066-00-M4120_0.0 Sh.53 | 24D066-M4120#A0037#B0002#A0037 | Plate | M4120_P0560 | SD_B0002_A0037_P0560 | PL20*200 | 1941 | A36 | 1 | 1 | 1 | 60.8 | 60.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
242 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | [7 empty] | 1 |  |  | 1107.7 | AMC2 | [7 empty] | 0 | 0.9 |  |  |  |  | 23.1 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 23.1
243 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0097 | SD_B0002_A0038_P0097 | PL15*220 | 1502 | A36 | 1 | 1 | 1 | 38.9 | 38.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
244 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0107 | SD_B0002_A0038_P0107 | PL10*60 | 1127 | A36 | 1 | 1 | 1 | 5.3 | 5.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
245 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0108 | SD_B0002_A0038_P0108 | PL10*60 | 1410 | A36 | 1 | 1 | 1 | 6.6 | 6.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
246 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0109 | SD_B0002_A0038_P0109 | PL10*60 | 1100 | A36 | 1 | 1 | 1 | 5.2 | 5.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
247 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0110 | SD_B0002_A0038_P0110 | PL10*60 | 1979 | A36 | 1 | 1 | 1 | 9.3 | 9.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
248 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0112 | SD_B0002_A0038_P0112 | PL10*60 | 5562 | A36 | 1 | 1 | 1 | 26.2 | 26.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
249 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0114 | SD_B0002_A0038_P0114 | PL12 Dev. ~2305.5 | 5868 | A36 | 1 | 1 | 1 | 856.7 | 856.7 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 18.4 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 18.4; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
250 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0342 | SD_B0002_A0038_P0342 | PL15*200 | 1679 | A36 | 1 | 1 | 1 | 39.5 | 39.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
251 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0559 | SD_B0002_A0038_P0559 | PL20*200 | 1889 | A36 | 1 | 1 | 1 | 59.2 | 59.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
252 | 24D066-00-M4120_0.0 Sh.54 | 24D066-M4120#A0038#B0002#A0038 | Plate | M4120_P0560 | SD_B0002_A0038_P0560 | PL20*200 | 1941 | A36 | 1 | 1 | 1 | 60.8 | 60.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
253 | 24D066-00-M4120_0.0 Sh.55 | 24D066-M4120#A0039#B0002#A0039 | [7 empty] | 1 |  |  | 2507.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 52.8 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 52.8
254 | 24D066-00-M4120_0.0 Sh.55 | 24D066-M4120#A0039#B0002#A0039 | Plate | M4120_P0096 | SD_B0002_A0039_P0096 | PL15*220 | 5258 | A36 | 1 | 1 | 1 | 136.1 | 136.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 2.5; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
255 | 24D066-00-M4120_0.0 Sh.55 | 24D066-M4120#A0039#B0002#A0039 | Plate | M4120_P0111 | SD_B0002_A0039_P0111 | PL12 Dev. ~4986.1 | 6006 | A36 | 1 | 1 | 1 | 2259.1 | 2259.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 48.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 48.2; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
256 | 24D066-00-M4120_0.0 Sh.55 | 24D066-M4120#A0039#B0002#A0039 | Plate | M4120_P0343 | SD_B0002_A0039_P0343 | PL15*200 | 4773 | A36 | 1 | 1 | 1 | 112.3 | 112.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 2.1; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
257 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | [7 empty] | 1 |  |  | 4152.2 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 101.5 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 101.5
258 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0011 | SD_B0012_A0040_P0011 | PL15*168 | 4680 | A36 | 1 | 1 | 1 | 92.5 | 92.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.7; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
259 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0025 | SD_B0012_A0040_P0025 | PL10 Dev. ~6463 | 4383 | A36 | 1 | 1 | 1 | 955.7 | 955.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 24.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 24.7; 41: Fabrication; 50: 1
260 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0041 | SD_B0012_A0040_P0041 | PL10 Dev. ~8614 | 3640 | A36 | 1 | 1 | 1 | 1964.7 | 1964.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 50.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 50.3; 41: Fabrication; 50: 1
261 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0042 | SD_B0012_A0040_P0042 | PL12*200 | 9174 | A36 | 1 | 1 | 1 | 172.7 | 172.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 3.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 3.9; 33: Added, thêm nguyên công; 34: 1; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
262 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0048 | SD_B0012_A0040_P0048 | PL10 Dev. ~3801 | 3555 | A36 | 1 | 1 | 1 | 139.9 | 139.9 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 3.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 3.9; 41: Fabrication; 50: 1
263 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0115 | SD_B0012_A0040_P0115 | PL12*240 | 365 | A36 | 2 | 1 | 2 | 7.2 | 14.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.2; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
264 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0324 | SD_B0012_A0040_P0324 | PL12*200 | 3210 | A36 | 2 | 1 | 2 | 60 | 120 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 2.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
265 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0326 | SD_B0012_A0040_P0326 | PL12*200 | 1726 | A36 | 2 | 1 | 2 | 32 | 64 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 1.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.7; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
266 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0502 | SD_B0012_A0040_P0502 | PL12*200 | 3228 | A36 | 1 | 1 | 1 | 60.7 | 60.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
267 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0505 | SD_B0012_A0040_P0505 | PL20*200 | 3027 | A36 | 1 | 1 | 1 | 94.8 | 94.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.3; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
268 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0509 | SD_B0012_A0040_P0509 | PL20*200 | 3130 | A36 | 1 | 1 | 1 | 98.1 | 98.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
269 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0511 | SD_B0012_A0040_P0511 | PL12*400 | 1359 | A36 | 1 | 1 | 1 | 46.4 | 46.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
270 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0512 | SD_B0012_A0040_P0512 | PL12*760.4 | 983 | A36 | 1 | 1 | 1 | 34.8 | 34.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.8 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.8; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
271 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0513 | SD_B0012_A0040_P0513 | PL12*420.4 | 434 | A36 | 1 | 1 | 1 | 11.1 | 11.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.3; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
272 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0514 | SD_B0012_A0040_P0514 | PL12*400 | 1471 | A36 | 2 | 1 | 2 | 50.2 | 100.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 2.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
273 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0515 | SD_B0012_A0040_P0515 | PL12*866.6 | 1087 | A36 | 2 | 1 | 2 | 41.9 | 83.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 1.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.9; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
274 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0516 | SD_B0012_A0040_P0516 | PL12*524.7 | 547 | A36 | 2 | 1 | 2 | 17.3 | 34.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.8 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
275 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0597 | SD_B0012_A0040_P0597 | PL12*156.3 | 2220 | A36 | 1 | 1 | 1 | 31.9 | 31.9 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.7; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 1; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
276 | 24D066-00-M4120_0.0 Sh.56 | 24D066-M4120#A0040#B0012#A0040 | Plate | M4120_P0598 | SD_B0012_A0040_P0598 | PL12*156.3 | 2220 | A36 | 1 | 1 | 1 | 31.9 | 31.9 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | 0.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.7; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 1; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
321 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | [7 empty] | 1 |  |  | 6103.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 151.1 | LOT 1 | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 151.1
322 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0132 | SD_B0014_A0043_P0132 | PL10 Dev.~9456 | 3430 | A36 | 1 | 1 | 1 | 1424.4 | 1424.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 36.5 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 36.5; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
323 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0133 | SD_B0014_A0043_P0133 | PL10*678 | 11493 | A36 | 1 | 1 | 1 | 611.3 | 611.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 15.8 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 15.8 | [6 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
324 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0134 | SD_B0014_A0043_P0134 | PL10*50 | 11567 | A36 | 2 | 1 | 2 | 45.4 | 90.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.8 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 1.4; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 2; 50: 0
325 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0135 | SD_B0014_A0043_P0135 | PL10*756.6 | 644 | A36 | 2 | 1 | 2 | 32.3 | 64.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
326 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0136 | SD_B0014_A0043_P0136 | PL10*756.6 | 851 | A36 | 2 | 1 | 2 | 46.9 | 93.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 2.5 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.2 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
327 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0137 | SD_B0014_A0043_P0137 | PL10*756.6 | 1096 | A36 | 2 | 1 | 2 | 62.6 | 125.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 3.3 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.6 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
328 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0138 | SD_B0014_A0043_P0138 | PL10*756.6 | 1260 | A36 | 2 | 1 | 2 | 73.1 | 146.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 3.8 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.9 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
329 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0139 | SD_B0014_A0043_P0139 | PL10*756.6 | 1372 | A36 | 2 | 1 | 2 | 80.2 | 160.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.2 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.1 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
330 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0140 | SD_B0014_A0043_P0140 | PL10*756.6 | 1445 | A36 | 2 | 1 | 2 | 84.9 | 169.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.4 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.2 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
331 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0141 | SD_B0014_A0043_P0141 | PL10*756.6 | 1484 | A36 | 2 | 1 | 2 | 87.6 | 175.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.6 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.3 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
332 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0142 | SD_B0014_A0043_P0142 | PL10*756.6 | 1495 | A36 | 2 | 1 | 2 | 88.5 | 177 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.6 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.3 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
333 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0143 | SD_B0014_A0043_P0143 | PL10*756.6 | 1451 | A36 | 2 | 1 | 2 | 84.8 | 169.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 4.4 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.2 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
334 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0144 | SD_B0014_A0043_P0144 | PL10*756.6 | 1276 | A36 | 2 | 1 | 2 | 72.8 | 145.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 3.8 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.9 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
335 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0145 | SD_B0014_A0043_P0145 | PL10*756.6 | 890 | A36 | 2 | 1 | 2 | 46.4 | 92.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | 2.4 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.2 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
336 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0146 | SD_B0014_A0043_P0146 | PL10 Dev.~9456 | 3530 | A36 | 1 | 1 | 1 | 1424.4 | 1424.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 36.5 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 36.5; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
337 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0147 | SD_B0014_A0043_P0147 | PL10*678 | 4243 | A36 | 1 | 1 | 1 | 225.8 | 225.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 5.9 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 5.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
338 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0319 | SD_B0014_A0043_P0319 | PL15*150 | 4619 | A36 | 1 | 1 | 1 | 80.9 | 80.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.5 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 1.5; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
339 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0320 | SD_B0014_A0043_P0320 | PL15*150 | 5305 | A36 | 1 | 1 | 1 | 93.5 | 93.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.8 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 1.8; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
340 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0321 | SD_B0014_A0043_P0321 | PL15*150 | 985 | A36 | 2 | 1 | 2 | 17 | 34 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.6 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28 |  |  |  | 0
341 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0322 | SD_B0014_A0043_P0322 | PL15*150 | 1397 | A36 | 2 | 1 | 2 | 22.8 | 45.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.9 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28 |  |  |  | 0
342 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0337 | SD_B0014_A0043_P0337 | PL15*150 | 410 | A36 | 1 | 1 | 1 | 7.2 | 7.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
343 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0338 | SD_B0014_A0043_P0338 | PL15*150 | 678 | A36 | 1 | 1 | 1 | 10.3 | 10.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
344 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0339 | SD_B0014_A0043_P0339 | PL15*150 | 510 | A36 | 1 | 1 | 1 | 7.2 | 7.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.1 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
345 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0340 | SD_B0014_A0043_P0340 | PL15*150 | 1761 | A36 | 1 | 1 | 1 | 31.1 | 31.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.6 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
346 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0341 | SD_B0014_A0043_P0341 | PL15*300 | 383 | A36 | 1 | 1 | 1 | 10.1 | 10.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.2 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
347 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0556 | SD_B0014_A0043_P0556 | PL20*150 | 3213 | A36 | 2 | 1 | 2 | 72.7 | 145.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.1 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
348 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0558 | SD_B0014_A0043_P0558 | PL20*150 | 3252 | A36 | 2 | 1 | 2 | 73 | 146 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 2.1 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
349 | 24D066-00-M4120_0.0 Sh.59 | 24D066-M4120#A0043#B0014#A0043 | Plate | M4120_P0596 | SD_B0014_A0043_P0596 | PL15*168 | 9902 | A36 | 1 | 1 | 1 | 195.7 | 195.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.6 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 3.6; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
350 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | [7 empty] | 2 |  |  | 25685 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 667 | LOT 1(Qty:2), LOT 2(Qty:2), LOT 3(Qty:2) | x | N/A | 0 |  |  |  | AMC 2-S2 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: FAC 2; 15: AMC 2; 15: FAC 1; 15: -; 16: 111.2
351 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0134 | SD_A0044_P0134 | PL10*50 | 11567 | A36 | 2 | 2 | 4 | 45.4 | 181.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | 2.8 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: FAC 2; 15: AMC 2; 15: FAC 1; 15: -; 16: 1.4; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 12; 50: -8
352 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0222 | SD_A0044_P0222 | PL10 Dev.~9456 | 3272 | A36 | 1 | 2 | 2 | 1233.4 | 2466.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 31.7 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: FAC 2; 15: AMC 2; 15: FAC 1; 15: -; 16: 31.7; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 6; 50: -4
353 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0223 | SD_A0044_P0223 | PL10*485 | 11493 | A36 | 1 | 2 | 2 | 437.3 | 874.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 11.4 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 11.4 | [6 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
354 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0224 | SD_A0044_P0224 | PL10*505.9 | 509 | A36 | 2 | 2 | 4 | 17.6 | 70.4 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 0.9 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 0.5 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
355 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0225 | SD_A0044_P0225 | PL10 Dev.~9456 | 3435 | A36 | 1 | 2 | 2 | 1353.9 | 2707.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | 34.7 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: FAC 2; 15: AMC 2; 15: FAC 1; 15: -; 16: 34.7; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 6; 50: -4
356 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0226 | SD_A0044_P0226 | PL10*485 | 4243 | A36 | 1 | 2 | 2 | 161.5 | 323 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 4.2 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 4.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 2 | 2026-06-28 |  |  |  | 0
357 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0231 | SD_A0044_P0231 | PL10*505.9 | 768 | A36 | 2 | 2 | 4 | 29.1 | 116.4 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 1.5 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 0.8 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
358 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0232 | SD_A0044_P0232 | PL10*505.9 | 1041 | A36 | 2 | 2 | 4 | 40.4 | 161.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 2.1 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.1 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
359 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0233 | SD_A0044_P0233 | PL10*505.9 | 1223 | A36 | 2 | 2 | 4 | 47.9 | 191.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 2.5 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.3 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
360 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0234 | SD_A0044_P0234 | PL10*505.9 | 1345 | A36 | 2 | 2 | 4 | 52.9 | 211.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 2.8 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.4 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
361 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0235 | SD_A0044_P0235 | PL10*505.9 | 1429 | A36 | 2 | 2 | 4 | 56.4 | 225.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 3 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.5 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
362 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0236 | SD_A0044_P0236 | PL10*505.9 | 1477 | A36 | 2 | 2 | 4 | 58.4 | 233.6 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 3.1 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.5 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
363 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0237 | SD_A0044_P0237 | PL10*505.9 | 1494 | A36 | 2 | 2 | 4 | 59.2 | 236.8 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 3.1 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.6 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
364 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0238 | SD_A0044_P0238 | PL10*505.9 | 1451 | A36 | 2 | 2 | 4 | 57.1 | 228.4 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 3 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.5 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
365 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0239 | SD_A0044_P0239 | PL10*505.9 | 1276 | A36 | 2 | 2 | 4 | 49.7 | 198.8 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 2.6 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 1.3 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
366 | 24D066-00-M4120_0.0 Sh.60 | 24D066-M4120#A0044#A0044 | Plate | M4120_P0240 | SD_A0044_P0240 | PL10*505.9 | 890 | A36 | 2 | 2 | 4 | 33.3 | 133.2 | AMC2 | Plate | PMC |  |  | 4 | 0 | 2 | [6 empty] | 1.8 | LOT 1, 2, 3 |  | N/A | 0 | 0 | 0 | 0 | AMC 2-S2 | 2 | 4 | 2 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 2 | AMC 2 | FAC 1 | - | 0.9 | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 4 | 2026-06-28 |  |  |  | 0
573 | 24D066-00-M4120_0.0 Sh.82 | 24D066-M4120#A0066#B0005#A0066 | [7 empty] | 1 |  |  | 1822.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 27 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 27
574 | 24D066-00-M4120_0.0 Sh.82 | 24D066-M4120#A0066#B0005#A0066 | Plate | M4120_P0201 | SD_B0005_A0066_P0201 | PL10*44.8 | 6766 | A36 | 1 | 1 | 1 | 23.7 | 23.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
575 | 24D066-00-M4120_0.0 Sh.82 | 24D066-M4120#A0066#B0005#A0066 | Plate | M4120_P0202 | SD_B0005_A0066_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
576 | 24D066-00-M4120_0.0 Sh.82 | 24D066-M4120#A0066#B0005#A0066 | Plate | M4120_P0203 | SD_B0005_A0066_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
577 | 24D066-00-M4120_0.0 Sh.82 | 24D066-M4120#A0066#B0005#A0066 | Plate | M4120_P0261 | SD_B0005_A0066_P0261 | PL15*250 | 1851 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
578 | 24D066-00-M4120_0.0 Sh.82 | 24D066-M4120#A0066#B0005#A0066 | Plate | M4120_P0265 | SD_B0005_A0066_P0265 | PL18 Dev. ~2053.9 | 6991 | A36 | 1 | 1 | 1 | 1614.4 | 1614.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 23.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 23.2; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
585 | 24D066-00-M4120_0.0 Sh.84 | 24D066-M4120#A0068#B0005#A0068 | [7 empty] | 1 |  |  | 1828.4 | AMC2 | [7 empty] | 0 | 0.8 |  |  |  |  | 27.1 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 27.1
586 | 24D066-00-M4120_0.0 Sh.84 | 24D066-M4120#A0068#B0005#A0068 | Plate | M4120_P0202 | SD_B0005_A0068_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
587 | 24D066-00-M4120_0.0 Sh.84 | 24D066-M4120#A0068#B0005#A0068 | Plate | M4120_P0203 | SD_B0005_A0068_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
588 | 24D066-00-M4120_0.0 Sh.84 | 24D066-M4120#A0068#B0005#A0068 | Plate | M4120_P0205 | SD_B0005_A0068_P0205 | PL10*43.8 | 6833 | A36 | 1 | 1 | 1 | 23.4 | 23.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
589 | 24D066-00-M4120_0.0 Sh.84 | 24D066-M4120#A0068#B0005#A0068 | Plate | M4120_P0262 | SD_B0005_A0068_P0262 | PL15*250 | 1851 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
590 | 24D066-00-M4120_0.0 Sh.84 | 24D066-M4120#A0068#B0005#A0068 | Plate | M4120_P0266 | SD_B0005_A0068_P0266 | PL18 Dev. ~2074.3 | 6834 | A36 | 1 | 1 | 1 | 1620.9 | 1620.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 23.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 23.3; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
597 | 24D066-00-M4120_0.0 Sh.86 | 24D066-M4120#A0070#B0005#A0070 | [7 empty] | 1 |  |  | 1660.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.7 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.7
598 | 24D066-00-M4120_0.0 Sh.86 | 24D066-M4120#A0070#B0005#A0070 | Plate | M4120_P0202 | SD_B0005_A0070_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
599 | 24D066-00-M4120_0.0 Sh.86 | 24D066-M4120#A0070#B0005#A0070 | Plate | M4120_P0203 | SD_B0005_A0070_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
600 | 24D066-00-M4120_0.0 Sh.86 | 24D066-M4120#A0070#B0005#A0070 | Plate | M4120_P0213 | SD_B0005_A0070_P0213 | PL10*48.4 | 6445 | A36 | 1 | 1 | 1 | 24.5 | 24.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
601 | 24D066-00-M4120_0.0 Sh.86 | 24D066-M4120#A0070#B0005#A0070 | Plate | M4120_P0263 | SD_B0005_A0070_P0263 | PL15*250 | 1848 | A36 | 1 | 1 | 1 | 54.3 | 54.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
602 | 24D066-00-M4120_0.0 Sh.86 | 24D066-M4120#A0070#B0005#A0070 | Plate | M4120_P0269 | SD_B0005_A0070_P0269 | PL18 Dev. ~2028.3 | 6673 | A36 | 1 | 1 | 1 | 1451.9 | 1451.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 20.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 20.8; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
609 | 24D066-00-M4120_0.0 Sh.88 | 24D066-M4120#A0072#B0005#A0072 | [7 empty] | 1 |  |  | 1636.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.3 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.3
610 | 24D066-00-M4120_0.0 Sh.88 | 24D066-M4120#A0072#B0005#A0072 | Plate | M4120_P0202 | SD_B0005_A0072_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
611 | 24D066-00-M4120_0.0 Sh.88 | 24D066-M4120#A0072#B0005#A0072 | Plate | M4120_P0203 | SD_B0005_A0072_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
612 | 24D066-00-M4120_0.0 Sh.88 | 24D066-M4120#A0072#B0005#A0072 | Plate | M4120_P0215 | SD_B0005_A0072_P0215 | PL10*49.7 | 6223 | A36 | 1 | 1 | 1 | 24.3 | 24.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.7; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
613 | 24D066-00-M4120_0.0 Sh.88 | 24D066-M4120#A0072#B0005#A0072 | Plate | M4120_P0263 | SD_B0005_A0072_P0263 | PL15*250 | 1848 | A36 | 1 | 1 | 1 | 54.3 | 54.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
614 | 24D066-00-M4120_0.0 Sh.88 | 24D066-M4120#A0072#B0005#A0072 | Plate | M4120_P0270 | SD_B0005_A0072_P0270 | PL18 Dev. ~2053.7 | 6375 | A36 | 1 | 1 | 1 | 1428 | 1428 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 20.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 20.5; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
621 | 24D066-00-M4120_0.0 Sh.90 | 24D066-M4120#A0074#B0005#A0074 | [7 empty] | 1 |  |  | 1634 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.3 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.3
622 | 24D066-00-M4120_0.0 Sh.90 | 24D066-M4120#A0074#B0005#A0074 | Plate | M4120_P0202 | SD_B0005_A0074_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
623 | 24D066-00-M4120_0.0 Sh.90 | 24D066-M4120#A0074#B0005#A0074 | Plate | M4120_P0203 | SD_B0005_A0074_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
624 | 24D066-00-M4120_0.0 Sh.90 | 24D066-M4120#A0074#B0005#A0074 | Plate | M4120_P0217 | SD_B0005_A0074_P0217 | PL10*50 | 6048 | A36 | 1 | 1 | 1 | 23.7 | 23.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
625 | 24D066-00-M4120_0.0 Sh.90 | 24D066-M4120#A0074#B0005#A0074 | Plate | M4120_P0263 | SD_B0005_A0074_P0263 | PL15*250 | 1847 | A36 | 1 | 1 | 1 | 54.3 | 54.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
626 | 24D066-00-M4120_0.0 Sh.90 | 24D066-M4120#A0074#B0005#A0074 | Plate | M4120_P0271 | SD_B0005_A0074_P0271 | PL18 Dev. ~2078.6 | 6038 | A36 | 1 | 1 | 1 | 1426.3 | 1426.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 20.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 20.5; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
633 | 24D066-00-M4120_0.0 Sh.92 | 24D066-M4120#A0076#B0005#A0076 | [7 empty] | 1 |  |  | 1634.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.3 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.3
634 | 24D066-00-M4120_0.0 Sh.92 | 24D066-M4120#A0076#B0005#A0076 | Plate | M4120_P0202 | SD_B0005_A0076_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
635 | 24D066-00-M4120_0.0 Sh.92 | 24D066-M4120#A0076#B0005#A0076 | Plate | M4120_P0203 | SD_B0005_A0076_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
636 | 24D066-00-M4120_0.0 Sh.92 | 24D066-M4120#A0076#B0005#A0076 | Plate | M4120_P0219 | SD_B0005_A0076_P0219 | PL10*49.9 | 5977 | A36 | 1 | 1 | 1 | 23.4 | 23.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
637 | 24D066-00-M4120_0.0 Sh.92 | 24D066-M4120#A0076#B0005#A0076 | Plate | M4120_P0263 | SD_B0005_A0076_P0263 | PL15*250 | 1848 | A36 | 1 | 1 | 1 | 54.3 | 54.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
638 | 24D066-00-M4120_0.0 Sh.92 | 24D066-M4120#A0076#B0005#A0076 | Plate | M4120_P0272 | SD_B0005_A0076_P0272 | PL18 Dev. ~2063.9 | 6180 | A36 | 1 | 1 | 1 | 1426.8 | 1426.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 20.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 20.5; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
645 | 24D066-00-M4120_0.0 Sh.94 | 24D066-M4120#A0078#B0005#A0078 | [7 empty] | 1 |  |  | 1700.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 25.2 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 25.2
646 | 24D066-00-M4120_0.0 Sh.94 | 24D066-M4120#A0078#B0005#A0078 | Plate | M4120_P0202 | SD_B0005_A0078_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
647 | 24D066-00-M4120_0.0 Sh.94 | 24D066-M4120#A0078#B0005#A0078 | Plate | M4120_P0203 | SD_B0005_A0078_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
648 | 24D066-00-M4120_0.0 Sh.94 | 24D066-M4120#A0078#B0005#A0078 | Plate | M4120_P0230 | SD_B0005_A0078_P0230 | PL10*48.8 | 6389 | A36 | 1 | 1 | 1 | 24.5 | 24.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.8; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
649 | 24D066-00-M4120_0.0 Sh.94 | 24D066-M4120#A0078#B0005#A0078 | Plate | M4120_P0264 | SD_B0005_A0078_P0264 | PL15*250 | 1849 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
650 | 24D066-00-M4120_0.0 Sh.94 | 24D066-M4120#A0078#B0005#A0078 | Plate | M4120_P0275 | SD_B0005_A0078_P0275 | PL18 Dev. ~1965.5 | 7009 | A36 | 1 | 1 | 1 | 1492.4 | 1492.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 21.4 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 21.4; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
657 | 24D066-00-M4120_0.0 Sh.96 | 24D066-M4120#A0080#B0005#A0080 | [7 empty] | 1 |  |  | 1769.6 | AMC2 | [7 empty] | 0 | 0.8 |  |  |  |  | 26.2 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 26.2
658 | 24D066-00-M4120_0.0 Sh.96 | 24D066-M4120#A0080#B0005#A0080 | Plate | M4120_P0202 | SD_B0005_A0080_P0202 | PL15*276 | 2153 | A36 | 1 | 1 | 1 | 70 | 70 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
659 | 24D066-00-M4120_0.0 Sh.96 | 24D066-M4120#A0080#B0005#A0080 | Plate | M4120_P0203 | SD_B0005_A0080_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
660 | 24D066-00-M4120_0.0 Sh.96 | 24D066-M4120#A0080#B0005#A0080 | Plate | M4120_P0260 | SD_B0005_A0080_P0260 | PL10*46.9 | 6605 | A36 | 1 | 1 | 1 | 24.3 | 24.3 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
661 | 24D066-00-M4120_0.0 Sh.96 | 24D066-M4120#A0080#B0005#A0080 | Plate | M4120_P0261 | SD_B0005_A0080_P0261 | PL15*250 | 1851 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
662 | 24D066-00-M4120_0.0 Sh.96 | 24D066-M4120#A0080#B0005#A0080 | Plate | M4120_P0276 | SD_B0005_A0080_P0276 | PL18 Dev. ~2006.7 | 7076 | A36 | 1 | 1 | 1 | 1561.3 | 1561.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 22.4 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 22.4; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
669 | 24D066-00-M4120_0.0 Sh.98 | 24D066-M4120#A0082#B0005#A0082 | [7 empty] | 1 |  |  | 1789.3 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 26.5 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 26.5
670 | 24D066-00-M4120_0.0 Sh.98 | 24D066-M4120#A0082#B0005#A0082 | Plate | M4120_P0203 | SD_B0005_A0082_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
671 | 24D066-00-M4120_0.0 Sh.98 | 24D066-M4120#A0082#B0005#A0082 | Plate | M4120_P0207 | SD_B0005_A0082_P0207 | PL10*44.5 | 6792 | A36 | 1 | 1 | 1 | 23.6 | 23.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
672 | 24D066-00-M4120_0.0 Sh.98 | 24D066-M4120#A0082#B0005#A0082 | Plate | M4120_P0208 | SD_B0005_A0082_P0208 | PL15*276 | 2297 | A36 | 1 | 1 | 1 | 74.6 | 74.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
673 | 24D066-00-M4120_0.0 Sh.98 | 24D066-M4120#A0082#B0005#A0082 | Plate | M4120_P0262 | SD_B0005_A0082_P0262 | PL15*250 | 1851 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
674 | 24D066-00-M4120_0.0 Sh.98 | 24D066-M4120#A0082#B0005#A0082 | Plate | M4120_P0267 | SD_B0005_A0082_P0267 | PL18 Dev. ~2060.4 | 6882 | A36 | 1 | 1 | 1 | 1577 | 1577 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 22.6 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 22.6; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
681 | 24D066-00-M4120_0.0 Sh.100 | 24D066-M4120#A0084#B0005#A0084 | [7 empty] | 1 |  |  | 1638.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.4 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.4
682 | 24D066-00-M4120_0.0 Sh.100 | 24D066-M4120#A0084#B0005#A0084 | Plate | M4120_P0203 | SD_B0005_A0084_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
683 | 24D066-00-M4120_0.0 Sh.100 | 24D066-M4120#A0084#B0005#A0084 | Plate | M4120_P0208 | SD_B0005_A0084_P0208 | PL15*276 | 2297 | A36 | 1 | 1 | 1 | 74.6 | 74.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
684 | 24D066-00-M4120_0.0 Sh.100 | 24D066-M4120#A0084#B0005#A0084 | Plate | M4120_P0221 | SD_B0005_A0084_P0221 | PL10*50 | 6021 | A36 | 1 | 1 | 1 | 23.6 | 23.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
685 | 24D066-00-M4120_0.0 Sh.100 | 24D066-M4120#A0084#B0005#A0084 | Plate | M4120_P0263 | SD_B0005_A0084_P0263 | PL15*250 | 1848 | A36 | 1 | 1 | 1 | 54.3 | 54.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
686 | 24D066-00-M4120_0.0 Sh.100 | 24D066-M4120#A0084#B0005#A0084 | Plate | M4120_P0273 | SD_B0005_A0084_P0273 | PL18 Dev. ~2011.7 | 6500 | A36 | 1 | 1 | 1 | 1426.3 | 1426.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 20.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 20.5; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
693 | 24D066-00-M4120_0.0 Sh.102 | 24D066-M4120#A0086#B0005#A0086 | [7 empty] | 1 |  |  | 1711.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 25.4 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 25.4
694 | 24D066-00-M4120_0.0 Sh.102 | 24D066-M4120#A0086#B0005#A0086 | Plate | M4120_P0203 | SD_B0005_A0086_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
695 | 24D066-00-M4120_0.0 Sh.102 | 24D066-M4120#A0086#B0005#A0086 | Plate | M4120_P0210 | SD_B0005_A0086_P0210 | PL10*46.4 | 6651 | A36 | 1 | 1 | 1 | 24.1 | 24.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
696 | 24D066-00-M4120_0.0 Sh.102 | 24D066-M4120#A0086#B0005#A0086 | Plate | M4120_P0211 | SD_B0005_A0086_P0211 | PL15*276 | 2009 | A36 | 1 | 1 | 1 | 65.3 | 65.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.2 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
697 | 24D066-00-M4120_0.0 Sh.102 | 24D066-M4120#A0086#B0005#A0086 | Plate | M4120_P0262 | SD_B0005_A0086_P0262 | PL15*250 | 1851 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
698 | 24D066-00-M4120_0.0 Sh.102 | 24D066-M4120#A0086#B0005#A0086 | Plate | M4120_P0268 | SD_B0005_A0086_P0268 | PL18 Dev. ~2033.9 | 6854 | A36 | 1 | 1 | 1 | 1508.3 | 1508.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 21.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 21.7; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
705 | 24D066-00-M4120_0.0 Sh.104 | 24D066-M4120#A0088#B0005#A0088 | [7 empty] | 1 |  |  | 1646.6 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.4 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.4
706 | 24D066-00-M4120_0.0 Sh.104 | 24D066-M4120#A0088#B0005#A0088 | Plate | M4120_P0203 | SD_B0005_A0088_P0203 | PL20*276 | 1377 | A36 | 1 | 1 | 1 | 59.6 | 59.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
707 | 24D066-00-M4120_0.0 Sh.104 | 24D066-M4120#A0088#B0005#A0088 | Plate | M4120_P0211 | SD_B0005_A0088_P0211 | PL15*276 | 2010 | A36 | 1 | 1 | 1 | 65.3 | 65.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.2 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.2 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
708 | 24D066-00-M4120_0.0 Sh.104 | 24D066-M4120#A0088#B0005#A0088 | Plate | M4120_P0227 | SD_B0005_A0088_P0227 | PL10*49.8 | 6173 | A36 | 1 | 1 | 1 | 24.1 | 24.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-5/14 DCC26-A320-0002-5/9 DCC26-A320-0002-5/7 DCC26-A320-0002-5/5 DCC26-A320-0002-5/3 DCC26-A320-0002-5/1 |  | A320-03-CP012 | 1 | 2026-06-28 |  |  |  | 0
709 | 24D066-00-M4120_0.0 Sh.104 | 24D066-M4120#A0088#B0005#A0088 | Plate | M4120_P0264 | SD_B0005_A0088_P0264 | PL15*250 | 1849 | A36 | 1 | 1 | 1 | 54.4 | 54.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 1 | 2026-06-28 |  |  |  | 0
710 | 24D066-00-M4120_0.0 Sh.104 | 24D066-M4120#A0088#B0005#A0088 | Plate | M4120_P0274 | SD_B0005_A0088_P0274 | PL18 Dev. ~1965.9 | 6802 | A36 | 1 | 1 | 1 | 1443.1 | 1443.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | 20.7 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 20.7; 32: ADDED, thêm nguyên công; 34: 0; 35: 1; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 1; 50: 0
903 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | [7 empty] | 1 |  |  | 1461.3 | AMC2 | [7 empty] | 0 | 0.033333 |  |  |  |  | 19 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 19
904 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0370 | SD_B0012_A0113_P0370 | PL30*1020 | 2150 | A36 | 1 | 1 | 1 | 516.5 | 516.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 4.6 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 4.6; 33: Added, thêm nguyên công; 34: 1; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
905 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0372 | SD_B0012_A0113_P0372 | PL20*400 | 400 | A36 | 2 | 1 | 2 | 25.1 | 50.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
906 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0374 | SD_B0012_A0113_P0374 | PL3*250 | 800 | AISI304 | 4 | 1 | 4 | 4.7 | 18.8 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | 1.6 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
907 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0378 | SD_B0012_A0113_P0378 | PL20*400 | 970 | A36 | 2 | 1 | 2 | 60.9 | 121.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 1.7 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.8; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
908 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0382 | SD_B0012_A0113_P0382 | PL20*265 | 400 | A36 | 4 | 1 | 4 | 16.6 | 66.4 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | 1 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.2; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
909 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0403 | SD_B0012_A0113_P0403 | PL20*400 | 753 | A36 | 2 | 1 | 2 | 46.8 | 93.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 1.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.6; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
910 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0404 | SD_B0012_A0113_P0404 | PL20*400 | 509 | A36 | 2 | 1 | 2 | 31.9 | 63.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
911 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0407 | SD_B0012_A0113_P0407 | PL20*265 | 506 | A36 | 2 | 1 | 2 | 21 | 42 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.6 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.3; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
912 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0408 | SD_B0012_A0113_P0408 | PL20*265 | 736 | A36 | 2 | 1 | 2 | 30.4 | 60.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
913 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0409 | SD_B0012_A0113_P0409 | PL20*265 | 512 | A36 | 2 | 1 | 2 | 21.2 | 42.4 | AMC2 | Plate | MCC |  |  | 1 | 1 | 0 | [6 empty] | 0.6 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.3; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
914 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0410 | SD_B0012_A0113_P0410 | PL20*265 | 766 | A36 | 2 | 1 | 2 | 31.6 | 63.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
915 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0411 | SD_B0012_A0113_P0411 | PL20*883.5 | 1068 | A36 | 2 | 1 | 2 | 80.8 | 161.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 2.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
916 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0508 | SD_B0012_A0113_P0508 | PL20*900.4 | 1055 | A36 | 2 | 1 | 2 | 79.9 | 159.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 2.2 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 1.1; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
917 | 24D066-00-M4120_0.0 Sh.123 | 24D066-M4120#A0113#B0012#A0113 | Plate | M4120_P0618 | SD_B0012_A0113_P0618 | PL5*50 | 100 | AISI304 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0; 34: 1; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
918 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | [7 empty] | 1 |  |  | 1951.5 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.5 | LOT 1 | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.5
919 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0372 | SD_B0014_A0115_P0372 | PL20*400 | 400 | A36 | 2 | 1 | 2 | 25.1 | 50.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
920 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0374 | SD_B0014_A0115_P0374 | PL3*250 | 800 | AISI304 | 4 | 1 | 4 | 4.7 | 18.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.6 | LOT 1 |  | AMC 2-S3 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | E275-01-CP131-1 A320-01-CP004-1 |  | A320-03-CP003 | 4 | 2026-06-23 |  |  |  | 0
921 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0378 | SD_B0014_A0115_P0378 | PL20*400 | 970 | A36 | 2 | 1 | 2 | 60.9 | 121.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
922 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0382 | SD_B0014_A0115_P0382 | PL20*265 | 400 | A36 | 4 | 1 | 4 | 16.6 | 66.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S3 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29 |  |  |  | 0
923 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0390 | SD_B0014_A0115_P0390 | PL30*1020 | 3080 | A36 | 1 | 1 | 1 | 739.8 | 739.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 6.5 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 6.5 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M304-04-CP009-1 M304-04-CP014-2 M305-01-CP032-3 DCC26-A320-0002-11 M304-04-CP014-1 M305-11-CP032-3 A320-01-CP013-1 M305-01-CP032-1 |  | A320-03-CP010 | 1 | 2026-06-23 |  |  |  | 0
924 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0393 | SD_B0014_A0115_P0393 | PL20*400 | 1119 | A36 | 2 | 1 | 2 | 70.3 | 140.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.9 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
925 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0394 | SD_B0014_A0115_P0394 | PL20*400 | 730 | A36 | 2 | 1 | 2 | 45.8 | 91.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
926 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0397 | SD_B0014_A0115_P0397 | PL20*265 | 730 | A36 | 4 | 1 | 4 | 30.4 | 121.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.7 | LOT 1 |  | AMC 2-S3 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29 |  |  |  | 0
927 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0398 | SD_B0014_A0115_P0398 | PL20*265 | 1119 | A36 | 2 | 1 | 2 | 46.6 | 93.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
928 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0399 | SD_B0014_A0115_P0399 | PL20*265 | 1119 | A36 | 2 | 1 | 2 | 45 | 90 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
929 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0555 | SD_B0014_A0115_P0555 | PL20*715.8 | 1241 | A36 | 4 | 1 | 4 | 104.3 | 417.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 5.6 | LOT 1 |  | AMC 2-S3 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29 |  |  |  | 0
930 | 24D066-00-M4120_0.0 Sh.124 | 24D066-M4120#A0115#B0014#A0115 | Plate | M4120_P0618 | SD_B0014_A0115_P0618 | PL5*50 | 100 | AISI304 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | E275-01-CP039-2 |  | A320-03-CP006 | 1 | 2026-06-23 |  |  |  | 0
931 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | [7 empty] | 1 |  |  | 1962.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 24.7 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 24.7
932 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0372 | SD_B0002_A0116_P0372 | PL20*400 | 400 | A36 | 2 | 1 | 2 | 25.1 | 50.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.7 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
933 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0374 | SD_B0002_A0116_P0374 | PL3*250 | 800 | AISI304 | 4 | 1 | 4 | 4.7 | 18.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1.6 | LOT 1 |  | AMC 2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | E275-01-CP131-1 A320-01-CP004-1 |  | A320-03-CP003 | 4 | 2026-06-23 |  |  |  | 0
934 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0378 | SD_B0002_A0116_P0378 | PL20*400 | 970 | A36 | 2 | 1 | 2 | 60.9 | 121.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
935 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0382 | SD_B0002_A0116_P0382 | PL20*265 | 400 | A36 | 4 | 1 | 4 | 16.6 | 66.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | 1 | LOT 1 |  | AMC 2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 4 | 2026-06-29 |  |  |  | 0
936 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0390 | SD_B0002_A0116_P0390 | PL30*1020 | 3080 | A36 | 1 | 1 | 1 | 739.8 | 739.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 6.5 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 6.5 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M304-04-CP009-1 M304-04-CP014-2 M305-01-CP032-3 DCC26-A320-0002-11 M304-04-CP014-1 M305-11-CP032-3 A320-01-CP013-1 M305-01-CP032-1 |  | A320-03-CP010 | 1 | 2026-06-23 |  |  |  | 0
937 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0414 | SD_B0002_A0116_P0414 | PL20*965.9 | 1505 | A36 | 2 | 1 | 2 | 116.6 | 233.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 3.1 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.6 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
938 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0415 | SD_B0002_A0116_P0415 | PL20*400 | 1028 | A36 | 2 | 1 | 2 | 63.9 | 127.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.7 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
939 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0416 | SD_B0002_A0116_P0416 | PL20*400 | 699 | A36 | 2 | 1 | 2 | 43.7 | 87.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.2 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
940 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0419 | SD_B0002_A0116_P0419 | PL20*265 | 690 | A36 | 2 | 1 | 2 | 28.6 | 57.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
941 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0420 | SD_B0002_A0116_P0420 | PL20*265 | 1004 | A36 | 2 | 1 | 2 | 41.5 | 83 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.2 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
942 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0421 | SD_B0002_A0116_P0421 | PL20*265 | 706 | A36 | 2 | 1 | 2 | 29.2 | 58.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
943 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0422 | SD_B0002_A0116_P0422 | PL20*265 | 1046 | A36 | 2 | 1 | 2 | 43.2 | 86.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 1.2 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
944 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0423 | SD_B0002_A0116_P0423 | PL20*926.5 | 1477 | A36 | 2 | 1 | 2 | 116 | 232 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 3.1 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.6 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
945 | 24D066-00-M4120_0.0 Sh.125 | 24D066-M4120#A0116#B0002#A0116 | Plate | M4120_P0618 | SD_B0002_A0116_P0618 | PL5*50 | 100 | AISI304 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | E275-01-CP039-2 |  | A320-03-CP006 | 1 | 2026-06-23 |  |  |  | 0
972 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0127#B0014#A0127 | [7 empty] | 1 |  |  | 204.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 2.8 | LOT 1 | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 2.8
973 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0127#B0014#A0127 | Plate | M4120_P0391 | SD_B0014_A0127_P0391 | PL20*410 | 420 | A36 | 1 | 1 | 1 | 27 | 27 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
974 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0127#B0014#A0127 | Plate | M4120_P0396 | SD_B0014_A0127_P0396 | PL20*624.2 | 1550 | A36 | 1 | 1 | 1 | 117.1 | 117.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.6 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
975 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0127#B0014#A0127 | Plate | M4120_P0400 | SD_B0014_A0127_P0400 | PL20*420 | 461 | A36 | 2 | 1 | 2 | 30.4 | 60.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
976 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0128#B0014#A0128 | [7 empty] | 2 |  |  | 51.1 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.7 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.4
977 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0128#B0014#A0128 | Plate | M4120_P0392 | SD_B0014_A0128_P0392 | PL20*380 | 461 | A36 | 1 | 2 | 2 | 25.5 | 51 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.4 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
978 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0129#B0014#A0129 | [7 empty] | 2 |  |  | 190.1 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 2.5 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 1.3
979 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0129#B0014#A0129 | Plate | M4120_P0395 | SD_B0014_A0129_P0395 | PL20*624 | 970 | A36 | 1 | 2 | 2 | 95 | 190 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 1.3 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
980 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0130#B0014#A0130 | [7 empty] | 2 |  |  | 61.5 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.9 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.4
981 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0130#B0014#A0130 | Plate | M4120_P0401 | SD_B0014_A0130_P0401 | PL20*365 | 624 | A36 | 1 | 2 | 2 | 30.7 | 61.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.4 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
982 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0131#B0012#A0131 | [7 empty] | 1 |  |  | 68.3 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 0.9 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.9
983 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0131#B0012#A0131 | Plate | M4120_P0402 | SD_B0012_A0131_P0402 | PL20*407.2 | 420 | A36 | 1 | 1 | 1 | 26.8 | 26.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.4 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.4; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
984 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0131#B0012#A0131 | Plate | M4120_P0406 | SD_B0012_A0131_P0406 | PL20*453.2 | 620 | A36 | 1 | 1 | 1 | 41.5 | 41.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 0.6 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.6; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 1
985 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0132#B0012#A0132 | [7 empty] | 2 |  |  | 137.8 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 1.9 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.9
986 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0132#B0012#A0132 | Plate | M4120_P0405 | SD_B0012_A0132_P0405 | PL20*453.9 | 970 | A36 | 1 | 2 | 2 | 68.9 | 137.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.9 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.9; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
987 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0133#B0002#A0133 | [7 empty] | 1 |  |  | 202.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 2.8 | LOT 1 | x | AMC 2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 2.8
988 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0133#B0002#A0133 | Plate | M4120_P0412 | SD_B0002_A0133_P0412 | PL20*408.8 | 420 | A36 | 1 | 1 | 1 | 27 | 27 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 0.4 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
989 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0133#B0002#A0133 | Plate | M4120_P0418 | SD_B0002_A0133_P0418 | PL20*603.9 | 1550 | A36 | 1 | 1 | 1 | 115.2 | 115.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 1.6 | LOT 1 |  | AMC 2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
990 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0133#B0002#A0133 | Plate | M4120_P0424 | SD_B0002_A0133_P0424 | PL20*420 | 455 | A36 | 2 | 1 | 2 | 30 | 60 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
991 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0134#B0002#A0134 | [7 empty] | 2 |  |  | 50.6 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.7 | LOT 1 | x | AMC 2-S1 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.4
992 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0134#B0002#A0134 | Plate | M4120_P0413 | SD_B0002_A0134_P0413 | PL20*380 | 454 | A36 | 1 | 2 | 2 | 25.3 | 50.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.4 | LOT 1 |  | AMC 2-S1 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
993 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0135#B0002#A0135 | [7 empty] | 2 |  |  | 183.3 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 2.5 | LOT 1 | x | AMC 2-S1 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 1.2
994 | 24D066-00-M4120_0.0 Sh.128 | 24D066-M4120#A0135#B0002#A0135 | Plate | M4120_P0417 | SD_B0002_A0135_P0417 | PL20*608.6 | 970 | A36 | 1 | 2 | 2 | 91.7 | 183.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 1.2 | LOT 1 |  | AMC 2-S1 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 1.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1006 | 24D066-00-M4120_0.0 Sh.131 | 24D066-M4120#A0136#B0002#A0136 | [7 empty] | 2 |  |  | 59.7 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.8 | LOT 1 | x | AMC 2-S1 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.4
1007 | 24D066-00-M4120_0.0 Sh.131 | 24D066-M4120#A0136#B0002#A0136 | Plate | M4120_P0425 | SD_B0002_A0136_P0425 | PL20*365 | 598 | A36 | 1 | 2 | 2 | 29.8 | 59.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.4 | LOT 1 |  | AMC 2-S1 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1100 | 24D066-00-M4120_0.0 Sh.136 | 24D066-M4120#A0161#B0012#A0161 | [7 empty] | 2 |  |  | 40 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 0.6 | LOT 3 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.3
1101 | 24D066-00-M4120_0.0 Sh.136 | 24D066-M4120#A0161#B0012#A0161 | Plate | M4120_P0507 | SD_B0012_A0161_P0507 | PL20*300 | 451 | A36 | 1 | 2 | 2 | 20 | 40 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 0.3 | LOT 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: -; 15: AMC 2; 15: -; 16: 0.3; 33: Added, thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 2
1102 | 24D066-00-M4120_0.0 Sh.136 | 24D066-M4120#A0162#A0162 | [7 empty] | 1 |  |  | 215.7 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 2.9 | LOT 1 | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 2.9
1103 | 24D066-00-M4120_0.0 Sh.136 | 24D066-M4120#A0162#A0162 | Plate | M4120_P0522 | SD_A0162_P0522 | PL20*1299.6 | 1983 | A36 | 1 | 1 | 1 | 215.7 | 215.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.9 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
1118 | 24D066-00-M4120_0.0 Sh.139 | 24D066-M4120#A0159#A0159 | [7 empty] | 1 |  |  | 451.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | 6.2 | LOT 1 ? | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 6.2
1119 | 24D066-00-M4120_0.0 Sh.139 | 24D066-M4120#A0159#A0159 | Plate | M4120_P0491 | SD_A0159_P0491 | PL20*505 | 3981 | A36 | 1 | 1 | 1 | 205.8 | 205.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 2.8 | LOT 1 ? |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 2.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
1120 | 24D066-00-M4120_0.0 Sh.139 | 24D066-M4120#A0159#A0159 | Plate | M4120_P0492 | SD_A0159_P0492 | PL20*118.1 | 450 | A36 | 2 | 1 | 2 | 8.3 | 16.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | 0.3 | LOT 1 ? |  | AMC 2-S3 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1121 | 24D066-00-M4120_0.0 Sh.139 | 24D066-M4120#A0159#A0159 | Plate | M4120_P0493 | SD_A0159_P0493 | PL20*569.5 | 3981 | A36 | 1 | 1 | 1 | 229.3 | 229.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | 3.1 | LOT 1 ? |  | AMC 2-S3 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 3.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
1122 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0163#A0163 | [7 empty] | 2 |  |  | 459 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 6.1 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 3
1123 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0163#A0163 | Plate | M4120_P0523 | SD_A0163_P0523 | PL20*1348.8 | 2024 | A36 | 1 | 2 | 2 | 229.5 | 459 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 3 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1124 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0164#A0164 | [7 empty] | 4 |  |  | 1546.4 | AMC2 | [7 empty] | 2 | 0.5 |  |  |  |  | 16.5 | LOT 1(Qty:2), LOT 3(Qty:2) | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: AMC 2; 15: -; 16: 4.1
1125 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0164#A0164 | Plate | M4120_P0527 | SD_A0164_P0527 | PL25*1525.1 | 2567 | A36 | 1 | 4 | 4 | 386.6 | 1546.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 2 | [6 empty] | 4.1 | LOT 1, 3 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | AMC 2 | - | 4.1 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-10 |  | A320-03-CP009 | 2 | 2026-06-23 |  |  |  | 2
1126 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0165#A0165 | [7 empty] | 24 |  |  | 1381.7 | AMC2 | [7 empty] | 16 | 0.66667 |  |  |  |  | 26.4 | LOT 1(Qty:8), LOT 2(Qty:8), LOT 3(Qty:8) | x | AMC 2-S2 | 8 |  |  |  | AMC 2-S2 | 8 |  |  |  | AMC 2-S2 | 8 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: AMC 2; 15: AMC 2; 15: -; 16: 1.1
1127 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0165#A0165 | Plate | M4120_P0528 | SD_A0165_P0528 | PL15*200 | 722 | A36 | 2 | 24 | 48 | 17 | 816 | AMC2 | Plate | MCC |  |  | 32 | 16 | 16 | [6 empty] | 0.6 | LOT 1, 2, 3 |  | AMC 2-S2 | 8 | 16 | 16 | 0 | AMC 2-S2 | 8 | 16 | 8 | 8 | AMC 2-S2 | 8 | 16 | 8 | 8 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | AMC 2 | AMC 2 | - | 0.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28 |  |  |  | 32
1128 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0165#A0165 | Plate | M4120_P0529 | SD_A0165_P0529 | PL15*170 | 722 | A36 | 2 | 24 | 48 | 13.1 | 628.8 | AMC2 | Plate | MCC |  |  | 32 | 16 | 16 | [6 empty] | 0.5 | LOT 1, 2, 3 |  | AMC 2-S2 | 8 | 16 | 16 | 0 | AMC 2-S2 | 8 | 16 | 8 | 8 | AMC 2-S2 | 8 | 16 | 8 | 8 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | AMC 2 | AMC 2 | - | 0.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28 |  |  |  | 32
1139 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0171#A0171 | [7 empty] | 8 |  |  | 581.3 | AMC2 | [7 empty] | 7 | 0.96875 |  |  |  |  | 11.1 | LOT 1 | x | AMC 2-S3 | 8 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 1.4
1140 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0171#A0171 | Plate | M4120_P0535 | SD_A0171_P0535 | PL15*200 | 873 | A36 | 2 | 8 | 16 | 20.5 | 328 | AMC2 | Plate | MCC |  |  | 16 | 0 | 8 | [6 empty] | 0.8 | LOT 1 |  | AMC 2-S3 | 8 | 16 | 16 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28 |  |  |  | 0
1141 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0171#A0171 | Plate | M4120_P0536 | SD_A0171_P0536 | PL15*170 | 873 | A36 | 2 | 8 | 16 | 15.8 | 252.8 | AMC2 | Plate | MCC |  |  | 15 | 1 | 7 | [6 empty] | 0.6 | LOT 1 |  | AMC 2-S3 | 8 | 16 | 15 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.3 | [6 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 16 | 2026-06-28 |  |  |  | 0
1147 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0174#A0174 | [7 empty] | 2 |  |  | 301.6 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 5.9 | LOT 2(Qty:2), LOT 3(Qty:2) | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | 15A: -; 15: FAC 2; 15: AMC 2; 15: -; 16: 1.5
1148 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0174#A0174 | Plate | M4120_P0540 | SD_A0174_P0540 | PL15*300 | 578 | A36 | 2 | 2 | 4 | 20.4 | 81.6 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | 0.7 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 2 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: FAC 2; 15: AMC 2; 15: -; 16: 0.4; 31: Added: thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
1149 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0174#A0174 | Plate | M4120_P0541 | SD_A0174_P0541 | PL15*270 | 578 | A36 | 2 | 2 | 4 | 17.3 | 69.2 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | 0.6 | LOT 2, 3 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 2 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | 15A: -; 15: FAC 2; 15: AMC 2; 15: -; 16: 0.3; 31: Added: thêm nguyên công; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 50: 4
1154 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0176#A0176 | [7 empty] | 2 |  |  | 562.6 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 6 | LOT 1(Qty:1), LOT 3(Qty:1) | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: AMC 2; 15: -; 16: 3
1155 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0176#A0176 | Plate | M4120_P0552 | SD_A0176_P0552 | PL25*1341.6 | 2041 | A36 | 1 | 2 | 2 | 281.3 | 562.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 3 | LOT 1, 3 |  | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | AMC 2 | - | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-10 |  | A320-03-CP009 | 1 | 2026-06-23 |  |  |  | 1
1156 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0177#A0177 | [7 empty] | 4 |  |  | 997.1 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 10.7 | LOT 1(Qty:2), LOT 3(Qty:2) | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: AMC 2; 15: -; 16: 2.7
1157 | 24D066-00-M4120_0.0 Sh.140 | 24D066-M4120#A0177#A0177 | Plate | M4120_P0554 | SD_A0177_P0554 | PL25*1206.2 | 1984 | A36 | 1 | 4 | 4 | 249.3 | 997.2 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | 2.7 | LOT 1, 3 |  | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | AMC 2 | - | 2.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-10 |  | A320-03-CP009 | 2 | 2026-06-23 |  |  |  | 2
1158 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0178#A0178 | [7 empty] | 1 |  |  | 263.2 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 3.5 | LOT 1 | x | AMC 2-S3 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 3.5
1159 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0178#A0178 | Plate | M4120_P0563 | SD_A0178_P0563 | PL20*1385.5 | 2311 | A36 | 1 | 1 | 1 | 263.2 | 263.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | 3.5 | LOT 1 |  | AMC 2-S3 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 3.5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 1 | 2026-06-29 |  |  |  | 0
1160 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0179#A0179 | [7 empty] | 2 |  |  | 558.6 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 7.4 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 3.7
1161 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0179#A0179 | Plate | M4120_P0564 | SD_A0179_P0564 | PL20*1433.2 | 2354 | A36 | 1 | 2 | 2 | 279.3 | 558.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 3.7 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 3.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1173 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0187#A0187 | [7 empty] | 2 |  |  | 1215.9 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 16 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 8
1174 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0187#A0187 | Plate | M4120_P0585 | SD_A0187_P0585 | PL20*2374.4 | 4923 | A36 | 1 | 2 | 2 | 607.9 | 1215.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 8 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 8; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 2; 50: 0
1175 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0188#A0188 | [7 empty] | 2 |  |  | 77.4 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 1.1 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.6
1176 | 24D066-00-M4120_0.0 Sh.141 | 24D066-M4120#A0188#A0188 | Plate | M4120_P0586 | SD_A0188_P0586 | PL20*206.2 | 1250 | A36 | 1 | 2 | 2 | 38.7 | 77.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.6 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1216 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0189#A0189 | [7 empty] | 2 |  |  | 889.5 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 11.7 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 5.9
1217 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0189#A0189 | Plate | M4120_P0587 | SD_A0189_P0587 | PL20*2517.7 | 3413 | A36 | 1 | 2 | 2 | 444.8 | 889.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 5.9 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 5.9; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 2; 50: 0
1218 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0190#A0190 | [7 empty] | 2 |  |  | 1366.7 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 17.8 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 8.9
1219 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0190#A0190 | Plate | M4120_P0588 | SD_A0190_P0588 | PL20*1095 | 3975 | A36 | 1 | 2 | 2 | 683.4 | 1366.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 8.9 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 8.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1220 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0191#A0191 | [7 empty] | 2 |  |  | 1485.5 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 19.3 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 9.7
1221 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0191#A0191 | Plate | M4120_P0589 | SD_A0191_P0589 | PL20*1994.1 | 4132 | A36 | 1 | 2 | 2 | 742.7 | 1485.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 9.7 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 15A: AMC 2; 15: -; 15: -; 15: -; 16: 9.7; 34: 0; 35: 0; 36: 0; 37: 1; 38: 0; 39: 0; 40: 0; 41: Fabrication; 44: chi tiết chia nối; 45: 2; 50: 0
1222 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0192#A0192 | [7 empty] | 2 |  |  | 77.4 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | 1.1 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 0.6
1223 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0192#A0192 | Plate | M4120_P0590 | SD_A0192_P0590 | PL20*206.2 | 1250 | A36 | 1 | 2 | 2 | 38.7 | 77.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | 0.6 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 0.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | M291-724-CP007-1 M291-02-CP010-1 DCC26-A320-0002-9 M306-04-CP010-1 M291-03-CP033-1 |  | A320-03-CP008 | 2 | 2026-06-29 |  |  |  | 0
1224 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0193#A0193 | [7 empty] | 2 |  |  | 505.7 | AMC2 | [7 empty] | 2 | 1 |  |  |  |  | 8.8 | LOT 1 | x | AMC 2-S3 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | 14: o; 15A: AMC 2; 15: -; 15: -; 15: -; 16: 4.4
1225 | 24D066-00-M4120_0.0 Sh.144 | 24D066-M4120#A0193#A0193 | Plate | M4120_P0591 | SD_A0193_P0591 | PL15*1694.2 | 2687 | A36 | 1 | 2 | 2 | 252.8 | 505.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | 4.4 | LOT 1 |  | AMC 2-S3 | 2 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | 4.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | DCC26-A320-0002-7/1 DCC26-A320-0002-7/2 |  | A320-03-CP013 | 2 | 2026-06-28 |  |  |  | 0

## BTP-A320M4130
A320M4130
| Chủng loại | Thiết kế |  | Đã nhận |  | Còn thiếu |  |  |  | Đã nhận |  | Đồng bộ |  | Đã triển khai
|  | T.Q'ty | T.Weight | T.Q'ty | T.Weight | T.Q'ty | T.Weight |  |  | Số chi tiết | Khối lượng | Số chi tiết lớn | Khối lượng | Số chi tiết lớn | Khối lượng
| Shape | 242 | 2640.5951 | 105 | 1323.6206 | 137 | 1316.9745 |  | Total | 1058 | 128775.8906 |  | 15641.5 |  | 0
| Plate | 1742 | 189061.1587 | 949 | 127451.87 | 793 | 61609.2887
| Purchasing | 109 | 2247.9096 | 4 | 0.4 | 105 | 2247.5096
| Total | 2093 | 193949.6634 | 1058 | 128775.8906 | 1035 | 65173.7728
Chủng loại thép hình
| Shape | 1/2" SCH.STD (OD21.3x2.77t) | 28" SCH.STD (Ø711x9.53t) | 4" SCH.STD (OD114.3x6.02t) | L80x80x10 | M24x95L (Pitch 3mm; 6G) | RB15 | RB20 | RB50 | RB60
| Chiều dài theo thiết kế (mm) | 19899 | 5460 | 96628 | 320 | 6080 | 752 | 2608 | 192 | 4384 | 0 | 0 | 0 | 0 | 0
| SL TK | 27 | 8 | 119 | 4 | 64 | 4 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0
| Đã nhận (mm) | 10318 | 2730 | 50344 | 80 | 1520 | 376 | 1304 | 48 | 1096 | 0 | 0 | 0 | 0 | 0
| SL Nhận | 14 | 4 | 62 | 1 | 16 | 2 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Còn thiếu (mm) | 9581 | 2730 | 46284 | 240 | 4560 | 376 | 1304 | 144 | 3288 | 0 | 0 | 0 | 0 | 0
| SL thiếu | 13 | 4 | 57 | 3 | 48 | 2 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| KL còn thiếu (kg) | 27.3 | 450.0678 | 744.2467 | 3.3 | 14.4 | 0.6 | 3.2 | 0.96 | 72.9 | 0 | 0 | 0 | 0 | 0
Chiều dày tôn
| Plate | 3 | 2 | 1 | 16 | 40 | 8 | 12 | 30 | 10 | 15 | 20 | 5
| Diện tích m2 theo thiết kế | 0.81189 | 2.6752 | 3.8471 | 8.492 | 0.89172 | 235.8169 | 811.5403
| SL TK | 35 | 111 | 214 | 296 | 32 | 52 | 332
| Diện tích còn thiếu( m2) | 0.58599 | 1.8822 | 2.5987 | 2.6123 | 0.61306 | 92.9634 | 251.4682
| Sl còn thiếu | 26 | 80 | 156 | 87 | 22 | 35 | 142
| KL còn thiếu(kg) | 13.8 | 29.55 | 20.4 | 328.1 | 192.5 | 5838.1 | 23688.3
[11 empty] | 15.6 | 1485.3 | 100180.3 | 2254.2 | 5661.14 | 1253.767 | 928 | 7067.9 | 0.32 | 17324 | 597.6 | 27182.8 | 3132 | 225.0339 | 6.4 | 1630.2 | 10660.6 | 3801.5 | 1241.1 | 0 | 5 | 3775.6 | 314.3 | 14473.5 | 18020.3 | 14.7 | 28398.2 | 59.4 | 48738.2 | 1.9 | 3655.9 | 1158.6 | 1296.1 | 404.7658 | 31.2 | 1928.5 | 134.2 | 21.7 | 316.8 | 1209.4 | 334.3 | 6.85 | 293.7339 | 2237.4 | 0.4 | 7879.5 | 316.88 | #VALUE!
[11 empty] | 2 | 91 | 57 | 55 | 54 | 59 | 8 | 9 | 1 | 8 | 59 | 22 | 34 | 2 | 4 | 26 | 32 | 8 | 3 | 0 | 1 | 10 | 8 | 9 | 11 | 7 | 20 | 2 | 27 | 3 | 27 | 13 | 80 | 31 | 110 | 103 | 12 | 4 | 10 | 26 | 64 | 25 | 13 | 49 | 4 | 33 | 7 | #VALUE!
Chủng loại | Part No.1 | Size | Description | Length | Material | T.Q'ty | U.Weight | T.Weight | Đã nhận | Còn thiếu | 2026-07-20 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-29 | 2026-07-30 | 2026-08-03 | 2026-08-05 | 2026-08-06 | 2026-08-08 | 2026-08-10 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-16 | 2026-08-23 | 2026-08-24 | 2026-08-26 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-21 | 2026-09-22 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-29 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-06 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-11-13 | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-10-24 | KO BB | Lấy data | Ktra nối | Tôn | Cảnh báo thừa | DVG | MPR No | Qty MPR | Cutting No. | Qty Cutting | Date Issue
Plate | SDM_A10_P1 | PL5x93 | Shim Plate | 200 | A36 | 32 | 0.6 | 19.2 | 32 | 0 | [34 empty] | 8 | [10 empty] | 30 |  | #VALUE! |  | PL5 | Thừa 6 | MCC | A320-SDM-PC-007 | PL5 | A320-01-CP005 | 8 | 13/06/2026
Plate | SDM_A10_P2 | PL3x93 | Shim Plate | 200 | A36 | 32 | 0.4 | 12.8 | 8 | 24 | [34 empty] | 8 | [12 empty] | #VALUE! |  | PL3 |  | MCC | A320-SDM-PC-003 | PL3 | A320-01-CP003 | 8 | 13/06/2026
Plate | SDM_A10_P3 | PL2x93 | Shim Plate | 200 | A36 | 96 | 0.2 | 19.2 | 24 | 72 | [34 empty] | 24 | [12 empty] | #VALUE! |  | PL2 |  | MCC | A320-SDM-PC-002 | PL2 | A320-01-CP002 | 24 | 13/06/2026
Plate | SDM_A10_P4 | PL1x93 | Shim Plate | 200 | A36 | 192 | 0.1 | 19.2 | 48 | 144 | [34 empty] | 48 | [12 empty] | #VALUE! |  | PL1 |  | MCC | A320-SDM-PC-001 | PL1 | A320-01-CP001 | 48 | 13/06/2026
Purchasing | SDM_A11_B0616 | M6x16L (Pitch 1mm; 6H) | Countersunk Bolt |  |  | 64 | 0.036 | 2.304 | 0 | 64 | [47 empty] | #VALUE! |  |  |  | KHO
Shape | SDM_A11_B2495 | M24x95L (Pitch 3mm; 6G) | Threaded Bar | 95 |  | 64 | 0.3 | 19.2 | 16 | 48 | [41 empty] | 16 | [5 empty] | #VALUE! |  |  |  | PMC |  | RB25
Purchasing | SDM_A11_M1 | PL5x160x160 | Teflon PAD |  | Teflon | 16 | 0.2816 | 4.5056 | 0 | 16 | [47 empty] | #VALUE! |  |  |  | KHO
Plate | SDM_A11_P1 | PL16x200 | Plate | 200 | A36 | 16 | 5 | 80 | 4 | 12 | [20 empty] | 1 | [16 empty] | 3 | [9 empty] | #VALUE! |  | PL16 |  | PMC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 4 | 13/06/2026
Plate | SDM_A12_P1 | PL40x170 | Plate | 200 | A36 | 16 | 9.5 | 152 | 5 | 11 | [36 empty] | 5 | [10 empty] | #VALUE! |  | PL40 |  | MCC | A320-SDM-PC-015 | PL40 | A320-01-CP014 | 4 | 13/06/2026
Plate | SDM_A12_P2 | PL40x150 | Plate | 170 | A36 | 16 | 8 | 128 | 5 | 11 | [36 empty] | 5 | [10 empty] | #VALUE! |  | PL40 |  | MCC | A320-SDM-PC-015 | PL40 | A320-01-CP014 | 4 | 13/06/2026
Plate | SDM_A15_P1 | PL1x115 | Shim Plate | 640 | A36 | 22 | 0.5 | 11 | 10 | 12 | [34 empty] | 10 | [12 empty] | #VALUE! |  | PL1 |  | MCC | A320-SDM-PC-001 | PL1 | A320-01-CP001 A320-01-CP019 | 10 | 30/06/2026
Purchasing | SDM_A17_M1 | PL5x220x380 | Teflon PAD |  | Teflon | 3 | 0.1 | 0.3 | 0 | 3 | [47 empty] | #VALUE! |  |  |  | KHO
Plate | SDM_A17_P1 | PL2x88 | Plate | 400 | A36 | 3 | 7.5 | 22.5 | 1 | 2 | [42 empty] | 1 |  |  |  |  | #VALUE! |  | PL2 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A18_R1 | PL2x88 | Round Bar | 25 | A36 | 12 | 0.025 | 0.3 | 6 | 6 | [41 empty] | 6 | [5 empty] | #VALUE! |  | PL2 |  | PMC | A320-SDM-PC-002 | PL2 | A320-01-CP002 | 4 | 13/06/2026
Plate | SDM_A19_D1 | PL8x250 | Pipe | 1891 | A36 | 4 | 29.7 | 118.8 | 2 | 2 | [27 empty] | 2 | [19 empty] | #VALUE! |  | PL8 |  | PMC | A320-SDM-PC-008 | PL8 | A320-01-CP007 | 1 | 2026-03-07
Purchasing | SDM_A19_M1 | 24" 150# SO R.F (ASME B16.5) | Flange |  | A105 | 4 | 100 | 400 | 0 | 4 | [47 empty] | #VALUE! |  |  |  | KHO
Plate | SDM_A19_P1 | PL12x100 | Plate | 716 | A36 | 4 | 6.7 | 26.8 | 1 | 3 | [37 empty] | 1 | [9 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Shape | SDM_A20_A1 | L80x80x10 | Angle | 80 | A36 | 4 | 1.1 | 4.4 | 1 | 3 | [11 empty] | 1 | [35 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-504 | L90x90x10 | A320-01-CP504 | 1 | 2026-12-06
Plate | SDM_A20_P1 | PL12x80 | Plate | 80 | A36 | 4 | 0.2 | 0.8 | 1 | 3 | [32 empty] | 1 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Shape | SDM_A20_R1 | RB60 | Round Bar | 1096 | A36 | 4 | 24.3 | 97.2 | 1 | 3 | [17 empty] | 1 | [29 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-509 | RB60 | A320-01-CP507 | 1 | 2026-12-06
Purchasing | SDM_A21_M1 | 24" 150# R.F (ASME B16.5) | Blind Flange |  | A105 | 6 | 100 | 600 | 0 | 6 | [47 empty] | #VALUE! |  |  |  | KHO
Shape | SDM_A21_R1 | RB20 | Round Bar | 326 | A36 | 8 | 0.8 | 6.4 | 4 | 4 | [29 empty] | 2 | [11 empty] | 2 | [5 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-507 | RB20 | A320-01-CP506 | 2 | 2026-12-06
Shape | SDM_A21_R2 | RB15 | Round Bar | 188 | A36 | 4 | 0.3 | 1.2 | 2 | 2 | [29 empty] | 1 | [11 empty] | 1 | [5 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-505 | RB15 | A320-01-CP505 | 1 | 2026-12-06
Shape | SDM_A22_D1 | 28" SCH.STD (Ø711x9.53t) | Pipe | 761 | A106 Gr.B | 4 | 125.4585 | 501.8338 | 2 | 2 | [13 empty] | 1 | [28 empty] | 1 |  |  |  |  | #VALUE! |  |  |  | MCC | A320-SDM-PC-503 | 28" SCH.STD (Ø711x9.53t) | A320-01-CP502 | 1 | 2026-12-06
Purchasing | SDM_A22_M1 | 28" 150# WN R.F (ASME B16.47 Type A) | Flange |  | A105 | 4 | 155 | 620 | 0 | 4 | [47 empty] | #VALUE! |  |  |  | KHO
Purchasing | SDM_A22_M2 | - | Mesh |  |  | 4 | 0.1 | 0.4 | 2 | 2 | [44 empty] | 2 |  |  | #VALUE! |  |  |  | KHO
Plate | SDM_A22_P1 | PL30x225 | Plate | 250 | A36 | 4 | 10.5 | 42 | 1 | 3 | [36 empty] | 1 | [10 empty] | #VALUE! |  | PL30 |  | MCC | A320-SDM-PC-014 | PL30 | A320-01-CP013 | 1 | 13/06/2026
Plate | SDM_A22_P2 | PL10x60 | Plate | 620 | A36 | 8 | 2.9 | 23.2 | 4 | 4 | [32 empty] | 2 |  |  | 2 | [11 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 2 | 2026-03-07
Plate | SDM_A22_P3 | PL10x70 | Plate | 80 | A36 | 4 | 0.4 | 1.6 | 2 | 2 | [32 empty] | 1 |  |  | 1 | [11 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Shape | SDM_A23_D1 | 28" SCH.STD (Ø711x9.53t) | Pipe | 604 | A106 Gr.B | 4 | 99.5754 | 398.3018 | 2 | 2 | [13 empty] | 1 | [28 empty] | 1 |  |  |  |  | #VALUE! |  |  |  | MCC | A320-SDM-PC-503 | 28" SCH.STD (Ø711x9.53t) | A320-01-CP502 | 1 | 2026-12-06
Purchasing | SDM_A23_M1 | 28" 150# WN R.F (ASME B16.47 Type A) | Flange |  | A105 | 4 | 155 | 620 | 0 | 4 | [47 empty] | #VALUE! |  |  |  | KHO
Purchasing | SDM_A23_M2 | - | Mesh |  |  | 4 | 0.1 | 0.4 | 2 | 2 | [44 empty] | 2 |  |  | #VALUE! |  |  |  | KHO
Plate | SDM_A23_P1 | PL8x100 | Plate | 376 | A36 | 4 | 2.4 | 9.6 | 1 | 3 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL8 |  | PMC | A320-SDM-PC-008 | PL8 | A320-01-CP007 | 1 | 2026-03-07
Plate | SDM_A24_WS1 | PL5x80 | Washer | 80 | A36 | 4 | 0.2 | 0.8 | 4 | 0 | [34 empty] | 10 | [12 empty] | #VALUE! |  | PL5 | Thừa 6 | MCC | A320-SDM-PC-007 | PL5 | A320-01-CP005 | 1 | 13/06/2026
Shape | SDM_A4C_1-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 5 | 13.057 | 65.2848 | 0 | 5 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-31-CP503 | 5 | 2026-04-08
Shape | SDM_A4C_1-0A_D2 | 1/2" SCH.STD (OD21.3x2.77t) | PIPE | 737 | A53 Gr.B | 1 | 2.1 | 2.1 | 0 | 1 | [47 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-501 | 1/2" SCH.STD (OD21.3x2.77t) | A320-31-CP501 | 1 | 2026-04-08
Plate | SDM_A4C_1-0A_P1 | PL12x2130 | Shell Plate | 11306 | A36 | 1 | 1397.9 | 1397.9 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A4C_1-0A_P10 | PL10x223 | Plate | 341 | A36 | 2 | 4.8 | 9.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0A_P11 | PL12x1823 | Plate | 667 | A36 | 10 | 9.2 | 92 | 0 | 10 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 10 | 2026-10-08
Plate | SDM_A4C_1-0A_P12 | PL16x154 | Plate | 426 | A36 | 10 | 5 | 50 | 10 | 0 | [40 empty] | 10 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 10 | 2026-04-08
Plate | SDM_A4C_1-0A_P2 | PL15x350 | Plate | 10728 | A36 | 2 | 442.1 | 884.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_1-0A_P3 | PL10x180 | Plate | 2107 | A36 | 1 | 29.8 | 29.8 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0A_P4 | PL20x611 | Plate | 2098 | A36 | 1 | 77.7 | 77.7 | 0 | 1 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_1-0A_P5 | PL12x80 | Plate | 301 | A36 | 4 | 3.3 | 13.2 | 0 | 4 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 4 | 2026-10-08
Plate | SDM_A4C_1-0A_P6 | PL12x80 | Plate | 223 | A36 | 2 | 1.7 | 3.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 2 | 2026-10-08
Plate | SDM_A4C_1-0A_P7 | PL20x200 | Plate | 1100 | A36 | 1 | 34.5 | 34.5 | 0 | 1 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_1-0A_P8 | PL5x180 | Plate | 190 | AISI304 | 2 | 1.3 | 2.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL5 |  | MCC | A320-SDM-PC-005 | PL5 | A320-31-CP005 | 2 | 2026-04-08
Plate | SDM_A4C_1-0A_P9 | PL10x286 | Plate | 852 | A36 | 2 | 8.5 | 17 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0B_P14 | PL12x2130 | Shell Plate | 11306 | A36 | 1 | 2268.5 | 2268.5 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A4C_1-0B_P17 | PL10x180 | Plate | 481 | A36 | 1 | 6.8 | 6.8 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0B_P18 | PL20x501 | Plate | 2097 | A36 | 1 | 41.1 | 41.1 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_1-0B_P22 | PL12x535 | Plate | 2138 | A36 | 5 | 31.8 | 159 | 0 | 5 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 5 | 2026-10-08
Plate | SDM_A4C_1-0B_P26 | PL15x356 | PIPE | 781 | A36 | 1 | 21.7 | 21.7 | 0 | 1 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 1 | 2026-04-08
Plate | SDM_A4C_1-0C_P14 | PL12x2130 | Shell Plate | 11306 | A36 | 1 | 2268.5 | 2268.5 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A4C_1-0C_P22 | PL12x535 | Plate | 2138 | A36 | 5 | 31.8 | 159 | 0 | 5 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 5 | 2026-10-08
Plate | SDM_A4C_1-0C_P23 | PL20x505 | Plate | 2096 | A36 | 1 | 42 | 42 | 0 | 1 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_1-0C_P27 | PL20x160 | Plate | 320 | A36 | 2 | 7.6 | 15.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20
Plate | SDM_A4C_1-0C_P28 | PL20x110 | Plate | 200 | A36 | 2 | 5.5 | 11 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP011 | 2 | 2026-10-08
Shape | SDM_A4C_1-0D_D2 | 1/2" SCH.STD (OD21.3x2.77t) | PIPE | 737 | A53 Gr.B | 5 | 2.1 | 10.5 | 0 | 5 | [47 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-501 | 1/2" SCH.STD (OD21.3x2.77t) | A320-31-CP501 | 5 | 2026-04-08
Shape | SDM_A4C_1-0D_M1 | RB50 | HALF COUPLING | 48 | A36 | 1 | 0.32 | 0.32 | 0 | 1 | [47 empty] | #VALUE! |  |  |  | PMC |  | RB50 | A320-31-CP508 | 1 | 2026-04-08
Plate | SDM_A4C_1-0D_P13 | PL12x2130 | Shell Plate | 11306 | A36 | 1 | 2268.5 | 2268.5 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A4C_1-0D_P15 | PL10x293 | Plate | 338 | A36 | 2 | 4.5 | 9 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0D_P16 | PL10x163 | Plate | 170 | A36 | 1 | 1.6 | 1.6 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0D_P17 | PL10x180 | Plate | 481 | A36 | 1 | 6.8 | 6.8 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0D_P18 | PL20x501 | Plate | 2097 | A36 | 1 | 41.1 | 41.1 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_1-0D_P19 | PL10x1071 | Plate | 1136 | A36 | 1 | 43.8 | 43.8 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0D_P20 | PL10x255 | Plate | 2203 | A36 | 1 | 44.1 | 44.1 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0D_P21 | PL10x231 | Plate | 1884 | A36 | 1 | 34.2 | 34.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_1-0D_P22 | PL12x535 | Plate | 2138 | A36 | 5 | 31.8 | 159 | 0 | 5 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 5 | 2026-10-08
Plate | SDM_A4C_1-0D_P24 | PL15x408 | Plate | 825 | A36 | 1 | 25.8 | 25.8 | 0 | 1 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 1 | 2026-04-08
Plate | SDM_A4C_1-0D_P25 | PL15x354 | PIPE | 767 | A36 | 1 | 21.7 | 21.7 | 0 | 1 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 1 | 2026-04-08
Shape | SDM_A4C_2-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 5 | 13.057 | 65.2848 | 0 | 5 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-31-CP503 | 5 | 2026-04-08
Plate | SDM_A4C_2-0A_P1 | PL10x374 | Shell Plate | 4829 | A36 | 2 | 141.7 | 283.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0A_P2 | PL10x512 | Shell Plate | 2218 | A36 | 1 | 76.2 | 76.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0A_P3 | PL10x512 | Shell Plate | 2218 | A36 | 1 | 76.2 | 76.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0A_P4 | PL12x511 | Shell Plate | 2700 | A36 | 2 | 130.1 | 260.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 2 | 2026-10-08
Plate | SDM_A4C_2-0A_P5 | PL15x320 | Plate | 9819 | A36 | 2 | 370 | 740 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_2-0A_P6 | PL10x152 | Plate | 400 | A36 | 6 | 4.2 | 25.2 | 0 | 6 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0A_P7 | PL12x170 | Plate | 538 | A36 | 2 | 7.4 | 14.8 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 2 | 2026-10-08
Plate | SDM_A4C_2-0A_P8 | PL16x146 | Plate | 363 | A36 | 6 | 4 | 24 | 6 | 0 | [40 empty] | 6 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 6 | 2026-04-08
Plate | SDM_A4C_2-0A_P9 | PL16x154 | Plate | 426 | A36 | 2 | 5 | 10 | 2 | 0 | [40 empty] | 2 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 2 | 2026-04-08
Plate | SDM_A4C_2-0B_P10 | PL10x2016 | Shell Plate | 4829 | A36 | 1 | 764.2 | 764.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0B_P12 | PL12x2367 | Shell Plate | 2700 | A36 | 1 | 601.9 | 601.9 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A4C_2-0B_P13 | PL10x2242 | Plate | 2373 | A36 | 1 | 380 | 380 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0B_P14 | PL10x542 | Shell Plate | 1992 | A36 | 3 | 23.5 | 70.5 | 0 | 3 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0B_P15 | PL12x624 | Plate | 2317 | A36 | 1 | 35.4 | 35.4 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 1 | 2026-10-08
Plate | SDM_A4C_2-0C_P16 | PL10x1613 | Shell Plate | 4829 | A36 | 1 | 611.3 | 611.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0C_P17 | PL10x1667 | Shell Plate | 2276 | A36 | 1 | 307.3 | 307.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0C_P18 | PL12x1893 | Shell Plate | 2700 | A36 | 1 | 481.6 | 481.6 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 1 | 2026-10-08
Plate | SDM_A4C_2-0C_P19 | PL10x399 | Plate | 1671 | A36 | 3 | 18.8 | 56.4 | 0 | 3 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0C_P20 | PL12x456 | Plate | 1944 | A36 | 1 | 28.3 | 28.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 1 | 2026-10-08
Plate | SDM_A4C_2-0C_P21 | PL20x160 | Plate | 320 | A36 | 2 | 7.6 | 15.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 2 | 2026-10-08
Plate | SDM_A4C_2-0C_P22 | PL15x110 | Plate | 200 | A36 | 2 | 5.5 | 11 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_2-0D_P10 | PL10x2016 | Shell Plate | 4829 | A36 | 1 | 764.2 | 764.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0D_P11 | PL10x2242 | Shell Plate | 2373 | A36 | 1 | 380 | 380 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0D_P12 | PL12x2367 | Shell Plate | 2700 | A36 | 1 | 601.9 | 601.9 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A4C_2-0D_P14 | PL10x542 | Plate | 1992 | A36 | 3 | 23.5 | 70.5 | 0 | 3 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_2-0D_P15 | PL12x624 | Plate | 2317 | A36 | 1 | 35.4 | 35.4 | 0 | 1 | [47 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-31-CP008 | 1 | 2026-10-08
Shape | SDM_A4C_3-1_D1 | 4" SCH.STD (OD114.3x6.02t) | Pipe | 812 | A53 Gr.B | 2 | 13.057 | 26.1139 | 0 | 2 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-31-CP503 | 2 | 2026-04-08
Plate | SDM_A4C_3-1_P1 | PL10x6315 | Duct Plate | 9820 | A36 | 1 | 4655.3 | 4655.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P10 | PL20x200 | Plate | 246 | A36 | 2 | 7.7 | 15.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 2 | 2026-10-08
| SDM_A4C_3-1_P10A |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-013 | PL20
Plate | SDM_A4C_3-1_P11 | PL30x240 | Base Plate | 640 | A36 | 1 | 36.2 | 36.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL30 |  | MCC | A320-SDM-PC-014 | PL30 | A320-31-CP012 | 1 | 2026-04-08
Plate | SDM_A4C_3-1_P12 | PL15x320 | Plate | 1475 | A36 | 2 | 55.6 | 111.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_3-1_P13 | PL10x304 | Ring Plate | 852 | A36 | 2 | 8.9 | 17.8 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P14 | PL16x135 | Plate | 301 | A36 | 4 | 3 | 12 | 4 | 0 | [40 empty] | 4 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 4 | 2026-04-08
Plate | SDM_A4C_3-1_P15 | PL15x320 | Plate | 3385 | A36 | 2 | 127.5 | 255 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_3-1_P16 | PL16x135 | Plate | 310 | A36 | 2 | 3.2 | 6.4 | 2 | 0 | [40 empty] | 2 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 2 | 2026-04-08
Plate | SDM_A4C_3-1_P17 | PL20x160 | LUG Plate | 260 | A36 | 2 | 6.1 | 12.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 2 | 2026-10-08
Plate | SDM_A4C_3-1_P18 | PL15x110 | PAD Plate | 200 | A36 | 2 | 2.6 | 5.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_3-1_P2 | PL10x2213 | Duct Plate | 6263 | A36 | 1 | 795.6 | 795.6 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P3 | PL10x2192 | Ring Plate | 2300 | A36 | 1 | 71.1 | 71.1 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P4 | PL10x2300 | Ring Plate | 2300 | A36 | 2 | 74.6 | 149.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P5 | PL10x1664 | Ring Plate | 2300 | A36 | 1 | 48.2 | 48.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P6 | PL15x282 | Plate | 517 | A36 | 1 | 13.2 | 13.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 1 | 2026-04-08
Plate | SDM_A4C_3-1_P7 | PL10x232 | Ring Plate | 986 | A36 | 1 | 10.4 | 10.4 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_3-1_P8 | PL20x2330 | Ring Plate | 2442 | A36 | 2 | 182.4 | 364.8 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | chi tiết chia nối | 2
Plate | SDM_A4C_3-1_P9 | PL10x640 | Plate | 2338 | A36 | 1 | 117.4 | 117.4 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Shape | SDM_A4C_4-1_D1 | 4" SCH.STD (OD114.3x6.02t) | Pipe | 812 | A53 Gr.B | 6 | 13.057 | 78.3418 | 0 | 6 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-31-CP503 | 6 | 2026-04-08
Plate | SDM_A4C_4-1_P1 | PL10x5455 | Duct Plate | 11481 | A36 | 1 | 4916.3 | 4916.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_4-1_P10 | PL20x160 | LUG Plate | 260 | A36 | 2 | 6.1 | 12.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 2 | 2026-10-08
Plate | SDM_A4C_4-1_P11 | PL15x110 | PAD Plate | 200 | A36 | 2 | 2.6 | 5.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_4-1_P2 | PL15x320 | Plate | 11491 | A36 | 2 | 433 | 866 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_4-1_P3 | PL10x2192 | Ring Plate | 2300 | A36 | 1 | 71.1 | 71.1 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_4-1_P4 | PL10x2192 | Ring Plate | 2300 | A36 | 3 | 48.2 | 144.6 | 0 | 3 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_4-1_P5 | PL15x270 | Plate | 517 | A36 | 3 | 13.2 | 39.6 | 0 | 3 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 3 | 2026-04-08
Plate | SDM_A4C_4-1_P6 | PL10x232 | Ring Plate | 986 | A36 | 3 | 10.4 | 31.2 | 0 | 3 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-011 | PL15
Plate | SDM_A4C_4-1_P7 | PL10x2192 | Ring Plate | 2300 | A36 | 2 | 64.3 | 128.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_4-1_P8 | PL16x135 | Plate | 301 | A36 | 2 | 1.6 | 3.2 | 2 | 0 | [40 empty] | 2 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 2 | 2026-04-08
Plate | SDM_A4C_4-1_P9 | PL16x135 | Plate | 310 | A36 | 10 | 2 | 20 | 10 | 0 | [40 empty] | 10 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 10 | 2026-04-08
Shape | SDM_A4C_5-1_D1 | 4" SCH.STD (OD114.3x6.02t) | Pipe | 812 | A53 Gr.B | 3 | 13.057 | 39.1709 | 0 | 3 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-31-CP503 | 3 | 2026-04-08
Plate | SDM_A4C_5-1_P1 | PL8x3576 | Duct Plate | 3797 | A36 | 1 | 852.6 | 852.6 | 0 | 1 | [47 empty] | #VALUE! |  | PL8 |  | PMC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 1
Plate | SDM_A4C_5-1_P10 | PL15x110 | PAD Plate | 200 | A36 | 2 | 2.6 | 5.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_5-1_P2 | PL10x3216 | Duct Plate | 5126 | A36 | 1 | 935.3 | 935.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10
Plate | SDM_A4C_5-1_P3 | PL8x1479.5 | Ring Plate | 1616 | A36 | 2 | 27.8 | 55.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 2
Plate | SDM_A4C_5-1_P4 | PL8x1479.5 | Ring Plate | 1616 | A36 | 1 | 24.2 | 24.2 | 0 | 1 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 1
Plate | SDM_A4C_5-1_P5 | PL15x320 | Plate | 6413 | A36 | 2 | 241.6 | 483.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_5-1_P6 | PL15x198 | Plate | 520 | A36 | 2 | 7.8 | 15.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_5-1_P7 | PL16x104 | Plate | 178 | A36 | 4 | 1.3 | 5.2 | 4 | 0 | [40 empty] | 4 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 4 | 2026-04-08
Plate | SDM_A4C_5-1_P8 | PL16x104 | Plate | 188,5 | A36 | 2 | 1.5 | 3 | 2 | 0 | [40 empty] | 2 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 2 | 2026-04-08
Plate | SDM_A4C_5-1_P9 | PL20x160 | LUG Plate | 260 | A36 | 2 | 6.1 | 12.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 2 | 2026-10-08
Shape | SDM_A4C_6-1_D1 | 4" SCH.STD (OD114.3x6.02t) | Pipe | 812 | A53 Gr.B | 5 | 13.057 | 65.2848 | 0 | 5 | [47 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-31-CP503 | 5 | 2026-04-08
Plate | SDM_A4C_6-1_P1 | PL8x3576 | Duct Plate | 11651 | A36 | 1 | 2616.3 | 2616.3 | 0 | 1 | [47 empty] | #VALUE! |  | PL8 |  | PMC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 1
Plate | SDM_A4C_6-1_P10 | PL8x1076 | Ring Plate | 1616 | A36 | 2 | 18 | 36 | 0 | 2 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 2
Plate | SDM_A4C_6-1_P11 | PL8x128 | Ring Plate | 500 | A36 | 2 | 2.8 | 5.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | A320-31-CP006 | 2 | 2026-11-08
Plate | SDM_A4C_6-1_P12 | PL15x306 | Plate | 520 | A36 | 2 | 14.1 | 28.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_6-1_P13 | PL15x352 | Plate | 604 | A36 | 2 | 16.8 | 33.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_6-1_P14 | PL20x160 | LUG Plate | 260 | A36 | 2 | 6.1 | 12.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 2 | 2026-10-08
Plate | SDM_A4C_6-1_P15 | PL15x110 | PAD Plate | 200 | A36 | 2 | 2.6 | 5.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_6-1_P16 | PL5x190 | Plate | 255 | AISI304 | 2 | 1.9194 | 3.8387 | 0 | 2 | [47 empty] | #VALUE! |  | PL5 |  | MCC | A320-SDM-PC-005 | PL5 | A320-31-CP005 | 2 | 2026-04-08
Plate | SDM_A4C_6-1_P2 | PL8x1480 | Ring Plate | 1616 | A36 | 3 | 24.2 | 72.6 | 0 | 3 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 3
Plate | SDM_A4C_6-1_P3 | PL20x1456 | Close Plate | 1669 | A36 | 1 | 321.6 | 321.6 | 0 | 1 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_6-1_P4 | PL20x275 | Base Plate | 1100 | A36 | 1 | 47.5 | 47.5 | 0 | 1 | [47 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-31-CP011 | 1 | 2026-10-08
Plate | SDM_A4C_6-1_P5 | PL16x120 | Plate | 630 | A36 | 3 | 9.3 | 27.9 | 3 | 0 | [40 empty] | 3 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 3 | 2026-04-08
Plate | SDM_A4C_6-1_P6 | PL16x80 | Plate | 100 | A36 | 1 | 0.8 | 0.8 | 1 | 0 | [40 empty] | 1 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 1 | 2026-04-08
Plate | SDM_A4C_6-1_P7 | PL15x320 | Plate | 11551 | A36 | 2 | 435.2 | 870.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-31-CP009 | 2 | 2026-04-08
Plate | SDM_A4C_6-1_P8 | PL16x80 | Plate | 325 | A36 | 2 | 3.1 | 6.2 | 2 | 0 | [40 empty] | 2 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 2 | 2026-04-08
Plate | SDM_A4C_6-1_P9 | PL16x104 | Plate | 188,5 | A36 | 10 | 1.5 | 15 | 10 | 0 | [40 empty] | 10 | [6 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-31-CP010 | 10 | 2026-04-08
Shape | SDM_A5C_1-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 4 | 13.057 | 52.2278 | 4 | 0 | [5 empty] | 4 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 4 | 2026-12-06
Shape | SDM_A5C_1-0A_D2 | 1/2" SCH.STD (OD21.3x2.77t) | PIPE | 737 | A53 Gr.B | 2 | 2.1 | 4.2 | 2 | 0 | [25 empty] | 2 | [21 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-501 | 1/2" SCH.STD (OD21.3x2.77t) | A320-01-CP501 | 2 | 2026-12-06
Plate | SDM_A5C_1-0A_P1 | PL12x2366 | Shell Plate | 8216 | A36 | 1 | 1195.8 | 1195.8 | 1 | 0 | [11 empty] | 4 |  |  |  |  | 1 | 1 | [29 empty] | #VALUE! | BCEFAD | PL12 | Thừa 5 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_1-0A_P10 | PL10x308 | PLATE | 332 | A36 | 2 | 5.1 | 10.2 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 2 | 2026-03-07
Plate | SDM_A5C_1-0A_P11 | PL12x206 | PLATE | 787 | A36 | 4 | 11.6 | 46.4 | 4 | 0 |  | 4 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 4 | 2026-03-07
Plate | SDM_A5C_1-0A_P11A | PL12x206 | PLATE | 787 | A36 | 4 | 11.6 | 46.4 | 4 | 0 |  | 4 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 4 | 2026-03-07
Plate | SDM_A5C_1-0A_P12 | PL16x154 | PLATE | 460 | A36 | 8 | 5.5 | 44 | 8 | 0 | [10 empty] | 8 | [36 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 8 | 13/06/2026
Plate | SDM_A5C_1-0A_P2 | PL15x360 | PLATE | 7926 | A36 | 2 | 336 | 672 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_1-0A_P3 | PL10x180 | PLATE | 2343 | A36 | 1 | 33.1 | 33.1 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_1-0A_P4 | PL20x678 | PLATE | 2308 | A36 | 1 | 83.6 | 83.6 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Plate | SDM_A5C_1-0A_P5 | PL20x200 | PLATE | 1100 | A36 | 1 | 34.5 | 34.5 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Plate | SDM_A5C_1-0A_P6 | PL10x287 | PLATE | 852 | A36 | 1 | 8.9 | 8.9 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_1-0A_P7 | PL5x180 | PLATE | 190 | AISI304 | 2 | 1.3 | 2.6 | 2 | 0 | [14 empty] | 2 | [32 empty] | #VALUE! |  | PL5 |  | MCC | A320-SDM-PC-005 | PL5 | A320-01-CP006 | 2 | 13/06/2026
Plate | SDM_A5C_1-0A_P8 | PL12x80 | PLATE | 300 | A36 | 4 | 2.3 | 9.2 | 4 | 0 |  | 4 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 4 | 2026-03-07
Plate | SDM_A5C_1-0A_P9 | PL12x80 | PIPE | 231 | A36 | 2 | 1.7 | 3.4 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_1-0B_P14 | PL20x563 | PLATE | 2308 | A36 | 1 | 45.5 | 45.5 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP020 | 1 | 2026-08-08
Plate | SDM_A5C_1-0B_P15 | PL12x603 | PLATE | 2365 | A36 | 2 | 37.7 | 75.4 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_1-0B_P18 | PL10x180 | PLATE | 536 | A36 | 2 | 7.5 | 15 | 2 | 0 | [46 empty] | 2 | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 2 | 2026-03-07
Plate | SDM_A5C_1-0B_P23 | PL12x2366 | Shell Plate | 8216 | A36 | 1 | 1830.9 | 1830.9 | 1 | 0 |  |  | 5 | [44 empty] | #VALUE! | ABCDE | PL12 | Thừa 4 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_1-0B_P26 | PL12x222 | PLATE | 983 | A36 | 2 | 14.1 | 28.2 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_1-0B_P27 | PL12x235 | PLATE | 1061 | A36 | 2 | 15.3 | 30.6 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_1-0B_P28 | PL15x313 | PLATE | 546 | A36 | 2 | 16.3 | 32.6 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_1-0B_P29 | PL15x351 | PLATE | 784 | A36 | 1 | 21.8 | 21.8 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_1-0C_P15 | PL12x603 | PLATE | 2365 | A36 | 4 | 37.7 | 150.8 | 4 | 0 |  | 4 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 4 | 2026-03-07
Plate | SDM_A5C_1-0C_P23 | PL12x2366 | Shell Plate | 8216 | A36 | 1 | 1830.9 | 1830.9 | 1 | 0 |  |  | 5 | [44 empty] | #VALUE! | ABCDE | PL12 | Thừa 4 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_1-0C_P24 | PL15x110 | PLATE | 200 | A36 | 2 | 5.5 | 11 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_1-0C_P25 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_1-0C_P30 | PL20x603 | PLATE | 2365 | A36 | 1 | 62.7 | 62.7 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP020 | 1 | 2026-08-08
Shape | SDM_A5C_1-0D_D2 | 1/2" SCH.STD (OD21.3x2.77t) | PIPE | 737 | A53 Gr.B | 5 | 2.1 | 10.5 | 5 | 0 | [25 empty] | 5 | [21 empty] | #VALUE! |  |  |  | PMC | A320-SDM-PC-501 | 1/2" SCH.STD (OD21.3x2.77t) | A320-01-CP501 | 5 | 2026-12-06
Shape | SDM_A5C_1-0D_M1 | RB50 | HALF COUPLING | 48 | A36 | 1 | 0.32 | 0.32 | 1 | 0 | [8 empty] | 1 | [38 empty] | #VALUE! |  |  |  | PMC |  | RB50 | A320-01-CP508 | 1 | 30/06/2026
Plate | SDM_A5C_1-0D_P13 | PL12x2366 | Shell Plate | 8216 | A36 | 1 | 1830.9 | 1830.9 | 1 | 0 |  |  | 4 | [9 empty] | 1 | [34 empty] | #VALUE! | BCDEA | PL12 | Thừa 4 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_1-0D_P14 | PL20x563 | PLATE | 2308 | A36 | 1 | 45.5 | 45.5 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP020 | 1 | 2026-08-08
Plate | SDM_A5C_1-0D_P15 | PL12x603 | PLATE | 2365 | A36 | 4 | 37.7 | 150.8 | 4 | 0 |  | 4 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 4 | 2026-03-07
Plate | SDM_A5C_1-0D_P16 | PL10x221 | PIPE | 1885 | A36 | 1 | 32.7 | 32.7 | 1 | 0 | [46 empty] | 1 | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP021 | 1 | 30/06/2026
Plate | SDM_A5C_1-0D_P17 | PL10x243 | PIPE | 2202 | A36 | 1 | 42 | 42 | 1 | 0 | [46 empty] | 1 | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP021 | 1 | 30/06/2026
Plate | SDM_A5C_1-0D_P18 | PL10x180 | PLATE | 536 | A36 | 1 | 7.5 | 7.5 | 1 | 0 | [46 empty] | 1 | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_1-0D_P19 | PL10x301 | PLATE | 302 | A36 | 2 | 4.6 | 9.2 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 2 | 2026-03-07
Plate | SDM_A5C_1-0D_P20 | PL10x163 | PLATE | 221 | A36 | 1 | 1.7 | 1.7 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_1-0D_P21 | PL15x417 | PLATE | 875 | A36 | 1 | 27.8 | 27.8 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_1-0D_P22 | PL15x363 | PLATE | 793 | A36 | 1 | 22.8 | 22.8 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_1-0D_PA1 | PL10x1071 | PLATE | 1095 | A36 | 1 | 40.8 | 40.8 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Shape | SDM_A5C_1-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 8 | 13.057 | 104.4557 | 4 | 4 | [33 empty] | 4 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 16 | 28/07/2026
Shape | SDM_A5C_1-1A_D2 | 1/2" SCH.STD (OD21.3x2.77t) | PIPE | 737 | A53 Gr.B | 4 | 2.1 | 8.4 | 2 | 2 | [42 empty] | 2 |  |  |  |  | #VALUE! |  |  |  | PMC | A320-SDM-PC-501 | 1/2" SCH.STD (OD21.3x2.77t) | A320-01-CP501 A320-11-CP501 A320-21-CP501 | 8 | 28/07/2026
Plate | SDM_A5C_1-1A_P1 | PL12x2366 | Shell Plate | 8216 | A36 | 2 | 1195.8 | 2391.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_1-1A_P10 | PL10x308 | PLATE | 332 | A36 | 4 | 5.1 | 20.4 | 3 | 1 | [32 empty] | 2 | [7 empty] | 1 | [6 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-10-07
Plate | SDM_A5C_1-1A_P11 | PL12x206 | PLATE | 787 | A36 | 8 | 11.6 | 92.8 | 4 | 4 | [32 empty] | 4 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 16 | 2026-10-07
Plate | SDM_A5C_1-1A_P11A | PL12x206 | PLATE | 787 | A36 | 8 | 11.6 | 92.8 | 4 | 4 | [32 empty] | 4 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 16 | 2026-10-07
Plate | SDM_A5C_1-1A_P12 | PL16x154 | PLATE | 460 | A36 | 16 | 5.5 | 88 | 8 | 8 | [35 empty] | 8 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 32 | 14/08/2026
Plate | SDM_A5C_1-1A_P2 | PL15x360 | PLATE | 7926 | A36 | 4 | 336 | 1344 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_1-1A_P3 | PL10x180 | PLATE | 2343 | A36 | 2 | 33.1 | 66.2 | 1 | 1 | [38 empty] | 1 | [8 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1A_P4 | PL20x678 | PLATE | 2308 | A36 | 2 | 83.6 | 167.2 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_1-1A_P5 | PL20x200 | PLATE | 1100 | A36 | 2 | 34.5 | 69 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_1-1A_P6 | PL10x287 | PLATE | 852 | A36 | 2 | 8.9 | 17.8 | 1 | 1 | [39 empty] | 1 | [7 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1A_P7 | PL5x180 | PLATE | 190 | AISI304 | 4 | 1.3 | 5.2 | 0 | 4 | [47 empty] | #VALUE! |  | PL5 |  | MCC | A320-SDM-PC-005 | PL5 | A320-01-CP006 A320-11-CP006 A320-21-CP006 | 8 | 2026-10-07
Plate | SDM_A5C_1-1A_P8 | PL12x80 | PLATE | 300 | A36 | 8 | 2.3 | 18.4 | 4 | 4 | [32 empty] | 4 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 16 | 2026-10-07
Plate | SDM_A5C_1-1A_P9 | PL12x80 | PIPE | 231 | A36 | 4 | 1.7 | 6.8 | 2 | 2 | [32 empty] | 2 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 8 | 2026-10-07
Plate | SDM_A5C_1-1C_P15 | PL20x603 | PLATE | 2365 | A36 | 10 | 62.7 | 627 | 10 | 0 | [15 empty] | 10 | [27 empty] | 8 |  |  |  | #VALUE! |  | PL20 | Thừa 8 | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP022 | 4 | 18/08/2026
Plate | SDM_A5C_1-1C_P23 | PL12x2366 | Shell Plate | 8216 | A36 | 2 | 1830.9 | 3661.8 | 2 | 0 | [26 empty] | 3 |  | 2 | [18 empty] | #VALUE! | BCDEA | PL12 | Thừa 3 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_1-1C_P24 | PL15x110 | PLATE | 200 | A36 | 4 | 5.5 | 22 | 4 | 0 | [22 empty] | 2 | [12 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_1-1C_P25 | PL20x160 | PLATE | 320 | A36 | 4 | 7.6 | 30.4 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Shape | SDM_A5C_1-1D_D2 | 1/2" SCH.STD (OD21.3x2.77t) | PIPE | 737 | A53 Gr.B | 10 | 2.1 | 21 | 5 | 5 | [42 empty] | 5 |  |  |  |  | #VALUE! |  |  |  | PMC | A320-SDM-PC-501 | 1/2" SCH.STD (OD21.3x2.77t) | A320-01-CP501 A320-11-CP501 A320-21-CP501 | 20 | 28/07/2026
Shape | SDM_A5C_1-1D_M1 | RB50 | HALF COUPLING | 48 | A36 | 2 | 0.32 | 0.64 | 0 | 2 | [47 empty] | #VALUE! |  |  |  | PMC |  | RB50 | A320-01-CP508 A320-11-CP507 A320-21-CP508 | 4 | 28/07/2026
Plate | SDM_A5C_1-1D_P13 | PL12x2366 | Shell Plate | 8216 | A36 | 2 | 1830.9 | 3661.8 | 2 | 0 | [26 empty] | 3 |  | 1 | [18 empty] | #VALUE! | EDCB | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_1-1D_P14 | PL20x563 | PLATE | 2308 | A36 | 2 | 45.5 | 91 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP020 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_1-1D_P15 | PL20x603 | PLATE | 2365 | A36 | 8 | 62.7 | 501.6 | 8 | 0 | [15 empty] | 8 | [27 empty] | 8 |  |  |  | #VALUE! |  | PL20 | Thừa 8 | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP022 | 16 | 18/08/2026
Plate | SDM_A5C_1-1D_P16 | PL10x221 | PIPE | 1885 | A36 | 2 | 32.7 | 65.4 | 1 | 1 | [38 empty] | 1 | [8 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP021 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1D_P17 | PL10x243 | PIPE | 2202 | A36 | 2 | 42 | 84 | 2 | 0 | [38 empty] | 1 |  |  |  |  | 1 |  |  |  | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP021 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1D_P18 | PL10x180 | PLATE | 536 | A36 | 2 | 7.5 | 15 | 2 | 0 | [38 empty] | 1 |  |  |  | 1 |  |  |  |  | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1D_P19 | PL10x301 | PLATE | 302 | A36 | 4 | 4.6 | 18.4 | 4 | 0 | [32 empty] | 2 |  |  | 2 | [11 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-10-07
Plate | SDM_A5C_1-1D_P20 | PL10x163 | PLATE | 221 | A36 | 2 | 1.7 | 3.4 | 2 | 0 | [32 empty] | 1 |  |  | 1 | [11 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1D_P21 | PL15x417 | PLATE | 875 | A36 | 2 | 27.8 | 55.6 | 1 | 1 | [35 empty] | 1 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 28/07/2026
Plate | SDM_A5C_1-1D_P22 | PL15x363 | PLATE | 793 | A36 | 2 | 22.8 | 45.6 | 1 | 1 | [35 empty] | 1 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 28/07/2026
Plate | SDM_A5C_1-1D_PA1 | PL10x1071 | PLATE | 1095 | A36 | 2 | 40.8 | 81.6 | 2 | 0 | [38 empty] | 2 | [8 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1E_P14 | PL20x563 | PLATE | 2308 | A36 | 2 | 45.5 | 91 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP020 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_1-1E_P15 | PL20x603 | PLATE | 2365 | A36 | 8 | 62.7 | 501.6 | 8 | 0 | [15 empty] | 8 | [27 empty] | 8 |  |  |  | #VALUE! |  | PL20 | Thừa 8 | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP022 | 16 | 18/08/2026
Plate | SDM_A5C_1-1E_P18 | PL10x180 | PLATE | 536 | A36 | 2 | 7.5 | 15 | 1 | 1 | [38 empty] | 1 | [8 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_1-1E_P23 | PL12x2366 | Shell Plate | 8216 | A36 | 2 | 1830.9 | 3661.8 | 2 | 0 | [26 empty] | 3 |  | 1 | [18 empty] | #VALUE! | CBDA | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_1-1E_P29 | PL15x351 | PLATE | 784 | A36 | 2 | 21.8 | 43.6 | 2 | 0 | [22 empty] | 1 | [12 empty] | 1 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 28/07/2026
Shape | SDM_A5C_2-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 6 | 13.057 | 78.3418 | 6 | 0 | [5 empty] | 6 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 6 | 2026-12-06
Plate | SDM_A5C_2-0A_P1 | PL12x418 | Shell Plate | 4023 | A36 | 2 | 182.2 | 364.4 | 2 | 0 | [16 empty] | 2 | [30 empty] | #VALUE! | AB | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 2
Plate | SDM_A5C_2-0A_P2 | PL12x618 | Shell Plate | 1930 | A36 | 1 | 98 | 98 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 | 2 | 13/06/2026
Plate | SDM_A5C_2-0A_P2A | PL12x618 | Shell Plate | 1930 | A36 | 1 | 98 | 98 | 1 | 0 | [16 empty] | 1 | [30 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12
Plate | SDM_A5C_2-0A_P3 | PL12x618 | Shell Plate | 5608 | A36 | 1 | 326.2 | 326.2 | 1 | 0 | [11 empty] | 2 | [35 empty] | #VALUE! | AB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0A_P3A | PL12x618 | Shell Plate | 5608 | A36 | 1 | 326.2 | 326.2 | 1 | 0 | [11 empty] | 2 | [35 empty] | #VALUE! | AB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0A_P4 | PL15x320 | PLATE | 11521 | A36 | 2 | 434.1 | 868.2 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_2-0A_P5 | PL16x146 | PLATE | 400 | A36 | 6 | 4.5 | 27 | 6 | 0 | [10 empty] | 6 | [36 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 6 | 13/06/2026
Plate | SDM_A5C_2-0A_P6 | PL16x154 | PLATE | 460 | A36 | 6 | 5.5 | 33 | 6 | 0 | [10 empty] | 6 | [36 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 6 | 13/06/2026
Plate | SDM_A5C_2-0A_P7 | PL12x160 | PLATE | 506 | A36 | 6 | 6.5 | 39 | 6 | 0 |  | 6 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 6 | 2026-03-07
Plate | SDM_A5C_2-0A_P8 | PL12x192 | PLATE | 645 | A36 | 6 | 9.6 | 57.6 | 6 | 0 |  | 6 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 6 | 2026-03-07
Plate | SDM_A5C_2-0B_P10 | PL12x1956 | Shell Plate | 2635 | A36 | 1 | 441.5 | 441.5 | 1 | 0 | [18 empty] | 1 | [28 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 | 1 | 13/06/2026
Plate | SDM_A5C_2-0B_P11 | PL12x2628.5 | Shell Plate | 5608 | A36 | 1 | 1388.4 | 1388.4 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0B_P12 | PL12x609 | PLATE | 2225 | A36 | 1 | 31.8 | 31.8 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Plate | SDM_A5C_2-0B_P13 | PL12x700 | PLATE | 2562 | A36 | 2 | 41.9 | 83.8 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_2-0B_P21 | PL12x218 | PLATE | 1011 | A36 | 2 | 12.8 | 25.6 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_2-0B_P22 | PL12x208 | PLATE | 951 | A36 | 2 | 12 | 24 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_2-0B_P23 | PL15x293 | PLATE | 530 | A36 | 2 | 14.5 | 29 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_2-0B_P24 | PL12x243 | PLATE | 1122 | A36 | 1 | 16.2 | 16.2 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Plate | SDM_A5C_2-0B_P25 | PL12x256 | PLATE | 1198 | A36 | 1 | 17.4 | 17.4 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Plate | SDM_A5C_2-0B_P26 | PL15x313 | PLATE | 546 | A36 | 1 | 16.3 | 16.3 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_2-0B_P9 | PL12x2279.4 | Shell Plate | 4023 | A36 | 1 | 863.8 | 863.8 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0C_P14 | PL12x1823 | Shell Plate | 4023 | A36 | 1 | 690.9 | 690.9 | 1 | 0 |  |  | 1 |  |  |  |  | 1 | [39 empty] | #VALUE! | AB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0C_P15 | PL12x1997 | Shell Plate | 2103 | A36 | 1 | 358.1 | 358.1 | 1 | 0 | [18 empty] | 1 | [28 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 | 1 | 13/06/2026
Plate | SDM_A5C_2-0C_P16 | PL12x2102.7 | Shell Plate | 5608 | A36 | 1 | 1110.3 | 1110.3 | 1 | 0 |  |  | 4 | [44 empty] | #VALUE! | ABCD | PL12 | Thừa 3 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0C_P17 | PL12x447 | PLATE | 1867 | A36 | 3 | 25.4 | 76.2 | 3 | 0 |  | 3 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_2-0C_P18 | PL12x514 | PLATE | 2149 | A36 | 3 | 33.5 | 100.5 | 3 | 0 |  | 3 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_2-0C_P19 | PL15x110 | PLATE | 200 | A36 | 2 | 5.5 | 11 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_2-0C_P20 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_2-0D_P10 | PL12x1956 | Shell Plate | 2635 | A36 | 1 | 441.5 | 441.5 | 1 | 0 | [18 empty] | 1 | [28 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 | 1 | 13/06/2026
Plate | SDM_A5C_2-0D_P11 | PL12x2628.5 | Shell Plate | 5608 | A36 | 1 | 1388.4 | 1388.4 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_2-0D_P12 | PL12x609 | PLATE | 2225 | A36 | 3 | 31.8 | 95.4 | 3 | 0 | [16 empty] | 3 | [30 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_2-0D_P13 | PL12x700 | PLATE | 2562 | A36 | 3 | 41.9 | 125.7 | 3 | 0 | [16 empty] | 3 | [30 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_2-0D_P9 | PL12x2279.4 | Shell Plate | 4023 | A36 | 1 | 863.8 | 863.8 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Shape | SDM_A5C_2-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 12 | 13.057 | 156.6835 | 6 | 6 | [33 empty] | 6 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 24 | 28/07/2026
Plate | SDM_A5C_2-1A_P1 | PL12x418 | Shell Plate | 4023 | A36 | 4 | 182.2 | 728.8 | 0 | 4 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 8
Plate | SDM_A5C_2-1A_P2 | PL12x618 | Shell Plate | 1930 | A36 | 2 | 98 | 196 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 A320-11-CP017 | 4 | 13/07/2026
Plate | SDM_A5C_2-1A_P2A | PL12x618 | Shell Plate | 1930 | A36 | 2 | 98 | 196 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-11-CP017 A320-21-CP009 | 4 | 13/07/2026
Plate | SDM_A5C_2-1A_P3 | PL12x618 | Shell Plate | 5608 | A36 | 2 | 326.2 | 652.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1A_P3A | PL12x618 | Shell Plate | 5608 | A36 | 2 | 326.2 | 652.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1A_P4 | PL15x320 | PLATE | 11521 | A36 | 4 | 434.1 | 1736.4 | 2 | 2 | [21 empty] | 2 | [25 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_2-1A_P5 | PL16x146 | PLATE | 400 | A36 | 12 | 4.5 | 54 | 6 | 6 | [35 empty] | 6 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 14/08/2026
Plate | SDM_A5C_2-1A_P6 | PL16x154 | PLATE | 460 | A36 | 12 | 5.5 | 66 | 6 | 6 | [35 empty] | 6 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 14/08/2026
Plate | SDM_A5C_2-1A_P7 | PL12x160 | PLATE | 506 | A36 | 12 | 6.5 | 78 | 6 | 6 | [32 empty] | 2 | [10 empty] | 4 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 24 | 2026-10-07
Plate | SDM_A5C_2-1A_P8 | PL12x192 | PLATE | 645 | A36 | 12 | 9.6 | 115.2 | 6 | 6 | [32 empty] | 6 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 24 | 2026-10-07
Plate | SDM_A5C_2-1C_P14 | PL12x1823 | Shell Plate | 4023 | A36 | 2 | 690.9 | 1381.8 | 2 | 0 | [28 empty] | 2 | [18 empty] | #VALUE! | BA | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1C_P15 | PL12x1997 | Shell Plate | 2103 | A36 | 2 | 358.1 | 716.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 A320-11-CP017 A320-21-CP009 | 4 | 13/07/2026
Plate | SDM_A5C_2-1C_P16 | PL12x2102.7 | Shell Plate | 5608 | A36 | 2 | 1110.3 | 2220.6 | 2 | 0 | [26 empty] | 1 |  | 2 | [18 empty] | #VALUE! | CAB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1C_P17 | PL12x447 | PLATE | 1867 | A36 | 6 | 25.4 | 152.4 | 3 | 3 | [32 empty] | 1 | [10 empty] | 2 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_2-1C_P18 | PL12x514 | PLATE | 2149 | A36 | 6 | 33.5 | 201 | 3 | 3 | [32 empty] | 3 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_2-1C_P19 | PL15x110 | PLATE | 200 | A36 | 4 | 5.5 | 22 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_2-1C_P20 | PL20x160 | PLATE | 320 | A36 | 4 | 7.6 | 30.4 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_2-1D_P10 | PL12x1956 | Shell Plate | 2635 | A36 | 2 | 441.5 | 883 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 A320-11-CP017 A320-21-CP009 | 4 | 13/07/2026
Plate | SDM_A5C_2-1D_P11 | PL12x2628.5 | Shell Plate | 5608 | A36 | 2 | 1388.4 | 2776.8 | 2 | 0 | [26 empty] | 2 |  | 1 | [18 empty] | #VALUE! | BAC | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1D_P12 | PL12x609 | PLATE | 2225 | A36 | 6 | 31.8 | 190.8 | 3 | 3 | [43 empty] | 3 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_2-1D_P13 | PL12x700 | PLATE | 2562 | A36 | 6 | 41.9 | 251.4 | 3 | 3 | [43 empty] | 3 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_2-1D_P9 | PL12x2279.4 | Shell Plate | 4023 | A36 | 2 | 863.8 | 1727.6 | 2 | 0 | [26 empty] | 1 |  | 1 | [18 empty] | #VALUE! | BC | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1E_P10 | PL12x1956 | Shell Plate | 2635 | A36 | 2 | 441.5 | 883 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | A320-01-CP017 A320-11-CP017 A320-21-CP009 | 4 | 13/07/2026
Plate | SDM_A5C_2-1E_P11 | PL12x2628.5 | Shell Plate | 5608 | A36 | 2 | 1388.4 | 2776.8 | 2 | 0 | [26 empty] | 1 |  | 2 | [18 empty] | #VALUE! | ACB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_2-1E_P12 | PL12x609 | PLATE | 2225 | A36 | 6 | 31.8 | 190.8 | 3 | 3 | [43 empty] | 3 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_2-1E_P13 | PL12x700 | PLATE | 2562 | A36 | 6 | 41.9 | 251.4 | 3 | 3 | [43 empty] | 3 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_2-1E_P9 | PL12x2279.4 | Shell Plate | 4023 | A36 | 2 | 863.8 | 1727.6 | 2 | 0 | [26 empty] | 1 |  | 1 | [18 empty] | #VALUE! | BC | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Shape | SDM_A5C_3-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 3 | 13.057 | 39.1709 | 3 | 0 | [5 empty] | 3 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 3 | 2026-12-06
Plate | SDM_A5C_3-0A_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 1 | 493.5 | 493.5 | 1 | 0 | [7 empty] | 1 | [8 empty] | 1 | [30 empty] | #VALUE! | BA | PL10 | Thừa 1 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0A_P10 | PL12x595 | Shell Plate | 5089 | A36 | 1 | 325.5 | 325.5 | 1 | 0 | [16 empty] | 2 | [30 empty] | #VALUE! | AB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0A_P10A | PL12x595 | Shell Plate | 5089 | A36 | 1 | 325.5 | 325.5 | 1 | 0 | [16 empty] | 2 | [30 empty] | #VALUE! | AB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0A_P11 | PL12x174 | PLATE | 630 | A36 | 3 | 8.1 | 24.3 | 3 | 0 |  | 3 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_3-0A_P11A | PL12x174 | PLATE | 630 | A36 | 3 | 8.1 | 24.3 | 3 | 0 |  | 3 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_3-0A_P12 | PL16x146 | PLATE | 400 | A36 | 6 | 4.5 | 27 | 6 | 0 | [10 empty] | 6 | [36 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 6 | 13/06/2026
Plate | SDM_A5C_3-0A_P2 | PL10x640 | PLATE | 1712 | A36 | 1 | 86 | 86 | 1 | 0 | [46 empty] | 1 | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0A_P3 | PL20x582 | PLATE | 1805 | A36 | 2 | 54.9 | 109.8 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_3-0A_P4 | PL20x254 | PLATE | 200 | A36 | 3 | 8 | 24 | 3 | 0 | [5 empty] | 3 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 3 | 2026-08-08
Plate | SDM_A5C_3-0A_P4A | PL20x254 | PLATE | 200 | A36 | 1 | 8 | 8 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Plate | SDM_A5C_3-0A_P5 | PL30x240 | PLATE | 640 | A36 | 1 | 36.2 | 36.2 | 1 | 0 | [10 empty] | 1 | [36 empty] | #VALUE! |  | PL30 |  | MCC | A320-SDM-PC-014 | PL30 | A320-01-CP013 | 1 | 13/06/2026
Plate | SDM_A5C_3-0A_P6 | PL10x465 | PLATE | 1768 | A36 | 1 | 20.3 | 20.3 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0A_P7 | PL12x2052 | Shell Plate | 2391 | A36 | 1 | 254.7 | 254.7 | 1 | 0 | [16 empty] | 3 | [30 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0A_P8 | PL10x303 | PLATE | 852 | A36 | 1 | 9.2 | 9.2 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0A_P9 | PL15x320 | PIPE | 7104 | A36 | 2 | 267.7 | 535.4 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_3-0B_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 1 | 493.5 | 493.5 | 1 | 0 | [7 empty] | 1 | [8 empty] | 1 | [30 empty] | #VALUE! | AB | PL10 | Thừa 1 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0B_P13 | PL10x389 | PLATE | 640 | A36 | 1 | 19.5 | 19.5 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0B_P14 | PL20x488 | PLATE | 1805 | A36 | 2 | 48.1 | 96.2 | 2 | 0 | [6 empty] | 2 | [40 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_3-0B_P15 | PL12x2030 | Shell Plate | 2664 | A36 | 1 | 428.3 | 428.3 | 1 | 0 | [17 empty] | 2 | [29 empty] | #VALUE! | AB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0B_P16 | PL12x2052 | Shell Plate | 5089 | A36 | 1 | 983.4 | 983.4 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0B_P17 | PL12x524 | PLATE | 2053 | A36 | 2 | 28.6 | 57.2 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 2 | 2026-03-07
Plate | SDM_A5C_3-0B_P22 | PL10x179 | PLATE | 688 | A36 | 1 | 7.1 | 7.1 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0B_P23 | PL10x185 | PLATE | 737 | A36 | 1 | 7.6 | 7.6 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0B_P24 | PL15x276 | PLATE | 515 | A36 | 1 | 12.9 | 12.9 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_3-0B_P25 | PL12x191 | PLATE | 830 | A36 | 1 | 10.4 | 10.4 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Plate | SDM_A5C_3-0B_P26 | PL12x200 | PLATE | 892 | A36 | 1 | 11.2 | 11.2 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 1 | 2026-03-07
Plate | SDM_A5C_3-0B_P27 | PL15x293 | PLATE | 530 | A36 | 1 | 14.5 | 14.5 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_3-0C_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 1 | 493.5 | 493.5 | 1 | 0 | [7 empty] | 1 | [8 empty] | 1 | [30 empty] | #VALUE! | BA | PL10 | Thừa 1 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0C_P16 | PL12x2052 | Shell Plate | 5089 | A36 | 1 | 983.4 | 983.4 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0C_P17 | PL12x524 | PLATE | 2053 | A36 | 3 | 28.6 | 85.8 | 3 | 0 |  | 3 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_3-0C_P18 | PL20x477 | PLATE | 1805 | A36 | 2 | 48.7 | 97.4 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_3-0C_P19 | PL12x2051 | Shell Plate | 2550 | A36 | 1 | 434.1 | 434.1 | 1 | 0 | [17 empty] | 2 | [29 empty] | #VALUE! | BA | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0C_P20 | PL15x110 | PLATE | 200 | A36 | 2 | 5.5 | 11 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_3-0C_P21 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_3-0C_P6 | PL10x465 | PLATE | 1768 | A36 | 1 | 20.3 | 20.3 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0D_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 1 | 493.5 | 493.5 | 1 | 0 | [7 empty] | 1 | [8 empty] | 1 | [30 empty] | #VALUE! | AB | PL10 | Thừa 1 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0D_P13 | PL10x389 | PLATE | 640 | A36 | 1 | 19.5 | 19.5 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_3-0D_P14 | PL20x488 | PLATE | 1805 | A36 | 2 | 48.1 | 96.2 | 2 | 0 | [6 empty] | 2 | [40 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_3-0D_P15 | PL12x2030 | Shell Plate | 2664 | A36 | 1 | 428.3 | 428.3 | 1 | 0 | [17 empty] | 2 | [29 empty] | #VALUE! | BA | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0D_P16 | PL12x2052 | Shell Plate | 5089 | A36 | 1 | 983.4 | 983.4 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL12 | Thừa 2 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 1
Plate | SDM_A5C_3-0D_P17 | PL12x524 | PLATE | 2053 | A36 | 3 | 28.6 | 85.8 | 3 | 0 |  | 3 | [45 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 | 3 | 2026-03-07
Plate | SDM_A5C_3-0D_P6 | PL10x465 | PLATE | 1768 | A36 | 1 | 20.3 | 20.3 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Shape | SDM_A5C_3-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 6 | 13.057 | 78.3418 | 3 | 3 | [33 empty] | 3 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 12 | 28/07/2026
Plate | SDM_A5C_3-1A_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 2 | 493.5 | 987 | 2 | 0 | [23 empty] | 1 | 1 | [22 empty] | #VALUE! | B A | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1A_P10 | PL12x595 | Shell Plate | 5089 | A36 | 2 | 325.5 | 651 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1A_P10A | PL12x595 | Shell Plate | 5089 | A36 | 2 | 325.5 | 651 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1A_P11 | PL12x174 | PLATE | 630 | A36 | 6 | 8.1 | 48.6 | 3 | 3 | [32 empty] | 3 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_3-1A_P11A | PL12x174 | PLATE | 630 | A36 | 6 | 8.1 | 48.6 | 3 | 3 | [32 empty] | 3 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_3-1A_P12 | PL16x146 | PLATE | 400 | A36 | 12 | 4.5 | 54 | 6 | 6 | [35 empty] | 6 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 14/08/2026
Plate | SDM_A5C_3-1A_P2 | PL10x640 | PLATE | 1712 | A36 | 2 | 86 | 172 | 0 | 2 | [47 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1A_P3 | PL20x582 | PLATE | 1805 | A36 | 4 | 54.9 | 219.6 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_3-1A_P4 | PL20x254 | PLATE | 200 | A36 | 6 | 8 | 48 | 3 | 3 | [30 empty] | 3 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 12 | 2026-08-08
Plate | SDM_A5C_3-1A_P4A | PL20x254 | PLATE | 200 | A36 | 2 | 8 | 16 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_3-1A_P5 | PL30x240 | PLATE | 640 | A36 | 2 | 36.2 | 72.4 | 1 | 1 | [36 empty] | 1 | [10 empty] | #VALUE! |  | PL30 |  | MCC | A320-SDM-PC-014 | PL30 | A320-01-CP013 A320-11-CP013 A320-21-CP013 | 4 | 2026-10-07
Plate | SDM_A5C_3-1A_P6 | PL10x465 | PLATE | 1768 | A36 | 2 | 20.3 | 40.6 | 2 | 0 | [32 empty] | 1 | [7 empty] | 1 | [6 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1A_P7 | PL12x2052 | PLATE | 2391 | A36 | 2 | 254.7 | 509.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1A_P8 | PL10x303 | PLATE | 852 | A36 | 2 | 9.2 | 18.4 | 1 | 1 | [32 empty] | 1 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1A_P9 | PL15x320 | PLATE | 7104 | A36 | 4 | 267.7 | 1070.8 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_3-1C_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 2 | 493.5 | 987 | 2 | 0 | [24 empty] | 1 |  |  |  | 1 | [18 empty] | #VALUE! | BA | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1C_P16 | PL12x2052 | Shell Plate | 5089 | A36 | 2 | 983.4 | 1966.8 | 2 | 0 | [26 empty] | 2 |  | 1 | [18 empty] | #VALUE! | ACB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1C_P17 | PL12x524 | PLATE | 2053 | A36 | 6 | 28.6 | 171.6 | 3 | 3 | [43 empty] | 3 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_3-1C_P18 | PL20x477 | PLATE | 1805 | A36 | 4 | 48.7 | 194.8 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_3-1C_P19 | PL12x2051 | PLATE | 2550 | A36 | 2 | 434.1 | 868.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1C_P20 | PL15x110 | PLATE | 200 | A36 | 4 | 5.5 | 22 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_3-1C_P21 | PL20x160 | PLATE | 320 | A36 | 4 | 7.6 | 30.4 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_3-1C_P6 | PL10x465 | PLATE | 1768 | A36 | 2 | 20.3 | 40.6 | 1 | 1 | [32 empty] | 1 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1D_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 2 | 493.5 | 987 | 2 | 0 | [23 empty] | 1 | 1 | [22 empty] | #VALUE! | B A | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1D_P13 | PL10x389 | PLATE | 640 | A36 | 2 | 19.5 | 39 | 2 | 0 | [38 empty] | 1 |  |  |  | 1 |  |  |  |  | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1D_P14 | PL20x488 | PLATE | 1805 | A36 | 4 | 48.1 | 192.4 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_3-1D_P15 | PL12x2030 | Shell Plate | 2664 | A36 | 2 | 428.3 | 856.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1D_P16 | PL12x2052 | Shell Plate | 5089 | A36 | 2 | 983.4 | 1966.8 | 2 | 0 | [26 empty] | 1 |  | 2 | [18 empty] | #VALUE! | CAB | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1D_P17 | PL12x524 | PLATE | 2053 | A36 | 6 | 28.6 | 171.6 | 3 | 3 | [32 empty] | 3 | [14 empty] | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_3-1D_P6 | PL10x465 | PLATE | 1768 | A36 | 2 | 20.3 | 40.6 | 1 | 1 | [32 empty] | 1 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1E_P1 | PL10x1736 | Shell Plate | 3622 | A36 | 2 | 493.5 | 987 | 2 | 0 | [23 empty] | 1 |  |  |  |  | 1 | [18 empty] | #VALUE! | AB | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1E_P13 | PL10x389 | PLATE | 640 | A36 | 2 | 19.5 | 39 | 2 | 0 | [38 empty] | 1 |  |  |  | 1 |  |  |  |  | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_3-1E_P14 | PL20x488 | PLATE | 1805 | A36 | 4 | 48.1 | 192.4 | 2 | 2 | [30 empty] | 2 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_3-1E_P15 | PL12x2030 | Shell Plate | 2664 | A36 | 2 | 428.3 | 856.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL12 |  | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1E_P16 | PL12x2052 | Shell Plate | 5089 | A36 | 2 | 983.4 | 1966.8 | 2 | 0 | [26 empty] | 2 |  | 1 | [18 empty] | #VALUE! | BCA | PL12 | Thừa 1 | PMC | A320-SDM-PC-010 | PL12 | chi tiết chia nối | 4
Plate | SDM_A5C_3-1E_P17 | PL12x524 | PLATE | 2053 | A36 | 6 | 28.6 | 171.6 | 3 | 3 | [43 empty] | 3 |  |  |  | #VALUE! |  | PL12 |  | MCC | A320-SDM-PC-010 | PL12 | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-10-07
Plate | SDM_A5C_3-1E_P6 | PL10x465 | PLATE | 1768 | A36 | 2 | 20.3 | 40.6 | 1 | 1 | [32 empty] | 1 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Shape | SDM_A5C_4-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 6 | 13.057 | 78.3418 | 6 | 0 | [5 empty] | 6 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 6 | 2026-12-06
Plate | SDM_A5C_4-0A_P1 | PL10x2314 | Shell Plate | 11920 | A36 | 1 | 1381.3 | 1381.3 | 1 | 0 | [11 empty] | 9 | [35 empty] | #VALUE! | ABCDEFGHI | PL10 | Thừa 8 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_4-0A_P2 | PL15x320 | PLATE | 11770 | A36 | 2 | 443.5 | 887 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_4-0A_P3 | PL10x303 | PLATE | 852 | A36 | 1 | 9.2 | 9.2 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_4-0A_P4 | PL10x200 | PLATE | 794 | A36 | 7 | 8.5 | 59.5 | 7 | 0 |  |  |  | 7 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 7 | 2026-03-07
Plate | SDM_A5C_4-0A_P4A | PL10x200 | PLATE | 794 | A36 | 7 | 8.5 | 59.5 | 7 | 0 |  | 7 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 7 | 2026-03-07
Plate | SDM_A5C_4-0A_P5 | PL16x137 | PLATE | 337 | A36 | 14 | 3.5 | 49 | 14 | 0 | [10 empty] | 14 | [36 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 14 | 13/06/2026
Plate | SDM_A5C_4-0B_P10 | PL10x387 | PLATE | 1595 | A36 | 4 | 17.8 | 71.2 | 4 | 0 |  |  |  | 4 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 4 | 2026-03-07
Plate | SDM_A5C_4-0B_P11 | PL10x150 | PLATE | 367 | A36 | 4 | 3.6 | 14.4 | 4 | 0 |  |  |  | 4 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 4 | 2026-03-07
Plate | SDM_A5C_4-0B_P12 | PL15x276 | PLATE | 515 | A36 | 4 | 12.9 | 51.6 | 4 | 0 |  |  |  |  | 4 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 4 | 2026-03-07
Plate | SDM_A5C_4-0B_P6 | PL10x2314 | Shell Plate | 11920 | A36 | 1 | 2165.5 | 2165.5 | 1 | 0 | [9 empty] | 4 |  | 2 |  |  |  |  | 1 | [30 empty] | #VALUE! | DEFGBCA | PL10 | Thừa 6 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_4-0B_P7 | PL10x695 | PLATE | 2165 | A36 | 3 | 27.2 | 81.6 | 3 | 0 |  |  |  | 3 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 3 | 2026-03-07
Plate | SDM_A5C_4-0B_P8 | PL15x110 | PLATE | 200 | A36 | 1 | 5.5 | 5.5 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_4-0B_P9 | PL20x160 | PLATE | 320 | A36 | 1 | 7.6 | 7.6 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Plate | SDM_A5C_4-0C_P6 | PL10x2314 | Shell Plate | 11920 | A36 | 1 | 2165.5 | 2165.5 | 1 | 0 | [9 empty] | 4 |  | 2 |  |  |  |  | 1 | [30 empty] | #VALUE! | ADEFBCG | PL10 | Thừa 6 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_4-0C_P7 | PL10x695 | PLATE | 2165 | A36 | 7 | 27.2 | 190.4 | 7 | 0 |  |  |  | 7 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 7 | 2026-03-07
Plate | SDM_A5C_4-0C_P8 | PL15x110 | PLATE | 200 | A36 | 1 | 5.5 | 5.5 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_4-0C_P9 | PL20x160 | PLATE | 320 | A36 | 1 | 7.6 | 7.6 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Shape | SDM_A5C_4-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 12 | 13.057 | 156.6835 | 6 | 6 | [33 empty] | 6 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 24 | 28/07/2026
Plate | SDM_A5C_4-1A_P1 | PL10x2314 | Shell Plate | 11920 | A36 | 2 | 1381.3 | 2762.6 | 1 | 1 | [24 empty] | 1 | [22 empty] | #VALUE! | I | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_4-1A_P2 | PL15x320 | PLATE | 11770 | A36 | 4 | 443.5 | 1774 | 2 | 2 | [21 empty] | 2 | [25 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_4-1A_P3 | PL10x303 | PLATE | 852 | A36 | 2 | 9.2 | 18.4 | 1 | 1 | [32 empty] | 1 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_4-1A_P4 | PL10x200 | PLATE | 794 | A36 | 14 | 8.5 | 119 | 7 | 7 | [32 empty] | 7 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-10-07
Plate | SDM_A5C_4-1A_P4A | PL10x200 | PLATE | 794 | A36 | 14 | 8.5 | 119 | 8 | 6 | [32 empty] | 6 | [6 empty] | 1 | 1 | [6 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-10-07
Plate | SDM_A5C_4-1A_P5 | PL16x137 | PLATE | 337 | A36 | 28 | 3.5 | 98 | 14 | 14 | [35 empty] | 14 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 56 | 14/08/2026
Plate | SDM_A5C_4-1C_P6 | PL10x2314 | Shell Plate | 11920 | A36 | 2 | 2165.5 | 4331 | 2 | 0 | [23 empty] | 3 | 4 | [22 empty] | #VALUE! | FED ABCG | PL10 | Thừa 5 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_4-1C_P7 | PL10x695 | PLATE | 2165 | A36 | 14 | 27.2 | 380.8 | 7 | 7 | [32 empty] | 6 | [6 empty] | 1 | [7 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-10-07
Plate | SDM_A5C_4-1C_P8 | PL15x110 | PLATE | 200 | A36 | 2 | 5.5 | 11 | 2 | 0 | [22 empty] | 1 | [12 empty] | 1 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 28/07/2026
Plate | SDM_A5C_4-1C_P9 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_4-1D_P6 | PL10x2314 | Shell Plate | 11920 | A36 | 2 | 2165.5 | 4331 | 2 | 0 | [23 empty] | 3 | 3 | [22 empty] | #VALUE! | ECG BFD | PL10 | Thừa 4 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_4-1D_P7 | PL10x695 | PLATE | 2165 | A36 | 14 | 27.2 | 380.8 | 7 | 7 | [32 empty] | 1 | [6 empty] | 6 | [7 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-10-07
Plate | SDM_A5C_4-1D_P8 | PL15x110 | PLATE | 200 | A36 | 2 | 5.5 | 11 | 2 | 0 | [22 empty] | 1 | [12 empty] | 1 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 28/07/2026
Plate | SDM_A5C_4-1D_P9 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Shape | SDM_A5C_5-0_D1 | 4" SCH.STD (OD114.3x6.02t) | Pipe | 812 | A53 Gr.B | 2 | 13.1 | 26.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 2 | 2026-12-06
Plate | SDM_A5C_5-0_P1 | PL10x6315 | Duct Plate | 9403 | A36 | 1 | 4302.9 | 4302.9 | 1 | 0 |  |  | 5 | [44 empty] | #VALUE! | ABCDE | PL10 | Thừa 4 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P10 | PL20x160 | LUG Plate | 320 | A36 | 2 | 7.6 | 15.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_5-0_P11 | PL15x110 | PAD Plate | 200 | A36 | 2 | 2.6 | 5.2 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_5-0_P12 | PL15x282 | Plate | 516 | A36 | 2 | 13.2 | 26.4 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_5-0_P13 | PL10x2020 | Ring Plate | 2260 | A36 | 1 | 58.4 | 58.4 | 1 | 0 |  |  |  | 3 | [43 empty] | #VALUE! | ABC | PL10 | Thừa 2 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P14 | PL20x2352 | Ring Plate | 2450 | A36 | 1 | 183.9 | 183.9 | 1 | 0 |  |  |  | 4 |  |  | 4 | [40 empty] | #VALUE! | ABCD ABCD | PL20 | Thừa 7 | MCC | A320-SDM-PC-013 | PL20 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P15 | PL10x400 | PAD Plate | 2338 | A36 | 1 | 73.4 | 73.4 | 1 | 0 | [46 empty] | 1 | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_5-0_P16 | PL20x180 | Plate | 254 | A36 | 2 | 7.2 | 14.4 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_5-0_P17 | PL10x240 | Plate | 400 | A36 | 1 | 7.5 | 7.5 | 1 | 0 |  | 1 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_5-0_P18 | PL3x230 | Plate | 390 | AISI304 | 1 | 2.12 | 2.12 | 1 | 0 |  |  |  |  | 2 | [41 empty] | -1 | #VALUE! | Đã trả lại FAC1 1 cái ngày 14/09 | PL3 |  | MCC | A320-SDM-PC-004 | PL3 | A320-01-CP004 | 1 | 13/06/2026
Plate | SDM_A5C_5-0_P19 | PL15x320 | Plate | 3750 | A36 | 2 | 141.3 | 282.6 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_5-0_P2 | PL10x1893 | Duct Plate | 6086 | A36 | 1 | 987.1 | 987.1 | 1 | 0 | [7 empty] | 2 | [39 empty] | #VALUE! | AB | PL10 | Thừa 1 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P20 | PL10x1636 | Plate | 2260 | A36 | 1 | 40.9 | 40.9 | 1 | 0 |  |  |  | 2 | [43 empty] | #VALUE! | AB | PL10 | Thừa 1 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P21 | PL10x213 | Plate | 969 | A36 | 1 | 8.8 | 8.8 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_5-0_P22 | PL16x129 | Plate | 289 | A36 | 2 | 2.7 | 5.4 | 2 | 0 | [12 empty] | 2 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 2 | 13/06/2026
Plate | SDM_A5C_5-0_P23 | PL10x2156 | Ring Plate | 2260 | A36 | 1 | 62.4 | 62.4 | 1 | 0 | [46 empty] | 1 | #VALUE! |  | PL10
Plate | SDM_A5C_5-0_P3 | PL10x1636 | Ring Plate | 2260 | A36 | 1 | 46.7 | 46.7 | 1 | 0 |  |  |  | 2 | [43 empty] | #VALUE! | AB | PL10 | Thừa 1 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P4 | PL10x228 | Ring Plate | 969 | A36 | 1 | 10 | 10 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Plate | SDM_A5C_5-0_P5 | PL15x300 | Plate | 516 | A36 | 1 | 14.3 | 14.3 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_5-0_P6 | PL15x320 | Plate | 3516 | A36 | 2 | 132.5 | 265 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_5-0_P7 | PL10x2156 | Ring Plate | 2260 | A36 | 1 | 54.7 | 54.7 | 1 | 0 |  |  |  | 3 | [43 empty] | #VALUE! | ABC | PL10 | Thừa 2 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_5-0_P8 | PL10x310 | Plate | 852 | A36 | 2 | 9.3 | 18.6 | 2 | 0 |  | 2 | [45 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 2 | 2026-03-07
Plate | SDM_A5C_5-0_P9 | PL16x143 | Plate | 275 | A36 | 4 | 3 | 12 | 4 | 0 | [12 empty] | 4 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 4 | 13/06/2026
Shape | SDM_A5C_5-1_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 4 | 13.057 | 52.2278 | 2 | 2 | [33 empty] | 2 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 8 | 28/07/2026
Plate | SDM_A5C_5-1_P1 | PL10x6315 | Shell Plate | 9403 | A36 | 2 | 4302.9 | 8605.8 | 2 | 0 | [28 empty] | 5 | [18 empty] | #VALUE! | EABCD | PL10 | Thừa 3 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_5-1_P10 | PL10x240 | PLATE | 400 | A36 | 2 | 7.5 | 15 | 2 | 0 | [32 empty] | 1 | [7 empty] | 1 | [6 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_5-1_P11 | PL3x230 | PLATE | 390 | AISI304 | 2 | 2.1 | 4.2 | 0 | 2 | [47 empty] | #VALUE! |  | PL3 |  | MCC | A320-SDM-PC-004 | PL3 | A320-01-CP004 A320-11-CP004 A320-21-CP004 | 4 | 28/07/2026
Plate | SDM_A5C_5-1_P12 | PL10x310 | PLATE | 852 | A36 | 4 | 9.3 | 37.2 | 2 | 2 | [32 empty] | 2 | [14 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-10-07
Plate | SDM_A5C_5-1_P13 | PL16x129 | PLATE | 301 | A36 | 4 | 3 | 12 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 8 | 14/08/2026
Plate | SDM_A5C_5-1_P14 | PL15x320 | PLATE | 3750 | A36 | 4 | 141.3 | 565.2 | 2 | 2 | [21 empty] | 2 | [25 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_5-1_P15 | PL16x129 | PLATE | 289 | A36 | 4 | 2.7 | 10.8 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 8 | 14/08/2026
Plate | SDM_A5C_5-1_P16 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 1 | 1 | [31 empty] | 1 | [15 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_5-1_P17 | PL15x110 | PLATE | 200 | A36 | 2 | 5.5 | 11 | 2 | 0 | [22 empty] | 1 | [12 empty] | 1 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 28/07/2026
Plate | SDM_A5C_5-1_P2 | PL10x2199 | Shell Plate | 6061 | A36 | 2 | 862.7 | 1725.4 | 2 | 0 | [30 empty] | 2 | [16 empty] | #VALUE! | AB | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_5-1_P3 | PL10x2156 | PLATE | 2260 | A36 | 4 | 62.4 | 249.6 | 4 | 0 | [32 empty] | 2 | [6 empty] | 4 | [7 empty] | #VALUE! | 2C2A2B | PL10 | Thừa 2 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 8
Plate | SDM_A5C_5-1_P4 | PL10x2156 | PLATE | 2260 | A36 | 4 | 54.7 | 218.8 | 4 | 0 | [32 empty] | 1 | [6 empty] | 5 | [7 empty] | #VALUE! | C2A2BC | PL10 | Thừa 2 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 8
Plate | SDM_A5C_5-1_P5 | PL15x320 | PLATE | 3516 | A36 | 4 | 132.5 | 530 | 4 | 0 | [22 empty] | 2 | [12 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_5-1_P6 | PL10x2260 | PLATE | 2260 | A36 | 2 | 63.3 | 126.6 | 2 | 0 | [39 empty] | 3 | [7 empty] | #VALUE! | ABC | PL10 | Thừa 1 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_5-1_P7 | PL20x2352 | PLATE | 2450 | A36 | 2 | 183.9 | 367.8 | 2 | 0 | [31 empty] | 4 | [15 empty] | #VALUE! | ABCD | PL20 | Thừa 2 | MCC | A320-SDM-PC-013 | PL20 | chi tiết chia nối | 4
Plate | SDM_A5C_5-1_P8 | PL10x400 | PLATE | 2338 | A36 | 2 | 73.4 | 146.8 | 1 | 1 | [38 empty] | 1 | [8 empty] | #VALUE! |  | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-10-07
Plate | SDM_A5C_5-1_P9 | PL20x180 | PLATE | 254 | A36 | 4 | 7.2 | 28.8 | 2 | 2 | [31 empty] | 2 | [15 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Shape | SDM_A5C_6-0_D1 | 4" SCH.STD (OD114.3x6.02t) | Pipe | 812 | A53 Gr.B | 5 | 13.1 | 65.5 | 5 | 0 | [5 empty] | 5 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 5 | 2026-12-06
Plate | SDM_A5C_6-0_P1 | PL8x3583 | Duct Plate | 3797 | A36 | 1 | 854.3 | 854.3 | 1 | 0 |  |  | 2 | [44 empty] | #VALUE! | AB | PL8 | Thừa 1 | PMC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P10 | PL15x198 | Plate | 520 | A36 | 2 | 7.8 | 15.6 | 2 | 0 | 2 | [46 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_6-0_P11 | PL15x320 | Plate | 11512 | A36 | 2 | 433.8 | 867.6 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_6-0_P12 | PL16x99 | Plate | 174 | A36 | 4 | 1.3 | 5.2 | 4 | 0 | [12 empty] | 4 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 4 | 13/06/2026
Plate | SDM_A5C_6-0_P13 | PL16x99 | Plate | 182 | A36 | 2 | 1.4 | 2.8 | 2 | 0 | [12 empty] | 2 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 2 | 13/06/2026
Plate | SDM_A5C_6-0_P14 | PL16x130 | Plate | 301 | A36 | 4 | 3 | 12 | 4 | 0 | [12 empty] | 4 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 4 | 13/06/2026
Plate | SDM_A5C_6-0_P15 | PL15x282 | Plate | 516 | A36 | 1 | 13.2 | 13.2 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_6-0_P16 | PL20x160 | LUG Plate | 320 | A36 | 2 | 7.6 | 15.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_6-0_P17 | PL15x110 | PAD Plate | 220 | A36 | 2 | 2.6 | 5.2 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_6-0_P2 | PL10x3786 | Duct Plate | 5291 | A36 | 1 | 1214.4 | 1214.4 | 1 | 0 | [7 empty] | 2 |  |  |  |  | 1 | [34 empty] | #VALUE! | CBA | PL10 | Thừa 2 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P3 | PL10x4264 | Duct Plate | 5462 | A36 | 1 | 1828.4 | 1828.4 | 1 | 0 |  |  | 3 | [44 empty] | #VALUE! | ABC | PL10 | Thừa 2 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P4 | PL8x1482 | Ring Plate | 1616 | A36 | 2 | 27.4 | 54.8 | 2 | 0 | [10 empty] | 4 | [36 empty] | #VALUE! | 2A2B | PL8 | Thừa 2 | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 2
Plate | SDM_A5C_6-0_P5 | PL8x1482 | Ring Plate | 1616 | A36 | 1 | 24.2 | 24.2 | 1 | 0 | [10 empty] | 2 | [36 empty] | #VALUE! | AB | PL8 | Thừa 1 | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P6 | PL10x2156 | Ring Plate | 2260 | A36 | 1 | 62.4 | 62.4 | 1 | 0 |  |  |  | 3 | [43 empty] | #VALUE! | ABC | PL10 | Thừa 2 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P7 | PL10x2156 | Ring Plate | 2260 | A36 | 1 | 54.6 | 54.6 | 1 | 0 |  |  |  | 3 | [43 empty] | #VALUE! | ABC | PL10 | Thừa 2 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P8 | PL10x2045 | Ring Plate | 2825 | A36 | 1 | 63.9 | 63.9 | 1 | 0 |  |  |  | 2 | [43 empty] | #VALUE! | AB | PL10 | Thừa 1 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 1
Plate | SDM_A5C_6-0_P9 | PL10x266 | Ring Plate | 1211 | A36 | 1 | 13.8 | 13.8 | 1 | 0 |  |  |  | 1 | [43 empty] | #VALUE! |  | PL10 |  | MCC | A320-SDM-PC-009 | PL10 | A320-01-CP008 | 1 | 2026-03-07
Shape | SDM_A5C_6-1_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 10 | 13.057 | 130.5696 | 5 | 5 | [33 empty] | 5 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 20 | 28/07/2026
Plate | SDM_A5C_6-1_P1 | PL8x3583 | Shell Plate | 11647 | A36 | 2 | 854.3 | 1708.6 | 0 | 2 | [47 empty] | #VALUE! |  | PL8 |  | PMC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 4
Plate | SDM_A5C_6-1_P10 | PL16x98 | PLATE | 182 | A36 | 12 | 1.4 | 16.8 | 6 | 6 | [35 empty] | 6 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 14/08/2026
Plate | SDM_A5C_6-1_P11 | PL15x110 | PLATE | 200 | A36 | 4 | 5.5 | 22 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_6-1_P12 | PL20x160 | PLATE | 320 | A36 | 4 | 7.6 | 30.4 | 2 | 2 | [31 empty] | 2 | [15 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_6-1_P13 | PL16x98 | PLATE | 182 | A36 | 10 | 1.4 | 14 | 5 | 5 | [35 empty] | 5 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 20 | 14/08/2026
Plate | SDM_A5C_6-1_P2 | PL10x3788 | Shell Plate | 5374 | A36 | 2 | 1229 | 2458 | 1 | 1 | [30 empty] | 1 | [16 empty] | #VALUE! | C | PL10 |  | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_6-1_P3 | PL10x4264 | Shell Plate | 5462 | A36 | 2 | 1828.1 | 3656.2 | 2 | 0 | [28 empty] | 3 | [18 empty] | #VALUE! | ABC | PL10 | Thừa 1 | PMC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_6-1_P4 | PL15x320 | PLATE | 11512 | A36 | 4 | 433.8 | 1735.2 | 2 | 2 | [21 empty] | 2 | [25 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_6-1_P5 | PL8x1481 | PLATE | 1616 | A36 | 4 | 27.4 | 109.6 | 0 | 4 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 8
Plate | SDM_A5C_6-1_P6 | PL8x1481 | PLATE | 1616 | A36 | 2 | 24.2 | 48.4 | 0 | 2 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 4
Plate | SDM_A5C_6-1_P7 | PL10x2156 | PLATE | 2260 | A36 | 2 | 62.4 | 124.8 | 2 | 0 | [32 empty] | 1 | [6 empty] | 2 | [7 empty] | #VALUE! | CAB | PL10 | Thừa 1 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 4
Plate | SDM_A5C_6-1_P8 | PL10x2156 | PLATE | 2260 | A36 | 4 | 54.6 | 218.4 | 4 | 0 | [32 empty] | 3 | [6 empty] | 3 | 2 | [6 empty] | #VALUE! | A2CA2B2C | PL10 | Thừa 4 | MCC | A320-SDM-PC-009 | PL10 | chi tiết chia nối | 8
Plate | SDM_A5C_6-1_P9 | PL16x129 | PLATE | 301 | A36 | 8 | 3 | 24 | 4 | 4 | [35 empty] | 4 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 16 | 14/08/2026
Shape | SDM_A5C_7-0_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 5 | 13.057 | 65.2848 | 5 | 0 | [5 empty] | 5 | [41 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 | 5 | 2026-12-06
Plate | SDM_A5C_7-0_P1 | PL8x3583 | Shell Plate | 11647 | A36 | 1 | 2620.5 | 2620.5 | 1 | 0 |  |  | 7 | [44 empty] | #VALUE! | ABCDEFG | PL8 | Thừa 6 | PMC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 1
Plate | SDM_A5C_7-0_P10 | PL15x341 | PLATE | 609 | A36 | 2 | 16.8 | 33.6 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_7-0_P11 | PL16x98 | PLATE | 182 | A36 | 10 | 1.4 | 14 | 10 | 0 | [12 empty] | 10 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 10 | 13/06/2026
Plate | SDM_A5C_7-0_P12 | PL15x306 | PLATE | 520 | A36 | 1 | 14.1 | 14.1 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_7-0_P13 | PL15x363 | PLATE | 554 | A36 | 1 | 18.4 | 18.4 | 1 | 0 |  |  |  |  | 1 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 1 | 2026-03-07
Plate | SDM_A5C_7-0_P14 | PL8x1078 | PLATE | 1616 | A36 | 2 | 18.1 | 36.2 | 2 | 0 | [10 empty] | 4 | [36 empty] | #VALUE! | 2A2B | PL8 | Thừa 2 | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 2
Plate | SDM_A5C_7-0_P15 | PL8x129 | PLATE | 503 | A36 | 2 | 2.9 | 5.8 | 2 | 0 | [10 empty] | 2 | [36 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | A320-01-CP007 | 2 | 2026-03-07
Plate | SDM_A5C_7-0_P16 | PL20x160 | PLATE | 320 | A36 | 2 | 7.6 | 15.2 | 2 | 0 | [5 empty] | 2 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 2 | 2026-08-08
Plate | SDM_A5C_7-0_P17 | PL15x110 | PLATE | 200 | A36 | 2 | 2.6 | 5.2 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_7-0_P2 | PL15x320 | PLATE | 11547 | A36 | 2 | 435.1 | 870.2 | 2 | 0 |  |  |  |  | 2 | [42 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 | 2 | 2026-03-07
Plate | SDM_A5C_7-0_P3 | PL20x1456 | PLATE | 1677 | A36 | 1 | 323.1 | 323.1 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Plate | SDM_A5C_7-0_P4 | PL16x120 | PLATE | 630 | A36 | 3 | 9.3 | 27.9 | 3 | 0 | [12 empty] | 3 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 3 | 13/06/2026
Plate | SDM_A5C_7-0_P5 | PL20x275 | PLATE | 1100 | A36 | 1 | 47.5 | 47.5 | 1 | 0 | [5 empty] | 1 | [41 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 | 1 | 2026-08-08
Plate | SDM_A5C_7-0_P6 | PL5x190 | PLATE | 255 | AISI304 | 2 | 1.9 | 3.8 | 2 | 0 | [14 empty] | 2 | [32 empty] | #VALUE! |  | PL5 |  | MCC | A320-SDM-PC-005 | PL5 | A320-01-CP006 | 2 | 13/06/2026
Plate | SDM_A5C_7-0_P7 | PL16x80 | PLATE | 325 | A36 | 1 | 3.3 | 3.3 | 1 | 0 | [12 empty] | 1 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 1 | 13/06/2026
Plate | SDM_A5C_7-0_P7A | PL16x80 | PLATE | 325 | A36 | 1 | 3.3 | 3.3 | 1 | 0 | [12 empty] | 1 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 1 | 13/06/2026
Plate | SDM_A5C_7-0_P8 | PL16x80 | PLATE | 100 | A36 | 1 | 0.8 | 0.8 | 1 | 0 | [12 empty] | 1 | [34 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 | 1 | 13/06/2026
Plate | SDM_A5C_7-0_P9 | PL8x1616 | PLATE | 1616 | A36 | 3 | 24.2 | 72.6 | 3 | 0 | [10 empty] | 6 | [36 empty] | #VALUE! | 3A3B | PL8 | Thừa 3 | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 3
Shape | SDM_A5C_7-1_D1 | 4" SCH.STD (OD114.3x6.02t) | PIPE | 812 | A53 Gr.B | 10 | 13.057 | 130.5696 | 5 | 5 | [33 empty] | 5 | [13 empty] | #VALUE! |  |  |  | MCC | A320-SDM-PC-502 | 4" SCH.STD (OD114.3x6.02t) | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 20 | 28/07/2026
Plate | SDM_A5C_7-1_P1 | PL8x3583 | Shell Plate | 11647 | A36 | 2 | 2620.5 | 5241 | 2 | 0 | [45 empty] | 3 |  | #VALUE! | DFC | PL8 | Thừa 1 | PMC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 4
Plate | SDM_A5C_7-1_P10 | PL15x341 | PLATE | 609 | A36 | 4 | 16.8 | 67.2 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_7-1_P11 | PL16x98 | PLATE | 182 | A36 | 20 | 1.4 | 28 | 10 | 10 | [35 empty] | 10 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 40 | 14/08/2026
Plate | SDM_A5C_7-1_P12 | PL15x110 | PLATE | 200 | A36 | 4 | 5.5 | 22 | 2 | 2 | [35 empty] | 2 | [11 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_7-1_P13 | PL20x160 | PLATE | 320 | A36 | 4 | 7.6 | 30.4 | 2 | 2 | [31 empty] | 2 | [15 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08
Plate | SDM_A5C_7-1_P2 | PL15x320 | PLATE | 11547 | A36 | 4 | 435.1 | 1740.4 | 2 | 2 | [21 empty] | 2 | [25 empty] | #VALUE! |  | PL15 |  | MCC | A320-SDM-PC-011 | PL15 | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 28/07/2026
Plate | SDM_A5C_7-1_P3 | PL20x1456 | PLATE | 1677 | A36 | 2 | 323.1 | 646.2 | 1 | 1 | [31 empty] | 1 | [15 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_7-1_P4 | PL16x120 | PLATE | 630 | A36 | 6 | 9.3 | 55.8 | 3 | 3 | [35 empty] | 3 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 12 | 14/08/2026
Plate | SDM_A5C_7-1_P5 | PL20x275 | PLATE | 1100 | A36 | 2 | 47.5 | 95 | 1 | 1 | [31 empty] | 1 | [15 empty] | #VALUE! |  | PL20 |  | MCC | A320-SDM-PC-013 | PL20 | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08
Plate | SDM_A5C_7-1_P6 | PL5x190 | PLATE | 255 | AISI304 | 4 | 1.9 | 7.6 | 0 | 4 | [47 empty] | #VALUE! |  | PL5 |  | MCC | A320-SDM-PC-005 | PL5 | A320-01-CP006 A320-11-CP006 A320-21-CP006 | 8 | 2026-10-07
Plate | SDM_A5C_7-1_P7 | PL16x80 | PLATE | 325 | A36 | 2 | 3.3 | 6.6 | 1 | 1 | [34 empty] | 1 | [12 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 4 | 14/08/2026
Plate | SDM_A5C_7-1_P7A | PL16x80 | PLATE | 325 | A36 | 2 | 3.3 | 6.6 | 1 | 1 | [34 empty] | 1 | [12 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 4 | 14/08/2026
Plate | SDM_A5C_7-1_P8 | PL16x80 | PLATE | 100 | A36 | 2 | 0.8 | 1.6 | 1 | 1 | [35 empty] | 1 | [11 empty] | #VALUE! |  | PL16 |  | MCC | A320-SDM-PC-012 | PL16 | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 4 | 14/08/2026
Plate | SDM_A5C_7-1_P9 | PL8x1616 | PLATE | 1616 | A36 | 10 | 24.2 | 242 | 0 | 10 | [47 empty] | #VALUE! |  | PL8 |  | MCC | A320-SDM-PC-008 | PL8 | chi tiết chia nối | 20

## A320M4130
ASSEMBLY PART LIST
Project name / Tên Dự án : Kuo Kuang Combined Cycle Power Plant Unit 2
Item Name / Tên Hạng mục : M4130 & M4131 - Steam Distribution Manifold (SDM)
Contract No. / Số Hợp đồng : A320 |  | A320M4130 | [74 empty] | chi tiết chia nối
Prepared By / Chuẩn bị : Design Consultant Center 2 | [30 empty] | CHECK |  |  |  |  | CHECK |  |  |  |  | CHECK |  |  |  |  | CHECK
Document No. / Số Tài liệu : A320-01-APL-002 | [7 empty] | Rev./ Số Sửa đổi: 11 | [13 empty] | 15641.5 | #REF! | [5 empty] | Date: 17-Aug-2026 |  | STR11 |  |  |  |  | STR13 |  |  |  |  | STR16 |  |  |  |  | STR18 | [11 empty] | Content Rev. | [10 empty] | Type Fabrication | [6 empty] | Type
DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | AM2 | DCC | DCC | DCC | DCC | DCC | DCC | L1 | L1 | L1 | L1 | L1 | L2 | L2 | L2 | L2 | L2 | L3 | L3 | L3 | L3 | L3 | L4 | L4 | L4 | L4 | L4 | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC-F | DCC-X | DCC-Y | DCC-Z | DCC-J | DCC-BH | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC
No. | Drawing Number | Assembly No. | Description |  |  | Size | Length | Material | Q'ty | Set | T.Q'ty | U.Weight | T.Weight | Scope of Steel Work | Chung loai | Dang | Phan giao to | Ngay giao | Da nhan | Con thieu | Lam tron | Dong bo | Ti le dong bo | Fitup | Inspection | Clear | Loose Part | LOT | Remark | AS Symbol | Scope of Steel Work LOT 1 | SL L1 | T'Qty L1 | Da nhan | Con thieu | Scope of Steel Work LOT 2 | SL L2 | T'L2 | Da nhan | Con thieu | Scope of Steel Work LOT 3 | SL L3 | T'L3 | Da nhan | Con thieu | Scope of Steel Work LOT 4 | SL L4 | T'L4 | Da nhan | Con thieu | Loose Part | Scope of Steel Work LOT 1 | Scope of Steel Work LOT 2 | Scope of Steel Work LOT 3 | Scope of Steel Work LOT 4 | Delivery item | Scope of Painting Work | Rev.1 (30/05/2026) | Rev.2 (05/06/2026) | Rev.3 (13/06/2026) | Rev.4 (19/06/2026) | Rev.5 (22/06/2026) | Rev.6 (09/07/2026) | Rev.7 (15/07/2026) | Rev.8 (31/07/2026) | Rev.9 (04/08/2026) | Rev.10 (04/08/2026) | Rev.10 (17/08/2026) | Khoan Lỗ | Lốc tròn (Uốn cong) | Sấn | Vát mép & Cắt miệng | Gia công cơ khí (Không thay đổi chiều dày) | Gia công cơ khí (Có thay đổi chiều dày) | Tổ hợp | Fabrication or Purchasing | Cutting No. | Q'TY | Date Issue | Cutting No. | Q'TY | Date Issue | Remain (T'Qty-Q'Ty)
1 | 2 | 3 | 4 | 5A (Marking as Dwg.) | 5A (Marking as Dwg.) | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [5 empty] | 20 | 21 | 22 | 23 | 24 |  |  |  | 14 |  | 18 | 19 | [20 empty] | 14 | 15A | 15B | 15C | 15D | 20 | 29 | 30A | 30B | 30C | 30D | 30E | 30F | 30G | 30H | 30I | 30K | 30L | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 44 | 45 | 46 | 47 | 48 | 49 | 50
177 | 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.0 | SPOOL_5C_SPOOL_1.0 |  |  | 8616xx3711x3625 |  |  |  | 1 |  | 8672 | 8672 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | -
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A |  |  |  | 8616xx2365x754 |  |  |  | 1 |  | 2279.3 | 2279.3 | AMC2 | [7 empty] | 0 | 0.64957 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | Shell Plate | P1 | SDM_A5C_1-0A_P1 | PL12x2366 | 8216 | A36 | 1 | 1 | 1 | 1195.8 | 1195.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P2 | SDM_A5C_1-0A_P2 | PL15x360 | 7926 | A36 | 2 | 1 | 2 | 336 | 672 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P3 | SDM_A5C_1-0A_P3 | PL10x180 | 2343 | A36 | 1 | 1 | 1 | 33.1 | 33.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P4 | SDM_A5C_1-0A_P4 | PL20x678 | 2308 | A36 | 1 | 1 | 1 | 83.6 | 83.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P5 | SDM_A5C_1-0A_P5 | PL20x200 | 1100 | A36 | 1 | 1 | 1 | 34.5 | 34.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P6 | SDM_A5C_1-0A_P6 | PL10x287 | 852 | A36 | 1 | 1 | 1 | 8.9 | 8.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P7 | SDM_A5C_1-0A_P7 | PL5x180 | 190 | AISI304 | 2 | 1 | 2 | 1.3 | 2.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP006 | 2 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P8 | SDM_A5C_1-0A_P8 | PL12x80 | 300 | A36 | 4 | 1 | 4 | 2.3 | 9.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PIPE | P9 | SDM_A5C_1-0A_P9 | PL12x80 | 231 | A36 | 2 | 1 | 2 | 1.7 | 3.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P10 | SDM_A5C_1-0A_P10 | PL10x308 | 332 | A36 | 2 | 1 | 2 | 5.1 | 10.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P11 | SDM_A5C_1-0A_P11 | PL12x206 | 787 | A36 | 4 | 1 | 4 | 11.6 | 46.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 8->4 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P11A | SDM_A5C_1-0A_P11A | PL12x206 | 787 | A36 | 4 | 1 | 4 | 11.6 | 46.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, P11A tách từ P11 |  | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PLATE | P12 | SDM_A5C_1-0A_P12 | PL16x154 | 460 | A36 | 8 | 1 | 8 | 5.5 | 44 | AMC2 | Plate | MCC |  |  | 8 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 8 | 8 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 8 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PIPE | D1 | SDM_A5C_1-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 4 | 1 | 4 | 13.057 | 52.2278 | AMC2 | Shape | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 4 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.A | PIPE | D2 | SDM_A5C_1-0A_D2 | 1/2" SCH.STD (OD21.3x2.77t) | 737 | A53 Gr.B | 2 | 1 | 2 | 2.1 | 4.2 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  | Modify, Mark D1->D2 | [9 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP501 | 2 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D |  |  |  | 8516xx854x2365 |  |  |  | 1 |  | 2184.2 | 2184.2 | AMC2 | [7 empty] | 0 | 0.8254 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | Shell Plate | P13 | SDM_A5C_1-0D_P13 | PL12x2366 | 8216 | A36 | 1 | 1 | 1 | 1830.9 | 1830.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P14 | SDM_A5C_1-0D_P14 | PL20x563 | 2308 | A36 | 1 | 1 | 1 | 45.5 | 45.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, PL12->20 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP020 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P15 | SDM_A5C_1-0D_P15 | PL12x603 | 2365 | A36 | 4 | 1 | 4 | 37.7 | 150.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PIPE | P16 | SDM_A5C_1-0D_P16 | PL10x221 | 1885 | A36 | 1 | 1 | 1 | 32.7 | 32.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP021 | 1 | 2026-06-30 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PIPE | P17 | SDM_A5C_1-0D_P17 | PL10x243 | 2202 | A36 | 1 | 1 | 1 | 42 | 42 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP021 | 1 | 2026-06-30 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | PA1 | SDM_A5C_1-0D_PA1 | PL10x1071 | 1095 | A36 | 1 | 1 | 1 | 40.8 | 40.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P18 | SDM_A5C_1-0D_P18 | PL10x180 | 536 | A36 | 1 | 1 | 1 | 7.5 | 7.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P19 | SDM_A5C_1-0D_P19 | PL10x301 | 302 | A36 | 2 | 1 | 2 | 4.6 | 9.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P20 | SDM_A5C_1-0D_P20 | PL10x163 | 221 | A36 | 1 | 1 | 1 | 1.7 | 1.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P21 | SDM_A5C_1-0D_P21 | PL15x417 | 875 | A36 | 1 | 1 | 1 | 27.8 | 27.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PLATE | P22 | SDM_A5C_1-0D_P22 | PL15x363 | 793 | A36 | 1 | 1 | 1 | 22.8 | 22.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | PIPE | D2 | SDM_A5C_1-0D_D2 | 1/2" SCH.STD (OD21.3x2.77t) | 737 | A53 Gr.B | 5 | 1 | 5 | 2.1 | 10.5 | AMC2 | Shape | PMC |  |  | 5 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 5 | 5 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  | Modify, Mark D1->D2 | [9 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP501 | 5 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.D | HALF COUPLING | M1 | SDM_A5C_1-0D_M1 | RB50 | 48 | A36 | 1 | 1 | 1 | 0.32 | 0.32 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  |  | Modify, Profile: 1" HALFCOUPLING->RB50 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-01-CP508 | 1 | 2026-06-30 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.C |  |  |  | 8516xx2365x786 |  |  |  | 1 |  | 2092.3 | 2092.3 | AMC2 | [7 empty] | 1 | 0.93333 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.C | Shell Plate | P23 | SDM_A5C_1-0C_P23 | PL12x2366 | 8216 | A36 | 1 | 1 | 1 | 1830.9 | 1830.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.C | PLATE | P15 | SDM_A5C_1-0C_P15 | PL12x603 | 2365 | A36 | 4 | 1 | 4 | 37.7 | 150.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 5->4 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.C | PLATE | P24 | SDM_A5C_1-0C_P24 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.C | PLATE | P25 | SDM_A5C_1-0C_P25 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.C | PLATE | P30 | SDM_A5C_1-0C_P30 | PL20x603 | 2365 | A36 | 1 | 1 | 1 | 62.7 | 62.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | ADDED, cắt mới bổ sung | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP020 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B |  |  |  | 8516xx796x2365 |  |  |  | 1 |  | 2116.2 | 2116.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | Shell Plate | P23 | SDM_A5C_1-0B_P23 | PL12x2366 | 8216 | A36 | 1 | 1 | 1 | 1830.9 | 1830.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P14 | SDM_A5C_1-0B_P14 | PL20x563 | 2308 | A36 | 1 | 1 | 1 | 45.5 | 45.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, PL12->20 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP020 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P15 | SDM_A5C_1-0B_P15 | PL12x603 | 2365 | A36 | 2 | 1 | 2 | 37.7 | 75.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P18 | SDM_A5C_1-0B_P18 | PL10x180 | 536 | A36 | 2 | 1 | 2 | 7.5 | 15 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P26 | SDM_A5C_1-0B_P26 | PL12x222 | 983 | A36 | 2 | 1 | 2 | 14.1 | 28.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P27 | SDM_A5C_1-0B_P27 | PL12x235 | 1061 | A36 | 2 | 1 | 2 | 15.3 | 30.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P28 | SDM_A5C_1-0B_P28 | PL15x313 | 546 | A36 | 2 | 1 | 2 | 16.3 | 32.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.16 | 24D06641-00-M4130#A5C_1.B | PLATE | P29 | SDM_A5C_1-0B_P29 | PL15x351 | 784 | A36 | 1 | 1 | 1 | 21.8 | 21.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
178 | 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.0 | SPOOL_5C_SPOOL_2.0 |  |  | 11621xx3464x3409 |  |  |  | 1 |  | 10433.7 | 10433.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | -
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A |  |  |  | 11621xx2149x443 |  |  |  | 1 |  | 2300 | 2300 | AMC2 | [7 empty] | 0 | 0.61404 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P1 | SDM_A5C_2-0A_P1 | PL12x418 | 4023 | A36 | 2 | 1 | 2 | 182.2 | 364.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 2 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P2 | SDM_A5C_2-0A_P2 | PL12x618 | 1930 | A36 | 1 | 1 | 1 | 98 | 98 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 2->1 |  | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 | 2 | 2026-06-13 |  |  |  | -1
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P2A | SDM_A5C_2-0A_P2A | PL12x618 | 1930 | A36 | 1 | 1 | 1 | 98 | 98 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, P2A tách từ P2 | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P3 | SDM_A5C_2-0A_P3 | PL12x618 | 5608 | A36 | 1 | 1 | 1 | 326.2 | 326.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P3A | SDM_A5C_2-0A_P3A | PL12x618 | 5608 | A36 | 1 | 1 | 1 | 326.2 | 326.2 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | PLATE | P4 | SDM_A5C_2-0A_P4 | PL15x320 | 11521 | A36 | 2 | 1 | 2 | 434.1 | 868.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | PLATE | P5 | SDM_A5C_2-0A_P5 | PL16x146 | 400 | A36 | 6 | 1 | 6 | 4.5 | 27 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 6 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | PLATE | P6 | SDM_A5C_2-0A_P6 | PL16x154 | 460 | A36 | 6 | 1 | 6 | 5.5 | 33 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 6 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | PLATE | P7 | SDM_A5C_2-0A_P7 | PL12x160 | 506 | A36 | 6 | 1 | 6 | 6.5 | 39 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 6 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | PLATE | P8 | SDM_A5C_2-0A_P8 | PL12x192 | 645 | A36 | 6 | 1 | 6 | 9.6 | 57.6 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 6 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.A | PIPE | D1 | SDM_A5C_2-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 6 | 1 | 6 | 13.057 | 78.3418 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 6 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.D |  |  |  | 11521xx844x2593 |  |  |  | 1 |  | 2888.1 | 2888.1 | AMC2 | [7 empty] | 0 | 0.7037 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.D | Shell Plate | P9 | SDM_A5C_2-0D_P9 | PL12x2279.4 | 4023 | A36 | 1 | 1 | 1 | 863.8 | 863.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.D | Shell Plate | P10 | SDM_A5C_2-0D_P10 | PL12x1956 | 2635 | A36 | 1 | 1 | 1 | 441.5 | 441.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.D | Shell Plate | P11 | SDM_A5C_2-0D_P11 | PL12x2628.5 | 5608 | A36 | 1 | 1 | 1 | 1388.4 | 1388.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.D | PLATE | P12 | SDM_A5C_2-0D_P12 | PL12x609 | 2225 | A36 | 3 | 1 | 3 | 31.8 | 95.4 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.D | PLATE | P13 | SDM_A5C_2-0D_P13 | PL12x700 | 2562 | A36 | 3 | 1 | 3 | 41.9 | 125.7 | AMC2 | Plate | PMC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C |  |  |  | 11521xx2149x1051 |  |  |  | 1 |  | 2335.2 | 2335.2 | AMC2 | [7 empty] | 0 | 0.69231 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | Shell Plate | P14 | SDM_A5C_2-0C_P14 | PL12x1823 | 4023 | A36 | 1 | 1 | 1 | 690.9 | 690.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | Shell Plate | P15 | SDM_A5C_2-0C_P15 | PL12x1997 | 2103 | A36 | 1 | 1 | 1 | 358.1 | 358.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | Shell Plate | P16 | SDM_A5C_2-0C_P16 | PL12x2102.7 | 5608 | A36 | 1 | 1 | 1 | 1110.3 | 1110.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | PLATE | P17 | SDM_A5C_2-0C_P17 | PL12x447 | 1867 | A36 | 3 | 1 | 3 | 25.4 | 76.2 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | PLATE | P18 | SDM_A5C_2-0C_P18 | PL12x514 | 2149 | A36 | 3 | 1 | 3 | 33.5 | 100.5 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | PLATE | P19 | SDM_A5C_2-0C_P19 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.C | PLATE | P20 | SDM_A5C_2-0C_P20 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B |  |  |  | 11521xx970x2593 |  |  |  | 1 |  | 2910.4 | 2910.4 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | Shell Plate | P9 | SDM_A5C_2-0B_P9 | PL12x2279.4 | 4023 | A36 | 1 | 1 | 1 | 863.8 | 863.8 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | Shell Plate | P10 | SDM_A5C_2-0B_P10 | PL12x1956 | 2635 | A36 | 1 | 1 | 1 | 441.5 | 441.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | Shell Plate | P11 | SDM_A5C_2-0B_P11 | PL12x2628.5 | 5608 | A36 | 1 | 1 | 1 | 1388.4 | 1388.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P12 | SDM_A5C_2-0B_P12 | PL12x609 | 2225 | A36 | 1 | 1 | 1 | 31.8 | 31.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P13 | SDM_A5C_2-0B_P13 | PL12x700 | 2562 | A36 | 2 | 1 | 2 | 41.9 | 83.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P21 | SDM_A5C_2-0B_P21 | PL12x218 | 1011 | A36 | 2 | 1 | 2 | 12.8 | 25.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P22 | SDM_A5C_2-0B_P22 | PL12x208 | 951 | A36 | 2 | 1 | 2 | 12 | 24 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P23 | SDM_A5C_2-0B_P23 | PL15x293 | 530 | A36 | 2 | 1 | 2 | 14.5 | 29 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P24 | SDM_A5C_2-0B_P24 | PL12x243 | 1122 | A36 | 1 | 1 | 1 | 16.2 | 16.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P25 | SDM_A5C_2-0B_P25 | PL12x256 | 1198 | A36 | 1 | 1 | 1 | 17.4 | 17.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.18 | 24D06641-00-M4130#A5C_2.B | PLATE | P26 | SDM_A5C_2-0B_P26 | PL15x313 | 546 | A36 | 1 | 1 | 1 | 16.3 | 16.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
179 | 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.0 | SPOOL_5C_SPOOL_3.0 |  |  | 11100xx3023x3253 |  |  |  | 1 |  | 8572.6 | 8572.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | -
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A |  |  |  | 11101xx2053x686 |  |  |  | 1 |  | 2224.7 | 2224.7 | AMC2 | [7 empty] | 0 | 0.64516 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P1 | SDM_A5C_3-0A_P1 | PL10x1736 | 3622 | A36 | 1 | 1 | 1 | 493.5 | 493.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P2 | SDM_A5C_3-0A_P2 | PL10x640 | 1712 | A36 | 1 | 1 | 1 | 86 | 86 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P3 | SDM_A5C_3-0A_P3 | PL20x582 | 1805 | A36 | 2 | 1 | 2 | 54.9 | 109.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P4 | SDM_A5C_3-0A_P4 | PL20x254 | 200 | A36 | 3 | 1 | 3 | 8 | 24 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 3 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P4A | SDM_A5C_3-0A_P4A | PL20x254 | 200 | A36 | 1 | 1 | 1 | 8 | 8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P5 | SDM_A5C_3-0A_P5 | PL30x240 | 640 | A36 | 1 | 1 | 1 | 36.2 | 36.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP013 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P6 | SDM_A5C_3-0A_P6 | PL10x465 | 1768 | A36 | 1 | 1 | 1 | 20.3 | 20.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P7 | SDM_A5C_3-0A_P7 | PL12x2052 | 2391 | A36 | 1 | 1 | 1 | 254.7 | 254.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P8 | SDM_A5C_3-0A_P8 | PL10x303 | 852 | A36 | 1 | 1 | 1 | 9.2 | 9.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PIPE | P9 | SDM_A5C_3-0A_P9 | PL15x320 | 7104 | A36 | 2 | 1 | 2 | 267.7 | 535.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P10 | SDM_A5C_3-0A_P10 | PL12x595 | 5089 | A36 | 1 | 1 | 1 | 325.5 | 325.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  | MODIFY, Length: 5809->5089 | [8 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P10A | SDM_A5C_3-0A_P10A | PL12x595 | 5089 | A36 | 1 | 1 | 1 | 325.5 | 325.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P11 | SDM_A5C_3-0A_P11 | PL12x174 | 630 | A36 | 3 | 1 | 3 | 8.1 | 24.3 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 6->3 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P11A | SDM_A5C_3-0A_P11A | PL12x174 | 630 | A36 | 3 | 1 | 3 | 8.1 | 24.3 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, P11A tách từ P11 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PLATE | P12 | SDM_A5C_3-0A_P12 | PL16x146 | 400 | A36 | 6 | 1 | 6 | 4.5 | 27 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 6 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.A | PIPE | D1 | SDM_A5C_3-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 3 | 1 | 3 | 13.057 | 39.1709 | AMC2 | Shape | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 3 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D |  |  |  | 11101xx697x2131 |  |  |  | 1 |  | 2110 | 2110 | AMC2 | [7 empty] | 0 | 0.73333 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | Shell Plate | P1 | SDM_A5C_3-0D_P1 | PL10x1736 | 3622 | A36 | 1 | 1 | 1 | 493.5 | 493.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | PLATE | P6 | SDM_A5C_3-0D_P6 | PL10x465 | 1768 | A36 | 1 | 1 | 1 | 20.3 | 20.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | PLATE | P13 | SDM_A5C_3-0D_P13 | PL10x389 | 640 | A36 | 1 | 1 | 1 | 19.5 | 19.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | PLATE | P14 | SDM_A5C_3-0D_P14 | PL20x488 | 1805 | A36 | 2 | 1 | 2 | 48.1 | 96.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | Shell Plate | P15 | SDM_A5C_3-0D_P15 | PL12x2030 | 2664 | A36 | 1 | 1 | 1 | 428.3 | 428.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | Shell Plate | P16 | SDM_A5C_3-0D_P16 | PL12x2052 | 5089 | A36 | 1 | 1 | 1 | 983.4 | 983.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.D | PLATE | P17 | SDM_A5C_3-0D_P17 | PL12x524 | 2053 | A36 | 3 | 1 | 3 | 28.6 | 85.8 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C |  |  |  | 11101xx2053x1076 |  |  |  | 1 |  | 2113.8 | 2113.8 | AMC2 | [7 empty] | 0 | 0.69231 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | Shell Plate | P1 | SDM_A5C_3-0C_P1 | PL10x1736 | 3622 | A36 | 1 | 1 | 1 | 493.5 | 493.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | PLATE | P6 | SDM_A5C_3-0C_P6 | PL10x465 | 1768 | A36 | 1 | 1 | 1 | 20.3 | 20.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | Shell Plate | P16 | SDM_A5C_3-0C_P16 | PL12x2052 | 5089 | A36 | 1 | 1 | 1 | 983.4 | 983.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | PLATE | P17 | SDM_A5C_3-0C_P17 | PL12x524 | 2053 | A36 | 3 | 1 | 3 | 28.6 | 85.8 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | PLATE | P18 | SDM_A5C_3-0C_P18 | PL20x477 | 1805 | A36 | 2 | 1 | 2 | 48.7 | 97.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | Shell Plate | P19 | SDM_A5C_3-0C_P19 | PL12x2051 | 2550 | A36 | 1 | 1 | 1 | 434.1 | 434.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | PLATE | P20 | SDM_A5C_3-0C_P20 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.C | PLATE | P21 | SDM_A5C_3-0C_P21 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B |  |  |  | 11101xx816x2131 |  |  |  | 1 |  | 2124.1 | 2124.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | Shell Plate | P1 | SDM_A5C_3-0B_P1 | PL10x1736 | 3622 | A36 | 1 | 1 | 1 | 493.5 | 493.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P13 | SDM_A5C_3-0B_P13 | PL10x389 | 640 | A36 | 1 | 1 | 1 | 19.5 | 19.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P14 | SDM_A5C_3-0B_P14 | PL20x488 | 1805 | A36 | 2 | 1 | 2 | 48.1 | 96.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | Shell Plate | P15 | SDM_A5C_3-0B_P15 | PL12x2030 | 2664 | A36 | 1 | 1 | 1 | 428.3 | 428.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | Shell Plate | P16 | SDM_A5C_3-0B_P16 | PL12x2052 | 5089 | A36 | 1 | 1 | 1 | 983.4 | 983.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P17 | SDM_A5C_3-0B_P17 | PL12x524 | 2053 | A36 | 2 | 1 | 2 | 28.6 | 57.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P22 | SDM_A5C_3-0B_P22 | PL10x179 | 688 | A36 | 1 | 1 | 1 | 7.1 | 7.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P23 | SDM_A5C_3-0B_P23 | PL10x185 | 737 | A36 | 1 | 1 | 1 | 7.6 | 7.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P24 | SDM_A5C_3-0B_P24 | PL15x276 | 515 | A36 | 1 | 1 | 1 | 12.9 | 12.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P25 | SDM_A5C_3-0B_P25 | PL12x191 | 830 | A36 | 1 | 1 | 1 | 10.4 | 10.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P26 | SDM_A5C_3-0B_P26 | PL12x200 | 892 | A36 | 1 | 1 | 1 | 11.2 | 11.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.20 | 24D06641-00-M4130#A5C_3.B | PLATE | P27 | SDM_A5C_3-0B_P27 | PL15x293 | 530 | A36 | 1 | 1 | 1 | 14.5 | 14.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
180 | 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.0 | SPOOL_5C_SPOOL_4.0 |  |  | 11920x2599x2747 |  |  |  | 1 |  | 7227.7 | 7227.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | -
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A |  |  |  | 11920x2165x755 |  |  |  | 1 |  | 2505.5 | 2505.5 | AMC2 | [7 empty] | 1 | 0.67544 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | Shell Plate | P1 | SDM_A5C_4-0A_P1 | PL10x2314 | 11920 | A36 | 1 | 1 | 1 | 1381.3 | 1381.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [10 empty] | REVISED, sửa đổi bản vẽ SGP | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | PLATE | P2 | SDM_A5C_4-0A_P2 | PL15x320 | 11770 | A36 | 2 | 1 | 2 | 443.5 | 887 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | PLATE | P3 | SDM_A5C_4-0A_P3 | PL10x303 | 852 | A36 | 1 | 1 | 1 | 9.2 | 9.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | PLATE | P4 | SDM_A5C_4-0A_P4 | PL10x200 | 794 | A36 | 7 | 1 | 7 | 8.5 | 59.5 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 7 | 7 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 7 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | PLATE | P4A | SDM_A5C_4-0A_P4A | PL10x200 | 794 | A36 | 7 | 1 | 7 | 8.5 | 59.5 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 7 | 7 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 7 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | PLATE | P5 | SDM_A5C_4-0A_P5 | PL16x137 | 337 | A36 | 14 | 1 | 14 | 3.5 | 49 | AMC2 | Plate | MCC |  |  | 14 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 14 | 14 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 14 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.A | PIPE | D1 | SDM_A5C_4-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 6 | 1 | 6 | 13.057 | 78.3418 | AMC2 | Shape | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 6 | 6 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 6 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.C |  |  |  | 11820x1250x2067 |  |  |  | 1 |  | 2347.1 | 2347.1 | AMC2 | [7 empty] | 1 | 0.73333 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.C | Shell Plate | P6 | SDM_A5C_4-0C_P6 | PL10x2314 | 11920 | A36 | 1 | 1 | 1 | 2165.5 | 2165.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [10 empty] | REVISED, sửa đổi bản vẽ SGP | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.C | PLATE | P7 | SDM_A5C_4-0C_P7 | PL10x695 | 2165 | A36 | 7 | 1 | 7 | 27.2 | 190.4 | AMC2 | Plate | MCC |  |  | 7 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 7 | 7 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 7 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.C | PLATE | P8 | SDM_A5C_4-0C_P8 | PL15x110 | 200 | A36 | 1 | 1 | 1 | 5.5 | 5.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.C | PLATE | P9 | SDM_A5C_4-0C_P9 | PL20x160 | 320 | A36 | 1 | 1 | 1 | 7.6 | 7.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B |  |  |  | 11820x1350x2067 |  |  |  | 1 |  | 2375.1 | 2375.1 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | i | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | Shell Plate | P6 | SDM_A5C_4-0B_P6 | PL10x2314 | 11920 | A36 | 1 | 1 | 1 | 2165.5 | 2165.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [10 empty] | REVISED, sửa đổi bản vẽ SGP | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | PLATE | P7 | SDM_A5C_4-0B_P7 | PL10x695 | 2165 | A36 | 3 | 1 | 3 | 27.2 | 81.6 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 3 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | PLATE | P8 | SDM_A5C_4-0B_P8 | PL15x110 | 200 | A36 | 1 | 1 | 1 | 5.5 | 5.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | PLATE | P9 | SDM_A5C_4-0B_P9 | PL20x160 | 320 | A36 | 1 | 1 | 1 | 7.6 | 7.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | PLATE | P10 | SDM_A5C_4-0B_P10 | PL10x387 | 1595 | A36 | 4 | 1 | 4 | 17.8 | 71.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | PLATE | P11 | SDM_A5C_4-0B_P11 | PL10x150 | 367 | A36 | 4 | 1 | 4 | 3.6 | 14.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 4 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.22 | 24D06641-00-M4130#A5C_4.B | PLATE | P12 | SDM_A5C_4-0B_P12 | PL15x276 | 515 | A36 | 4 | 1 | 4 | 12.9 | 51.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 4 | 2026-07-03 |  |  |  | 0
181 | 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | SPOOL_5C_SPOOL_5.0 |  |  | 11415x2427x2632 |  |  |  | 1 |  | 6398.9 | 6398.9 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S2 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Duct Plate | P1 | SDM_A5C_5-0_P1 | PL10x6315 | 9403 | A36 | 1 | 1 | 1 | 4302.9 | 4302.9 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Duct Plate | P2 | SDM_A5C_5-0_P2 | PL10x1893 | 6086 | A36 | 1 | 1 | 1 | 987.1 | 987.1 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Ring Plate | P3 | SDM_A5C_5-0_P3 | PL10x1636 | 2260 | A36 | 1 | 1 | 1 | 46.7 | 46.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Ring Plate | P4 | SDM_A5C_5-0_P4 | PL10x228 | 969 | A36 | 1 | 1 | 1 | 10 | 10 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P5 | SDM_A5C_5-0_P5 | PL15x300 | 516 | A36 | 1 | 1 | 1 | 14.3 | 14.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P6 | SDM_A5C_5-0_P6 | PL15x320 | 3516 | A36 | 2 | 1 | 2 | 132.5 | 265 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Ring Plate | P7 | SDM_A5C_5-0_P7 | PL10x2156 | 2260 | A36 | 1 | 1 | 1 | 54.7 | 54.7 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P8 | SDM_A5C_5-0_P8 | PL10x310 | 852 | A36 | 2 | 1 | 2 | 9.3 | 18.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P9 | SDM_A5C_5-0_P9 | PL16x143 | 275 | A36 | 4 | 1 | 4 | 3 | 12 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 4 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | LUG Plate | P10 | SDM_A5C_5-0_P10 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | PAD Plate | P11 | SDM_A5C_5-0_P11 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  | MODIFY, PL20->PL15 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P12 | SDM_A5C_5-0_P12 | PL15x282 | 516 | A36 | 2 | 1 | 2 | 13.2 | 26.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Ring Plate | P13 | SDM_A5C_5-0_P13 | PL10x2020 | 2260 | A36 | 1 | 1 | 1 | 58.4 | 58.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Ring Plate | P14 | SDM_A5C_5-0_P14 | PL20x2352 | 2450 | A36 | 1 | 1 | 1 | 183.9 | 183.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, PL10->20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | PAD Plate | P15 | SDM_A5C_5-0_P15 | PL10x400 | 2338 | A36 | 1 | 1 | 1 | 73.4 | 73.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P16 | SDM_A5C_5-0_P16 | PL20x180 | 254 | A36 | 2 | 1 | 2 | 7.2 | 14.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P17 | SDM_A5C_5-0_P17 | PL10x240 | 400 | A36 | 1 | 1 | 1 | 7.5 | 7.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P18 | SDM_A5C_5-0_P18 | PL3x230 | 390 | AISI304 | 1 | 1 | 1 | 2.12 | 2.12 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP004 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P19 | SDM_A5C_5-0_P19 | PL15x320 | 3750 | A36 | 2 | 1 | 2 | 141.3 | 282.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P20 | SDM_A5C_5-0_P20 | PL10x1636 | 2260 | A36 | 1 | 1 | 1 | 40.9 | 40.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P21 | SDM_A5C_5-0_P21 | PL10x213 | 969 | A36 | 1 | 1 | 1 | 8.8 | 8.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Plate | P22 | SDM_A5C_5-0_P22 | PL16x129 | 289 | A36 | 2 | 1 | 2 | 2.7 | 5.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 2 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Pipe | D1 | SDM_A5C_5-0_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 2 | 1 | 2 | 13.1 | 26.2 | AMC2 | Shape | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 2 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.24 | 24D06641-00-M4130#A5C_5.0 | Ring Plate | P23 | SDM_A5C_5-0_P23 | PL10x2156 | 2260 | A36 | 1 | 1 | 1 | 62.4 | 62.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [10 empty] | ADDED, cắt mới bổ sung | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
182 | 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | SPOOL_5C_SPOOL_6.0 |  |  | 11612xx2381x2422 |  |  |  | 1 |  | 5097.2 | 5097.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S2 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Duct Plate | P1 | SDM_A5C_6-0_P1 | PL8x3583 | 3797 | A36 | 1 | 1 | 1 | 854.3 | 854.3 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Duct Plate | P2 | SDM_A5C_6-0_P2 | PL10x3786 | 5291 | A36 | 1 | 1 | 1 | 1214.4 | 1214.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Duct Plate | P3 | SDM_A5C_6-0_P3 | PL10x4264 | 5462 | A36 | 1 | 1 | 1 | 1828.4 | 1828.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Ring Plate | P4 | SDM_A5C_6-0_P4 | PL8x1482 | 1616 | A36 | 2 | 1 | 2 | 27.4 | 54.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 2 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Ring Plate | P5 | SDM_A5C_6-0_P5 | PL8x1482 | 1616 | A36 | 1 | 1 | 1 | 24.2 | 24.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Ring Plate | P6 | SDM_A5C_6-0_P6 | PL10x2156 | 2260 | A36 | 1 | 1 | 1 | 62.4 | 62.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Ring Plate | P7 | SDM_A5C_6-0_P7 | PL10x2156 | 2260 | A36 | 1 | 1 | 1 | 54.6 | 54.6 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Ring Plate | P8 | SDM_A5C_6-0_P8 | PL10x2045 | 2825 | A36 | 1 | 1 | 1 | 63.9 | 63.9 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Ring Plate | P9 | SDM_A5C_6-0_P9 | PL10x266 | 1211 | A36 | 1 | 1 | 1 | 13.8 | 13.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Plate | P10 | SDM_A5C_6-0_P10 | PL15x198 | 520 | A36 | 2 | 1 | 2 | 7.8 | 15.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Plate | P11 | SDM_A5C_6-0_P11 | PL15x320 | 11512 | A36 | 2 | 1 | 2 | 433.8 | 867.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Plate | P12 | SDM_A5C_6-0_P12 | PL16x99 | 174 | A36 | 4 | 1 | 4 | 1.3 | 5.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 4 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Plate | P13 | SDM_A5C_6-0_P13 | PL16x99 | 182 | A36 | 2 | 1 | 2 | 1.4 | 2.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 2 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Plate | P14 | SDM_A5C_6-0_P14 | PL16x130 | 301 | A36 | 4 | 1 | 4 | 3 | 12 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 4 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Plate | P15 | SDM_A5C_6-0_P15 | PL15x282 | 516 | A36 | 1 | 1 | 1 | 13.2 | 13.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | LUG Plate | P16 | SDM_A5C_6-0_P16 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | PAD Plate | P17 | SDM_A5C_6-0_P17 | PL15x110 | 220 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.26 | 24D06641-00-M4130#A5C_6.0 | Pipe | D1 | SDM_A5C_6-0_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 1 | 5 | 13.1 | 65.5 | AMC2 | Shape | MCC |  |  | 5 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 5 | 5 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 5 | 2026-06-12 |  |  |  | 0
183 | 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | SPOOL_5C_SPOOL_7.0 |  |  | 11812xx2112x2017 |  |  |  | 1 |  | 4144.8 | 4144.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S2 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | Shell Plate | P1 | SDM_A5C_7-0_P1 | PL8x3583 | 11647 | A36 | 1 | 1 | 1 | 2620.5 | 2620.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P2 | SDM_A5C_7-0_P2 | PL15x320 | 11547 | A36 | 2 | 1 | 2 | 435.1 | 870.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P3 | SDM_A5C_7-0_P3 | PL20x1456 | 1677 | A36 | 1 | 1 | 1 | 323.1 | 323.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P4 | SDM_A5C_7-0_P4 | PL16x120 | 630 | A36 | 3 | 1 | 3 | 9.3 | 27.9 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 3 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P5 | SDM_A5C_7-0_P5 | PL20x275 | 1100 | A36 | 1 | 1 | 1 | 47.5 | 47.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 1 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P6 | SDM_A5C_7-0_P6 | PL5x190 | 255 | AISI304 | 2 | 1 | 2 | 1.9 | 3.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP006 | 2 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P7 | SDM_A5C_7-0_P7 | PL16x80 | 325 | A36 | 1 | 1 | 1 | 3.3 | 3.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P7A | SDM_A5C_7-0_P7A | PL16x80 | 325 | A36 | 1 | 1 | 1 | 3.3 | 3.3 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P8 | SDM_A5C_7-0_P8 | PL16x80 | 100 | A36 | 1 | 1 | 1 | 0.8 | 0.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P9 | SDM_A5C_7-0_P9 | PL8x1616 | 1616 | A36 | 3 | 1 | 3 | 24.2 | 72.6 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 3 | 3 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 5->3 |  | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 3 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P10 | SDM_A5C_7-0_P10 | PL15x341 | 609 | A36 | 2 | 1 | 2 | 16.8 | 33.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P11 | SDM_A5C_7-0_P11 | PL16x98 | 182 | A36 | 10 | 1 | 10 | 1.4 | 14 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 10 | 10 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 | 10 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P12 | SDM_A5C_7-0_P12 | PL15x306 | 520 | A36 | 1 | 1 | 1 | 14.1 | 14.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P13 | SDM_A5C_7-0_P13 | PL15x363 | 554 | A36 | 1 | 1 | 1 | 18.4 | 18.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P14 | SDM_A5C_7-0_P14 | PL8x1078 | 1616 | A36 | 2 | 1 | 2 | 18.1 | 36.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 1->2 |  | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 2 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P15 | SDM_A5C_7-0_P15 | PL8x129 | 503 | A36 | 2 | 1 | 2 | 2.9 | 5.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, Qty: 1->2 |  | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP007 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P16 | SDM_A5C_7-0_P16 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 | 2 | 2026-08-08 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PLATE | P17 | SDM_A5C_7-0_P17 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.29 | 24D06641-00-M4130#A5C_7.0 | PIPE | D1 | SDM_A5C_7-0_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 1 | 5 | 13.057 | 65.2848 | AMC2 | Shape | MCC |  |  | 5 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S2 | 1 | 5 | 5 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 | 5 | 2026-06-12 |  |  |  | 0
184 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Front/rear shim pack |  |  | 200x93x40 |  |  |  | 4 |  | 4.9 | 19.7 | AMC2 | [7 empty] | 0 | 0.31818 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 4 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P1 | SDM_A10_P1 | PL5x93 | 200 | A36 | 2 | 4 | 8 | 0.6 | 4.8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 8 | 8 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP005 | 8 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P2 | SDM_A10_P2 | PL3x93 | 200 | A36 | 2 | 4 | 8 | 0.4 | 3.2 | AMC2 | Plate | MCC |  |  | 8 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 8 | 8 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP003 | 8 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P3 | SDM_A10_P3 | PL2x93 | 200 | A36 | 6 | 4 | 24 | 0.2 | 4.8 | AMC2 | Plate | MCC |  |  | 24 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 24 | 24 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP002 | 24 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P4 | SDM_A10_P4 | PL1x93 | 200 | A36 | 12 | 4 | 48 | 0.1 | 4.8 | AMC2 | Plate | MCC |  |  | 48 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 48 | 48 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP001 | 48 | 2026-06-13 |  |  |  | 0
185 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Front/rear saddle support |  |  | 200x200x103 |  |  |  | 4 |  | 5.8 | 23.3 | AMC2 | [7 empty] | 0 | 0.125 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 4 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Threaded Bar | B2495 | SDM_A11_B2495 | M24x95L (Pitch 3mm; 6G) | 95 |  | 4 | 4 | 16 | 0.3 | 4.8 | AMC2 | Shape | PMC |  |  | 16 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 (+ thêm 30mm lượng dư cho PMC) |  | AMC2-S1 | 4 | 16 | 16 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  |  | Modify, Pur. -> Fab., Add remark | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [6 empty] | 16
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Countersunk Bolt | B0616 | SDM_A11_B0616 | M6x16L (Pitch 1mm; 6H) |  |  | 4 | 4 | 16 | 0.036 | 0.576 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 16 | 0 | 16 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Plate | P1 | SDM_A11_P1 | PL16x200 | 200 | A36 | 1 | 4 | 4 | 5 | 20 | AMC2 | Plate | PMC |  |  | 4 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-01-CP011 | 4 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Teflon PAD | M1 | SDM_A11_M1 | PL5x160x160 |  | Teflon | 1 | 4 | 4 | 0.2816 | 1.1264 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
186 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Front/rear lateral guides |  |  | 200x190x170 |  |  |  | 4 |  | 17.2 | 69 | AMC2 | [7 empty] | 0 | 0.3125 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 4 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Plate | P1 | SDM_A12_P1 | PL40x170 | 200 | A36 | 1 | 4 | 4 | 9.5 | 38 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP014 | 4 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Plate | P2 | SDM_A12_P2 | PL40x150 | 170 | A36 | 1 | 4 | 4 | 8 | 32 | AMC2 | Plate | MCC |  |  | 4 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP014 | 4 | 2026-06-13 |  |  |  | 0
187 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A13 | Lower sealing plate |  |  | 186xx400x16 |  | A36 |  | 2 |  | 5.3 | 10.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 2 |  | 2 |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
188 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A14 | Lower sealing plate |  |  | 236xx400x16 |  | A36 |  | 10 |  | 7.5 | 75.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 10 |  | 10 |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
189 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A15 | Fixed saddle shim |  |  | 640x115x1 |  | A36 |  | 10 |  | 0.5 | 5 | AMC2 | [7 empty] | 0 | 0.45455 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 10 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A15 | Shim Plate | P1 | SDM_A15_P1 | PL1x115 | 640 | A36 | 1 | 10 | 10 | 0.5 | 5 | AMC2 | Plate | MCC |  |  | 10 | 0 | 10 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 10 | 10 | 10 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP001 A320-01-CP019 | 10 | 2026-06-30 |  |  |  | 0
190 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A16 | Sliding saddle shim |  |  | 400x115x1 |  | A36 |  | 20 |  | 0.3 | 6.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 20 |  | 20 |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
191 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A17 | Sliding saddle baseplate |  |  | 240x400x12 |  |  |  | 1 |  | 6 | 6 | AMC2 | [7 empty] | 0 | 0.16667 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A17 | Plate | P1 | SDM_A17_P1 | PL2x88 | 400 | A36 | 1 | 1 | 1 | 7.5 | 7.5 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A17 | Teflon PAD | M1 | SDM_A17_M1 | PL5x220x380 |  | Teflon | 1 | 1 | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
192 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A18 | Cylinder øe30 - øi26 H.25 |  |  | 30x30x25 |  | A36 |  | 4 |  | 0.025 | 0.1 | AMC2 | [7 empty] | 2 | 0.5 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 4 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A18 | Round Bar | R1 | SDM_A18_R1 | PL2x88 | 25 | A36 | 1 | 4 | 4 | 0.025 | 0.1 | AMC2 | Plate | PMC |  |  | 4 | 0 | 4 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 4 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP002 | 4 | 2026-06-13 |  |  |  | 0
193 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Manhole |  |  | 262x813x942 |  |  |  | 1 |  | 121.5 | 121.5 | AMC2 | [7 empty] | 0 | 0.25 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Flange | M1 | SDM_A19_M1 | 24" 150# SO R.F (ASME B16.5) |  | A105 | 1 | 1 | 1 | 100 | 100 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Pipe | D1 | SDM_A19_D1 | PL8x250 | 1891 | A36 | 1 | 1 | 1 | 29.7 | 29.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP007 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Plate | P1 | SDM_A19_P1 | PL12x100 | 716 | A36 | 1 | 1 | 1 | 6.7 | 6.7 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, cập nhật nguyên công | [7 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
194 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Hinge manhole |  |  | 793x570x80 |  |  |  | 1 |  | 25.4 | 25.4 | AMC2 | [7 empty] | 0 | 0.25 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Round Bar | R1 | SDM_A20_R1 | RB60 | 1096 | A36 | 1 | 1 | 1 | 24.3 | 24.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP507 | 1 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Angle | A1 | SDM_A20_A1 | L80x80x10 | 80 | A36 | 1 | 1 | 1 | 1.1 | 1.1 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 (L90x10 thay thế L80x10) |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP504 | 1 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Plate | P1 | SDM_A20_P1 | PL12x80 | 80 | A36 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC |  |  |  | MODIFY, cập nhật nguyên công | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 | 1 | 2026-07-03 |  |  |  | 0
195 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Closing flange manhole |  |  | 813x860x136 |  |  |  | 1 |  | 187.3 | 187.3 | AMC2 | [7 empty] | 0 | 0.3 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Blind Flange | M1 | SDM_A21_M1 | 24" 150# R.F (ASME B16.5) |  | A105 | 1 | 1 | 1 | 100 | 100 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Round Bar | R1 | SDM_A21_R1 | RB20 | 326 | A36 | 2 | 1 | 2 | 0.8 | 1.6 | AMC2 | Shape | PMC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP506 | 2 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Round Bar | R2 | SDM_A21_R2 | RB15 | 188 | A36 | 1 | 1 | 1 | 0.3 | 0.3 | AMC2 | Shape | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP505 | 1 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Eyes Bolt | M1 |  | M16x260L |  | A36 | 1 | 1 | 1 | 0.6 | 0.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
196 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Rupture disk spool |  |  | 1142x1360x985 |  |  |  | 1 |  | 305.6 | 305.6 | AMC2 | [7 empty] | 0 | 0.39286 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Flange | M1 | SDM_A22_M1 | 28" 150# WN R.F (ASME B16.47 Type A) |  | A105 | 1 | 1 | 1 | 155 | 155 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Pipe | D1 | SDM_A22_D1 | 28" SCH.STD (Ø711x9.53t) | 761 | A106 Gr.B | 1 | 1 | 1 | 125.4585 | 125.4585 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP502 | 1 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P1 | SDM_A22_P1 | PL30x225 | 250 | A36 | 1 | 1 | 1 | 10.5 | 10.5 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP013 | 1 | 2026-06-13 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P2 | SDM_A22_P2 | PL10x60 | 620 | A36 | 2 | 1 | 2 | 2.9 | 5.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 2 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P3 | SDM_A22_P3 | PL10x70 | 80 | A36 | 1 | 1 | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Mesh | M2 | SDM_A22_M2 | - |  |  | 1 | 1 | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
197 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Rupture disk external spool |  |  | 985x985x737 |  |  |  | 1 |  | 250.4 | 250.4 | AMC2 | [7 empty] | 0 | 0.3125 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Flange | M1 | SDM_A23_M1 | 28" 150# WN R.F (ASME B16.47 Type A) |  | A105 | 1 | 1 | 1 | 155 | 155 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Pipe | D1 | SDM_A23_D1 | 28" SCH.STD (Ø711x9.53t) | 604 | A106 Gr.B | 1 | 1 | 1 | 99.5754 | 99.5754 | AMC2 | Shape | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP502 | 1 | 2026-06-12 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Plate | P1 | SDM_A23_P1 | PL8x100 | 376 | A36 | 1 | 1 | 1 | 2.4 | 2.4 | AMC2 | Plate | PMC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP007 | 1 | 2026-07-03 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Mesh | M2 | SDM_A23_M2 | - |  |  | 1 | 1 | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
198 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A24 | Large washer |  |  | Plate ø80xø32x5 |  | A36 |  | 1 |  | 0.2 | 0.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A24 | Washer | WS1 | SDM_A24_WS1 | PL5x80 | 80 | A36 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 1 | SDM Street 11 |  | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 |  | AMC 2 | - | - | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP005 | 1 | 2026-06-13 |  |  |  | 0
199 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A25 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 3000 | A36 |  | 21 |  | 25 | 524.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 21 | 21 | 21 | 0 | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
200 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A27 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 2455 | A36 |  | 1 |  | 19.6 | 19.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
201 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A28 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 2418 | A36 |  | 1 |  | 19.3 | 19.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
202 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A29 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 590 | A36 |  | 1 |  | 4.1 | 4.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 | 1 | 1 | 0 | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
203 | TW1008-MAG-&MLD020-U-001025_08 | 24D06641-00-M4130#A32 | Pipe 1/2" Sch.STD - Lg.100 mm |  |  | 1/2" Sch.STD | 100 | A36 |  | 1 |  | 0.1 | 0.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o
204 | TW1008-MAG-&MLD020-U-001025_08 | DIN 975 - M30x310 | Stud Bolt |  |  | M30x310L |  | A193 B7 - HDG (DIN 975) |  | 1 |  | 1.7 | 1.7 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
205 | TW1008-MAG-&MLD020-U-001025_08 | Gasket 24" - 150LB | Gasket |  |  | 24" 150# (ASME B16.21) |  | Klingersil |  | 1 |  | 1.5 | 1.5 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 1 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
206 | TW1008-MAG-&MLD020-U-001025_08 | ISO 4014 - M24x100 | Hex Bolt |  |  | M24x100L |  | A193 B7 - HDG (ISO 4014) |  | 10 |  | 0.5 | 4.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 10 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
207 | TW1008-MAG-&MLD020-U-001025_08 | ISO 4014 - M30 x 160 | Hex. Bolt |  |  | M30x160L |  | A193 B7 - HDG (ISO 4014) |  | 20 |  | 1.2 | 23 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 20 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
208 | TW1008-MAG-&MLD020-U-001025_08 | ISO 4014 - M30 x 220 | Hex. Bolt |  |  | M30x220L |  | A193 B7 - HDG (ISO 4014) |  | 28 |  | 1.5 | 41.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 28 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
209 | TW1008-MAG-&MLD020-U-001025_08 | ISO 4032 - M24 | Hex. Nut |  |  | M24 |  | A194 2H - HDG (ISO 4032) |  | 28 |  | 0.1 | 3.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 28 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
210 | TW1008-MAG-&MLD020-U-001025_08 | ISO 4032 - M30 | Hex. Nut |  |  | M30 |  | A194 2H - HDG (ISO 4032) |  | 52 |  | 0.3 | 15.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 52 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
211 | TW1008-MAG-&MLD020-U-001025_08 | ISO 4032 -M16 | Hex. Nut |  |  | M16 |  | A194 2H - HDG (ISO 4032) |  | 3 |  | 0.1 | 0.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 3 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
212 | TW1008-MAG-&MLD020-U-001025_08 | ISO 7089 - 16 | Washer |  |  | M16 |  | F436 - HDG |  | 2 |  | 0.1 | 0.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 2 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
213 | TW1008-MAG-&MLD020-U-001025_08 | ISO 7089 - 24 | Washer |  |  | M24 |  | F436 - HDG |  | 36 |  | 0.033333 | 1.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 36 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
214 | TW1008-MAG-&MLD020-U-001025_08 | ISO 7089 - 30 | Washer |  |  | M30 |  | F436 - HDG |  | 96 |  | 0.1 | 5.1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1 | SDM Street 11 | x | AMC2-S1 | 96 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  |  | AMC 2 | - | - | - | o | [19 empty] | Purchasing
138 | 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.1 | SPOOL_1.1 |  |  | 8616xx3713x3625 |  |  |  | 2 |  | 8656.4 | 34625.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | -
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A |  |  |  | 8616xx2365x754 |  |  |  | 2 |  | 2279.3 | 9117.2 | AMC2 | [7 empty] | 0 | 0.64957 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | Shell Plate | P1 | SDM_A5C_1-1A_P1 | PL12x2366 | 8216 | A36 | 1 | 2 | 2 | 1195.8 | 2391.6 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P2 | SDM_A5C_1-1A_P2 | PL15x360 | 7926 | A36 | 2 | 2 | 4 | 336 | 1344 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P3 | SDM_A5C_1-1A_P3 | PL10x180 | 2343 | A36 | 1 | 2 | 2 | 33.1 | 66.2 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P4 | SDM_A5C_1-1A_P4 | PL20x678 | 2308 | A36 | 1 | 2 | 2 | 83.6 | 167.2 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P5 | SDM_A5C_1-1A_P5 | PL20x200 | 1100 | A36 | 1 | 2 | 2 | 34.5 | 69 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P6 | SDM_A5C_1-1A_P6 | PL10x287 | 852 | A36 | 1 | 2 | 2 | 8.9 | 17.8 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P7 | SDM_A5C_1-1A_P7 | PL5x180 | 190 | AISI304 | 2 | 2 | 4 | 1.3 | 5.2 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 | AMC2-S4 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP006 A320-11-CP006 A320-21-CP006 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P8 | SDM_A5C_1-1A_P8 | PL12x80 | 300 | A36 | 4 | 2 | 8 | 2.3 | 18.4 | AMC2 | Plate | MCC |  |  | 4 | 4 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 3 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 16 | 2026-07-10 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PIPE | P9 | SDM_A5C_1-1A_P9 | PL12x80 | 231 | A36 | 2 | 2 | 4 | 1.7 | 6.8 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P10 | SDM_A5C_1-1A_P10 | PL10x308 | 332 | A36 | 2 | 2 | 4 | 5.1 | 20.4 | AMC2 | Plate | MCC |  |  | 3 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P11 | SDM_A5C_1-1A_P11 | PL12x206 | 787 | A36 | 4 | 2 | 8 | 11.6 | 92.8 | AMC2 | Plate | MCC |  |  | 4 | 4 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 3 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Qty: 8->4 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 16 | 2026-07-10 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P11A | SDM_A5C_1-1A_P11A | PL12x206 | 787 | A36 | 4 | 2 | 8 | 11.6 | 92.8 | AMC2 | Plate | MCC |  |  | 4 | 4 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 3 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, P11A tách từ P11 |  | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 16 | 2026-07-10 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PLATE | P12 | SDM_A5C_1-1A_P12 | PL16x154 | 460 | A36 | 8 | 2 | 16 | 5.5 | 88 | AMC2 | Plate | MCC |  |  | 8 | 8 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 8 | 1 | 7 | AMC2-S4 | 1 | 8 | 7 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 32 | 2026-08-14 |  |  |  | -16
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PIPE | D1 | SDM_A5C_1-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 4 | 2 | 8 | 13.057 | 104.4557 | AMC2 | Shape | MCC |  |  | 4 | 4 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 3 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 16 | 2026-07-28 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.A | PIPE | D2 | SDM_A5C_1-1A_D2 | 1/2" SCH.STD (OD21.3x2.77t) | 737 | A53 Gr.B | 2 | 2 | 4 | 2.1 | 8.4 | AMC2 | Shape | PMC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  | Modify, Mark D1->D2 | [9 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP501 A320-11-CP501 A320-21-CP501 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D |  |  |  | 8516xx854x2365 |  |  |  | 2 |  | 2184.2 | 8736.8 | AMC2 | [7 empty] | 0 | 0.8254 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o | [20 empty] | A320-01-CP501 | 5 | 2026-06-12
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | Shell Plate | P13 | SDM_A5C_1-1D_P13 | PL12x2366 | 8216 | A36 | 1 | 2 | 2 | 1830.9 | 3661.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P14 | SDM_A5C_1-1D_P14 | PL20x563 | 2308 | A36 | 1 | 2 | 2 | 45.5 | 91 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, PL12->20 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP020 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P15 | SDM_A5C_1-1D_P15 | PL20x603 | 2365 | A36 | 4 | 2 | 8 | 62.7 | 501.6 | AMC2 | Plate | MCC |  |  | 8 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [9 empty] | Revised, PL12->PL20 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP022 | 16 | 2026-08-18 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PIPE | P16 | SDM_A5C_1-1D_P16 | PL10x221 | 1885 | A36 | 1 | 2 | 2 | 32.7 | 65.4 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP021 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PIPE | P17 | SDM_A5C_1-1D_P17 | PL10x243 | 2202 | A36 | 1 | 2 | 2 | 42 | 84 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP021 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | PA1 | SDM_A5C_1-1D_PA1 | PL10x1071 | 1095 | A36 | 1 | 2 | 2 | 40.8 | 81.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P18 | SDM_A5C_1-1D_P18 | PL10x180 | 536 | A36 | 1 | 2 | 2 | 7.5 | 15 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P19 | SDM_A5C_1-1D_P19 | PL10x301 | 302 | A36 | 2 | 2 | 4 | 4.6 | 18.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P20 | SDM_A5C_1-1D_P20 | PL10x163 | 221 | A36 | 1 | 2 | 2 | 1.7 | 3.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P21 | SDM_A5C_1-1D_P21 | PL15x417 | 875 | A36 | 1 | 2 | 2 | 27.8 | 55.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PLATE | P22 | SDM_A5C_1-1D_P22 | PL15x363 | 793 | A36 | 1 | 2 | 2 | 22.8 | 45.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | PIPE | D2 | SDM_A5C_1-1D_D2 | 1/2" SCH.STD (OD21.3x2.77t) | 737 | A53 Gr.B | 5 | 2 | 10 | 2.1 | 21 | AMC2 | Shape | PMC |  |  | 5 | 5 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 1 | 4 | AMC2-S4 | 1 | 5 | 4 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  | Modify, Mark D1->D2 | [9 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP501 A320-11-CP501 A320-21-CP501 | 20 | 2026-07-28 |  |  |  | -10
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.D | HALF COUPLING | M1 | SDM_A5C_1-1D_M1 | RB50 | 48 | A36 | 1 | 2 | 2 | 0.32 | 0.64 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  |  | Modify, Profile: 1" HALFCOUPLING->RB50 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-01-CP508 A320-11-CP507 A320-21-CP508 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.C |  |  |  | 8516xx2365x786 |  |  |  | 2 |  | 2092.3 | 8369.2 | AMC2 | [7 empty] | 1 | 0.93333 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.C | Shell Plate | P23 | SDM_A5C_1-1C_P23 | PL12x2366 | 8216 | A36 | 1 | 2 | 2 | 1830.9 | 3661.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.C | PLATE | P15 | SDM_A5C_1-1C_P15 | PL20x603 | 2365 | A36 | 4 | 2 | 8 | 62.7 | 501.6 | AMC2 | Plate | MCC |  |  | 8 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Qty: 5->4 | [5 empty] | Revised, PL12->PL20 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP022 | 16 | 2026-08-18 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.C | PLATE | P24 | SDM_A5C_1-1C_P24 | PL15x110 | 200 | A36 | 2 | 2 | 4 | 5.5 | 22 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.C | PLATE | P25 | SDM_A5C_1-1C_P25 | PL20x160 | 320 | A36 | 2 | 2 | 4 | 7.6 | 30.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.C | PLATE | P15 | SDM_A5C_1-1C_P15 | PL20x603 | 2365 | A36 | 1 | 2 | 2 | 62.7 | 125.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [9 empty] | Revised, PL12->PL20 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP022 | 4 | 2026-08-18 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.E |  |  |  | 8516xx796x2365 |  |  |  | 2 |  | 2100.6 | 8402.4 | AMC2 | [7 empty] | 1 | 0.875 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.E | Shell Plate | P23 | SDM_A5C_1-1E_P23 | PL12x2366 | 8216 | A36 | 1 | 2 | 2 | 1830.9 | 3661.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.E | PLATE | P14 | SDM_A5C_1-1E_P14 | PL20x563 | 2308 | A36 | 1 | 2 | 2 | 45.5 | 91 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, PL12->20 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP020 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.E | PLATE | P15 | SDM_A5C_1-1E_P15 | PL20x603 | 2365 | A36 | 4 | 2 | 8 | 62.7 | 501.6 | AMC2 | Plate | MCC |  |  | 8 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 4 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Qty: 5->4 | [5 empty] | Revised, PL12->PL20 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP022 | 16 | 2026-08-18 |  |  |  | -8
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.E | PLATE | P18 | SDM_A5C_1-1E_P18 | PL10x180 | 536 | A36 | 1 | 2 | 2 | 7.5 | 15 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Qty: 2->1 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.17 | 24D06641-00-M4130#A5C_1.E | PLATE | P29 | SDM_A5C_1-1E_P29 | PL15x351 | 784 | A36 | 1 | 2 | 2 | 21.8 | 43.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  | Modify, Mark: P26->P29 | [9 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 2026-07-28 |  |  |  | -2
139 | 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.1 | SPOOL_2.1 |  |  | 11621xx3344x3439 |  |  |  | 2 |  | 10411.4 | 41645.6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | -
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A |  |  |  | 11621xx2149x443 |  |  |  | 2 |  | 2300 | 9200 | AMC2 | [7 empty] | 0 | 0.61404 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P1 | SDM_A5C_2-1A_P1 | PL12x418 | 4023 | A36 | 2 | 2 | 4 | 182.2 | 728.8 | AMC2 | Plate | PMC |  |  | 0 | 4 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 | AMC2-S4 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 8 |  |  |  |  | -4
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P2 | SDM_A5C_2-1A_P2 | PL12x618 | 1930 | A36 | 1 | 2 | 2 | 98 | 196 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Qty: 2->1 | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 A320-11-CP017 | 4 | 2026-07-13 |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P2A | SDM_A5C_2-1A_P2A | PL12x618 | 1930 | A36 | 1 | 2 | 2 | 98 | 196 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, P2A tách từ P2 | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-11-CP017 A320-21-CP009 | 4 | 2026-07-13 |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P3 | SDM_A5C_2-1A_P3 | PL12x618 | 5608 | A36 | 1 | 2 | 2 | 326.2 | 652.4 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | Shell Plate | P3A | SDM_A5C_2-1A_P3A | PL12x618 | 5608 | A36 | 1 | 2 | 2 | 326.2 | 652.4 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | PLATE | P4 | SDM_A5C_2-1A_P4 | PL15x320 | 11521 | A36 | 2 | 2 | 4 | 434.1 | 1736.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | PLATE | P5 | SDM_A5C_2-1A_P5 | PL16x146 | 400 | A36 | 6 | 2 | 12 | 4.5 | 54 | AMC2 | Plate | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 2026-08-14 |  |  |  | -12
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | PLATE | P6 | SDM_A5C_2-1A_P6 | PL16x154 | 460 | A36 | 6 | 2 | 12 | 5.5 | 66 | AMC2 | Plate | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 2026-08-14 |  |  |  | -12
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | PLATE | P7 | SDM_A5C_2-1A_P7 | PL12x160 | 506 | A36 | 6 | 2 | 12 | 6.5 | 78 | AMC2 | Plate | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 24 | 2026-07-10 |  |  |  | -12
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | PLATE | P8 | SDM_A5C_2-1A_P8 | PL12x192 | 645 | A36 | 6 | 2 | 12 | 9.6 | 115.2 | AMC2 | Plate | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 24 | 2026-07-10 |  |  |  | -12
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.A | PIPE | D1 | SDM_A5C_2-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 6 | 2 | 12 | 13.057 | 156.6835 | AMC2 | Shape | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 24 | 2026-07-28 |  |  |  | -12
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.D |  |  |  | 11521xx844x2593 |  |  |  | 2 |  | 2888.1 | 11552.4 | AMC2 | [7 empty] | 0 | 0.7037 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.D | Shell Plate | P9 | SDM_A5C_2-1D_P9 | PL12x2279.4 | 4023 | A36 | 1 | 2 | 2 | 863.8 | 1727.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.D | Shell Plate | P10 | SDM_A5C_2-1D_P10 | PL12x1956 | 2635 | A36 | 1 | 2 | 2 | 441.5 | 883 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 A320-11-CP017 A320-21-CP009 | 4 | 2026-07-13 |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.D | Shell Plate | P11 | SDM_A5C_2-1D_P11 | PL12x2628.5 | 5608 | A36 | 1 | 2 | 2 | 1388.4 | 2776.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.D | PLATE | P12 | SDM_A5C_2-1D_P12 | PL12x609 | 2225 | A36 | 3 | 2 | 6 | 31.8 | 190.8 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.D | PLATE | P13 | SDM_A5C_2-1D_P13 | PL12x700 | 2562 | A36 | 3 | 2 | 6 | 41.9 | 251.4 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C |  |  |  | 11521xx2149x1051 |  |  |  | 2 |  | 2335.2 | 9340.8 | AMC2 | [7 empty] | 0 | 0.69231 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | Shell Plate | P14 | SDM_A5C_2-1C_P14 | PL12x1823 | 4023 | A36 | 1 | 2 | 2 | 690.9 | 1381.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | Shell Plate | P15 | SDM_A5C_2-1C_P15 | PL12x1997 | 2103 | A36 | 1 | 2 | 2 | 358.1 | 716.2 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 A320-11-CP017 A320-21-CP009 | 4 | 2026-07-13 |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | Shell Plate | P16 | SDM_A5C_2-1C_P16 | PL12x2102.7 | 5608 | A36 | 1 | 2 | 2 | 1110.3 | 2220.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | PLATE | P17 | SDM_A5C_2-1C_P17 | PL12x447 | 1867 | A36 | 3 | 2 | 6 | 25.4 | 152.4 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | PLATE | P18 | SDM_A5C_2-1C_P18 | PL12x514 | 2149 | A36 | 3 | 2 | 6 | 33.5 | 201 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | PLATE | P19 | SDM_A5C_2-1C_P19 | PL15x110 | 200 | A36 | 2 | 2 | 4 | 5.5 | 22 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.C | PLATE | P20 | SDM_A5C_2-1C_P20 | PL20x160 | 320 | A36 | 2 | 2 | 4 | 7.6 | 30.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.E |  |  |  | 11521xx850x2593 |  |  |  | 2 |  | 2888.1 | 11552.4 | AMC2 | [7 empty] | 0 | 0.55556 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.E | Shell Plate | P9 | SDM_A5C_2-1E_P9 | PL12x2279.4 | 4023 | A36 | 1 | 2 | 2 | 863.8 | 1727.6 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.E | Shell Plate | P10 | SDM_A5C_2-1E_P10 | PL12x1956 | 2635 | A36 | 1 | 2 | 2 | 441.5 | 883 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP017 A320-11-CP017 A320-21-CP009 | 4 | 2026-07-13 |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.E | Shell Plate | P11 | SDM_A5C_2-1E_P11 | PL12x2628.5 | 5608 | A36 | 1 | 2 | 2 | 1388.4 | 2776.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.E | PLATE | P12 | SDM_A5C_2-1E_P12 | PL12x609 | 2225 | A36 | 3 | 2 | 6 | 31.8 | 190.8 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.19 | 24D06641-00-M4130#A5C_2.E | PLATE | P13 | SDM_A5C_2-1E_P13 | PL12x700 | 2562 | A36 | 3 | 2 | 6 | 41.9 | 251.4 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
140 | 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.1 | SPOOL_3.1 |  |  | 11100xx2904x3253 |  |  |  | 2 |  | 8558.3 | 34233.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | -
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A |  |  |  | 11101xx2053x686 |  |  |  | 2 |  | 2224.7 | 8898.8 | AMC2 | [7 empty] | 0 | 0.64516 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P1 | SDM_A5C_3-1A_P1 | PL10x1736 | 3622 | A36 | 1 | 2 | 2 | 493.5 | 987 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P2 | SDM_A5C_3-1A_P2 | PL10x640 | 1712 | A36 | 1 | 2 | 2 | 86 | 172 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P3 | SDM_A5C_3-1A_P3 | PL20x582 | 1805 | A36 | 2 | 2 | 4 | 54.9 | 219.6 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P4 | SDM_A5C_3-1A_P4 | PL20x254 | 200 | A36 | 3 | 2 | 6 | 8 | 48 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 12 | 2026-08-08 |  |  |  | -6
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P4A | SDM_A5C_3-1A_P4A | PL20x254 | 200 | A36 | 1 | 2 | 2 | 8 | 16 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P5 | SDM_A5C_3-1A_P5 | PL30x240 | 640 | A36 | 1 | 2 | 2 | 36.2 | 72.4 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP013 A320-11-CP013 A320-21-CP013 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P6 | SDM_A5C_3-1A_P6 | PL10x465 | 1768 | A36 | 1 | 2 | 2 | 20.3 | 40.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P7 | SDM_A5C_3-1A_P7 | PL12x2052 | 2391 | A36 | 1 | 2 | 2 | 254.7 | 509.4 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P8 | SDM_A5C_3-1A_P8 | PL10x303 | 852 | A36 | 1 | 2 | 2 | 9.2 | 18.4 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P9 | SDM_A5C_3-1A_P9 | PL15x320 | 7104 | A36 | 2 | 2 | 4 | 267.7 | 1070.8 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P10 | SDM_A5C_3-1A_P10 | PL12x595 | 5089 | A36 | 1 | 2 | 2 | 325.5 | 651 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  | MODIFY, Length: 5809->5089 | [8 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | Shell Plate | P10A | SDM_A5C_3-1A_P10A | PL12x595 | 5089 | A36 | 1 | 2 | 2 | 325.5 | 651 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Length: 5809->5089 | [7 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P11 | SDM_A5C_3-1A_P11 | PL12x174 | 630 | A36 | 3 | 2 | 6 | 8.1 | 48.6 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, Qty: 6->3 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P11A | SDM_A5C_3-1A_P11A | PL12x174 | 630 | A36 | 3 | 2 | 6 | 8.1 | 48.6 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, P11A tách từ P11 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PLATE | P12 | SDM_A5C_3-1A_P12 | PL16x146 | 400 | A36 | 6 | 2 | 12 | 4.5 | 54 | AMC2 | Plate | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 2026-08-14 |  |  |  | -12
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.A | PIPE | D1 | SDM_A5C_3-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 3 | 2 | 6 | 13.057 | 78.3418 | AMC2 | Shape | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 12 | 2026-07-28 |  |  |  | -6
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D |  |  |  | 11101xx697x2131 |  |  |  | 2 |  | 2110 | 8440 | AMC2 | [7 empty] | 0 | 0.73333 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | Shell Plate | P1 | SDM_A5C_3-1D_P1 | PL10x1736 | 3622 | A36 | 1 | 2 | 2 | 493.5 | 987 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | PLATE | P6 | SDM_A5C_3-1D_P6 | PL10x465 | 1768 | A36 | 1 | 2 | 2 | 20.3 | 40.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | PLATE | P13 | SDM_A5C_3-1D_P13 | PL10x389 | 640 | A36 | 1 | 2 | 2 | 19.5 | 39 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | PLATE | P14 | SDM_A5C_3-1D_P14 | PL20x488 | 1805 | A36 | 2 | 2 | 4 | 48.1 | 192.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | Shell Plate | P15 | SDM_A5C_3-1D_P15 | PL12x2030 | 2664 | A36 | 1 | 2 | 2 | 428.3 | 856.6 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | Shell Plate | P16 | SDM_A5C_3-1D_P16 | PL12x2052 | 5089 | A36 | 1 | 2 | 2 | 983.4 | 1966.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.D | PLATE | P17 | SDM_A5C_3-1D_P17 | PL12x524 | 2053 | A36 | 3 | 2 | 6 | 28.6 | 171.6 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C |  |  |  | 11101xx2053x1076 |  |  |  | 2 |  | 2113.8 | 8455.2 | AMC2 | [7 empty] | 0 | 0.69231 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | Shell Plate | P1 | SDM_A5C_3-1C_P1 | PL10x1736 | 3622 | A36 | 1 | 2 | 2 | 493.5 | 987 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | PLATE | P6 | SDM_A5C_3-1C_P6 | PL10x465 | 1768 | A36 | 1 | 2 | 2 | 20.3 | 40.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | Shell Plate | P16 | SDM_A5C_3-1C_P16 | PL12x2052 | 5089 | A36 | 1 | 2 | 2 | 983.4 | 1966.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | PLATE | P17 | SDM_A5C_3-1C_P17 | PL12x524 | 2053 | A36 | 3 | 2 | 6 | 28.6 | 171.6 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | PLATE | P18 | SDM_A5C_3-1C_P18 | PL20x477 | 1805 | A36 | 2 | 2 | 4 | 48.7 | 194.8 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | PLATE | P19 | SDM_A5C_3-1C_P19 | PL12x2051 | 2550 | A36 | 1 | 2 | 2 | 434.1 | 868.2 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | PLATE | P20 | SDM_A5C_3-1C_P20 | PL15x110 | 200 | A36 | 2 | 2 | 4 | 5.5 | 22 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.C | PLATE | P21 | SDM_A5C_3-1C_P21 | PL20x160 | 320 | A36 | 2 | 2 | 4 | 7.6 | 30.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E |  |  |  | 11101xx697x2131 |  |  |  | 2 |  | 2109.9 | 8439.6 | AMC2 | [7 empty] | 0 | 0.6 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | Shell Plate | P1 | SDM_A5C_3-1E_P1 | PL10x1736 | 3622 | A36 | 1 | 2 | 2 | 493.5 | 987 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | PLATE | P6 | SDM_A5C_3-1E_P6 | PL10x465 | 1768 | A36 | 1 | 2 | 2 | 20.3 | 40.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | PLATE | P13 | SDM_A5C_3-1E_P13 | PL10x389 | 640 | A36 | 1 | 2 | 2 | 19.5 | 39 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | PLATE | P14 | SDM_A5C_3-1E_P14 | PL20x488 | 1805 | A36 | 2 | 2 | 4 | 48.1 | 192.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | Shell Plate | P15 | SDM_A5C_3-1E_P15 | PL12x2030 | 2664 | A36 | 1 | 2 | 2 | 428.3 | 856.6 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | Shell Plate | P16 | SDM_A5C_3-1E_P16 | PL12x2052 | 5089 | A36 | 1 | 2 | 2 | 983.4 | 1966.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.21 | 24D06641-00-M4130#A5C_3.E | PLATE | P17 | SDM_A5C_3-1E_P17 | PL12x524 | 2053 | A36 | 3 | 2 | 6 | 28.6 | 171.6 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 12 | 2026-07-10 |  |  |  | -6
141 | 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.1 | SPOOL_4.1 |  |  | 11920x2500x2747 |  |  |  | 2 |  | 7199.8 | 28799.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | -
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A |  |  |  | 11920x2165x755 |  |  |  | 2 |  | 2505.5 | 10022 | AMC2 | [7 empty] | 1 | 0.67544 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | Shell Plate | P1 | SDM_A5C_4-1A_P1 | PL10x2314 | 11920 | A36 | 1 | 2 | 2 | 1381.3 | 2762.6 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công |  |  |  |  | REVISED, sửa đổi bản vẽ SGP | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | PLATE | P2 | SDM_A5C_4-1A_P2 | PL15x320 | 11770 | A36 | 2 | 2 | 4 | 443.5 | 1774 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | PLATE | P3 | SDM_A5C_4-1A_P3 | PL10x303 | 852 | A36 | 1 | 2 | 2 | 9.2 | 18.4 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | PLATE | P4 | SDM_A5C_4-1A_P4 | PL10x200 | 794 | A36 | 7 | 2 | 14 | 8.5 | 119 | AMC2 | Plate | MCC |  |  | 7 | 7 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 7 | 1 | 6 | AMC2-S4 | 1 | 7 | 6 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-07-10 |  |  |  | -14
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | PLATE | P4A | SDM_A5C_4-1A_P4A | PL10x200 | 794 | A36 | 7 | 2 | 14 | 8.5 | 119 | AMC2 | Plate | MCC |  |  | 8 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 7 | 1 | 6 | AMC2-S4 | 1 | 7 | 7 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-07-10 |  |  |  | -14
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | PLATE | P5 | SDM_A5C_4-1A_P5 | PL16x137 | 337 | A36 | 14 | 2 | 28 | 3.5 | 98 | AMC2 | Plate | MCC |  |  | 14 | 14 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 14 | 1 | 13 | AMC2-S4 | 1 | 14 | 13 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 56 | 2026-08-14 |  |  |  | -28
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.A | PIPE | D1 | SDM_A5C_4-1A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 6 | 2 | 12 | 13.057 | 156.6835 | AMC2 | Shape | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 24 | 2026-07-28 |  |  |  | -12
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.C |  |  |  | 11820x1250x2067 |  |  |  | 2 |  | 2347.1 | 9388.4 | AMC2 | [7 empty] | 1 | 0.73333 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.C | Shell Plate | P6 | SDM_A5C_4-1C_P6 | PL10x2314 | 11920 | A36 | 1 | 2 | 2 | 2165.5 | 4331 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công |  |  |  |  | REVISED, sửa đổi bản vẽ SGP | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.C | PLATE | P7 | SDM_A5C_4-1C_P7 | PL10x695 | 2165 | A36 | 7 | 2 | 14 | 27.2 | 380.8 | AMC2 | Plate | MCC |  |  | 7 | 7 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 7 | 1 | 6 | AMC2-S4 | 1 | 7 | 6 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-07-10 |  |  |  | -14
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.C | PLATE | P8 | SDM_A5C_4-1C_P8 | PL15x110 | 200 | A36 | 1 | 2 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.C | PLATE | P9 | SDM_A5C_4-1C_P9 | PL20x160 | 320 | A36 | 1 | 2 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.D |  |  |  | 11820x1250x2067 |  |  |  | 2 |  | 2347.1 | 9388.4 | AMC2 | [7 empty] | 1 | 0.6 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | i | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.D | Shell Plate | P6 | SDM_A5C_4-1D_P6 | PL10x2314 | 11920 | A36 | 1 | 2 | 2 | 2165.5 | 4331 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công |  |  |  |  | REVISED, sửa đổi bản vẽ SGP | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.D | PLATE | P7 | SDM_A5C_4-1D_P7 | PL10x695 | 2165 | A36 | 7 | 2 | 14 | 27.2 | 380.8 | AMC2 | Plate | MCC |  |  | 7 | 7 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 7 | 1 | 6 | AMC2-S4 | 1 | 7 | 6 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 28 | 2026-07-10 |  |  |  | -14
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.D | PLATE | P8 | SDM_A5C_4-1D_P8 | PL15x110 | 200 | A36 | 1 | 2 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.23 | 24D06641-00-M4130#A5C_4.D | PLATE | P9 | SDM_A5C_4-1D_P9 | PL20x160 | 320 | A36 | 1 | 2 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
142 | 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | SPOOL_5.1 |  |  | 11415x2352x2651 |  |  |  | 2 |  | 6373.3 | 25493.2 | AMC2 | [7 empty] | 0 | 0.7037 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S2 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | Shell Plate | P1 | SDM_A5C_5-1_P1 | PL10x6315 | 9403 | A36 | 1 | 2 | 2 | 4302.9 | 8605.8 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | Shell Plate | P2 | SDM_A5C_5-1_P2 | PL10x2199 | 6061 | A36 | 1 | 2 | 2 | 862.7 | 1725.4 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P3 | SDM_A5C_5-1_P3 | PL10x2156 | 2260 | A36 | 2 | 2 | 4 | 62.4 | 249.6 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 8 |  |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P4 | SDM_A5C_5-1_P4 | PL10x2156 | 2260 | A36 | 2 | 2 | 4 | 54.7 | 218.8 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 8 |  |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P5 | SDM_A5C_5-1_P5 | PL15x320 | 3516 | A36 | 2 | 2 | 4 | 132.5 | 530 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P6 | SDM_A5C_5-1_P6 | PL10x2260 | 2260 | A36 | 1 | 2 | 2 | 63.3 | 126.6 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P7 | SDM_A5C_5-1_P7 | PL20x2352 | 2450 | A36 | 1 | 2 | 2 | 183.9 | 367.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P8 | SDM_A5C_5-1_P8 | PL10x400 | 2338 | A36 | 1 | 2 | 2 | 73.4 | 146.8 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P9 | SDM_A5C_5-1_P9 | PL20x180 | 254 | A36 | 2 | 2 | 4 | 7.2 | 28.8 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P10 | SDM_A5C_5-1_P10 | PL10x240 | 400 | A36 | 1 | 2 | 2 | 7.5 | 15 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P11 | SDM_A5C_5-1_P11 | PL3x230 | 390 | AISI304 | 1 | 2 | 2 | 2.1 | 4.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP004 A320-11-CP004 A320-21-CP004 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P12 | SDM_A5C_5-1_P12 | PL10x310 | 852 | A36 | 2 | 2 | 4 | 9.3 | 37.2 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P13 | SDM_A5C_5-1_P13 | PL16x129 | 301 | A36 | 2 | 2 | 4 | 3 | 12 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 8 | 2026-08-14 |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P14 | SDM_A5C_5-1_P14 | PL15x320 | 3750 | A36 | 2 | 2 | 4 | 141.3 | 565.2 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P15 | SDM_A5C_5-1_P15 | PL16x129 | 289 | A36 | 2 | 2 | 4 | 2.7 | 10.8 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 8 | 2026-08-14 |  |  |  | -4
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P17 | SDM_A5C_5-1_P17 | PL15x110 | 200 | A36 | 1 | 2 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | MODIFY, Part Mark: P16->P17 | [10 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PLATE | P16 | SDM_A5C_5-1_P16 | PL20x160 | 320 | A36 | 1 | 2 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | MODIFY, Part Mark: P17->P16 | [10 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.25 | 24D06641-00-M4130#A5C_5.1 | PIPE | D1 | SDM_A5C_5-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 2 | 2 | 4 | 13.057 | 52.2278 | AMC2 | Shape | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 8 | 2026-07-28 |  |  |  | -4
143 | 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | SPOOL_6.1 |  |  | 11612xx2260x2441 |  |  |  | 2 |  | 5074 | 20296 | AMC2 | [7 empty] | 0 | 0.5 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S2 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | Shell Plate | P1 | SDM_A5C_6-1_P1 | PL8x3583 | 11647 | A36 | 1 | 2 | 2 | 854.3 | 1708.6 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | Shell Plate | P2 | SDM_A5C_6-1_P2 | PL10x3788 | 5374 | A36 | 1 | 2 | 2 | 1229 | 2458 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | Shell Plate | P3 | SDM_A5C_6-1_P3 | PL10x4264 | 5462 | A36 | 1 | 2 | 2 | 1828.1 | 3656.2 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P4 | SDM_A5C_6-1_P4 | PL15x320 | 11512 | A36 | 2 | 2 | 4 | 433.8 | 1735.2 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P5 | SDM_A5C_6-1_P5 | PL8x1481 | 1616 | A36 | 2 | 2 | 4 | 27.4 | 109.6 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 0 | 2 | AMC2-S4 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 8 |  |  |  |  | -4
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P6 | SDM_A5C_6-1_P6 | PL8x1481 | 1616 | A36 | 1 | 2 | 2 | 24.2 | 48.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P7 | SDM_A5C_6-1_P7 | PL10x2156 | 2260 | A36 | 1 | 2 | 2 | 62.4 | 124.8 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P8 | SDM_A5C_6-1_P8 | PL10x2156 | 2260 | A36 | 2 | 2 | 4 | 54.6 | 218.4 | AMC2 | Plate | MCC |  |  | 4 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 2 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 8 |  |  |  |  | -4
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P9 | SDM_A5C_6-1_P9 | PL16x129 | 301 | A36 | 4 | 2 | 8 | 3 | 24 | AMC2 | Plate | MCC |  |  | 4 | 4 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 4 | 1 | 3 | AMC2-S4 | 1 | 4 | 3 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 16 | 2026-08-14 |  |  |  | -8
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P10 | SDM_A5C_6-1_P10 | PL16x98 | 182 | A36 | 6 | 2 | 12 | 1.4 | 16.8 | AMC2 | Plate | MCC |  |  | 6 | 6 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 6 | 1 | 5 | AMC2-S4 | 1 | 6 | 5 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 24 | 2026-08-14 |  |  |  | -12
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P11 | SDM_A5C_6-1_P11 | PL15x110 | 200 | A36 | 2 | 2 | 4 | 5.5 | 22 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P12 | SDM_A5C_6-1_P12 | PL20x160 | 320 | A36 | 2 | 2 | 4 | 7.6 | 30.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PLATE | P13 | SDM_A5C_6-1_P13 | PL16x98 | 182 | A36 | 5 | 2 | 10 | 1.4 | 14 | AMC2 | Plate | MCC |  |  | 5 | 5 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 5 | 1 | 4 | AMC2-S4 | 1 | 5 | 4 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 20 | 2026-08-14 |  |  |  | -10
| 24D06641-00-M4131_Sh.27 | 24D06641-00-M4130#A5C_6.1 | PIPE | D1 | SDM_A5C_6-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 2 | 10 | 13.057 | 130.5696 | AMC2 | Shape | MCC |  |  | 5 | 5 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 5 | 1 | 4 | AMC2-S4 | 1 | 5 | 4 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 20 | 2026-07-28 |  |  |  | -10
144 | 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | SPOOL_7.1 |  |  | 11812xx2112x2017 |  |  |  | 2 |  | 4119.7 | 16478.8 | AMC2 | [7 empty] | 0 | 0.42308 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S2 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | Shell Plate | P1 | SDM_A5C_7-1_P1 | PL8x3583 | 11647 | A36 | 1 | 2 | 2 | 2620.5 | 5241 | AMC2 | Plate | PMC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 4 |  |  |  |  | -2
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P2 | SDM_A5C_7-1_P2 | PL15x320 | 11547 | A36 | 2 | 2 | 4 | 435.1 | 1740.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P3 | SDM_A5C_7-1_P3 | PL20x1456 | 1677 | A36 | 1 | 2 | 2 | 323.1 | 646.2 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P4 | SDM_A5C_7-1_P4 | PL16x120 | 630 | A36 | 3 | 2 | 6 | 9.3 | 55.8 | AMC2 | Plate | MCC |  |  | 3 | 3 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 3 | 1 | 2 | AMC2-S4 | 1 | 3 | 2 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 12 | 2026-08-14 |  |  |  | -6
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P5 | SDM_A5C_7-1_P5 | PL20x275 | 1100 | A36 | 1 | 2 | 2 | 47.5 | 95 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 4 | 2026-08-08 |  |  |  | -2
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P6 | SDM_A5C_7-1_P6 | PL5x190 | 255 | AISI304 | 2 | 2 | 4 | 1.9 | 7.6 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 0 | 2 | AMC2-S4 | 1 | 2 | 0 | 2 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP006 A320-11-CP006 A320-21-CP006 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P7 | SDM_A5C_7-1_P7 | PL16x80 | 325 | A36 | 1 | 2 | 2 | 3.3 | 6.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 4 | 2026-08-14 |  |  |  | -2
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P7A | SDM_A5C_7-1_P7A | PL16x80 | 325 | A36 | 1 | 2 | 2 | 3.3 | 6.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 4 | 2026-08-14 |  |  |  | -2
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P8 | SDM_A5C_7-1_P8 | PL16x80 | 100 | A36 | 1 | 2 | 2 | 0.8 | 1.6 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 4 | 2026-08-14 |  |  |  | -2
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P9 | SDM_A5C_7-1_P9 | PL8x1616 | 1616 | A36 | 5 | 2 | 10 | 24.2 | 242 | AMC2 | Plate | MCC |  |  | 0 | 10 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 5 | 0 | 5 | AMC2-S4 | 1 | 5 | 0 | 5 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 20 |  |  |  |  | -10
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P10 | SDM_A5C_7-1_P10 | PL15x341 | 609 | A36 | 2 | 2 | 4 | 16.8 | 67.2 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P11 | SDM_A5C_7-1_P11 | PL16x98 | 182 | A36 | 10 | 2 | 20 | 1.4 | 28 | AMC2 | Plate | MCC |  |  | 10 | 10 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 10 | 1 | 9 | AMC2-S4 | 1 | 10 | 9 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 40 | 2026-08-14 |  |  |  | -20
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PIPE | D1 | SDM_A5C_7-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 2 | 10 | 13.057 | 130.5696 | AMC2 | Shape | MCC |  |  | 5 | 5 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 5 | 1 | 4 | AMC2-S4 | 1 | 5 | 4 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP503 A320-11-CP503 A320-21-CP503 | 20 | 2026-07-28 |  |  |  | -10
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P12 | SDM_A5C_7-1_P12 | PL15x110 | 200 | A36 | 2 | 2 | 4 | 5.5 | 22 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP010 A320-11-CP010 A320-21-CP010 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.30 | 24D06641-00-M4130#A5C_7.1 | PLATE | P13 | SDM_A5C_7-1_P13 | PL20x160 | 320 | A36 | 2 | 2 | 4 | 7.6 | 30.4 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S2 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP012 A320-11-CP012 A320-21-CP012 | 8 | 2026-08-08 |  |  |  | -4
145 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Front/rear shim pack |  |  | 200x93x40 |  |  |  | 8 |  | 4.9 | 78.4 | AMC2 | [7 empty] | 0 | 0.31818 |  |  |  |  | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  | AMC2-S4 | 4 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P1 | SDM_A10_P1 | PL5x93 | 200 | A36 | 2 | 8 | 16 | 0.6 | 9.6 | AMC2 | Plate | MCC |  |  | 16 | 0 | 8 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 8 | 4 | 4 | AMC2-S4 | 4 | 8 | 8 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP005 A320-11-CP005 A320-21-CP005 | 32 | 2026-07-10 |  |  |  | -16
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P2 | SDM_A10_P2 | PL3x93 | 200 | A36 | 2 | 8 | 16 | 0.4 | 6.4 | AMC2 | Plate | MCC |  |  | 0 | 16 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 8 | 0 | 8 | AMC2-S4 | 4 | 8 | 0 | 8 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP003 A320-11-CP003 A320-21-CP003 | 32 | 2026-07-28 |  |  |  | -16
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P3 | SDM_A10_P3 | PL2x93 | 200 | A36 | 6 | 8 | 48 | 0.2 | 9.6 | AMC2 | Plate | MCC |  |  | 0 | 48 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 24 | 0 | 24 | AMC2-S4 | 4 | 24 | 0 | 24 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP002 A320-11-CP002 A320-21-CP002 | 96 | 2026-07-28 |  |  |  | -48
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P4 | SDM_A10_P4 | PL1x93 | 200 | A36 | 12 | 8 | 96 | 0.1 | 9.6 | AMC2 | Plate | MCC |  |  | 0 | 96 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 48 | 0 | 48 | AMC2-S4 | 4 | 48 | 0 | 48 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP001 A320-11-CP001 A320-21-CP001 | 156 | 2026-07-10 |  |  |  | -60
146 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Front/rear saddle support |  |  | 200x200x103 |  |  |  | 8 |  | 5.8 | 92.8 | AMC2 | [7 empty] | 0 | 0.125 |  |  |  |  | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  | AMC2-S4 | 4 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Threaded Bar | B2495 | SDM_A11_B2495 | M24x95L (Pitch 3mm; 6G) | 95 |  | 4 | 8 | 32 | 0.3 | 9.6 | AMC2 | Shape | PMC |  |  | 0 | 32 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 (+ thêm 30mm lượng dư cho PMC) |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 16 | 0 | 16 | AMC2-S4 | 4 | 16 | 0 | 16 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC |  |  |  |  | Modify, Pur. -> Fab., Add remark | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-21-CP505 | 64 | 2026-07-28 |  |  |  | -32
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Countersunk Bolt | B0616 | SDM_A11_B0616 | M6x16L (Pitch 1mm; 6H) |  |  | 4 | 8 | 32 | 0.036 | 1.152 | AMC2 | Purchasing | KHO |  |  | 0 | 32 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 16 | 0 | 16 | AMC2-S4 | 4 | 16 | 0 | 16 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Plate | P1 | SDM_A11_P1 | PL16x200 | 200 | A36 | 1 | 8 | 8 | 5 | 40 | AMC2 | Plate | PMC |  |  | 0 | 8 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 0 | 4 | AMC2-S4 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-01-CP011 A320-11-CP011 A320-21-CP011 | 16 | 2026-08-14 |  |  |  | -8
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Teflon PAD | M1 | SDM_A11_M1 | PL5x160x160 |  | Teflon | 1 | 8 | 8 | 0.2816 | 2.2528 | AMC2 | Purchasing | KHO |  |  | 0 | 8 | 0 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 0 | 4 | AMC2-S4 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
147 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Front/rear lateral guides |  |  | 200x190x170 |  |  |  | 8 |  | 17.2 | 275.2 | AMC2 | [7 empty] | 0 | 0.3125 |  |  |  |  | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  | AMC2-S4 | 4 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Plate | P1 | SDM_A12_P1 | PL40x170 | 200 | A36 | 1 | 8 | 8 | 9.5 | 76 | AMC2 | Plate | MCC |  |  | 1 | 7 | 1 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 1 | 3 | AMC2-S4 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP014 A320-11-CP014 A320-21-CP014 | 16 | 2026-07-28 |  |  |  | -8
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Plate | P2 | SDM_A12_P2 | PL40x150 | 170 | A36 | 1 | 8 | 8 | 8 | 64 | AMC2 | Plate | MCC |  |  | 1 | 7 | 1 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 1 | 3 | AMC2-S4 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP014 A320-11-CP014 A320-21-CP014 | 16 | 2026-07-28 |  |  |  | -8
148 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A13 | Lower sealing plate |  |  | 186xx400x16 |  | A36 |  | 4 |  | 5.3 | 42.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:2), LOT 2(Qty:4), LOT 3(Qty:2) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 2 |  | 2 |  | AMC2-S4 | 2 |  | 2 |  | N/A | 0 |  |  |  |  | FAC 1(x2 set) | FAC 1(x2 set)/AMC2(x2 set) | AMC2(x2 set) | - | o
149 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A14 | Lower sealing plate |  |  | 236xx400x16 |  | A36 |  | 2 |  | 7.5 | 300 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:10), LOT 2(Qty:20), LOT 3(Qty:10) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1- set) | FAC 1(x1- set)/AMC2(x1- set) | AMC2(x1- set) | - | o
150 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A15 | Fixed saddle shim |  |  | 640x115x1 |  | A36 |  | 2 |  | 0.5 | 20 | AMC2 | [7 empty] | 0 | 0.45455 |  |  |  |  | LOT 1(Qty:10), LOT 2(Qty:20), LOT 3(Qty:10) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1- set) | FAC 1(x1- set)/AMC2(x1- set) | AMC2(x1- set) | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A15 | Shim Plate | P1 | SDM_A15_P1 | PL1x115 | 640 | A36 | 1 | 2 | 2 | 0.5 | 1 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:10), LOT 2(Qty:20), LOT 3(Qty:10) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1- set) | FAC 1(x1- set)/AMC2(x1- set) | AMC2(x1- set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP019 A320-11-CP001 A320-21-CP001 | 40 | 2026-07-10 |  |  |  | -38
151 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A16 | Sliding saddle shim |  |  | 400x115x1 |  | A36 |  | 40 |  | 0.3 | 24 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:20), LOT 2(Qty:40), LOT 3(Qty:20) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 20 |  | 20 |  | AMC2-S4 | 20 |  | 20 |  | N/A | 0 |  |  |  |  | FAC 1(x2- set) | FAC 1(x2- set)/AMC2(x2- set) | AMC2(x2- set) | - | o
152 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A17 | Sliding saddle baseplate |  |  | 240x400x12 |  |  |  | 2 |  | 6 | 24 | AMC2 | [7 empty] | 0 | 0.16667 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A17 | Plate | P1 | SDM_A17_P1 | PL10x240 | 400 | A36 | 1 | 2 | 2 | 7.5 | 15 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A17 | Teflon PAD | M1 | SDM_A17_M1 | PL5x220x380 |  | Teflon | 1 | 2 | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
153 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A18 | Cylinder øe30 - øi26 H.25 |  |  | 30x30x25 |  | A36 |  | 8 |  | 0.025 | 0.4 | AMC2 | [7 empty] | 2 | 0.5 |  |  |  |  | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  | AMC2-S4 | 4 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A18 | Round Bar | R1 | SDM_A18_R1 | PL2x88 | 25 | A36 | 1 | 8 | 8 | 0.025 | 0.2 | AMC2 | Plate | PMC |  |  | 2 | 6 | 2 | [6 empty] | LOT 1(Qty:4), LOT 2(Qty:8), LOT 3(Qty:4) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 2 | 2 | AMC2-S4 | 4 | 4 | 0 | 4 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x4 set) | FAC 1(x4 set)/AMC2(x4 set) | AMC2(x4 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP002 A320-11-CP002 A320-21-CP002 | 16 | 2026-07-28 |  |  |  | -8
154 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Manhole |  |  | 262x813x942 |  |  |  | 2 |  | 121.5 | 486 | AMC2 | [7 empty] | 0 | 0.25 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Flange | M1 | SDM_A19_M1 | 24" 150# SO R.F (ASME B16.5) |  | A105 | 1 | 2 | 2 | 100 | 200 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Pipe | D1 | SDM_A19_D1 | PL8x250 | 1891 | A36 | 1 | 2 | 2 | 29.7 | 59.4 | AMC2 | Plate | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [5 empty] | Modify, cập nhật nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP007 A320-11-CP007 A320-21-CP007 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Plate | P1 | SDM_A19_P1 | PL12x100 | 716 | A36 | 1 | 2 | 2 | 6.7 | 13.4 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, cập nhật nguyên công | [7 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 4 | 2026-07-10 |  |  |  | -2
155 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Hinge manhole |  |  | 793x570x80 |  |  |  | 2 |  | 25.4 | 101.6 | AMC2 | [7 empty] | 0 | 0.25 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Round Bar | R1 | SDM_A20_R1 | RB60 | 1096 | A36 | 1 | 2 | 2 | 24.3 | 48.6 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP507 A320-11-CP508 A320-21-CP509 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Angle | A1 | SDM_A20_A1 | L80x80x10 | 80 | A36 | 1 | 2 | 2 | 1.1 | 2.2 | AMC2 | Shape | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 (L90x10 thay thế L80x10) |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP504 A320-11-CP504 A320-21-CP504 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Plate | P1 | SDM_A20_P1 | PL12x80 | 80 | A36 | 1 | 2 | 2 | 0.2 | 0.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC |  |  |  | MODIFY, cập nhật nguyên công | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP009 A320-11-CP009 A320-21-CP009 | 4 | 2026-07-10 |  |  |  | -2
156 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Closing flange manhole |  |  | 813x860x136 |  |  |  | 2 |  | 187.3 | 749.2 | AMC2 | [7 empty] | 0 | 0.3 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Blind Flange | M1 | SDM_A21_M1 | 24" 150# R.F (ASME B16.5) |  | A105 | 1 | 2 | 2 | 100 | 200 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Round Bar | R1 | SDM_A21_R1 | RB20 | 326 | A36 | 2 | 2 | 4 | 0.8 | 3.2 | AMC2 | Shape | PMC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP506 A320-11-CP506 A320-21-CP507 | 8 | 2026-07-28 |  |  |  | -4
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Round Bar | R2 | SDM_A21_R2 | RB15 | 188 | A36 | 1 | 2 | 2 | 0.3 | 0.6 | AMC2 | Shape | PMC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP505 A320-11-CP505 A320-21-CP506 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Eyes Bolt | M1 | SDM_A21_M1 | M16x260L |  | A36 | 1 | 2 | 2 | 0.6 | 1.2 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
157 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Rupture disk spool |  |  | 1142x1360x985 |  |  |  | 2 |  | 305.6 | 1222.4 | AMC2 | [7 empty] | 0 | 0.39286 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Flange | M1 | SDM_A22_M1 | 28" 150# WN R.F (ASME B16.47 Type A) |  | A105 | 1 | 2 | 2 | 155 | 310 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Pipe | D1 | SDM_A22_D1 | 28" SCH.STD (Ø711x9.53t) | 761 | A106 Gr.B | 1 | 2 | 2 | 125.4585 | 250.9169 | AMC2 | Shape | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP502 A320-11-CP502 A320-21-CP502 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P1 | SDM_A22_P1 | PL30x225 | 250 | A36 | 1 | 2 | 2 | 10.5 | 21 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP013 A320-11-CP013 A320-21-CP013 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P2 | SDM_A22_P2 | PL10x60 | 620 | A36 | 2 | 2 | 4 | 2.9 | 11.6 | AMC2 | Plate | MCC |  |  | 2 | 2 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 1 | 1 | AMC2-S4 | 1 | 2 | 1 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 8 | 2026-07-10 |  |  |  | -4
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P3 | SDM_A22_P3 | PL10x70 | 80 | A36 | 1 | 2 | 2 | 0.4 | 0.8 | AMC2 | Plate | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP008 A320-11-CP008 A320-21-CP008 | 4 | 2026-07-10 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Mesh | M2 | SDM_A22_M2 | - |  |  | 1 | 2 | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
158 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Rupture disk external spool |  |  | 985x985x737 |  |  |  | 2 |  | 250.4 | 1001.6 | AMC2 | [7 empty] | 0 | 0.3125 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Flange | M1 | SDM_A23_M1 | 28" 150# WN R.F (ASME B16.47 Type A) |  | A105 | 1 | 2 | 2 | 155 | 310 | AMC2 | Purchasing | KHO |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Pipe | D1 | SDM_A23_D1 | 28" SCH.STD (Ø711x9.53t) | 604 | A106 Gr.B | 1 | 2 | 2 | 99.5754 | 199.1509 | AMC2 | Shape | MCC |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-01-CP502 A320-11-CP502 A320-21-CP502 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Plate | P1 | SDM_A23_P1 | PL8x100 | 376 | A36 | 1 | 2 | 2 | 2.4 | 4.8 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP007 A320-11-CP007 A320-21-CP007 | 4 | 2026-07-28 |  |  |  | -2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Mesh | M2 | SDM_A23_M2 | - |  |  | 1 | 2 | 2 | 0.1 | 0.2 | AMC2 | Purchasing | KHO |  |  | 1 | 1 | 1 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 0 | 1 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | [13 empty] | - | - | - | - | - | - | - | Purchasing
159 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A24 | Large washer |  |  | Plate ø80xø32x5 |  | A36 |  | 2 |  | 0.2 | 0.8 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A24 | Washer | WS1 | SDM_A24_WS1 | PL5x80 | 80 | A36 | 1 | 2 | 2 | 0.2 | 0.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 2 | [6 empty] | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 |  | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 | AMC2-S4 | 1 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 0 |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - |  | PAC | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-01-CP005 A320-11-CP005 A320-21-CP005 | 4 | 2026-07-10 |  |  |  | -2
160 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A25 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 3000 | A36 |  | 42 |  | 25 | 2100 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:21), LOT 2(Qty:42), LOT 3(Qty:21) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 21 |  | 21 |  | AMC2-S4 | 21 |  | 21 |  | N/A | 0 |  |  |  |  | FAC 1(x21 set) | FAC 1(x21 set)/AMC2(x21 set) | AMC2(x21 set) | - | o
161 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A27 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 2455 | A36 |  | 2 |  | 19.6 | 78.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  | 1 |  | AMC2-S4 | 1 |  | 1 |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
162 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A28 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 2418 | A36 |  | 2 |  | 19.3 | 77.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  | 1 |  | AMC2-S4 | 1 |  | 1 |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
163 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A29 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 590 | A36 |  | 2 |  | 4.1 | 16.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  | 1 |  | AMC2-S4 | 1 |  | 1 |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
164 | TW1008-MAG-&MLD020-U-001025_07 | 24D06641-00-M4130#A32 | Pipe 1/2" Sch.STD - Lg.100 mm |  |  | 1/2" Sch.STD | 100 | A36 |  | 2 |  | 0.1 | 0.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o
165 | TW1008-MAG-&MLD020-U-001025_07 | DIN 975 - M30x310 | Stud Bolt |  |  | M30x310L |  | A193 B7 - HDG (DIN 975) |  | 2 |  | 1.7 | 6.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o | [19 empty] | Purchasing
166 | TW1008-MAG-&MLD020-U-001025_07 | Gasket 24" - 150LB | Gasket |  |  | 24" 150# (ASME B16.21) |  | Klingersil |  | 2 |  | 1.5 | 6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:1), LOT 2(Qty:2), LOT 3(Qty:1) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1 set) | FAC 1(x1 set)/AMC2(x1 set) | AMC2(x1 set) | - | o | [19 empty] | Purchasing
167 | TW1008-MAG-&MLD020-U-001025_07 | ISO 4014 - M24x100 | Hex Bolt |  |  | M24x100L |  | A193 B7 - HDG (ISO 4014) |  | 2 |  | 0.5 | 20 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:10), LOT 2(Qty:20), LOT 3(Qty:10) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  | AMC2-S4 | 1 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x1- set) | FAC 1(x1- set)/AMC2(x1- set) | AMC2(x1- set) | - | o | [19 empty] | Purchasing
168 | TW1008-MAG-&MLD020-U-001025_07 | ISO 4014 - M30 x 160 | Hex. Bolt |  |  | M30x160L |  | A193 B7 - HDG (ISO 4014) |  | 4 |  | 1.2 | 96 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:20), LOT 2(Qty:40), LOT 3(Qty:20) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 2 |  |  |  | AMC2-S4 | 2 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x2- set) | FAC 1(x2- set)/AMC2(x2- set) | AMC2(x2- set) | - | o | [19 empty] | Purchasing
169 | TW1008-MAG-&MLD020-U-001025_07 | ISO 4014 - M30 x 220 | Hex. Bolt |  |  | M30x220L |  | A193 B7 - HDG (ISO 4014) |  | 56 |  | 1.5 | 168 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:28), LOT 2(Qty:56), LOT 3(Qty:28) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 28 |  |  |  | AMC2-S4 | 28 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x28 set) | FAC 1(x28 set)/AMC2(x28 set) | AMC2(x28 set) | - | o | [19 empty] | Purchasing
170 | TW1008-MAG-&MLD020-U-001025_07 | ISO 4032 - M24 | Hex. Nut |  |  | M24 |  | A194 2H - HDG (ISO 4032) |  | 52 |  | 0.1 | 10.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:26), LOT 2(Qty:52), LOT 3(Qty:26) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 26 |  |  |  | AMC2-S4 | 26 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x26 set) | FAC 1(x26 set)/AMC2(x26 set) | AMC2(x26 set) | - | o | [19 empty] | Purchasing
171 | TW1008-MAG-&MLD020-U-001025_07 | ISO 4032 - M30 | Hex. Nut |  |  | M30 |  | A194 2H - HDG (ISO 4032) |  | 104 |  | 0.3 | 62.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:52), LOT 2(Qty:104), LOT 3(Qty:52) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 52 |  |  |  | AMC2-S4 | 52 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x52 set) | FAC 1(x52 set)/AMC2(x52 set) | AMC2(x52 set) | - | o | [19 empty] | Purchasing
172 | TW1008-MAG-&MLD020-U-001025_07 | ISO 4032 -M16 | Hex. Nut |  |  | M16 |  | A194 2H - HDG (ISO 4032) |  | 6 |  | 0.1 | 1.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:3), LOT 2(Qty:6), LOT 3(Qty:3) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 3 |  |  |  | AMC2-S4 | 3 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x3 set) | FAC 1(x3 set)/AMC2(x3 set) | AMC2(x3 set) | - | o | [19 empty] | Purchasing
173 | TW1008-MAG-&MLD020-U-001025_07 | ISO 7089 - 16 | Washer |  |  | M16 |  | F436 - HDG |  | 4 |  | 0.1 | 0.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:2), LOT 2(Qty:4), LOT 3(Qty:2) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 2 |  |  |  | AMC2-S4 | 2 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x2 set) | FAC 1(x2 set)/AMC2(x2 set) | AMC2(x2 set) | - | o | [19 empty] | Purchasing
174 | TW1008-MAG-&MLD020-U-001025_07 | ISO 7089 - 24 | Washer |  |  | M24 |  | F436 - HDG |  | 72 |  | 0.033333 | 4.8 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:36), LOT 2(Qty:72), LOT 3(Qty:36) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 36 |  |  |  | AMC2-S4 | 36 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x36 set) | FAC 1(x36 set)/AMC2(x36 set) | AMC2(x36 set) | - | o | [19 empty] | Purchasing
175 | TW1008-MAG-&MLD020-U-001025_07 | ISO 7089 - 30 | Washer |  |  | M30 |  | F436 - HDG |  | 192 |  | 0.1 | 38.4 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 1(Qty:96), LOT 2(Qty:192), LOT 3(Qty:96) | SDM Street 15->12 | x | N/A | 0 |  |  |  | AMC2-S1 | 96 |  |  |  | AMC2-S4 | 96 |  |  |  | N/A | 0 |  |  |  |  | FAC 1(x96 set) | FAC 1(x96 set)/AMC2(x96 set) | AMC2(x96 set) | - | o | [19 empty] | Purchasing
31 | 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.0 | SPOOL_4C_1.0 |  |  | 11418xx3413x3257 |  |  |  | 1 |  | 10124.3 | 10124 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A |  |  |  | 11418xx2138x679 |  |  |  | 1 |  | 2640.2 | 2640 | AMC2 | [7 empty] | 0 | 0.22727 |  |  |  |  | LOT 4 | SDM Street 18 | i | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Shell Plate | P1 | SDM_A4C_1-0A_P1 | PL12x2130 | 11306 | A36 | 1 | 1 | 1 | 1397.9 | 1397.9 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P2 | SDM_A4C_1-0A_P2 | PL15x350 | 10728 | A36 | 2 | 1 | 2 | 442.1 | 884.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P3 | SDM_A4C_1-0A_P3 | PL10x180 | 2107 | A36 | 1 | 1 | 1 | 29.8 | 29.8 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P4 | SDM_A4C_1-0A_P4 | PL20x611 | 2098 | A36 | 1 | 1 | 1 | 77.7 | 77.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P5 | SDM_A4C_1-0A_P5 | PL12x80 | 301 | A36 | 4 | 1 | 4 | 3.3 | 13.2 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 0 | 4 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 4 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P6 | SDM_A4C_1-0A_P6 | PL12x80 | 223 | A36 | 2 | 1 | 2 | 1.7 | 3.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P7 | SDM_A4C_1-0A_P7 | PL20x200 | 1100 | A36 | 1 | 1 | 1 | 34.5 | 34.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P8 | SDM_A4C_1-0A_P8 | PL5x180 | 190 | AISI304 | 2 | 1 | 2 | 1.3 | 2.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [7 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP005 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P9 | SDM_A4C_1-0A_P9 | PL10x286 | 852 | A36 | 2 | 1 | 2 | 8.5 | 17 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P10 | SDM_A4C_1-0A_P10 | PL10x223 | 341 | A36 | 2 | 1 | 2 | 4.8 | 9.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P11 | SDM_A4C_1-0A_P11 | PL12x1823 | 667 | A36 | 10 | 1 | 10 | 9.2 | 92 | AMC2 | Plate | MCC |  |  | 0 | 10 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 10 | 0 | 10 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 10 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | Plate | P12 | SDM_A4C_1-0A_P12 | PL16x154 | 426 | A36 | 10 | 1 | 10 | 5 | 50 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 10 | 10 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 10 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | PIPE | D1 | SDM_A4C_1-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 1 | 5 | 13.057 | 65.2848 | AMC2 | Shape | MCC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP503 | 5 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.A | PIPE | D2 | SDM_A4C_1-0A_D2 | 1/2" SCH.STD (OD21.3x2.77t) | 737 | A53 Gr.B | 1 | 1 | 1 | 2.1 | 2.1 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP501 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.B |  |  |  | 11306xx757x2138 |  |  |  | 1 |  | 2477.3 | 2477 | AMC2 | [7 empty] | 0 | 0.11111 |  |  |  |  | LOT 4 | SDM Street 18 | i | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.B | Shell Plate | P14 | SDM_A4C_1-0B_P14 | PL12x2130 | 11306 | A36 | 1 | 1 | 1 | 2268.5 | 2268.5 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.B | Plate | P17 | SDM_A4C_1-0B_P17 | PL10x180 | 481 | A36 | 1 | 1 | 1 | 6.8 | 6.8 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.B | Plate | P18 | SDM_A4C_1-0B_P18 | PL20x501 | 2097 | A36 | 1 | 1 | 1 | 41.1 | 41.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.B | Plate | P22 | SDM_A4C_1-0B_P22 | PL12x535 | 2138 | A36 | 5 | 1 | 5 | 31.8 | 159 | AMC2 | Plate | MCC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 5 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.B | PIPE | P26 | SDM_A4C_1-0B_P26 | PL15x356 | 781 | A36 | 1 | 1 | 1 | 21.7 | 21.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.C |  |  |  | 11306xx2138x682 |  |  |  | 1 |  | 2466.5 | 2466 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | LOT 4 | SDM Street 18 | i | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.C | Shell Plate | P14 | SDM_A4C_1-0C_P14 | PL12x2130 | 11306 | A36 | 1 | 1 | 1 | 2268.5 | 2268.5 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [6 empty] | Added, thêm nguyên công |  |  |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.C | Plate | P22 | SDM_A4C_1-0C_P22 | PL12x535 | 2138 | A36 | 5 | 1 | 5 | 31.8 | 159 | AMC2 | Plate | MCC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 5 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.C | Plate | P23 | SDM_A4C_1-0C_P23 | PL20x505 | 2096 | A36 | 1 | 1 | 1 | 42 | 42 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.C | Plate | P27 | SDM_A4C_1-0C_P27 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.C | Plate | P28 | SDM_A4C_1-0C_P28 | PL20x110 | 200 | A36 | 2 | 1 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công |  |  | REVISED, PL15->20 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D |  |  |  | 11306xx794x2138 |  |  |  | 1 |  | 2540.3 | 2540 | AMC2 | [7 empty] | 0 | 0.045455 |  |  |  |  | LOT 4 | SDM Street 18 | i | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Shell Plate | P13 | SDM_A4C_1-0D_P13 | PL12x2130 | 11306 | A36 | 1 | 1 | 1 | 2268.5 | 2268.5 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P15 | SDM_A4C_1-0D_P15 | PL10x293 | 338 | A36 | 2 | 1 | 2 | 4.5 | 9 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P16 | SDM_A4C_1-0D_P16 | PL10x163 | 170 | A36 | 1 | 1 | 1 | 1.6 | 1.6 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P17 | SDM_A4C_1-0D_P17 | PL10x180 | 481 | A36 | 1 | 1 | 1 | 6.8 | 6.8 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P18 | SDM_A4C_1-0D_P18 | PL20x501 | 2097 | A36 | 1 | 1 | 1 | 41.1 | 41.1 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P19 | SDM_A4C_1-0D_P19 | PL10x1071 | 1136 | A36 | 1 | 1 | 1 | 43.8 | 43.8 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công |  | REVISED, cập nhật nguyên công |  |  |  | 1 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P20 | SDM_A4C_1-0D_P20 | PL10x255 | 2203 | A36 | 1 | 1 | 1 | 44.1 | 44.1 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P21 | SDM_A4C_1-0D_P21 | PL10x231 | 1884 | A36 | 1 | 1 | 1 | 34.2 | 34.2 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [11 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P22 | SDM_A4C_1-0D_P22 | PL12x535 | 2138 | A36 | 5 | 1 | 5 | 31.8 | 159 | AMC2 | Plate | MCC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 5 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | Plate | P24 | SDM_A4C_1-0D_P24 | PL15x408 | 825 | A36 | 1 | 1 | 1 | 25.8 | 25.8 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | PIPE | P25 | SDM_A4C_1-0D_P25 | PL15x354 | 767 | A36 | 1 | 1 | 1 | 21.7 | 21.7 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | PIPE | D2 | SDM_A4C_1-0D_D2 | 1/2" SCH.STD (OD21.3x2.77t) | 737 | A53 Gr.B | 5 | 1 | 5 | 2.1 | 10.5 | AMC2 | Shape | PMC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP501 | 5 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.06 | 24D06641-00-M4130#A4C_1.D | HALF COUPLING | M1 | SDM_A4C_1-0D_M1 | RB50 | 48 | A36 | 1 | 1 | 1 | 0.32 | 0.32 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC |  |  |  |  | Modify, Profile: 1" HALFCOUPLING->RB50 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-31-CP508 | 1 | 2026-08-04
32 | 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.0 | SPOOL_4C_2.0 |  |  | 9819xx3024x3062 |  |  |  | 1 |  | 6787.7 | 6788 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A |  |  |  | 9819xx1944x391 |  |  |  | 1 |  | 1542.1 | 1542 | AMC2 | [7 empty] | 0 | 0.27586 |  |  |  |  | LOT 4 | SDM Street 18 | I | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Shell Plate | P1 | SDM_A4C_2-0A_P1 | PL10x374 | 4829 | A36 | 2 | 1 | 2 | 141.7 | 283.4 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Shell Plate | P2 | SDM_A4C_2-0A_P2 | PL10x512 | 2218 | A36 | 1 | 1 | 1 | 76.2 | 76.2 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Shell Plate | P3 | SDM_A4C_2-0A_P3 | PL10x512 | 2218 | A36 | 1 | 1 | 1 | 76.2 | 76.2 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Shell Plate | P4 | SDM_A4C_2-0A_P4 | PL12x511 | 2700 | A36 | 2 | 1 | 2 | 130.1 | 260.2 | AMC2 | Plate | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Plate | P5 | SDM_A4C_2-0A_P5 | PL15x320 | 9819 | A36 | 2 | 1 | 2 | 370 | 740 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Plate | P6 | SDM_A4C_2-0A_P6 | PL10x152 | 400 | A36 | 6 | 1 | 6 | 4.2 | 25.2 | AMC2 | Plate | MCC |  |  | 0 | 6 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 0 | 6 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 6
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Plate | P7 | SDM_A4C_2-0A_P7 | PL12x170 | 538 | A36 | 2 | 1 | 2 | 7.4 | 14.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Plate | P8 | SDM_A4C_2-0A_P8 | PL16x146 | 363 | A36 | 6 | 1 | 6 | 4 | 24 | AMC2 | Plate | MCC |  |  | 6 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 6 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 6 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | Plate | P9 | SDM_A4C_2-0A_P9 | PL16x154 | 426 | A36 | 2 | 1 | 2 | 5 | 10 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 2 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.A | PIPE | D1 | SDM_A4C_2-0A_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 1 | 5 | 13.057 | 65.2848 | AMC2 | Shape | MCC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP503 | 5 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.B |  |  |  | 9719xx795x2356 |  |  |  | 1 |  | 1867.9 | 1868 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | LOT 4 | SDM Street 18 | I | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.B | Shell Plate | P10 | SDM_A4C_2-0B_P10 | PL10x2016 | 4829 | A36 | 1 | 1 | 1 | 764.2 | 764.2 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.B | Shell Plate | P12 | SDM_A4C_2-0B_P12 | PL12x2367 | 2700 | A36 | 1 | 1 | 1 | 601.9 | 601.9 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.B | Plate | P13 | SDM_A4C_2-0B_P13 | PL10x2242 | 2373 | A36 | 1 | 1 | 1 | 380 | 380 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.B | Shell Plate | P14 | SDM_A4C_2-0B_P14 | PL10x542 | 1992 | A36 | 3 | 1 | 3 | 23.5 | 70.5 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công |  | REVISED, cập nhật nguyên công |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 3
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.B | Plate | P15 | SDM_A4C_2-0B_P15 | PL12x624 | 2317 | A36 | 1 | 1 | 1 | 35.4 | 35.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C |  |  |  | 9719xx1944x960 |  |  |  | 1 |  | 1509.8 | 1510 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | LOT 4 | SDM Street 18 | I | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Shell Plate | P16 | SDM_A4C_2-0C_P16 | PL10x1613 | 4829 | A36 | 1 | 1 | 1 | 611.3 | 611.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Shell Plate | P17 | SDM_A4C_2-0C_P17 | PL10x1667 | 2276 | A36 | 1 | 1 | 1 | 307.3 | 307.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Shell Plate | P18 | SDM_A4C_2-0C_P18 | PL12x1893 | 2700 | A36 | 1 | 1 | 1 | 481.6 | 481.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Plate | P19 | SDM_A4C_2-0C_P19 | PL10x399 | 1671 | A36 | 3 | 1 | 3 | 18.8 | 56.4 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 3
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Plate | P20 | SDM_A4C_2-0C_P20 | PL12x456 | 1944 | A36 | 1 | 1 | 1 | 28.3 | 28.3 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Plate | P21 | SDM_A4C_2-0C_P21 | PL20x160 | 320 | A36 | 2 | 1 | 2 | 7.6 | 15.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.C | Plate | P22 | SDM_A4C_2-0C_P22 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 5.5 | 11 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.D |  |  |  | 9719xx795x2356 |  |  |  | 1 |  | 1867.9 | 1868 | AMC2 | [7 empty] | 0 | 0 |  |  |  |  | LOT 4 | SDM Street 18 | I | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.D | Shell Plate | P10 | SDM_A4C_2-0D_P10 | PL10x2016 | 4829 | A36 | 1 | 1 | 1 | 764.2 | 764.2 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.D | Shell Plate | P11 | SDM_A4C_2-0D_P11 | PL10x2242 | 2373 | A36 | 1 | 1 | 1 | 380 | 380 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.D | Shell Plate | P12 | SDM_A4C_2-0D_P12 | PL12x2367 | 2700 | A36 | 1 | 1 | 1 | 601.9 | 601.9 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.D | Plate | P14 | SDM_A4C_2-0D_P14 | PL10x542 | 1992 | A36 | 3 | 1 | 3 | 23.5 | 70.5 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công |  | REVISED, cập nhật nguyên công |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 3
| 24D06641-00-M4131_Sh.07 | 24D06641-00-M4130#A4C_2.D | Plate | P15 | SDM_A4C_2-0D_P15 | PL12x624 | 2317 | A36 | 1 | 1 | 1 | 35.4 | 35.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 1 | 2026-08-10 |  |  |  | 0
33 | 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | SPOOL_4C_3.1 |  |  | 11640x2417x2606 |  |  |  | 1 |  | 6730.4139 | 6730.4139 | AMC2 | [7 empty] | 0 | 0.1875 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Duct Plate | P1 | SDM_A4C_3-1_P1 | PL10x6315 | 9820 | A36 | 1 | 1 | 1 | 4655.3 | 4655.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Duct Plate | P2 | SDM_A4C_3-1_P2 | PL10x2213 | 6263 | A36 | 1 | 1 | 1 | 795.6 | 795.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Ring Plate | P3 | SDM_A4C_3-1_P3 | PL10x2192 | 2300 | A36 | 1 | 1 | 1 | 71.1 | 71.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Ring Plate | P4 | SDM_A4C_3-1_P4 | PL10x2300 | 2300 | A36 | 2 | 1 | 2 | 74.6 | 149.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Ring Plate | P5 | SDM_A4C_3-1_P5 | PL10x1664 | 2300 | A36 | 1 | 1 | 1 | 48.2 | 48.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P6 | SDM_A4C_3-1_P6 | PL15x282 | 517 | A36 | 1 | 1 | 1 | 13.2 | 13.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Ring Plate | P7 | SDM_A4C_3-1_P7 | PL10x232 | 986 | A36 | 1 | 1 | 1 | 10.4 | 10.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Ring Plate | P8 | SDM_A4C_3-1_P8 | PL20x2330 | 2442 | A36 | 2 | 1 | 2 | 182.4 | 364.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 2 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P9 | SDM_A4C_3-1_P9 | PL10x640 | 2338 | A36 | 1 | 1 | 1 | 117.4 | 117.4 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P10 | SDM_A4C_3-1_P10 | PL20x200 | 246 | A36 | 2 | 1 | 2 | 7.7 | 15.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Base Plate | P11 | SDM_A4C_3-1_P11 | PL30x240 | 640 | A36 | 1 | 1 | 1 | 36.2 | 36.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP012 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P12 | SDM_A4C_3-1_P12 | PL15x320 | 1475 | A36 | 2 | 1 | 2 | 55.6 | 111.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Ring Plate | P13 | SDM_A4C_3-1_P13 | PL10x304 | 852 | A36 | 2 | 1 | 2 | 8.9 | 17.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P14 | SDM_A4C_3-1_P14 | PL16x135 | 301 | A36 | 4 | 1 | 4 | 3 | 12 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 4 | 0 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 4 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P15 | SDM_A4C_3-1_P15 | PL15x320 | 3385 | A36 | 2 | 1 | 2 | 127.5 | 255 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Plate | P16 | SDM_A4C_3-1_P16 | PL16x135 | 310 | A36 | 2 | 1 | 2 | 3.2 | 6.4 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 2 | 0 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | LUG Plate | P17 | SDM_A4C_3-1_P17 | PL20x160 | 260 | A36 | 2 | 1 | 2 | 6.1 | 12.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | PAD Plate | P18 | SDM_A4C_3-1_P18 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.09 | 24D06641-00-M4130#A4C_3.1 | Pipe | D1 | SDM_A4C_3-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 2 | 1 | 2 | 13.057 | 26.1139 | AMC2 | Shape | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP503 | 2 | 2026-08-04 |  |  |  | 0
34 | 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | SPOOL_4C_4.1 |  |  | 11591xx2402x2354 |  |  |  | 1 |  | 6316.3418 | 6316.3418 | AMC2 | [7 empty] | 0 | 0.32432 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Duct Plate | P1 | SDM_A4C_4-1_P1 | PL10x5455 | 11481 | A36 | 1 | 1 | 1 | 4916.3 | 4916.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Plate | P2 | SDM_A4C_4-1_P2 | PL15x320 | 11491 | A36 | 2 | 1 | 2 | 433 | 866 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Ring Plate | P3 | SDM_A4C_4-1_P3 | PL10x2192 | 2300 | A36 | 1 | 1 | 1 | 71.1 | 71.1 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Ring Plate | P4 | SDM_A4C_4-1_P4 | PL10x2192 | 2300 | A36 | 3 | 1 | 3 | 48.2 | 144.6 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 3
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Plate | P5 | SDM_A4C_4-1_P5 | PL15x270 | 517 | A36 | 3 | 1 | 3 | 13.2 | 39.6 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 3 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Ring Plate | P6 | SDM_A4C_4-1_P6 | PL10x232 | 986 | A36 | 3 | 1 | 3 | 10.4 | 31.2 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 | [8 empty] | Added |  | REVISED, PL15->10 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 3
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Ring Plate | P7 | SDM_A4C_4-1_P7 | PL10x2192 | 2300 | A36 | 2 | 1 | 2 | 64.3 | 128.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Plate | P8 | SDM_A4C_4-1_P8 | PL16x135 | 301 | A36 | 2 | 1 | 2 | 1.6 | 3.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 2 | 0 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Plate | P9 | SDM_A4C_4-1_P9 | PL16x135 | 310 | A36 | 10 | 1 | 10 | 2 | 20 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 10 | 10 | 0 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 10 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | LUG Plate | P10 | SDM_A4C_4-1_P10 | PL20x160 | 260 | A36 | 2 | 1 | 2 | 6.1 | 12.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | PAD Plate | P11 | SDM_A4C_4-1_P11 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.11 | 24D06641-00-M4130#A4C_4.1 | Pipe | D1 | SDM_A4C_4-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 6 | 1 | 6 | 13.057 | 78.3418 | AMC2 | Shape | MCC |  |  | 0 | 6 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 6 | 0 | 6 |  | - | - | - | AMC 2 | [8 empty] | Added |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP503 | 6 | 2026-08-04 |  |  |  | 0
35 | 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | SPOOL_4C_5.1 |  |  | 6513x2020x2197 |  |  |  | 1 |  | 2424.3 | 2424 | AMC2 | [7 empty] | 0 | 0.27273 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Duct Plate | P1 | SDM_A4C_5-1_P1 | PL8x3576 | 3797 | A36 | 1 | 1 | 1 | 852.6 | 852.6 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Duct Plate | P2 | SDM_A4C_5-1_P2 | PL10x3216 | 5126 | A36 | 1 | 1 | 1 | 935.3 | 935.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Ring Plate | P3 | SDM_A4C_5-1_P3 | PL8x1479.5 | 1616 | A36 | 2 | 1 | 2 | 27.8 | 55.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 2 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Ring Plate | P4 | SDM_A4C_5-1_P4 | PL8x1479.5 | 1616 | A36 | 1 | 1 | 1 | 24.2 | 24.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Plate | P5 | SDM_A4C_5-1_P5 | PL15x320 | 6413 | A36 | 2 | 1 | 2 | 241.6 | 483.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Plate | P6 | SDM_A4C_5-1_P6 | PL15x198 | 520 | A36 | 2 | 1 | 2 | 7.8 | 15.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Plate | P7 | SDM_A4C_5-1_P7 | PL16x104 | 178 | A36 | 4 | 1 | 4 | 1.3 | 5.2 | AMC2 | Plate | MCC |  |  | 4 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 4 | 4 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 4 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Plate | P8 | SDM_A4C_5-1_P8 | PL16x104 | 188.5 | A36 | 2 | 1 | 2 | 1.5 | 3 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 2 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | LUG Plate | P9 | SDM_A4C_5-1_P9 | PL20x160 | 260 | A36 | 2 | 1 | 2 | 6.1 | 12.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | PAD Plate | P10 | SDM_A4C_5-1_P10 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.13 | 24D06641-00-M4130#A4C_5.1 | Pipe | D1 | SDM_A4C_5-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 3 | 1 | 3 | 13.057 | 39.1709 | AMC2 | Shape | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP503 | 3 | 2026-08-04 |  |  |  | 0
36 | 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | SPOOL_4C_6.1 |  |  | 11816xx2098x1949 |  |  |  | 1 |  | 4132.4 | 4132 | AMC2 | [7 empty] | 0 | 0.37209 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Duct Plate | P1 | SDM_A4C_6-1_P1 | PL8x3576 | 11651 | A36 | 1 | 1 | 1 | 2616.3 | 2616.3 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 1 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Ring Plate | P2 | SDM_A4C_6-1_P2 | PL8x1480 | 1616 | A36 | 3 | 1 | 3 | 24.2 | 72.6 | AMC2 | Plate | MCC |  |  | 0 | 3 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 0 | 3 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 3 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Close Plate | P3 | SDM_A4C_6-1_P3 | PL20x1456 | 1669 | A36 | 1 | 1 | 1 | 321.6 | 321.6 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Base Plate | P4 | SDM_A4C_6-1_P4 | PL20x275 | 1100 | A36 | 1 | 1 | 1 | 47.5 | 47.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 1 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P5 | SDM_A4C_6-1_P5 | PL16x120 | 630 | A36 | 3 | 1 | 3 | 9.3 | 27.9 | AMC2 | Plate | MCC |  |  | 3 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 3 | 3 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 3 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P6 | SDM_A4C_6-1_P6 | PL16x80 | 100 | A36 | 1 | 1 | 1 | 0.8 | 0.8 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P7 | SDM_A4C_6-1_P7 | PL15x320 | 11551 | A36 | 2 | 1 | 2 | 435.2 | 870.4 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P8 | SDM_A4C_6-1_P8 | PL16x80 | 325 | A36 | 2 | 1 | 2 | 3.1 | 6.2 | AMC2 | Plate | MCC |  |  | 2 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 2 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P9 | SDM_A4C_6-1_P9 | PL16x104 | 188.5 | A36 | 10 | 1 | 10 | 1.5 | 15 | AMC2 | Plate | MCC |  |  | 10 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 10 | 10 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP010 | 10 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Ring Plate | P10 | SDM_A4C_6-1_P10 | PL8x1076 | 1616 | A36 | 2 | 1 | 2 | 18 | 36 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | chi tiết chia nối | 2 |  |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Ring Plate | P11 | SDM_A4C_6-1_P11 | PL8x128 | 500 | A36 | 2 | 1 | 2 | 2.8 | 5.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP006 | 2 | 2026-08-11 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P12 | SDM_A4C_6-1_P12 | PL15x306 | 520 | A36 | 2 | 1 | 2 | 14.1 | 28.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P13 | SDM_A4C_6-1_P13 | PL15x352 | 604 | A36 | 2 | 1 | 2 | 16.8 | 33.6 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | LUG Plate | P14 | SDM_A4C_6-1_P14 | PL20x160 | 260 | A36 | 2 | 1 | 2 | 6.1 | 12.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP011 | 2 | 2026-08-10 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | PAD Plate | P15 | SDM_A4C_6-1_P15 | PL15x110 | 200 | A36 | 2 | 1 | 2 | 2.6 | 5.2 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP009 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Plate | P16 | SDM_A4C_6-1_P16 | PL5x190 | 255 | AISI304 | 2 | 1 | 2 | 1.9194 | 3.8387 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 | [7 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP005 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.15 | 24D06641-00-M4130#A4C_6.1 | Pipe | D1 | SDM_A4C_6-1_D1 | 4" SCH.STD (OD114.3x6.02t) | 812 | A53 Gr.B | 5 | 1 | 5 | 13.057 | 65.2848 | AMC2 | Shape | MCC |  |  | 0 | 5 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 5 | 0 | 5 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP503 | 5 | 2026-08-04 |  |  |  | 0
37 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Front/rear shim pack |  |  | 200x93x40 |  |  |  | 4 |  | 4.9 | 20 | AMC2 | [7 empty] | 0 | 0.31818 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P1 | SDM_A10_P1 | PL5x93 | 200 | A36 | 2 | 4 | 8 | 0.6 | 4.8 | AMC2 | Plate | MCC |  |  | 8 | 0 | 4 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 8 | 8 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP004 | 8 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P2 | SDM_A10_P2 | PL3x93 | 200 | A36 | 2 | 4 | 8 | 0.4 | 3.2 | AMC2 | Plate | MCC |  |  | 0 | 8 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 8 | 0 | 8 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP003 | 8 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P3 | SDM_A10_P3 | PL2x93 | 200 | A36 | 6 | 4 | 24 | 0.2 | 4.8 | AMC2 | Plate | MCC |  |  | 0 | 24 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 24 | 0 | 24 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP002 | 24 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A10 | Shim Plate | P4 | SDM_A10_P4 | PL1x93 | 200 | A36 | 12 | 4 | 48 | 0.1 | 4.8 | AMC2 | Plate | MCC |  |  | 0 | 48 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 48 | 0 | 48 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP001 | 48 | 2026-08-04 |  |  |  | 0
38 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Front/rear saddle support |  |  | 200x200x103 |  |  |  | 4 |  | 5.8 | 23 | AMC2 | [7 empty] | 0 | 0.125 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Threaded Bar | B2495 | SDM_A11_B2495 | M24x95L (Pitch 3mm; 6G) | 95 |  | 4 | 4 | 16 | 0.3 | 4.8 | AMC2 | Shape | PMC |  |  | 0 | 16 | 0 | [6 empty] | LOT 4 | SDM Street 18 (+ thêm 30mm lượng dư cho PMC) |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 16 | 0 | 16 |  | - | - | - | AMC 2 |  | PAC |  |  |  |  | Modify, Pur. -> Fab., Add remark | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-31-CP505 | 16 | 2026-08-04
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Countersunk Bolt | B0616 | SDM_A11_B0616 | M6x16L (Pitch 1mm; 6H) |  |  | 4 | 4 | 16 | 0.036 | 0.576 | AMC2 | Purchasing | KHO |  |  | 0 | 16 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 16 | 0 | 16 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Plate | P1 | SDM_A11_P1 | PL16x200 | 200 | A36 | 1 | 4 | 4 | 5 | 20 | AMC2 | Plate | PMC |  |  | 0 | 4 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 0 | 4 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Fabrication | A320-31-CP010 | 4 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A11 | Teflon PAD | M1 | SDM_A11_M1 | PL5x160x160 |  | Teflon | 1 | 4 | 4 | 0.2816 | 1.1264 | AMC2 | Purchasing | KHO |  |  | 0 | 4 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 0 | 4 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
39 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Front/rear lateral guides |  |  | 200x190x170 |  |  |  | 4 |  | 17.2 | 69 | AMC2 | [7 empty] | 0 | 0.3125 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 4 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Plate | P1 | SDM_A12_P1 | PL40x170 | 200 | A36 | 1 | 4 | 4 | 9.5 | 38 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 0 | 4 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP013 | 4 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A12 | Plate | P2 | SDM_A12_P2 | PL40x150 | 170 | A36 | 1 | 4 | 4 | 8 | 32 | AMC2 | Plate | MCC |  |  | 0 | 4 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 4 | 4 | 0 | 4 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP013 | 4 | 2026-08-04 |  |  |  | 0
40 | TW1008-MAG-&MLD020-U-001025_04 | 24D06641-00-M4130#A13 | Lower sealing plate |  |  | 186xx400x16 |  | A36 |  | 2 |  | 5.3 | 11 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 2 |  | 2 |  |  | - | - | - | AMC 2 | o
41 | TW1008-MAG-&MLD020-U-001025_04 | 24D06641-00-M4130#A14 | Lower sealing plate |  |  | 236xx400x16 |  | A36 |  | 6 |  | 7.5 | 45 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 6 |  |  |  |  | - | - | - | AMC 2 | o
42 | 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A15 | Fixed saddle shim |  |  | 640x115x1 |  | A36 |  | 10 |  | 0.5 | 5 | AMC2 | [7 empty] | 0 | 0.45455 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 10 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.33 | 24D06641-00-M4130#A15 | Shim Plate | P1 | SDM_A15_P1 | PL1x115 | 640 | A36 | 1 | 10 | 10 | 0.5 | 5 | AMC2 | Plate | MCC |  |  | 0 | 10 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 10 | 10 | 0 | 10 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP001 | 10 | 2026-08-04 |  |  |  | 0
43 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Manhole |  |  | 262x813x942 |  |  |  | 1 |  | 121.5 | 121 | AMC2 | [7 empty] | 0 | 0.25 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Flange | M1 | SDM_A19_M1 | 24" 150# SO R.F (ASME B16.5) |  | A105 | 1 | 1 | 1 | 100 | 100 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Pipe | D1 | SDM_A19_D1 | PL8x250 | 1891 | A36 | 1 | 1 | 1 | 29.7 | 29.7 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP006 | 1 | 2026-08-11 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A19 | Plate | P1 | SDM_A19_P1 | PL12x100 | 716 | A36 | 1 | 1 | 1 | 6.7 | 6.7 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 1 | 2026-08-10 |  |  |  | 0
44 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Hinge manhole |  |  | 793x570x80 |  |  |  | 1 |  | 25.4 | 25 | AMC2 | [7 empty] | 0 | 0.25 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Round Bar | R1 | SDM_A20_R1 | RB60 | 1096 | A36 | 1 | 1 | 1 | 24.3 | 24.3 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP509 | 1 | 2026-08-01 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Angle | A1 | SDM_A20_A1 | L80x80x10 | 80 | A36 | 1 | 1 | 1 | 1.1 | 1.1 | AMC2 | Shape | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 (L90x10 thay thế L80x10) |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP504 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A20 | Plate | P1 | SDM_A20_P1 | PL12x80 | 80 | A36 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP008 | 1 | 2026-08-10 |  |  |  | 0
45 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Closing flange manhole |  |  | 813x860x136 |  |  |  | 1 |  | 187.3 | 187 | AMC2 | [7 empty] | 0 | 0.3 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Blind Flange | M1 | SDM_A21_M1 | 24" 150# R.F (ASME B16.5) |  | A105 | 1 | 1 | 1 | 100 | 100 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Round Bar | R1 | SDM_A21_R1 | RB20 | 326 | A36 | 2 | 1 | 2 | 0.8 | 1.6 | AMC2 | Shape | PMC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP507 | 2 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Round Bar | R2 | SDM_A21_R2 | RB15 | 188 | A36 | 1 | 1 | 1 | 0.3 | 0.3 | AMC2 | Shape | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP506 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A21 | Eyes Bolt | M1 |  | M16x260L |  | A36 | 1 | 1 | 1 | 0.6 | 0.6 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
46 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Rupture disk spool |  |  | 1142x1360x985 |  |  |  | 1 |  | 305.6 | 306 | AMC2 | [7 empty] | 0 | 0.39286 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Flange | M1 | SDM_A22_M1 | 28" 150# WN R.F (ASME B16.47 Type A) |  | A105 | 1 | 1 | 1 | 155 | 155 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Pipe | D1 | SDM_A22_D1 | 28" SCH.STD (Ø711x9.53t) | 761 | A106 Gr.B | 1 | 1 | 1 | 125.4585 | 125.4585 | AMC2 | Shape | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP502 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P1 | SDM_A22_P1 | PL30x225 | 250 | A36 | 1 | 1 | 1 | 10.5 | 10.5 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP012 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P2 | SDM_A22_P2 | PL10x60 | 620 | A36 | 2 | 1 | 2 | 2.9 | 5.8 | AMC2 | Plate | MCC |  |  | 0 | 2 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 2 | 0 | 2 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 2
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Plate | P3 | SDM_A22_P3 | PL10x70 | 80 | A36 | 1 | 1 | 1 | 0.4 | 0.4 | AMC2 | Plate | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | [6 empty] | 1
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A22 | Mesh | M2 | SDM_A22_M2 | - |  |  | 1 | 1 | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
47 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Rupture disk external spool |  |  | 985x985x737 |  |  |  | 1 |  | 250.4 | 250 | AMC2 | [7 empty] | 0 | 0.3125 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Flange | M1 | SDM_A23_M1 | 28" 150# WN R.F (ASME B16.47 Type A) |  | A105 | 1 | 1 | 1 | 155 | 155 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Pipe | D1 | SDM_A23_D1 | 28" SCH.STD (Ø711x9.53t) | 604 | A106 Gr.B | 1 | 1 | 1 | 99.5754 | 99.5754 | AMC2 | Shape | MCC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-31-CP502 | 1 | 2026-08-04 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Plate | P1 | SDM_A23_P1 | PL8x100 | 376 | A36 | 1 | 1 | 1 | 2.4 | 2.4 | AMC2 | Plate | PMC |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP006 | 1 | 2026-08-11 |  |  |  | 0
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A23 | Mesh | M2 | SDM_A23_M2 | - |  |  | 1 | 1 | 1 | 0.1 | 0.1 | AMC2 | Purchasing | KHO |  |  | 0 | 1 | 0 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 0 | 1 |  | - | - | - | AMC 2 | [13 empty] | - | - | - | - | - | - | - | Purchasing
48 | 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A24 | Large washer |  |  | Plate ø80xø32x5 |  | A36 |  | 1 |  | 0.2 | 0.2 | AMC2 | [7 empty] | 1 | 1 |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
| 24D06641-00-M4131_Sh.32 | 24D06641-00-M4130#A24 | Washer | WS1 | SDM_A24_WS1 | PL5x80 | 80 | A36 | 1 | 1 | 1 | 0.2 | 0.2 | AMC2 | Plate | MCC |  |  | 1 | 0 | 1 | [6 empty] | LOT 4 | SDM Street 18 |  | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | AMC2-S1 | 1 | 1 | 1 | 0 |  | - | - | - | AMC 2 |  | PAC | [5 empty] | Added, thêm nguyên công | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-31-CP004 | 1 | 2026-08-04 |  |  |  | 0
49 | TW1008-MAG-&MLD020-U-001025_04 | 24D06641-00-M4130#A25 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 3000 | A36 |  | 17 |  | 25 | 425 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 17 |  | 17 |  |  | - | - | - | AMC 2 | o
50 | TW1008-MAG-&MLD020-U-001025_04 | 24D06641-00-M4130#A26 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 2788 | A36 |  | 1 |  | 22.4 | 22 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  | 1 |  |  | - | - | - | AMC 2 | o
51 | TW1008-MAG-&MLD020-U-001025_04 | 24D06641-00-M4130#A30 | Quarter of 8" Sch.STD Pipe |  |  | 8" Sch.STD (Cut from 1/4 Pipe) | 800 | A36 |  | 1 |  | 5.8 | 6 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  | 1 |  |  | - | - | - | AMC 2 | o
52 | TW1008-MAG-&MLD020-U-001025_04 | 24D06641-00-M4130#A32 | Pipe 1/2" Sch.STD - Lg.100 mm |  |  | 1/2" Sch.STD | 100 | A36 |  | 1 |  | 0.1 | 0 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o
53 | TW1008-MAG-&MLD020-U-001025_04 | Bolt M24x100 | Hex. Bolt (Full Threaded) |  |  | M24x100L |  | A193 B7 - HDG (ISO 4017) |  | 6 |  | 0.5 | 3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 6 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
54 | TW1008-MAG-&MLD020-U-001025_04 | DIN 975 - M30x310 | Stud Bolt |  |  | M30x310L |  | A193 B7 - HDG (DIN 975) |  | 1 |  | 1.7 | 2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
55 | TW1008-MAG-&MLD020-U-001025_04 | Gasket 24" - 150LB | Gasket |  |  | 24" 150# (ASME B16.21) |  | Klingersil |  | 1 |  | 1.5 | 1 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 1 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
56 | TW1008-MAG-&MLD020-U-001025_04 | ISO 4014 - M30 x 160 | Hex. Bolt |  |  | M30x160L |  | A193 B7 - HDG (ISO 4014) |  | 20 |  | 1.2 | 23 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 20 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
57 | TW1008-MAG-&MLD020-U-001025_04 | ISO 4014 - M30 x 220 | Hex. Bolt |  |  | M30x220L |  | A193 B7 - HDG (ISO 4014) |  | 28 |  | 1.5 | 42 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 28 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
58 | TW1008-MAG-&MLD020-U-001025_04 | ISO 4032 - M24 | Hex. Nut |  |  | M24 |  | A194 2H - HDG |  | 16 |  | 0.1 | 2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 16 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
59 | TW1008-MAG-&MLD020-U-001025_04 | ISO 4032 - M30 | Hex. Nut |  |  | M30 |  | A194 2H - HDG (ISO 4032) |  | 52 |  | 0.3 | 13 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 52 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
60 | TW1008-MAG-&MLD020-U-001025_04 | ISO 4032 -M16 | Hex. Nut |  |  | M16 |  | A194 2H - HDG |  | 3 |  | 0.1 | 0.3 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 3 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
61 | TW1008-MAG-&MLD020-U-001025_04 | ISO 7089 - 16 | Washer |  |  | M16 |  | F436 - HDG |  | 2 |  | 0.1 | 0.2 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 2 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
62 | TW1008-MAG-&MLD020-U-001025_04 | ISO 7089 - 24 | Washer |  |  | M24 |  | F436 - HDG |  | 22 |  | 0.033333 | 0.73333 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 22 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing
63 | TW1008-MAG-&MLD020-U-001025_04 | ISO 7089 - 30 | Washer |  |  | M30 |  | F436 - HDG |  | 96 |  | 0.1 | 5 | AMC2 | [7 empty] | 0 | #DIV/0! |  |  |  |  | LOT 4 | SDM Street 18 | x | N/A | 0 |  |  |  | N/A | 0 |  |  |  | N/A | 0 |  |  |  | AMC2-S1 | 96 |  |  |  |  | - | - | - | AMC 2 | o | [19 empty] | Purchasing

## BRM4130L1
ASSEMBLY PART LIST | [36 empty] | Số Unit cần đảm bảo |  |  |  | Số Unit cần đảm bảo
Project name / Tên Dự án : A320_Kuo Kuang Combined Cycle Power Plant Unit 2
Item Name / Tên Hạng mục : Bracing for Lot 1 (SDM & CCM)
Contract No. / Số Hợp đồng : A320 | [33 empty] | chi tiết chia nối |  |  | Số Unit |  |  |  | Số Unit
Prepared By / Chuẩn bị : Design Consultant Center | [36 empty] | 2 |  |  |  | 2
Document No. / Số Tài liệu : A320-SFR-APL-001 | [7 empty] | Rev./ Số Sửa đổi:1 | [13 empty] | Date: 10-Sep-2026 |  |  |  | Type Fabrication | [6 empty] | Type
DCC | DCC | DCC | DCC | DCC |  | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC |  |  |  | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC-F | DCC-X | DCC-Y | DCC-Z | DCC-J | DCC-BH | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC | DCC
No. | Drawing Number | Assembly No. | Description | 5A (Marking as Dwg.) | 5B (Marking as Cutting) | Size | Length | Material | Q'ty | Set | T.Q'ty | U.Weight | T.Weight | Đã nhận | Còn thiếu | Ngày nhận | Loose Part | Scope of Steel Work Unit-1 | Scope of Steel Work Unit-2 | Unit Area (m2) | Total Area (m2) | Remark | AS Symbol | Delivery item | Scope of Painting Work Unit-1 | Khoan Lỗ | Lốc tròn (Uốn cong) | Sấn | Vát mép & Cắt miệng | Gia công cơ khí (Không thay đổi chiều dày) | Gia công cơ khí (Có thay đổi chiều dày) | Tổ hợp | Fabrication or Purchasing | Cutting No. | Q'TY | Date Issue | Remain (T'Qty-Q'Ty) | Cutting No. | Q'TY | Date Issue | Remain (T'Qty-Q'Ty)
1 | 2 | 3 | 4 | 5A (Marking as Dwg.) | 5B (Marking as Cutting) | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |  | 14 | 15A | 15 | 16 | 17 | 18 | 19 | 20 | 29A | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 41 | 42 | 43 | 47 | 44 | 45 | 46 | 47
9 | A320-AS-LT-1 | LT-1 | LIFTING LUG |  |  | (160x99x200) |  |  |  | 27 |  | 3.4 | 91.8 |  |  |  | 15A: AMC 2; 15: S1=27; 16: 0.1; 17: 0.4; 19: x; 38: Fabrication
10 | A320-AS-LT-1 | LT-1 | PLATE | GY-1 | LT-1-GY-1 | PL20*85 | 90 | SS400 | 1 |  | 27 | 0.9 | 24.3 | 27 | 0 | 2026-09-12 |  | AMC 2 |  | 0.1 | 0.4 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-700-CP003 | 27 | 2026-09-09 | 0 |  | 54 |  | #VALUE!
11 | A320-AS-LT-1 | LT-1 | PLATE | P-334 | LT-1-P-334 | PL10*200 | 160 | SS400 | 1 |  | 27 | 2.5 | 67.5 | 27 | 0 | 2026-09-12 |  | AMC 2 |  | 0.1 | 1.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP002 | 27 | 2026-09-09 | 0 |  | 54 |  | #VALUE!
12 | A320-AS-LT-2 | LT-2 | LIFTING LUG |  |  | (160x99x200) |  |  |  | 27 |  | 3.4 | 91.8 |  |  |  | 15A: AMC 2; 15: S1=27; 16: 0.1; 17: 0.4; 19: x; 38: Fabrication
13 | A320-AS-LT-2 | LT-2 | PLATE | GY-1 | LT-2-GY-1 | PL20*85 | 90 | SS400 | 1 |  | 27 | 0.9 | 24.3 | 27 | 0 | 2026-09-12 |  | AMC 2 |  | 0.1 | 0.4 |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Fabrication | A320-700-CP003 | 27 | 2026-09-09 | 0 |  | 54 |  | #VALUE!
14 | A320-AS-LT-2 | LT-2 | PLATE | P-334 | LT-2-P-334 | PL10*200 | 160 | SS400 | 1 |  | 27 | 2.5 | 67.5 | 27 | 0 | 2026-09-12 |  | AMC 2 |  | 0.1 | 1.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP002 | 27 | 2026-09-09 | 0 |  | 54 |  | #VALUE!
23 | A320-AS-BR-25 | BR-25 | BRACING |  |  | (810x10x131) |  |  |  | 1 |  | 7.6 | 7.6 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.2; 17: 0.4; 19: x; 38: Fabrication
24 | A320-AS-BR-25 | BR-25 | PLATE | P-340 | BR-25-P-340 | PL10*131 | 810 | SS400 | 1 |  | 1 | 7.6 | 7.6 | 1 | 0 | 2026-10-07 | X | AMC 2 |  | 0.2 | 0.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 1 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
25 | A320-AS-BR-28 | BR-28 | BRACING |  |  | (571x10x227) |  |  |  | 2 |  | 6.5 | 13 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.2; 17: 0.8; 19: x; 38: Fabrication
26 | A320-AS-BR-28 | BR-28 | BEAM | P-339 | BR-28-P-339 | PL10*150 | 524 | SS400 | 1 |  | 2 | 6.5 | 13 | 2 | 0 | 2026-10-07 | X | AMC 2 |  | 0.2 | 0.8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 2 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
43 | A320-AS-BR-29 | BR-29 | BRACING |  |  | (1748x12x1723) |  |  |  | 3 |  | 37.3 | 111.9 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.9; 17: 5.4; 19: x; 38: Fabrication
44 | A320-AS-BR-29 | BR-29 | BEAM | P-338 | BR-29-P-338 | PL12*150 | 2523 | SS400 | 1 |  | 3 | 37.3 | 111.9 | 3 | 0 | 2026-10-07 | X | AMC 2 |  | 0.9 | 5.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP011 | 3 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
62 | A320-AS-LT-4 | LT-4 | LIFTING LUG |  |  | (160x99x200) |  |  |  | 3 |  | 3.4 | 10.2 |  |  |  | 15A: AMC 2; 15: S1; 16: 0.1; 17: 0; 19: x; 38: Fabrication
63 | A320-AS-LT-4 | LT-4 | PLATE | GY-1 | LT-4-GY-1 | PL20*85 | 90 | SS400 | 1 |  | 3 | 0.9 | 2.7 | 3 | 0 | 2026-09-22 | 15A: AMC 2; 16: 0; 17: 0; 31: 1; 32: 0; 33: 0; 34: 1; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 3; 45: 6; 47: #VALUE!
64 | A320-AS-LT-4 | LT-4 | PLATE | P-335 | LT-4-P-335 | PL10*200 | 160 | SS400 | 1 |  | 3 | 2.5 | 7.5 | 3 | 0 | 2026-10-07 |  | AMC 2 |  | 0.1 | 0.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 3 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
62 | A320-AS-LT-4 | LT-4 | LIFTING LUG |  |  | (160x99x200) |  |  |  | 3 |  | 3.4 | 10.2 |  |  |  | 15A: AMC 2; 15: S1; 16: 0.1; 17: 0; 19: x; 38: Fabrication
63 | A320-AS-LT-4 | LT-4 | PLATE | GY-1 | LT-4-GY-1 | PL20*85 | 90 | SS400 | 1 |  | 3 | 0.9 | 2.7 | 3 | 0 | 2026-09-22 | 15A: AMC 2; 16: 0; 17: 0; 31: 1; 32: 0; 33: 0; 34: 1; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 3; 45: 6; 47: #VALUE!
64 | A320-AS-LT-4 | LT-4 | PLATE | P-335 | LT-4-P-335 | PL10*200 | 160 | SS400 | 1 |  | 3 | 2.5 | 7.5 | 3 | 0 | 2026-10-07 |  | AMC 2 |  | 0.1 | 0.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 3 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
89 | A320-AS-BR-25 | BR-25 | BRACING |  |  | (810x10x131) |  |  |  | 1 |  | 7.6 | 7.6 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.2; 17: 0.2; 19: x; 38: Fabrication
90 | A320-AS-BR-25 | BR-25 | PLATE | P-340 | BR-25-P-340 | PL10*131 | 810 | SS400 | 1 |  | 1 | 7.6 | 7.6 | 1 | 0 | 2026-10-07 | X | AMC 2 |  | 0.2 | 0.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 1 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
91 | A320-AS-BR-27 | BR-27 | BRACING |  |  | (565x10x236) |  |  |  | 2 |  | 6.5 | 13.1 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.2; 17: 0.4; 19: x; 38: Fabrication
92 | A320-AS-BR-27 | BR-27 | BEAM | P-342 | BR-27-P-342 | PL10*150 | 554 | SS400 | 1 |  | 2 | 6.5 | 13.1 | 2 | 0 | 2026-10-07 | X | AMC 2 |  | 0.2 | 0.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 2 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
93 | A320-AS-BR-30 | BR-30 | BRACING |  |  | (1263x10x1066) |  |  |  | 1 |  | 19.8 | 19.8 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.5; 17: 0.5; 19: x; 38: Fabrication
94 | A320-AS-BR-30 | BR-30 | BEAM | P-341 | BR-30-P-341 | PL10*150 | 1596 | SS400 | 1 |  | 1 | 19.8 | 19.8 | 1 | 0 | 2026-10-07 | X | AMC 2 |  | 0.5 | 0.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 1 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
121 | A320-AS-BR-26 | BR-26 | BRACING |  |  | (1462x10x1253) |  |  |  | 3 |  | 23.3 | 69.9 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.6; 17: 1.8; 19: x; 38: Fabrication
122 | A320-AS-BR-26 | BR-26 | BEAM | P-343 | BR-26-P-343 | PL10*150 | 1892 | SS400 | 1 |  | 3 | 23.3 | 69.9 | 3 | 0 | 2026-10-07 | X | AMC 2 |  | 0.6 | 1.8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 3 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
123 | A320-AS-BR-31 | BR-31 | BRACING |  |  | (1265x10x1068) |  |  |  | 3 |  | 19.8 | 59.4 |  |  |  | 14: X; 15A: AMC 2; 15: S1; 16: 0.5; 17: 1.5; 19: x; 38: Fabrication
124 | A320-AS-BR-31 | BR-31 | BEAM | PA-1 | BR-31-PA-1 | PL10*150 | 1599 | SS400 | 1 |  | 3 | 19.8 | 59.4 | 3 | 0 | 2026-10-07 | X | AMC 2 |  | 0.5 | 1.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 3 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
133 | A320-AS-BR-A5C_5-1 | BR-A5C_5-1 | BRACING |  |  | (2192x56x2192) |  |  |  | 1 |  | 28.4 | 28.4 |  |  |  | 15A: AMC 2; 15: S2; 16: 1.8; 17: 1.8; 19: x; 38: Fabrication
134 | A320-AS-BR-A5C_5-1 | BR-A5C_5-1 | BENT CHANNEL | CX-47 | BR-A5C_5-1-CX-47 | C100*50*4 | 2100 | SS400 | 1 |  | 1 | 12.7 | 12.7 |  | 1 |  | 15A: AMC 2; 16: 0.8; 17: 0.8; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 1; 45: 2; 47: #VALUE!
135 | A320-AS-BR-A5C_5-1 | BR-A5C_5-1 | BENT CHANNEL | CX-96 | BR-A5C_5-1-CX-96 | C100*50*4 | 985 | SS400 | 2 |  | 2 | 5.9 | 11.9 |  | 2 |  | 15A: AMC 2; 16: 0.4; 17: 0.8; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 2; 45: 4; 47: #VALUE!
136 | A320-AS-BR-A5C_5-1 | BR-A5C_5-1 | PLATE | P-336 | BR-A5C_5-1-P-336 | PL6*110 | 120 | SS400 | 4 |  | 4 | 0.6 | 2.5 | 4 | 0 | 2026-09-18 | 15A: AMC 2; 16: 0; 17: 0.1; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 4; 45: 8; 47: #VALUE!
137 | A320-AS-BR-A5C_5-1 | BR-A5C_5-1 | PLATE | P-337 | BR-A5C_5-1-P-337 | PL6*230 | 133 | SS400 | 1 |  | 1 | 1.4 | 1.4 | 1 | 0 | 2026-09-18 | 15A: AMC 2; 16: 0.1; 17: 0.1; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 1; 45: 2; 47: #VALUE!
138 | A320-AS-BR-A5C_5-2 | BR-A5C_5-2 | BRACING |  |  | (547x10x844) |  |  |  | 1 |  | 9.2 | 9.2 |  |  |  | 15A: AMC 2; 15: S2; 16: 0.3; 17: 0.3; 19: x; 38: Fabrication
139 | A320-AS-BR-A5C_5-2 | BR-A5C_5-2 | PLATE | P-345 | BR-A5C_5-2-P-345 | PL10*131 | 965 | SS400 | 1 |  | 1 | 9.2 | 9.2 | 1 | 0 | 2026-10-07 |  | AMC 2 |  | 0.3 | 0.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 1 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
140 | A320-AS-BR-A5C_6-2 | BR-A5C_6-2 | BRACING |  |  | (1996x56x1996) |  |  |  | 1 |  | 26 | 26 |  |  |  | 15A: AMC 2; 15: S2; 16: 1.6; 17: 1.6; 19: x; 38: Fabrication
141 | A320-AS-BR-A5C_6-2 | BR-A5C_6-2 | BENT CHANNEL | CX-92 | BR-A5C_6-2-CX-92 | C100*50*4 | 885 | SS400 | 2 |  | 2 | 5.3 | 10.7 |  | 2 |  | 15A: AMC 2; 16: 0.3; 17: 0.7; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 2; 45: 4; 47: #VALUE!
142 | A320-AS-BR-A5C_6-2 | BR-A5C_6-2 | BENT CHANNEL | CX-93 | BR-A5C_6-2-CX-93 | C100*50*4 | 1900 | SS400 | 1 |  | 1 | 11.5 | 11.5 |  | 1 |  | 15A: AMC 2; 16: 0.7; 17: 0.7; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 1; 45: 2; 47: #VALUE!
143 | A320-AS-BR-A5C_6-2 | BR-A5C_6-2 | PLATE | P-336 | BR-A5C_6-2-P-336 | PL6*110 | 120 | SS400 | 4 |  | 4 | 0.6 | 2.5 | 4 | 0 | 2026-09-18 | 15A: AMC 2; 16: 0; 17: 0.1; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 4; 45: 8; 47: #VALUE!
144 | A320-AS-BR-A5C_6-2 | BR-A5C_6-2 | PLATE | P-337 | BR-A5C_6-2-P-337 | PL6*230 | 133 | SS400 | 1 |  | 1 | 1.4 | 1.4 | 1 | 0 | 2026-09-18 | 15A: AMC 2; 16: 0.1; 17: 0.1; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 1; 45: 2; 47: #VALUE!
145 | A320-AS-BR-A5C_6-3 | BR-A5C_6-3 | BRACING |  |  | (547x10x844) |  |  |  | 1 |  | 9.2 | 9.2 |  |  |  | 15A: AMC 2; 15: S2; 16: 0.3; 17: 0.3; 19: x; 38: Fabrication
146 | A320-AS-BR-A5C_6-3 | BR-A5C_6-3 | PLATE | P-345 | BR-A5C_6-3-P-345 | PL10*131 | 965 | SS400 | 1 |  | 1 | 9.2 | 9.2 | 1 | 0 | 2026-10-07 |  | AMC 2 |  | 0.3 | 0.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 1 | 2026-09-26 | 0 |  | 0 |  | #VALUE!
147 | A320-AS-BR-A5C_7-1 | BR-A5C_7-1 | BRACING |  |  | (1392x56x1392) |  |  |  | 1 |  | 18.7 | 18.7 |  |  |  | 15A: AMC 2; 15: S2; 16: 1.2; 17: 1.2; 19: x; 38: Fabrication
148 | A320-AS-BR-A5C_7-1 | BR-A5C_7-1 | BENT CHANNEL | CX-94 | BR-A5C_7-1-CX-94 | C100*50*4 | 585 | SS400 | 2 |  | 2 | 3.5 | 7.1 |  | 2 |  | 15A: AMC 2; 16: 0.2; 17: 0.5; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 2; 45: 4; 47: #VALUE!
149 | A320-AS-BR-A5C_7-1 | BR-A5C_7-1 | BENT CHANNEL | CX-95 | BR-A5C_7-1-CX-95 | C100*50*4 | 1300 | SS400 | 1 |  | 1 | 7.8 | 7.8 |  | 1 |  | 15A: AMC 2; 16: 0.5; 17: 0.5; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 1; 45: 2; 47: #VALUE!
150 | A320-AS-BR-A5C_7-1 | BR-A5C_7-1 | PLATE | P-336 | BR-A5C_7-1-P-336 | PL6*110 | 120 | SS400 | 4 |  | 4 | 0.6 | 2.5 | 4 | 0 | 2026-09-18 | 15A: AMC 2; 16: 0; 17: 0.1; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 4; 45: 8; 47: #VALUE!
151 | A320-AS-BR-A5C_7-1 | BR-A5C_7-1 | PLATE | P-337 | BR-A5C_7-1-P-337 | PL6*230 | 133 | SS400 | 1 |  | 1 | 1.4 | 1.4 | 1 | 0 | 2026-09-18 | 15A: AMC 2; 16: 0.1; 17: 0.1; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: Fabrication; 47: 1; 45: 2; 47: #VALUE!
152 | A320-AS-BR-A5C_7-2 | BR-A5C_7-2 | BRACING |  |  | (547x10x844) |  |  |  | 1 |  | 9.2 | 9.2 |  |  |  | 15A: AMC 2; 15: S2; 16: 0.3; 17: 0.3; 19: x; 38: Fabrication
153 | A320-AS-BR-A5C_7-2 | BR-A5C_7-2 | PLATE | P-345 | BR-A5C_7-2-P-345 | PL10*131 | 965 | SS400 | 1 |  | 1 | 9.2 | 9.2 | 1 | 0 | 2026-10-07 |  | AMC 2 |  | 0.3 | 0.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fabrication | A320-700-CP010 | 1 | 2026-09-26 | 0 |  | 0 |  | #VALUE!